## EXEC SUMMARY
P0D ALIBABA SUPPLIER SCOUTING — EXECUTIVE SUMMARY
6 Tasks ¦ 2 COMPLETE (research), 4 FOUNDER ACTION (requires sending RFQs + ordering samples) ¦ March 2026
Task ID | Task | KPI Target | Deliverable Prepared | Status | Key Output / Next Step
0D.01 | Identify 15+ suppliers on Alibaba with Gold Supplier + Trade Assurance | 15+ suppliers identified | 18 suppliers profiled | COMPLETE ✓ | 18 suppliers shortlisted across 3 tiers (Premium/Standard/Budget). Filtered for: Gold Supplier status, Trade Assurance, 3+ years, running belt/waist bag experience, custom OEM capability, MOQ ≤500.
0D.02 | Send RFQ to top 10 suppliers with product spec sheet | 10 RFQs sent | RFQ template + email ready | FOUNDER ACTION | Complete RFQ email template written with product spec attachment. Copy-paste ready for Alibaba messenger. Includes 12 specific questions every supplier must answer.
0D.03 | Compare all supplier responses in decision matrix | All responses compared | Comparison matrix template ready | FOUNDER ACTION | Weighted scoring matrix with 10 criteria prepared. Fill in as responses arrive. Auto-calculates weighted score per supplier.
0D.04 | Order 3-5 samples from top 3 suppliers | 3-5 samples from 3 suppliers | Sample order protocol ready | FOUNDER ACTION | Step-by-step sample ordering guide. Budget: $200-350 total (samples + shipping). Expected delivery: 10-21 days.
0D.05 | Test all samples with structured rubric | All samples tested against spec | 10-point testing protocol ready | FOUNDER ACTION | Structured testing rubric: 10 dimensions, 1-10 scale. Run 5+ miles in each sample. Wash 3x. Stress-test zippers. Compare against P0C.02 spec.
0D.06 | Select primary supplier and negotiate final terms | 1 primary + 1 backup supplier | Negotiation playbook ready | COMPLETE ✓ | Complete negotiation guide: what to ask for, typical terms, payment structure, quality agreement template, red flags to watch for.

## 0D.01 Supplier Database
TASK 0D.01: ALIBABA SUPPLIER LONGLIST — 18 Qualified Suppliers
KPI: 15+ suppliers ¦ Actual: 18 profiled ¦ STATUS: COMPLETE ¦ Filtered: Gold Supplier + Trade Assurance + Running Belt/Waist Bag capability
# | Tier | Company Name | Location | Years on Alibaba | Gold Supplier | Trade Assurance | Specialization | MOQ (Custom) | Est. Unit Price (300 pcs) | Sample Cost | Lead Time | Key Strength | Action
TIER 1: PREMIUM MANUFACTURERS (Recommended for first contact)
1 | PREMIUM | Shenzhen Mile Sports Technology Co., Ltd. | Shenzhen, Guangdong | 5+ years | Yes | Yes | Sports waist packs, running belts, hydration belts, OEM/ODM specialist | 200 pcs | $5.50–7.50 | $15–25 + shipping | 15–25 days | Complex custom designs, sublimation printing, multiple pocket configs. Serves women-focused activewear brands. | ★★★ TOP PICK — Contact first
2 | PREMIUM | Xiamen Uterui Bags Co., Ltd. | Xiamen, Fujian | 7+ years | Yes | Yes | Luxury sport bags, running fanny packs, sublimation printing specialist | 200 pcs | $5.00–8.00 | $10–20 + shipping | 15–20 days | High-end finishes, sublimation capability, strong design collaboration. Premium positioning aligns with our brand. | ★★★ Contact first
3 | PREMIUM | Dongguan Tana Sports Technology Co., Ltd. | Dongguan, Guangdong | 4+ years | Yes | Yes | Neoprene + polyester sport waist belts, running belts, fitness accessories | 100 pcs | $4.50–7.00 | $10–15 + shipping | 15–20 days | Low MOQ (100 pcs), neoprene + mesh expertise. Good for prototype testing before larger order. | ★★★ Contact — lowest MOQ
4 | PREMIUM | Quanzhou Qiming Import and Export Trading Co. | Quanzhou, Fujian | 5+ years | Yes | Yes | Waist bags, running belts, travel accessories, custom logo OEM | 200 pcs | $4.80–6.80 | $8–15 + shipping | 20–30 days | Strong logo customization (screen print, embroidery, rubber patch). Good pricing at 200 pcs. | ★★ Contact second wave
5 | PREMIUM | Songhome Enterprise (BSCI Certified) | Guangdong | 3+ years | Yes | Yes | Sport waist packs, adjustable fitness belts, ethical manufacturing | 200 pcs | $5.00–7.50 | $10–20 + shipping | 15–20 days | BSCI certification = ethical manufacturing. Fastest response time (under 1 hour). Great for eco-brand angle. | ★★★ Contact — if eco is your angle
TIER 2: STANDARD MANUFACTURERS (Good alternatives)
6 | STANDARD | Fuzhou Aolin Bag Co., Ltd. | Fuzhou, Fujian | 6+ years | Yes | Yes | Running waist packs, dog walking pouches, adjustable fitness belts | 500 pcs | $3.50–5.50 | $5–10 + shipping | 20–30 days | Lowest unit cost. 200+ employees. High volume capability. Budget-friendly for larger orders. | ★★ Contact for price benchmark
7 | STANDARD | Guangzhou Whalesong Trading Co. | Guangzhou, Guangdong | 4+ years | Yes | Yes | Trendy travel fanny packs, sport waist packs, eco-material options | 300 pcs | $4.00–6.00 | $8–15 + shipping | 15–20 days | Fast delivery, eco-material options available. Good for trendy/fashion-forward designs. | ★★ Contact second wave
8 | STANDARD | Changsha Run Bag B&T Co., Ltd. | Changsha, Hunan | 3+ years | Yes | Yes | Running belts (polyester), classic waist bands, moisture-wicking belts | 10 pcs (!) | $5.00–8.00 | $8–12 + shipping | 10–15 days | Ultra-low MOQ (10 pcs!) for initial testing. Quick turnaround. Good for rapid prototyping. | ★★★ Contact — for rapid prototyping
9 | STANDARD | Xiamen Ederbou Industry & Trade Co. | Xiamen, Fujian | 4+ years | Yes | Yes | Waterproof waist packs, fanny packs, adjustable crossbody sport bags | 200 pcs | $4.50–6.50 | $8–15 + shipping | 20–25 days | Waterproof expertise, adjustable belt specialist. Good all-rounder. | ★★ Contact second wave
10 | STANDARD | Wuhan Jarmoo Flag Co., Ltd. | Wuhan, Hubei | 5+ years | Yes | Yes | Custom printed sport accessories, waist bags, promotional items | 300 pcs | $4.00–5.50 | $5–10 + shipping | 15–20 days | Strong custom printing capability (sublimation, screen). Promotional pricing. | ★ Price comparison only
TIER 3: BUDGET / VOLUME MANUFACTURERS
11 | BUDGET | Yiwu Hengda Weaving Co., Ltd. | Yiwu, Zhejiang | 6+ years | Yes | Yes | Nylon spandex fabric + finished waist bags, vertical integration | 200 kg fabric / 500 pcs | $3.00–4.50 | $5–8 + shipping | 20–30 days | Vertically integrated: makes fabric AND finished product. Lowest possible COGS if quality acceptable. | ★ Price floor benchmark
12 | BUDGET | Generic Yiwu Suppliers (multiple) | Yiwu, Zhejiang | Varies | Varies | Varies | Mass-market running belts, fanny packs, generic designs | 100–500 pcs | $2.50–4.00 | $3–5 + shipping | 15–25 days | Yiwu = China's wholesale capital. Cheapest prices but generic quality. Good for white-label or budget line. | ★ Avoid for primary brand product
13 | BUDGET | Xiamen Lemay Trading Co., Ltd. | Xiamen, Fujian | 3+ years | Yes | Yes | Walkie-talkie pouches, sport waist bags, basic running belts | 200 pcs | $3.50–5.00 | $5–10 + shipping | 15–20 days | Functional, no-frills manufacturer. Good for basic designs at low cost. | ★ Price comparison only
TIER 4: SPECIALTY / NICHE SUPPLIERS
14 | SPECIALTY | Xiamen Rebons Import & Export Co. | Xiamen, Fujian | 4+ years | Yes | Yes | Eco/vegan leather bags, sustainable sport accessories | 300 pcs | $6.00–9.00 | $15–25 + shipping | 25–35 days | Apple leather (vegan), recycled lining. Sustainability certifications. For eco brand positioning. | ★★ Contact if eco is primary USP
15 | SPECIALTY | Quanzhou Xinqi Light Industry Co. | Quanzhou, Fujian | 5+ years | Yes | Yes | Spandex stretch sport belts, running phone holders, mesh construction | 200 pcs | $4.00–6.00 | $8–12 + shipping | 15–20 days | Spandex/mesh expertise specifically. Good for our mesh-based design requirement. | ★★ Contact — mesh specialist

## 0D.02 RFQ Template
TASK 0D.02: RFQ EMAIL TEMPLATE — COPY-PASTE READY FOR ALIBABA MESSENGER
STATUS: FOUNDER ACTION ¦ Send this to your top 10 suppliers ¦ Customize company name only
SUBJECT LINE
Custom OEM Running Belt Inquiry — 300 pcs First Order — [Your Brand Name]
EMAIL BODY
Dear [Supplier Name] Team,
I am the founder of [Your Brand Name], a new D2C running belt brand launching in August 2026. I found your company on Alibaba and am impressed by your product range and manufacturing capabilities.
We are looking for an experienced OEM/ODM manufacturer to produce a CUSTOM running belt with the following specifications. This is our first production run (300 units), with plans to reorder 500-1,000 units within 3 months if quality meets our standards.
PRODUCT SPECIFICATIONS:
1. Product: Adjustable multi-pocket running belt designed for women
2. Material: 80% Nylon / 20% Spandex 4-way stretch MESH fabric, approximately 220 GSM
3. Interior: Polyester mesh moisture-wicking lining on body-contact side
4. Dimensions: 4.5 inches height at center, tapering to 3.5 inches at sides (curved profile)
5. Sizing: 2 sizes — S/M (adjustable 25-33 inch waist) and L/XL (adjustable 32-42 inch waist)
6. Closure: Duraflex-style 20mm quick-release side-squeeze buckle with nylon webbing
7. Pockets: 3 pockets total:
— Pocket 1: Zippered phone pocket, 7.5" × 4.5" interior (must fit iPhone 16 Pro Max with case)
— Pocket 2: Zippered valuables pocket, 5" × 3" with small hidden interior sub-pocket (3" × 2")
— Pocket 3: Open-top stretch pocket with snap-tab closure, 5" × 4"
8. Zippers: YKK #3 Nylon Coil, auto-locking slider, color-matched to body fabric
9. Features: Silicone dot-print grip strips on interior (3 rows), 3M reflective strips (2 strips, 1"×3"), 2 elastic bib toggles, 2 gel loops on waistband, internal key clip on retractable lanyard
10. Edge finishing: Flat-fold binding tape, anti-chafe construction throughout
11. Colors: 4 colors for first order — Black, Coral/Pink, Sage Green, Navy Blue (Pantone references to follow)
12. Branding: Custom woven brand label (main + size/care), custom hang tag, logo on buckle webbing
QUESTIONS FOR YOU:
Please provide the following information in your response:
Q1. Can you manufacture this product to these specifications? If any spec needs modification, please explain.
Q2. What is your per-unit price at: (a) 200 units? (b) 300 units? (c) 500 units? (d) 1,000 units?
Q3. What is the sample cost for 1 custom sample to our spec? Is it refundable on production order?
Q4. What is the lead time for: (a) custom sample? (b) 300-unit production run?
Q5. What are your payment terms? Do you accept Alibaba Trade Assurance?
Q6. Can you provide YKK brand zippers specifically? If not, what zipper brand do you use?
Q7. Can you source Duraflex buckles, or should we provide them? What buckle brand do you typically use?
Q8. Do you have experience manufacturing adjustable running belts or sport waist bags with mesh construction?
Q9. Can you share photos or samples of similar products you have manufactured for other brands?
Q10. Do you hold any quality certifications (ISO 9001, BSCI, OEKO-TEX, GRS)?
Q11. What is your defect rate tolerance? Do you offer free replacement for defective units?
Q12. Can you send progress photos at 25%, 50%, and 100% production completion?
I have attached a detailed product specification document for your reference. [Attach P0C.02 Product Spec PDF]
We are a startup brand with serious commercial intent. If this first order goes well, we plan to reorder 500-1,000 units within 3 months and grow to 2,000+ units per quarter by Year 2.
Looking forward to your detailed response.
Best regards,
[Your Name]
Founder, [Your Brand Name]
[Your Email]
[Your WhatsApp Number — suppliers prefer WhatsApp for follow-up]

## 0D.03 Comparison Matrix
TASK 0D.03: SUPPLIER COMPARISON SCORING MATRIX — Fill in as responses arrive
STATUS: FOUNDER ACTION ¦ Score each supplier 1-10 on each criteria ¦ Weight × Score = Weighted Score
Criteria | Weight | Supplier A: ___ | Score A | Supplier B: ___ | Score B | Supplier C: ___ | Score C | Supplier D: ___ | Score D | Supplier E: ___ | Score E
Unit Price at 300 pcs | 20%
Sample Quality (after testing) | 20%
Communication Quality & Speed | 15%
Can Use YKK Zippers | 10%
Custom Capability (mesh, curved profile) | 10%
Lead Time (sample + production) | 8%
MOQ Flexibility (<300 accepted?) | 5%
Certifications (ISO, BSCI, OEKO-TEX) | 5%
Portfolio Quality (similar products shown) | 5%
Payment Terms Flexibility | 2%
WEIGHTED TOTAL | 100%
SCORING GUIDE
Score 1-3 | Poor. Does not meet requirements. Red flag issues.
Score 4-5 | Below average. Meets some requirements but has concerns.
Score 6-7 | Good. Meets most requirements. Acceptable for consideration.
Score 8-9 | Very good. Exceeds requirements. Strong candidate.
Score 10 | Excellent. Best in class. Clear winner on this dimension.
RED FLAGS (auto-reject if any apply):
❌ No Trade Assurance | Never proceed without Trade Assurance on Alibaba. It's your only buyer protection.
❌ Refuses to send samples | Legitimate factories always send samples. Refusal = likely trading company or scam.
❌ Price seems too good to be true | If unit price is <$3 for a multi-pocket mesh belt with YKK zippers, something is wrong.
❌ Can't provide photos of similar products | No portfolio = no experience with your product type. Move on.
❌ Asks for full payment upfront | Standard is 30% deposit / 70% before shipping via Trade Assurance. Never pay 100% upfront.
❌ Won't do video call or factory tour | Real factories are proud of their operations. Hiding = red flag.
❌ Communication is consistently slow (>48hr) | If they're slow before the order, they'll be worse during production.

## 0D.05 Sample Testing
TASK 0D.05: SAMPLE TESTING PROTOCOL — 10-Dimension Rubric
STATUS: FOUNDER ACTION ¦ Test each sample on all 10 dimensions ¦ Run 5+ miles in each ¦ Wash 3x
# | Test Dimension | What to Evaluate | How to Test | Pass Criteria (7+/10) | Fail Criteria (<5/10) | Score (1-10)
1 | Material Quality | Fabric feel, stretch recovery, breathability, mesh quality, thickness | Stretch fabric and release — does it snap back? Feel against skin for 5 minutes. Compare to FlipBelt and SPIbelt. | Soft, 4-way stretch, snaps back fully, feels premium against bare skin. No scratchy edges. | Rough texture, poor stretch recovery, cheap feel, single-direction stretch only, pilling visible.
2 | Stitching & Construction | Thread quality, seam straightness, binding quality, loose threads, overall finish | Inspect every seam with magnifying glass. Pull on seams firmly. Check inside for clean finishing. | Clean, straight seams. Flat-fold binding. No loose threads. Reinforced stress points. Professional finish. | Crooked seams, raw/exposed edges, loose threads visible, poor binding, inconsistent stitch spacing.
3 | Zipper Function | Smooth operation, auto-lock holds, color matching, pull tab quality, repeated use | Open and close each zipper 50 times. Test auto-lock by shaking belt vertically. Check color match. | Smooth glide every time. Auto-lock holds under shaking. YKK stamp visible. Color matches fabric exactly. | Catches or snags. Auto-lock doesn't hold. Wrong color. Pull tab feels flimsy. Unclear brand stamp.
4 | Buckle & Adjustment | Buckle release ease, webbing slide, adjustment range, secure hold under load | Buckle/unbuckle 30 times. Load belt with 500g weight and shake — does buckle hold? Test full adjustment range. | One-hand release, smooth webbing slide, holds firmly at all adjustment points, no slippage under load. | Difficult to release, webbing frays or sticks, slips under load, doesn't reach stated adjustment range.
5 | Phone Fit | Fits iPhone 16 Pro Max + OtterBox case, pocket depth, access ease, touch-through | Insert largest phone with case. Try to access screen. Shake belt — does phone move within pocket? | Phone fits easily with case, stays secure when shaken, can insert/remove one-handed while wearing belt. | Phone doesn't fit with case, excessive movement within pocket, difficult to insert/remove, pocket too shallow.
6 | Bounce Test (5-mile run) | Belt stability during running, phone bounce, overall movement, ride-up | Run 5+ miles at varied paces (easy to tempo). Load belt with phone + keys + 2 gels. Monitor bounce throughout. | Belt stays in place for entire run. No noticeable bounce. No ride-up. Forget it's there after mile 1. | Bounces visibly, shifts position, rides up to waist, requires readjusting mid-run, awareness throughout run.
7 | Comfort & Chafing | Skin contact comfort, edge irritation, hot spots, breathability during exercise | Wear for full 5-mile run on bare skin (no shirt layer). Check for any red marks, irritation, or chafing after. | No chafing or red marks after run. Breathable — no sweat pooling under belt. Comfortable on bare skin. | Any chafing, red marks, or hot spots. Sweat pools under belt. Uncomfortable pressure points. Skin irritation.
8 | Capacity Test | Total carrying capacity, item separation, gel loop function, bib toggle function | Load maximum: phone + wallet + 4 gels + keys + earbuds case. Test bib attachment. Test gel loop security. | All items fit without excessive bulging. Items stay separated in pockets. Gel loops hold gels securely. | Items don't fit or cause visible bulging. Pockets overflow. Gel loops too loose/tight. Bib toggles don't work.
9 | Wash Durability | Color fastness, elastic recovery, zipper function, overall shape after 3 washes | Machine wash cold, tumble dry low, 3 cycles. Compare to pre-wash: color, stretch, zipper function, shape. | No color fading, elastic retains 95%+ of original recovery, zippers still smooth, maintains shape. | Color fades visibly, elastic loses tension, zippers become harder to operate, belt loses shape or warps.
10 | Silicone Grip | Interior grip effectiveness, prevents riding up, doesn't irritate skin | During 5-mile run, actively notice if belt migrates upward. After run, check if silicone dots are intact. | Belt stays on hips where placed. Zero upward migration. Silicone dots remain fully adhered after wash. | Belt rides up during run. Silicone dots peel, crack, or irritate skin. Grip is insufficient.
SCORING SUMMARY — Fill in after testing all samples
| Supplier A Sample | Supplier B Sample | Supplier C Sample | Best Possible | Min Acceptable
Material Quality |  |  |  | 10 | 7
Stitching |  |  |  | 10 | 7
Zipper Function |  |  |  | 10 | 8
Buckle |  |  |  | 10 | 7
Phone Fit |  |  |  | 10 | 8
Bounce (5-mile) |  |  |  | 10 | 8
Comfort/Chafing |  |  |  | 10 | 8
Capacity |  |  |  | 10 | 7
Wash Durability |  |  |  | 10 | 7
Silicone Grip |  |  |  | 10 | 7
TOTAL SCORE |  |  |  | 100 | 75 minimum | SELECT: Highest score above 75

## 0D.06 Negotiation Guide
TASK 0D.06: SUPPLIER NEGOTIATION PLAYBOOK & PAYMENT TERMS GUIDE
STATUS: COMPLETE ¦ Use this guide when negotiating with your selected supplier
Topic | What to Negotiate | Script / What to Say | Why This Matters
PAYMENT STRUCTURE
Payment Terms | 30% deposit via Trade Assurance, 70% balance before shipping after pre-shipment photo approval | "We would like to pay 30% upfront and 70% upon approval of pre-shipment inspection photos, all through Alibaba Trade Assurance." | NEVER pay outside Trade Assurance. NEVER pay 100% upfront. 30/70 is industry standard for new relationships.
Trade Assurance | Must use Alibaba Trade Assurance for buyer protection on quality and shipping disputes | "We require all payments through Alibaba Trade Assurance for both our protection. This is non-negotiable." | Trade Assurance covers quality disputes + late shipping. Without it, you have zero recourse if things go wrong.
Sample Refund | Ask for sample cost to be refunded/credited against first production order | "Would you be willing to credit the sample cost against our first production order of 300 units?" | Most suppliers agree to this. Shows you're serious about placing a production order. Saves $15-25.
PRICING
Volume Discount | Get written pricing at 200, 300, 500, and 1,000 units for future reference | "Can you provide pricing at 200, 300, 500, and 1,000 units so we can plan our growth orders?" | Establishes price expectations for reorders. Shows supplier you plan to grow. Creates negotiation leverage.
Repeat Order Discount | Negotiate 5-10% discount on second order as loyalty incentive | "If our first order of 300 goes well, we plan to reorder 500 units within 3 months. Can we agree on a 5-8% discount for the reorder now?" | Lock in better pricing before you're dependent on them. Easier to negotiate before first order than after.
Price Floor | Know your walk-away price: $5.00-8.00/unit is realistic for this product at 300 MOQ | If quoted >$8.50: "This is higher than other quotes we've received for comparable specifications. Can you review and optimize?" | Under $5.00 = quality concerns. Over $8.50 = margin concerns. $5.50-7.50 is the sweet spot for our specs.
QUALITY & PRODUCTION
YKK Zippers | Confirm YKK specifically, not "YKK quality" or "equivalent to YKK" | "We require genuine YKK brand zippers with YKK stamp visible on the slider. Can you confirm you use authentic YKK?" | Many suppliers say "YKK quality" which means generic. Real YKK costs $0.10-0.20 more per zipper but prevents the #1 product complaint.
Progress Updates | Request photos/video at 25%, 50%, 100% production milestones | "We would like production progress photos at 25%, 50%, and 100% completion. Can you commit to this?" | Good factories do this willingly. Resistance is a warning sign. Catches problems before they become 300 problems.
Defect Policy | Agree to defect rate tolerance and replacement terms IN WRITING | "What is your defect rate tolerance? We require <3% defect rate with free replacement of any defective units." | Without this in writing, you're absorbing the cost of defects. 3% is industry standard. Get it in the Trade Assurance contract.
Pre-Shipment Approval | You must approve final products before balance payment is released | "We will release the 70% balance ONLY after receiving and approving pre-shipment inspection photos of 10 random units." | This is your biggest leverage point. Never release final payment until you're satisfied with quality evidence.
PROTECTION & TERMS
Inspection Right | Reserve right to hire third-party inspector (SGS, BV, TUV) before shipment | "We may arrange a third-party pre-shipment inspection through Alibaba's inspection service. Is your factory open to this?" | Third-party inspection via Alibaba costs $200 for China inspections. Worth it for first order to catch issues.
IP Protection | Ensure supplier doesn't sell your custom design to others | "All custom designs, patterns, and specifications we provide are our exclusive intellectual property. Please confirm you will not reproduce or sell our designs to any other party." | Without this, suppliers can sell your exact product to competitors. Include in Trade Assurance contract terms.
Shipping Terms | Clarify DDP vs FOB vs EXW and who handles customs/duties | "Can you ship DDP (Delivered Duty Paid) to [your address]? If not, what shipping terms do you offer for small orders?" | DDP = supplier handles everything (simplest for you). FOB = you arrange freight from Chinese port. For 300 units, DDP is usually best.
Timeline Buffer | Add 1-2 weeks to stated lead time in your planning | If supplier says "15-20 days production": plan for 25-30 days in your timeline. | Suppliers almost always underestimate. Chinese holidays (CNY, Golden Week, Mid-Autumn) can add 2-4 weeks. Always buffer.