## P10A EXEC SUMMARY
P10A HOME FULFILLMENT OPERATIONS — EXECUTIVE SUMMARY
4 Tasks ¦ Weeks 4-8 ¦ Cost: $50-$250 ¦ Your spare room is your warehouse. Optimize it like one.
Task ID | Task | KPI | Deliverable | Status | Why Fulfillment Ops Matter | Cost / Time
10A.01 | Set up home fulfillment station: packing table, label printer, organized shelving | Station operational + photo documented | Complete home fulfillment station guide: equipment list (table, shelving, printer, supplies), layout optimization for 90-second-per-order workflow (P3C.05), SKU organization system (8 variants × 2 attributes = label every shelf position), and a photo-documented setup for reference when scaling or delegating. Total equipment cost: $50-$250 depending on whether you use existing furniture or buy purpose-built shelving. The station handles up to 20 orders/day before a 3PL becomes more efficient. | COMPLETE ✓ | A disorganized packing station adds 2-3 minutes per order. At 10 orders/day: that's 20-30 minutes/day WASTED searching for the right SKU, finding tape, or reprinting labels. An optimized station (90 seconds/order) at 10 orders/day: 15 minutes total. The difference over a month: 10 hours saved. Over a year: 120 hours. The $50-$250 setup investment pays for itself in saved time within the first week of fulfillment. | $50-$250 one-time (shelving $30-$80, label printer $0-$200, supplies $20-$50). Ongoing: $15-$30/month for consumables (labels, tape, mailers).
10A.02 | Configure Shopify Shipping: labels, tracking emails, carrier setup | Shopify Shipping fully configured | Complete Shopify Shipping configuration: buy USPS labels directly in Shopify (20-40% discount vs retail USPS rates), automatic tracking email to customer when order is fulfilled, carrier accounts connected (USPS primary, UPS/DHL as backup for international), and label printing workflow (direct to thermal printer or PDF to regular printer). Shopify Shipping eliminates: trips to the post office for label purchases, manual tracking number entry, and carrier rate comparison — everything happens in 3 clicks within Shopify Admin. | COMPLETE ✓ | Shopify Shipping saves: $1-$2 per label (discounted rates vs retail), 5 minutes per order (no manual tracking entry), and 30 minutes/day (no post office trips — schedule USPS pickup from home). At 10 orders/day: Shopify Shipping saves ~$15/day in rate discounts + ~45 minutes/day in labor. The ROI is immediate and permanent. | $0 (Shopify Shipping is included in all Shopify plans). Label printing: $0 if using regular printer, $200 one-time for thermal printer (Rollo, recommended at 5+ orders/day).
10A.03 | Create SOP for order fulfillment: pick → QC → pack → label → ship → update | Fulfillment SOP documented | Complete step-by-step fulfillment SOP: the 10-step workflow from P3C.05 expanded into a trainable document with: decision points (what to do if an item is damaged, if a variant is out of stock, if the order has a note), quality checks (verify SKU matches order before sealing), and the critical handwritten-note trigger (first 20 orders + VIP orders + orders with personal messages). This SOP is the DELEGATION DOCUMENT — when you hire a VA or part-time packer, you hand them this SOP and they can fulfill orders on Day 1. | COMPLETE ✓ | Without an SOP: only YOU can fulfill orders (you hold the process in your head). With an SOP: anyone can fulfill orders correctly by following the document. This is the difference between a business that depends on the founder's presence for every shipment and a business that runs when the founder takes a day off. The SOP is written once and used thousands of times — the highest-leverage document in operations. | $0 (documentation). Time: 1 hour to write. Value: enables delegation, prevents errors, ensures consistency across 1,000+ orders.
10A.04 | Set fulfillment targets: same-day for orders before 2 PM, next-day for afternoon | Targets set + tracking operational | Complete fulfillment target framework: same-day shipping for orders placed before 2 PM EST (customers receive tracking within 4-8 hours of ordering), next-business-day for afternoon/weekend orders (tracking within 24 hours). These targets are tracked weekly in the P6E.01 KPI dashboard. The target is a PROMISE to yourself and your customers — it sets the standard that builds the "ships fast" reputation from Day 1. Tracking: average time from order placement to "fulfilled" status in Shopify. | COMPLETE ✓ | Fast shipping is the #1 controllable factor in customer satisfaction for D2C brands. Customers who receive tracking within hours: 3× more likely to leave a 5-star review mentioning "fast shipping." Customers who wait 3+ days for tracking: 2× more likely to email "where's my order?" (which costs YOU 5 minutes in support time). The fulfillment target is both a service standard and a cost-reduction strategy (fewer support tickets = less time on email). | $0 (target-setting). Time: 5 min to define + weekly tracking in KPI dashboard.

## 10A.01-02 Station + Shipping
P10A TASKS 10A.01-02: HOME FULFILLMENT STATION + SHOPIFY SHIPPING CONFIGURATION
$50-$250 for the station. $0 for Shopify Shipping. Together: a mini-warehouse that processes 20 orders/day in under an hour.
Element | Details | Cost | Why | Setup | Capacity | Notes
10A.01: HOME FULFILLMENT STATION — equipment, layout, and SKU organization
Packing Table | A dedicated flat surface at standing or comfortable sitting height. Minimum: 4' × 2' (120cm × 60cm). Enough space for: laptop (Shopify open), label printer, current order's items, packing supplies within arm's reach. Options: • Existing desk or dining table (free — repurpose what you have) • Folding table from Walmart/IKEA ($30-$50 — portable, stores flat) • Standing desk converter ($80-$150 — ergonomic for high-volume days) The table should be DEDICATED to fulfillment (not shared with meals or work). Even if it's a folding table that you set up and break down: it has a defined purpose. | $0-$150 (depends on what you already own) | Ergonomics matter when you're packing 10-30 orders in a session. A too-low table causes back strain. A cluttered table causes errors (wrong SKU grabbed). A dedicated, organized table = faster packing + fewer mistakes + less physical fatigue. | 1. Choose location: spare room, garage, or dedicated corner of a room. Needs: power outlet (printer + laptop), proximity to inventory shelving, and enough floor space for outgoing mail pile. 2. Set up table at comfortable height 3. Position: laptop on left (or right if left-handed), printer behind laptop, packing supplies on right, outgoing pile on floor or adjacent surface 4. Test: can you reach every supply without standing up or walking? If not: rearrange until everything is within arm's reach. | Handles up to 20 orders/day comfortably. Above 20/day: consider 3PL (P10B.04) or hiring part-time help (P11D.02). | Take a PHOTO of your completed station setup. This photo becomes: (1) the reference for resetting after disruption, (2) the visual guide for anyone you delegate packing to, and (3) BTS content for social media ("behind the scenes of a D2C brand").
Inventory Shelving | Organized shelving for 8 SKUs (4 colors × 2 sizes): • Each SKU gets its own labeled shelf position or bin • Labels: "BLK-SM", "BLK-LX", "RSE-SM", "RSE-LX", "SGE-SM", "SGE-LX", "OCN-SM", "OCN-LX" • Arrange by: color (vertical columns) × size (horizontal rows) — creates a visual grid Options: • Wire shelving unit ($30-$60 from Amazon/Walmart — the 4-tier chrome units work perfectly) • Stackable bins ($20-$40 for 8 bins) • Existing bookshelf or closet shelving (free) The shelving should be NEXT TO the packing table (within 1 step). Every step you add between shelf and table = wasted time × 1,000 orders. | $0-$60 (shelving unit) | The 1-step rule: you should be able to grab any SKU and return to the packing table in 1 step (no walking across the room). This saves 5-10 seconds per order × 10 orders/day × 300 days = 4-8 hours/year. Labeled positions prevent: grabbing the wrong color (Black vs Deep Ocean look similar in a dim garage), grabbing the wrong size (S/M and L/XL are identical except for the label), and miscounting inventory (labeled positions make physical counts easier). | 1. Assemble shelving unit next to packing table 2. Create labels for all 8 SKUs: print on paper, tape to shelf edge 3. Organize: top shelf = S/M (4 colors left to right: BLK, RSE, SGE, OCN). Bottom shelf = L/XL (same order). 4. Stock: place inventory on shelves per P3C.04 receiving protocol 5. Verify: every shelf matches its label, every belt is in the correct position 6. Restock weekly: move inventory from storage cartons to shelving as shelf stock depletes | 600 units across 8 SKUs fits on a single 4-tier wire shelving unit (75 units per shelf position = ~10 stacked belts each). | Keep BULK STORAGE (unopened factory cartons) separate from SHELF STOCK (ready to pick). Shelf stock = one week's worth of each SKU. Restock from bulk weekly during your Sunday inventory reconciliation (P7D.01).
Label Printer | TWO OPTIONS: OPTION A — Regular printer (free if you already own one): Print Shopify labels as PDF → print on regular paper → cut → tape to mailer. Pros: $0 cost. Cons: slower (cut + tape), uses ink, less professional appearance. OPTION B — Thermal label printer ($100-$200, recommended at 5+ orders/day): Rollo printer ($200) or MUNBYN ($100-$150). Prints 4×6 shipping labels directly — peel and stick. Pros: 10 seconds per label (vs 30 seconds cut+tape), no ink costs (thermal = no cartridges), professional appearance. Cons: upfront cost. RECOMMENDATION: start with Option A. Upgrade to thermal when consistently doing 5+ orders/day (the time savings justify the cost at that volume). | $0 (regular) or $100-$200 (thermal) | At 5 orders/day with regular printer: 5 × 30 sec extra (cut + tape) = 2.5 min/day = 12.5 min/week = 10+ hours/year of cutting and taping labels. Thermal printer eliminates this entirely: print → peel → stick → done. At 10+ orders/day: the thermal printer pays for itself in 2 months through time savings alone. | OPTION A: Shopify → Orders → order → Buy shipping label → Download PDF → print → cut → tape to mailer. OPTION B: Shopify → Orders → order → Buy shipping label → prints directly to Rollo/MUNBYN → peel → stick to mailer. Setup: Rollo plugs into laptop via USB. Install Rollo driver. In Shopify: Settings → Shipping → Label format → 4×6. Test print. | Regular printer: unlimited capacity (paper + ink). Thermal printer: 1 roll = 250-500 labels ($15-$20). At 10 orders/day: 1 roll lasts 25-50 days. | Shopify Shipping label rates (USPS Priority Mail): $4.00-$5.50 per domestic label. This is 20-40% cheaper than retail USPS rates. You MUST buy labels through Shopify to get the discount — don't buy postage at the post office.
Packing Supplies Station | Keep ALL supplies within arm's reach of the packing table: • Poly mailers (10×13" for the belt — order 100-pack from Amazon $15-$20) • Brand stickers (seal the mailer — from P2C.03, reorder in batches of 500) • Insert cards (from P2C.03, keep a stack of 50 on the table at all times) • Thank-you cards + pen (for handwritten notes — first 20 orders + VIP orders) • Tape (backup — poly mailers are self-sealing but tape reinforces) • Scissors (for cutting labels if using regular printer) • Notepad (for jotting order notes, flagging issues) RESTOCK TRIGGER: when any supply drops below 1 week's worth (20-30 units), reorder immediately. Running out of mailers mid-packing-session = post office trip = 45 min wasted. | $15-$30/month (mailers + stickers + insert cards + miscellaneous) | Every second of "looking for supplies" is waste. An organized supply station where everything is labeled and within reach = the 90-second-per-order target from P3C.05 is achievable. A messy station where you search for tape, walk to another room for mailers, and hunt for insert cards = 3-4 minutes per order. The difference at 10 orders/day: 15 min vs 35 min. Over a month: 7.5 hours vs 17.5 hours. Setup cost: $0 (organize what you have). | 1. Dedicate a box or drawer at arm's reach for EACH supply type 2. Label each: "MAILERS", "STICKERS", "INSERT CARDS", "NOTES + PEN" 3. Stock each with 2 weeks' worth of supplies 4. Set a "restock" calendar reminder every 2 weeks: check supply levels, reorder anything below 1 week's worth 5. Keep backup supplies in bulk storage (not on the packing table — table stays clean and organized) | Monthly supply cost at 50 orders/month: Mailers: $10 Stickers: $5 Insert cards: $5 Labels (thermal): $5 Misc: $5 Total: ~$30/mo | USPS pickup: schedule free daily pickup at usps.com/pickup. The mail carrier picks up your outgoing packages during their regular route — no post office trips needed. This saves 30+ min/day for any founder doing 3+ packages/day.
10A.02: SHOPIFY SHIPPING CONFIGURATION — buy labels, track automatically, save 20-40% on postage
Shopify Shipping Setup | Shopify Shipping lets you buy discounted USPS/UPS/DHL labels directly inside Shopify Admin. The label cost is deducted from your Shopify account balance or charged to your payment method. When you "fulfill" an order in Shopify and buy a label: Shopify automatically (1) generates the label, (2) enters the tracking number, and (3) sends the customer a "Your order has shipped" email with the tracking link. This eliminates: manual tracking number entry, separate carrier accounts, and post office label purchases. | $0 (included in all Shopify plans. Label cost: $4-$5.50 per domestic label at discounted rates.) | WITHOUT Shopify Shipping: buy label at post office ($7-$8 retail USPS Priority) → manually enter tracking number in Shopify → manually send tracking email. Time: 5-7 min per order. WITH Shopify Shipping: 3 clicks in Shopify Admin → label prints → tracking auto-sent. Time: 1-2 min per order. Plus: $2-$3 saved per label on postage. At 50 orders/month: saves $100-$150/month in postage + 3-4 hours in labor. | Shopify Admin → Settings → Shipping and delivery → Shopify Shipping: 1. Verify USPS is connected (should be by default) 2. Set package dimensions: 10" × 13" × 1" (poly mailer with belt) 3. Set package weight: 6 oz (belt + packaging) 4. Set label format: 4×6 (if thermal printer) or 8.5×11 (if regular printer) 5. TEST: go to any order → "Create shipping label" → verify: correct address, USPS Priority Mail selected, discounted rate shown → buy label → verify: tracking number auto-populated, customer email sent For international: Shopify also generates customs forms (CN22/CN23) automatically when buying international labels. HS code 4202.92 should auto-fill from product settings. | Shopify Shipping handles unlimited label volume. No caps, no minimum, no contract. | ALTERNATIVE: Pirate Ship (pirateship.com) offers the same USPS discount rates as Shopify Shipping, plus access to UPS cubic pricing (cheaper for dense, small packages). If you find Pirate Ship rates are lower for your specific package size/weight: use Pirate Ship and manually enter tracking in Shopify. But for most single-product D2C brands: Shopify Shipping is simpler and the rates are equivalent.

## 10A.03-04 SOP + Targets
P10A TASKS 10A.03-04: FULFILLMENT SOP (THE DELEGATION DOCUMENT) + SHIPPING TARGETS
10 steps, 90 seconds per order. Written once, used thousands of times. The document that lets you take a day off.
Step | Action | Time | Details | Decision Points | Quality Check | Notes
10A.03: FULFILLMENT SOP — 10 steps from Shopify notification to outgoing mail pile
1 | OPEN Shopify Admin → Orders → filter "Unfulfilled" | 5 sec | View all orders awaiting fulfillment. Sort by: oldest first (FIFO — first in, first out). Process in order of placement. | If 0 unfulfilled orders: done for this batch. Check again at next batch time (2 PM or 9 AM per P6B.03 schedule). | — | Process ALL unfulfilled orders in a single batch session. Don't cherry-pick — FIFO ensures fairness and prevents older orders from being delayed.
2 | SELECT the first unfulfilled order. READ: variant (color + size), shipping address, any order notes. | 10 sec | Click the order → read the details. Note: which SKU to pick, whether the customer left a note ("please include a handwritten note" or "gift — no receipt"), and whether there's a discount code (identifies founding members, ambassadors, VIPs). | IF order has a customer note: read it carefully. Accommodate reasonable requests (gift wrapping, include a message). IF order note says "gift": don't include pricing on the packing slip. IF order is from a founding member (HERSTRIDE20 code) or VIP: include handwritten note. | Verify: customer name + shipping address looks real (not obviously fraudulent). If suspicious: Google the address before shipping.
3 | PICK the correct belt from inventory shelving. | 10 sec | Walk to shelving → find the labeled position for [COLOR]-[SIZE] → grab one unit from the stack. | IF the shelf position is EMPTY: check Shopify inventory count. If Shopify shows 0: the variant is sold out (should not have been orderable — investigate why). If Shopify shows >0 but shelf is empty: check bulk storage cartons for unshelfed inventory. | VERIFY: the SKU label on the belt's poly bag matches the order. Read aloud: "Midnight Black, S/M" → check belt → matches? Proceed. Doesn't match? Put it back, grab the correct one. This 5-second check prevents the #1 fulfillment error (wrong variant shipped). | Wrong-variant shipments cost: $10.50 (exchange shipping) + 5 minutes (customer email) + customer frustration. The 5-second SKU check prevents 100% of this.
4 | PLACE belt on packing table. Open poly mailer. | 5 sec | Grab a poly mailer from your supply station. Open it flat on the table. | IF poly mailers are low (<10 remaining): add "reorder poly mailers" to your task list immediately. Don't wait until you're out. | —
5 | INSERT: belt + insert card. Optional: thank-you note. | 10 sec | Place belt in mailer (product label facing up so customer sees it first). Slide insert card in on top (QR code / care instructions visible). If this order qualifies for a handwritten note (first 20 orders, VIP, ambassador, customer requested): add the note card on top. | IF first 20 orders: include handwritten note per P6B.03 template. IF VIP customer (recognized from discount code or tag): include handwritten note. IF standard order after #20: insert card only (no note — saves 2 min/order at scale). | Check: is the insert card present? Is it face-up (QR code visible)? A missing insert card = a missed review request + missed referral prompt. | The handwritten note trigger should transition from "first 20 orders" to "VIP + ambassador + special request only" after Month 1. Scale demands efficiency.
6 | SEAL mailer with brand sticker. | 5 sec | Peel brand sticker → place over mailer's adhesive strip seal. The sticker serves double duty: sealing the mailer AND branding the package. | IF brand stickers run out: use the mailer's built-in adhesive seal (still secure, just not branded). Reorder stickers immediately. | — | The brand sticker is a small detail that signals: "a real brand packed this, not a dropshipper." It costs $0.10 per sticker and adds perceived value worth 100× that.
7 | BUY SHIPPING LABEL in Shopify. | 15 sec | In the order: click "Create shipping label" → verify address + carrier (USPS Priority Mail) + rate → "Buy label" → label generates. | IF address is undeliverable (Shopify shows a warning): contact customer via email before shipping. "Your address couldn't be verified — can you confirm [ADDRESS]?" IF international order: verify customs form auto-generated with HS code 4202.92 and declared value $34.99. | Verify: shipping address on the label matches the order. A label printed for the wrong address = a lost package + a replacement shipment at your cost. | Shopify automatically sends the tracking email to the customer the moment you buy the label + mark as fulfilled. No manual email needed.
8 | PRINT + ATTACH label to mailer. | 10 sec | Thermal printer: peel label, stick to mailer (center, flat, no wrinkles). Regular printer: print PDF, cut, tape to mailer. | IF printer jams or runs out of labels: have backup label stock nearby. If printer fails entirely: print label as PDF on regular paper and tape. Don't let a printer issue delay an entire batch. | Verify: label is flat, legible, barcode is not covered or wrinkled. USPS scanners can't read wrinkled barcodes → package gets lost.
9 | MARK ORDER AS FULFILLED in Shopify. | 10 sec | In the order: "Mark as fulfilled" → Shopify automatically updates: order status, inventory count (-1 unit), and sends tracking email to customer. | IF you already bought the label in Step 7: Shopify may auto-mark as fulfilled. Verify the status changed. If not: manually mark. | Verify: order status = "Fulfilled." Inventory count for that SKU decreased by 1. | This step is critical for inventory accuracy. A fulfilled order that isn't marked in Shopify = inventory mismatch that compounds over time.
10 | PLACE mailer in outgoing pile. Move to next order. | 5 sec | Place the sealed, labeled mailer on your outgoing pile (a shelf, bin, or designated floor area near the front door). When the batch is complete: schedule USPS pickup or drive to the post office. | IF this is the last order in the batch: schedule USPS pickup (usps.com/pickup, free) for same-day or next-morning collection. IF you do 2 batches/day (2 PM + 9 AM): combine both batches into a single daily pickup. | Final count: number of packages in outgoing pile should match number of orders fulfilled in this batch. Mismatch = a package was missed. | USPS pickup is free and saves 30+ minutes vs driving to the post office. Schedule it as a daily recurring pickup when you're consistently shipping 3+ packages/day.
TOTAL TIME PER ORDER: 90 seconds (Steps 1-10). BATCH OF 10: ~15 minutes. BATCH OF 30: ~45 minutes.
10A.04: FULFILLMENT TARGETS — the service standard that builds reputation
TARGET 1 | Orders placed before 2:00 PM EST: ship SAME DAY. | — | The customer receives tracking within 4-8 hours of ordering. This speed creates: "wow, that was fast!" reactions, shipping-related 5-star reviews, reduced "where's my order?" tickets, and a reputation that spreads through word-of-mouth. To hit this target: run your 2 PM packing batch EVERY weekday without fail. | IF you can't make the 2 PM batch (sick, emergency, travel): ship by 9 AM the next morning (still within 24 hours). Communicate if needed: "Your order is packed and shipping first thing tomorrow morning!" | Track in P6E.01 KPI dashboard: average hours from order placement to "Fulfilled" status. Target: <8 hours for pre-2PM orders. | This target is ambitious for a solo founder but ACHIEVABLE with a dedicated packing station and batched workflow. The key: treat the 2 PM batch as a non-negotiable daily commitment, like a workout.
TARGET 2 | Orders placed after 2:00 PM or on weekends: ship NEXT BUSINESS DAY by 9:00 AM. | — | The customer receives tracking within 24 hours maximum. For a 7 PM Friday order: ships Monday morning (the only acceptable delay is weekends/holidays). To hit this target: run your 9 AM packing batch EVERY weekday morning. | IF a batch exceeds 15 orders (high-volume day): prioritize oldest orders first. If you can't finish all in one session: complete by end of day (still within 24 hours for most). | Track: % of orders shipped within 24 hours. Target: 95%+ (5% allowance for weekends and genuinely exceptional circumstances). | At peak volume (post-viral-TikTok, post-sale event): you may need to add a third batch (evening session). This is a good problem to have — it means the business is growing.

## 10A FOUNDER ACTIONS
P10A HOME FULFILLMENT — FOUNDER ACTION CHECKLIST
Week 4-5: build station + configure Shopify Shipping (2-3 hrs). Week 6: write SOP (1 hr). Daily: fulfillment batches (15-45 min depending on volume).
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 4-5: STATION + SHIPPING SETUP
🔴 #1 | Build and organize home fulfillment station | 1-2 hrs + supply delivery | $50-$250 | 1. Choose location: spare room, garage corner, or dedicated area with power + proximity to front door (for pickups) 2. Set up packing table at comfortable height, position near inventory shelving 3. Assemble shelving unit (or designate existing shelves) → label all 8 SKU positions 4. Stock shelving with current inventory (organized per P3C.04) 5. Set up supply station: mailers, stickers, insert cards, note cards, pen, tape, scissors — all within arm's reach 6. If doing 5+ orders/day: purchase thermal label printer (Rollo $200 or MUNBYN $100) 7. Take a photo of the completed station for reference 8. Test: process a mock order through the full 10-step SOP — time yourself. Target: 90 seconds.
🔴 #2 | Configure Shopify Shipping + test label purchase | 30 min | $0 | 1. Shopify → Settings → Shipping → verify USPS connected 2. Set package: 10"×13"×1", 6 oz 3. Set label format: 4×6 (thermal) or 8.5×11 (regular printer) 4. Test: go to any order → Create shipping label → verify: correct rate (should be $4-$5.50, not $7-$8) → buy test label → verify: prints correctly, tracking number auto-populated, customer notification email sent 5. For international: verify customs form auto-generates with HS code 4202.92 6. Set up USPS daily recurring pickup: usps.com/pickup → schedule for your address → recurring daily
WEEK 6: SOP + TARGETS
🟡 #3 | Write the fulfillment SOP and set shipping targets | 1 hr | $0 | 1. Copy the 10-step SOP from Sheet 10A.03-04 into a Google Doc: "StrideHer Fulfillment SOP" 2. Customize: add YOUR specific details (return address, which orders get handwritten notes, your batch times) 3. Add decision points: what to do for each edge case (wrong address, out of stock variant, customer note, international order) 4. Define targets: same-day for pre-2PM, next-morning for post-2PM/weekends 5. Print and post at your packing station (physical reference while packing) 6. Add "Ship time" to P6E.01 KPI dashboard: track average hours from order → fulfilled weekly 7. This SOP is your DELEGATION DOCUMENT: when you hire a VA or packer, you hand them this doc on Day 1.
DAILY: FULFILLMENT OPERATIONS
🟡 #4 | Daily fulfillment batches: 2 PM + 9 AM next morning | 15-45 min/day (depends on volume) | $4-$5.50 per label | DAILY ROUTINE: 9:00 AM BATCH: process all orders from yesterday afternoon + overnight. 1. Open Shopify → Orders → Unfulfilled 2. Process each order through the 10-step SOP 3. Schedule USPS pickup for 12 PM (or place in mailbox for carrier) 2:00 PM BATCH: process all orders from this morning. 1. Same 10-step process 2. Schedule USPS pickup for 4-5 PM or combine with tomorrow's 9 AM batch Weekends: check for orders Saturday evening. If >5 accumulated: do a quick Sunday evening batch so Monday morning isn't overwhelming. Track: total orders fulfilled today, average time per order, any issues encountered.