## Risk Matrix Visual
P17 RISK REGISTER — PROBABILITY × IMPACT MATRIX
20 risks mapped on a 5×5 grid. Red = act now. Orange = monitor closely. Yellow = awareness. Green = accept.
PROBABILITY → |  | Very Low (5-10%) | Low (10-25%) | Medium (25-50%) | High (50-75%) | Very High (75-90%)
I M P A C T ↓ | Catastrophic | R5 | R20
| Major |  | R1 | R3,R4 | R6
| Moderate | R16 | R7,R8 | R2,R9 | R10 | R11
| Minor |  | R12 | R13,R14 | R15
| Negligible |  |  | R17 | R18,R19
| LEGEND: | RED = Critical risk — act immediately | ORANGE = High risk — monitor + prepare | YELLOW = Medium risk — awareness | GREEN = Low risk — accept

## Risk Register (20 Risks)
20 BUSINESS RISKS — PROBABILITY × IMPACT × MITIGATION × MONITORING
Each risk: what could happen, how likely, how bad, what to do about it, how to detect it early, and which workbook has the relevant protocol.
ID | Risk | Category | Probability | Impact | Risk Score | Mitigation Plan | Early Warning Signal | Cross-Ref
R1 | Competitor launches a women-specific running belt (FlipBelt Women, SPIbelt Her, or new brand) | Competitive | Low (10-25%) | Major | 🟠 HIGH | MITIGATION: Speed is your moat, not a patent. By the time a competitor launches, you should have: 200+ reviews, 5,000+ social followers, 50+ ambassador relationships, SEO authority for "women's running belt," and brand recognition that takes 12-18 months to replicate. RESPONSE IF IT HAPPENS: (1) do NOT panic-discount — compete on brand, not price, (2) analyze their product: what's better? worse? different?, (3) accelerate v2 improvements to maintain product superiority, (4) double down on community — your relationship with customers is the hardest thing to copy, (5) consider a comparison page on your blog (fair, specific, honest — shows confidence). | Google Alerts for "women running belt" + "women's running belt." Monthly Amazon search for new competitors in the category. Watch FlipBelt/SPIbelt social accounts for women-specific product announcements. | P0A Competitive Intelligence P11A Product Expansion
R2 | TikTok algorithm change reduces organic reach by 50%+ | Marketing | Medium (25-50%) | Moderate | 🟠 HIGH | MITIGATION: NEVER depend on a single platform. StrideHer's plan is deliberately multi-channel: TikTok + Instagram + email + SEO + Amazon + expos + referrals. If TikTok reach drops 50%: the other 6 channels continue. RESPONSE: (1) shift content effort to Instagram Reels (similar format, different algorithm), (2) increase email marketing frequency (owned channel, no algorithm), (3) invest more in SEO/blog content (compounds regardless of social algorithms), (4) explore YouTube Shorts (growing platform for running content). PREVENTION: build your email list aggressively — every TikTok follower should become an email subscriber. You OWN your email list. You RENT your social following. | Weekly: compare TikTok video views this week vs 4-week average. If views drop >40% for 2 consecutive weeks without a content quality change: algorithm shift likely. | P5B Content Strategy P4B Email P4D SEO
R3 | Supplier raises prices 15-25% on next PO (material costs, labor, MOQ change) | Supply Chain | Medium (25-50%) | Major | 🟠 HIGH | MITIGATION: (1) Negotiate: "We're a growing brand planning to scale to 1,000+ units/run. Can you hold pricing for 3 POs in exchange for volume commitment?", (2) Get competitive quotes from P0D backup suppliers BEFORE your reorder — negotiation leverage, (3) If price increase is unavoidable: absorb the first increase (margin drops from 50% to 45% — still healthy) and raise retail price on the NEXT reorder ($34.99 to $37.99), (4) Reduce COGS elsewhere: cheaper packaging supplier, lighter shipping materials, negotiate freight rates. PREVENTION: lock pricing for 2-3 POs in your P8D.01 supplier agreement (Clause 4: "Pricing valid for orders placed within 12 months of agreement date"). | Ask supplier for pricing confirmation 60 days before each reorder: "We're planning to reorder 600-800 units in [MONTH]. Please confirm current pricing." Any price increase signal gives you time to negotiate or source alternatives. | P0D Supplier Scouting P8D.01 Supplier Agreement P7D Reorder
R4 | Factory goes offline (fire, COVID lockdown, bankruptcy, unresponsive) | Supply Chain | Medium (25-50%) | Major | 🟠 HIGH | MITIGATION: fully documented in P10CD G7 Supply Chain Disruption SOP. Key actions: (1) maintain 2 backup suppliers from P0D with current contact info and confirmed capability, (2) keep safety stock at 338 units (45-60 day buffer), (3) activate backup supplier within 48 hours of factory going dark, (4) air freight 100-200 units if stockout is imminent ($3-5/unit premium). PREVENTION: monthly check-in with factory contact (even when no PO is active). Strong relationship = early warning of problems. | Factory stops responding to WeChat/email for 48+ hours. Or: supplier mentions "capacity issues," "material shortages," or "government inspection" — these are early signals of potential disruption. | P10CD G7 Supply Chain Disruption SOP P0D Backup Suppliers
R5 | Product recall required (safety defect discovered post-sale) | Legal/Safety | Very Low (5-10%) | Catastrophic | 🟠 HIGH | MITIGATION: fully documented in P8D G6 Product Recall Protocol. 4 phases: Contain (1 hour) → Investigate (48 hours) → Notify (72 hours) → Remediate (1-4 weeks). Key prevention: P2E quality standards + P3B pre-shipment inspection at AQL 2.5 catch 97%+ of defects before they reach customers. Product liability insurance (P8A.04, $300-500/year) covers legal defense + settlements. For a textile running belt with no electronics: recall probability is <0.1%. | 3+ customer reports of the SAME safety-related defect. Track in P9D return tracker — the defect category column is the early warning system. | P8D G6 Product Recall Protocol P2E Quality P3B Inspection P8A.04 Insurance
R6 | Cash flow crisis: expenses exceed revenue, cash reserve depleted | Financial | High (50-75%) | Major | 🔴 CRITICAL | MITIGATION: the P7B.03 budget includes $2,000 contingency (20% of budget). The P16 pessimistic scenario maps this risk in detail with 5 escalating interventions. Key actions: (1) monthly cash position tracking (P15 Cash Position sheet), (2) minimum 3-month runway maintained at all times, (3) if runway drops below 2 months: IMMEDIATELY pause all discretionary spend (ads, tools, events), (4) preservation mode: $200/month burn rate = 10+ months runway on $2,000, (5) personal bridge loan to LLC as Owner Capital Contribution (documented in Wave) as last resort. PREVENTION: don't overspend in Month 1-2 excitement. Follow the P7B.03 budget EXACTLY. | P15 Cash Position tracker: if closing balance trends toward <$2,000 within 2 months. P7B.04 monthly review: if net cash flow is negative for 3 consecutive months. | P7B Cash Flow P16 Pessimistic Scenario P15 Cash Position Tracker
R7 | USPS rate increase (annual, typically January) | Operations | Low (10-25%) | Moderate | 🟡 MEDIUM | MITIGATION: USPS raises rates 3-7% annually (January). A $0.25-0.50/package increase on 100 orders/month = $25-50/month margin erosion. Actions: (1) absorb the first year's increase (margin impact is <1%), (2) if cumulative increases exceed $1.00/package: evaluate Pirate Ship rates (sometimes cheaper than Shopify Shipping for specific package sizes), (3) consider DHL eCommerce for international (often cheaper than USPS FCPI after rate increases), (4) if free shipping becomes unsustainable: introduce a minimum order threshold ("Free shipping on orders over $30"). PREVENTION: budget 5% annual shipping cost increase in financial projections. | USPS publishes rate changes 60-90 days before implementation. Subscribe to USPS business updates. Pirate Ship blog also covers rate change analysis. | P10A Shopify Shipping P7C Shipping Rates P7B Unit Economics
R8 | Customs delay or duty rate increase on Chinese imports | Operations | Low (10-25%) | Moderate | 🟡 MEDIUM | MITIGATION: documented in P10CD G7 Scenario C (Customs Hold). Key actions: (1) maintain a "customs emergency file" with all documents ready, (2) respond to customs requests within 4 hours, (3) if duties increase: absorb if <5% increase, pass to COGS if >5%, (4) if persistent customs issues: consider routing through a different port or using a different customs broker. PREVENTION: verify HS code 4202.92 is correct (wrong HS code = higher duties or inspections). Maintain relationship with customs broker. | Freight forwarder alerts you to policy changes. Watch trade news for US-China tariff developments. Customs broker can flag rate changes proactively. | P10CD G7 Customs Hold P3C Shipping Logistics
R9 | Negative viral review or social media post damages brand reputation | Marketing | Medium (25-50%) | Moderate | 🟠 HIGH | MITIGATION: (1) respond within 6 hours — founder personally, not a template (P9B.04 1-star response protocol), (2) offer FULL resolution publicly (refund + replacement + personal apology), (3) do NOT argue, do NOT delete (deletion makes it worse), (4) if genuinely unfair or false: reply factually and let other reviews speak for themselves, (5) mobilize ambassadors — loyal customers often defend the brand voluntarily in comments. PREVENTION: excellent product quality (reduce defects to <2%) + fast support response (<4 hours) + generous returns policy = minimizes the ammunition for negative reviews. Most viral negative reviews happen when companies IGNORE complaints or make the customer fight for resolution. | Google Alert for "StrideHer." Social media monitoring: search brand name daily during the first 3 months. Judge.me notification for 1-2 star reviews (respond within 6 hours). | P9B.04 Review Response (1-star template) P9A Support Templates
R10 | Slow organic growth: social followers and email list grow slower than projected | Marketing | High (50-75%) | Moderate | 🟠 HIGH | MITIGATION: organic growth is the SLOWEST channel. The plan already accounts for this with paid ads (P6C/P6D) driving traffic while organic compounds in the background. If organic is slower than expected: (1) increase posting frequency temporarily (2x/day for 30 days), (2) invest in engagement over broadcasting (comment on 50 running accounts/day, DM 10 prospects/day), (3) run a giveaway ("Follow + tag a running friend = chance to win a StrideHer belt"), (4) leverage parkrun + local running events for IRL follower acquisition, (5) collaborate with 2-3 similar-sized running accounts for cross-promotion. PREVENTION: start organic building 4 weeks before launch (P13 Phase 1). The head start matters. | Track weekly: follower growth rate. If <2% week-over-week growth for 4 consecutive weeks: organic strategy needs a boost. Compare: email list growth rate (should be 5-10% weekly via popups + content upgrades). | P5B Content Strategy P1E Pre-Launch Community P5C Events
R11 | Sizing-related returns exceed 10% (wrong size is #1 return reason) | Product | Very High (75-90%) | Moderate | 🔴 CRITICAL | MITIGATION: the most PREDICTABLE risk — and the most preventable. Actions: (1) enhance size guide with fit photos on diverse bodies (P9A.05), (2) add "Find Your Size" button prominent on product page, (3) add size quiz (Kiwi Size Chart free app), (4) add reassurance: "Free size exchanges — we'll ship the right size today," (5) in the 33" overlap zone: explicitly recommend L/XL, (6) track return reasons weekly (P9D) — if sizing returns >8% for 2 weeks: the size guide needs IMMEDIATE improvement. PREVENTION: the size guide is the #1 ROI investment for reducing returns. Every hour spent improving it saves 10+ hours of return processing and $100+ in lost revenue. | P9D return tracker: "wrong size" category >8% of orders for 2 consecutive weeks. P9A support emails: if >50% of tickets are sizing questions, the pre-purchase experience is failing. | P9A.05 Size Tool P9D Returns P2D Size Guide P6E A/B Test #5
R12 | Shopify platform outage during peak sales period | Technical | Low (10-25%) | Minor | 🟡 MEDIUM | MITIGATION: Shopify's uptime is 99.98% (15 min/month average downtime). During major outages (rare, 1-2 per year): (1) check status.shopify.com for updates, (2) communicate to customers via social: "Our store is temporarily experiencing issues — we're working on it. In the meantime, DM us to place an order!", (3) take orders via DM/email manually if the outage is during a promotion, (4) DO NOT switch platforms reactively. PREVENTION: none needed — Shopify's infrastructure is enterprise-grade. Diversifying to Amazon (P4E) provides a backup sales channel during Shopify outages. | status.shopify.com — bookmark and check during any suspected issue. Shopify sends email alerts for major incidents. | P4A Shopify Setup P4E Amazon (backup channel)
R13 | Currency fluctuation impacts international pricing or supplier costs | Financial | Medium (25-50%) | Minor | 🟡 MEDIUM | MITIGATION: (1) Shopify Markets auto-adjusts displayed prices to local currency — you receive USD regardless of what the customer pays, (2) Shopify's FX rate includes a 1.5% markup — this is the cost of currency convenience, (3) for supplier payments: Wise uses mid-market rates with 0.5-0.7% fee (minimizes FX exposure on the COGS side), (4) if USD weakens significantly: your product becomes cheaper for international customers (good for sales, neutral for margin). If USD strengthens: international sales may slow (consider temporary international discount). PREVENTION: price in USD, sell globally, let Shopify and Wise handle conversion. Don't try to manage FX risk at this scale. | Monthly: check USD/GBP and USD/AUD rates. If USD moves >10% in a quarter: evaluate impact on international order volume and supplier payment costs. | P7C Multi- Currency Payments
R14 | International shipping delays exceed published timelines consistently | Operations | Medium (25-50%) | Minor | 🟡 MEDIUM | MITIGATION: (1) set CONSERVATIVE delivery estimates in shipping policy (promise 14-21 days, deliver in 10-14 = delight), (2) if a specific route is consistently slow: update the shipping FAQ with realistic timelines + add "International tracking may show limited updates" note, (3) at 20+ orders/month from one country: evaluate regional 3PL (P11C.03) to convert international into domestic delivery, (4) consider DHL eCommerce upgrade for better tracking + faster delivery (P10B.01). PREVENTION: the P10B.03 test shipments validate your estimates BEFORE customers experience them. | P9A support tickets: if >20% of international orders generate a "where's my order" email. Monthly: compare actual delivery times (from tracking data) to published estimates. | P10B Intl Shipping P7C Shipping Policy P11C Regional 3PL
R15 | Meta/Google ad fatigue: conversion rate declines as audience sees the same ads repeatedly | Marketing | High (50-75%) | Minor | 🟡 MEDIUM | MITIGATION: (1) refresh ad creative every 4-6 weeks (new images, new videos, new copy angles), (2) rotate between 3-5 active creatives at any time (P6C.03), (3) mine reviews for fresh customer language every 2-3 months (P6E.04), (4) test new ad formats (carousel, slideshow, story ads, Reels ads), (5) expand audience targeting periodically (new interest groups, new LAL seeds). PREVENTION: the P5B content batch system creates 20 pieces per batch — this provides 2-3 months of fresh creative. Ad fatigue is INEVITABLE; the solution is a creative PIPELINE, not a single evergreen ad. | Meta Ads Manager: if CTR drops >30% from baseline over 2 weeks while impressions remain stable: ad fatigue is occurring. Google Ads: declining Quality Score on existing keywords. | P6C Meta Ads P6E A/B Testing P5B Content Batch System
R16 | Product liability lawsuit from a customer claiming injury | Legal | Very Low (5-10%) | Moderate | 🟡 MEDIUM | MITIGATION: (1) product liability insurance (P8A.04, $300-500/year) covers legal defense + settlements up to $1M per occurrence / $2M aggregate, (2) the LLC structure (P8A.01) protects personal assets from business liability, (3) Terms of Service (P8C.01) limits liability to purchase price ($34.99), (4) quality standards (P2E) + pre-shipment inspection (P3B) minimize the probability of a defective product reaching a customer. For a textile running belt with no electronics, no chemical exposure, and no ingestible components: the injury risk profile is VERY LOW. PREVENTION: maintain insurance continuously once purchased (no coverage gaps). Respond promptly and generously to any injury-related complaint (the best defense against lawsuits is excellent customer service that resolves issues before they escalate). | Any customer support email mentioning "injury," "hurt," "damage," "medical," or "lawyer" = escalate to founder immediately. Do NOT use support templates for injury claims — respond personally with empathy and a generous resolution. | P8A.04 Insurance P8C.01 Terms of Service P8D G6 Recall Protocol
R17 | Domain/hosting issue (domain expires, DNS misconfiguration, SSL certificate failure) | Technical | Medium (25-50%) | Negligible | 🟢 LOW | MITIGATION: (1) set domain auto-renewal ON (registrar settings), (2) Shopify handles SSL certificates automatically — no action needed, (3) if DNS breaks: contact Shopify Support (they resolve DNS issues within hours), (4) keep registrar login credentials in 1Password (don't lose access to your own domain). PREVENTION: verify domain auto-renewal is enabled within the first week. Set a calendar reminder 30 days before domain expiration as a backup check. | Your website stops loading. Shopify sends email alerts for SSL issues. Uptime monitoring: use a free service like UptimeRobot to alert you if strideher.com goes down. | P4A Shopify Setup (domain configuration)
R18 | Seasonal demand dip (November-February for running gear) | Market | High (50-75%) | Negligible | 🟢 LOW | MITIGATION: seasonal dips are NORMAL and EXPECTED (mapped in P10C.04 reorder calendar). November-February running gear demand drops 20-30%. Actions: (1) don't panic — seasonal dips are not business failure, (2) holiday gifting angle ("the perfect gift for the runner in your life") partially offsets the dip, (3) January "new year new gear" campaign captures resolution runners, (4) reduce ad spend proportionally during slow months (preserve budget for August-September peak), (5) use slow months for: product development, content batching, and strategic planning. PREVENTION: the P16 scenario models already factor in seasonal adjustments. | Track monthly revenue vs P10C.04 seasonal factors. If revenue drops >40% in a traditionally slow month (vs >20-30% expected): the dip is deeper than seasonal — investigate other causes. | P10C.04 Reorder Calendar P16 Scenario Planning
R19 | Content creation burnout: founder runs out of ideas or energy for consistent posting | Operations | High (50-75%) | Negligible | 🟢 LOW | MITIGATION: (1) batch content creation (P5B.04): produce 20 pieces in one 4-5 hour session instead of daily creation, (2) repurpose: one run becomes a TikTok + IG Reel + Story + blog post + email, (3) UGC from customers and ambassadors replaces founder-created content over time (at 50+ customers: 2-3 organic UGC pieces/week), (4) hire a part-time content creator at Month 9-12 (P11D.02), (5) schedule "content sabbaticals": take 1 week off every 2 months — batched content covers the gap. PREVENTION: the 20-piece content batch system means you're never creating content under pressure. Batch day is planned and protected. | If posting frequency drops below 3x/week for 2 consecutive weeks: burnout is setting in. Solution: take 3 days off social completely, then batch 20 new pieces in one energized session. | P5B Content Batch System P11D Team Scaling (first content hire)
R20 | Data breach compromises customer information | Technical | Low (10-25%) | Catastrophic | 🟠 HIGH | MITIGATION: fully documented in P8C G5 Data Breach Response Plan. 5-step protocol: Contain → Assess → Notify → Remediate → Document. Key prevention: 2FA enabled on ALL business accounts (prevents 99% of credential-based breaches). Shopify Payments is PCI-compliant — credit card numbers are NOT stored in your admin (tokenized by Shopify). A breach of your admin exposes: names, emails, addresses, order history — but NOT payment data. RESPONSE: change all passwords within 1 hour, notify affected customers within 72 hours (GDPR requirement), file with EU DPA if EU customers affected. | 2FA alerts (failed login attempts). Shopify activity log: unfamiliar IP addresses or unexpected setting changes. Customer reports receiving suspicious emails "from StrideHer." | P8C G5 Data Breach Response Plan
RISK SUMMARY: 2 Critical (act now) + 6 High (monitor closely) + 7 Medium (awareness) + 3 Low (accept) + 2 Negligible