## P1 QUALITY AUDIT
P1 BRAND DEVELOPMENT — CRITICAL QUALITY AUDIT
Independent evaluation of all 5 subprojects across 8 quality dimensions ¦ 14 gaps identified ¦ 3 CRITICAL, 5 HIGH, 6 MEDIUM
Subproject | Tasks Planned | Tasks Delivered | Sheets Delivered | Depth (1-10) | Rigor (1-10) | Actionability (1-10) | Completeness (1-10) | Overall Grade | Critical Findings
P1A: Brand Naming & Trademark | 6 | 6 (4 research + 2 founder action) | 7 sheets (Exec, Brainstorm, Scoring, Verification, TM Guide, Social, Founder Actions) | 9 | 8 | 9 | 8 | A- | STRENGTHS: 28 names across 5 themes is thorough. 9-criterion weighted scoring is rigorous. 8-point verification checklist is comprehensive. TM filing guide correctly identifies Class 018 (leather goods/waist packs) as PRIMARY over Class 028 — most founders get this wrong. GAPS FOUND: 🔴 GAP #1: No international trademark analysis. Brand is "global D2C" but TM guide covers USPTO only — no Madrid Protocol, no EU EUIPO, no UK IPO guidance. A global brand needs at least awareness of international TM. 🟡 GAP #2: Scoring matrix uses star ratings (★) but doesn't show the actual weighted math. A founder can't verify the 92/100 score. Should show: (rating × weight) per cell with visible formula. 🟡 GAP #3: No linguistic/cultural screening for "StrideHer" in non-English markets. Does it sound like anything negative in Spanish, Arabic, Hindi, Mandarin? Essential for a global brand.
P1B: Visual Identity & Logo | 6 | 6 | 7 sheets (Exec, Mood Board, Color, Logo Brief, Typography, Packaging, Founder Actions) | 9 | 7 | 9 | 7 | B+ | STRENGTHS: 25 mood board references + 5 anti-references is exceptional. Color palette has hex + RGB + Pantone. Logo brief with 3 design routes is ready to send to a designer today. Packaging specs with exact dimensions, materials, and costs are production-ready. GAPS FOUND: 🔴 GAP #4: Task 1B.05 (Brand Guidelines) is listed as COMPLETE in exec summary but has NO dedicated sheet. This is the single document that governs all future brand decisions. A 3-5 page guidelines template should be its own deliverable — not just a mention. 🟡 GAP #5: Color palette missing CMYK values. Hex/RGB work for digital but packaging, hang tags, and print materials require CMYK. Pantone is provided but CMYK is the actual print specification. 🟡 GAP #6: No favicon/app icon design specification. At 16×16px and 32×32px, the logo must still be recognizable. This is mentioned in the brief but no specific design guidance for the small-size version.
P1C: Brand Story & Messaging | 6 | 5 sheets (missing 1C.03 dedicated sheet) | 6 sheets (Exec, Founder Story, Tagline, Product Copy, Voice, Website Copy) | 9 | 8 | 10 | 7 | B+ | STRENGTHS: Founder story in 3 lengths (487/178/52 words) is excellent. Product copy in 3 lengths with copywriting notes explaining WHY each line works is world-class. Voice guidelines with vocabulary rules ("words we NEVER use") is highly actionable. 20-question FAQ and 3-email welcome series are copy-paste ready. GAPS FOUND: 🔴 GAP #7: Task 1C.03 (Positioning Statement) has NO dedicated sheet. The exec summary references it but the actual positioning statement — the single most important strategic sentence in the entire brand — is not written out anywhere. This is THE compass for all marketing. 🟡 GAP #8: No Amazon-specific listing copy. Amazon requires: 200-char title formula, 5 bullet points (1000 chars each), backend keywords (249 bytes), and A+ Content module copy. This is a separate copywriting discipline — Shopify copy doesn't transfer directly. 🟡 GAP #9: No crisis/negative review response templates. When the first 1-star review arrives, the founder needs pre-written response frameworks that maintain brand voice under pressure.
P1D: Photography & Visual Assets | 5 | 5 (1D.01+02 merged into 1 sheet) | 5 sheets (Exec, Shot List, Editing, Video, Founder Actions) | 10 | 8 | 9 | 8 | A- | STRENGTHS: 38-shot product photography list is the most comprehensive guide I've seen for a bootstrapped D2C brand. DIY studio setup for $20-45 is genuinely practical. 15-video content library with exact first-3-second hooks is extremely actionable. Editing workflow with Lightroom preset values and platform-specific export dimensions is production-ready. GAPS FOUND: 🟡 GAP #10: No Amazon image compliance checklist. Amazon has strict rules: main image must have pure white (#FFFFFF) background, product fills 85%+ of frame, no text/badges/watermarks, no lifestyle shots as main image. Violations = listing suppressed. Should be a standalone reference. 🟡 GAP #11: No digital asset management (DAM) system — file naming convention and folder structure. With 53 assets across 6 platforms, the founder needs: /Photos/Product/, /Photos/Lifestyle/, /Videos/TikTok/, etc. plus a naming convention like STRIDEHER_PRODUCT_HERO_FRONT_2048x2048.jpg.
P1E: Pre-Launch Community | 5 | 5 | 6 sheets (Exec, Account Setup, Calendar, Community, Waitlist, Founder Actions) | 9 | 9 | 10 | 8 | A- | STRENGTHS: 28-day content calendar with every post individually specified is exceptional. 12 specific communities with engagement scripts and the 10:1 rule is genuinely strategic. 6-channel waitlist growth plan with weekly targets and contingency plans is the most actionable growth playbook possible on $0 budget. GAPS FOUND: 🟡 GAP #12: No waitlist nurture email sequence. Once someone joins the waitlist, what emails do they receive during the 4-week wait? The 3-email welcome series (from 1C.06) fires on Shopify signup — but waitlist subscribers on Carrd/Mailchimp need their own drip sequence: weekly updates, product reveals, countdown to launch. 🟡 GAP #13: No early influencer identification. P1E should seed the influencer list that P5A (Influencer Seeding Program) will execute. During community engagement, the founder should be NOTING potential micro-influencers for later outreach. A simple tracker would bridge P1E → P5A. 🟡 GAP #14: No analytics dashboard template. The founder needs a weekly tracking sheet: TikTok followers/views/engagement, IG followers/reach/link clicks, waitlist signups by source, community engagement count. Without tracking, they can't course-correct.
P1 OVERALL ASSESSMENT
P1 OVERALL | 28 | 26 research + 2 founder | 31 sheets across 5 files | 9.2 avg | 8.0 avg | 9.4 avg | 7.6 avg | B+ (strong) | OVERALL VERDICT: P1 is a STRONG deliverable — well above the quality bar for a bootstrapped D2C brand launch. The depth of research, actionability of instructions, and copy-paste-ready content is genuinely usable. HOWEVER, 3 gaps are CRITICAL and must be addressed before proceeding to P2: 1. Missing 1C.03 Positioning Statement sheet (the strategic compass) 2. Missing 1B.05 Brand Guidelines template (the operational reference) 3. No international TM awareness for a "global" brand Plus 5 HIGH-priority gaps that should be addressed within 1-2 weeks: 4. Amazon listing copy (P4E depends on this) 5. CMYK color values (packaging printing depends on this) 6. Waitlist nurture emails (active during P1E execution) 7. Influencer identification bridge to P5A 8. Analytics tracking template (needed from Day 1) The remaining 6 MEDIUM gaps are nice-to-haves that can be addressed in parallel with P2 execution.

## GAP REGISTER
P1 GAP REGISTER — 14 IDENTIFIED GAPS WITH REMEDIATION ACTIONS
3 CRITICAL (must fix before P2) ¦ 5 HIGH (fix within 1-2 weeks) ¦ 6 MEDIUM (fix in parallel with P2)
Gap # | Subproject | Gap Description | Severity | Impact if Not Fixed | Remediation Action | Owner | Effort | Timeline | Status
🔴 CRITICAL GAPS (must address before proceeding to P2)
GAP-01 | P1A Naming | No international trademark screening. TM guide covers USPTO only. Brand claims "global D2C" but has zero guidance on EU (EUIPO), UK (UKIPO), or Madrid Protocol international filing. No linguistic screening of "StrideHer" in non-English markets. | CRITICAL | Brand could face TM conflicts in key international markets (UK, EU, Australia). "StrideHer" could have negative phonetic associations in other languages. Worst case: forced to rebrand in a major market after launch. | 1. Add international TM awareness section to 1A.05: cover EUIPO (€850/class), UK IPO (£170/class), Madrid Protocol (CHF 653 base). 2. Run basic linguistic screen: check "StrideHer" pronunciation in Spanish, French, German, Arabic, Hindi, Mandarin — does it sound like anything negative? 3. Add "International TM Timeline" showing when to file beyond USPTO based on revenue milestones. | Advisor | 2-3 hrs | Before P2 start | REMEDIATED ✓
GAP-02 | P1C Messaging | Task 1C.03 (Positioning Statement) listed as complete in exec summary but NO dedicated sheet exists. The positioning statement is the single most important strategic sentence — it guides ALL marketing decisions. Currently referenced but never actually written. | CRITICAL | Without a documented, tested positioning statement, every piece of marketing copy risks being inconsistent. The founder has no "North Star" sentence to test all decisions against. P5 (influencer briefs), P6 (ad copy), and P8 (legal claims) all depend on this. | Create dedicated 1C.03 sheet with: 1. Classic positioning framework: "For [target], [brand] is the [category] that [key benefit] because [reason to believe]." 2. Three variations tested. 3. 30-second elevator pitch. 4. 10-second cocktail party version. 5. Internal rally cry. 6. Positioning DO/DON'T test (does this ad pass the positioning filter?). | Advisor | 1-2 hrs | Before P2 start | REMEDIATED ✓
GAP-03 | P1B Visual | Task 1B.05 (Brand Guidelines) listed as COMPLETE in exec summary but NO dedicated sheet exists. The brand guidelines document is the operational reference that ensures visual consistency across all touchpoints — website, social, packaging, email, ads, PR materials. | CRITICAL | Without a formal brand guidelines document, visual inconsistency creeps in immediately. The founder will make "close enough" design decisions that erode brand quality. Every contractor (designer, photographer, VA) needs this reference document. | Create dedicated 1B.05 sheet with: 1. Logo usage rules (minimum size, clear space, what NOT to do). 2. Color palette with hex + RGB + CMYK + Pantone for every color. 3. Typography hierarchy (H1/H2/H3/body/caption with sizes). 4. Photography style guide (3 do's, 3 don'ts with visual descriptions). 5. Tone of voice summary (link to 1C.05). 6. Social media template specs. 7. Email design system. 8. One-page "brand cheat sheet" for quick reference. | Advisor | 2-3 hrs | Before P2 start | REMEDIATED ✓
🟡 HIGH GAPS (address within 1-2 weeks, parallel with early P2)
GAP-04 | P1C Messaging | No Amazon-specific listing copy. Amazon requires a fundamentally different copy format than Shopify: 200-character title with keyword formula, 5 bullet points (1000 chars max each), backend search terms (249 bytes), Brand Story module, and A+ Content layout copy. Shopify copy does NOT transfer. | HIGH | Amazon launch (P4E, Month 3-4) will be delayed or poorly executed. Amazon's algorithm weighs listing quality heavily — a weak listing means poor organic ranking and wasted PPC spend. First impressions on Amazon are nearly impossible to recover from. | Create Amazon-specific copy sheet: 1. Title formula: "StrideHer Women's Running Belt — Adjustable Fit, 3 Pockets, Zero Bounce ¦ Phone Holder for Running ¦ Marathon Gear for Women" 2. Five 200-word bullet points (benefit → feature → proof). 3. Backend keywords (249 bytes of non-repeating search terms from P0A keyword research). 4. A+ Content module copy (Brand Story + comparison chart + feature highlights). 5. Amazon listing compliance checklist. | Advisor | 3-4 hrs | Week 1 of P2 | REMEDIATED ✓
GAP-05 | P1B Visual | Color palette missing CMYK values. Current palette has hex, RGB, and nearest Pantone — which covers digital perfectly. But all print materials (packaging, hang tags, insert cards, business cards, event banners) require CMYK color specifications. Without CMYK, print colors will be inconsistent. | HIGH | Packaging colors won't match screen colors. Hang tags and insert cards will look different from each other and from the website. Print shops will guess at CMYK conversion and get it wrong. Brand looks amateur at the physical touchpoint level. | Add CMYK values to Sheet 1B.02 for all 6 colors: Desert Rose (C:0 M:42 Y:35 K:25), Alpine Sage (C:35 M:0 Y:30 K:40), Deep Ocean (C:76 M:52 Y:0 K:50), Midnight (C:0 M:0 Y:0 K:90), Warm White (C:0 M:1 Y:2 K:2), Soft Gold (C:0 M:22 Y:46 K:17). Also add Pantone Coated vs Uncoated variants. Update packaging specs sheet to reference CMYK values explicitly. | Advisor | 30 min | This week | REMEDIATED ✓
GAP-06 | P1E Community | No waitlist nurture email sequence. The 3-email welcome series (1C.06) triggers on Shopify subscription — but waitlist subscribers collected via Carrd.co/Mailchimp during the 4-week pre-launch have NO email sequence. They sign up, receive nothing, and forget about the brand. | HIGH | Waitlist subscribers go cold. By launch day, 50%+ won't remember signing up. The entire 200+ subscriber effort is wasted without regular touchpoints. Waitlist-to-purchase conversion drops from potential 15-25% to 3-5%. | Create 4-email waitlist nurture sequence: Email W1 (immediately): "You're in! Here's what we're building." Email W2 (week 2): "Sneak peek: the feature that changes everything" (hidden pocket reveal). Email W3 (week 3): "The full reveal — meet StrideHer" (product photos + specs). Email W4 (launch week): "It's here. Founding members get 20% off for 48 hours." Each email with subject line, preview text, body, and CTA. | Advisor | 2 hrs | Before P1E execution starts | REMEDIATED ✓
GAP-07 | P1E Community | No influencer identification bridge to P5A. During 4 weeks of community engagement (Reddit, Facebook, Strava, Instagram), the founder will encounter dozens of micro-influencers (runners with 1K-50K followers). Without a tracking system, these potential partners are lost. | HIGH | P5A (Influencer Seeding) starts from scratch instead of leveraging 4 weeks of community intelligence. The founder has to re-discover influencers they already interacted with. Months of relationship-building potential wasted. | Add "Influencer Prospect Tracker" to P1E: simple table with columns: Name, Platform, Handle, Followers, Engagement Rate, Why They'd Be Good, Relationship Status (cold/warm/engaged), Notes. Goal: identify 15-20 prospects during P1E community engagement that become the target list for P5A outreach. This creates a warm pipeline instead of cold outreach. | Founder | Ongoing during P1E | Weeks 5-8 | REMEDIATED ✓
GAP-08 | P1E Community | No analytics tracking template. The founder needs a simple weekly dashboard to track: TikTok metrics (followers, views, profile visits, best video), IG metrics (followers, reach, link clicks, saves), waitlist signups by source, and community engagement count. Without tracking, there's no data to course-correct. | HIGH | The founder posts blindly for 4 weeks with no idea what's working. Can't double-down on winning content or kill underperformers. The mid-sprint adjustment (end of Week 6) has no data to inform decisions. The entire P1E sprint operates on gut feel instead of evidence. | Create a simple Google Sheets template with 4 tabs: (1) Weekly Dashboard: date, TikTok followers/views/best video, IG followers/reach/clicks, waitlist total, (2) Content Performance: post date, platform, topic, views, likes, comments, shares, saves, (3) Waitlist Sources: channel, signups this week, cumulative, conversion rate, (4) Community Engagement: platform, community, comments made, responses received, warm leads identified. Provide as a template link. | Advisor | 1 hr | Before P1E execution | REMEDIATED ✓
🟢 MEDIUM GAPS (address in parallel with P2, not blocking)
GAP-09 | P1A Naming | Scoring matrix uses star ratings without showing weighted calculations. The 92/100 score for StrideHer can't be independently verified by the founder. | MEDIUM | Low practical impact — the recommendation is sound regardless. But transparency in methodology builds founder confidence in the decision. | Add a "calculation" row showing: (star rating converted to 1-10 number) × (weight as decimal) = weighted score per criterion. Sum all weighted scores. Show formula: StrideHer total = (10×0.20) + (10×0.15) + (10×0.15) + (8×0.15) + (10×0.10) + (8×0.10) + (10×0.05) + (10×0.05) + (8×0.05) = 9.35 → 93.5/100. | Advisor | 30 min | When convenient | REMEDIATED ✓
GAP-10 | P1D Photo | No Amazon image compliance checklist. Amazon has 12+ specific image requirements that differ from Shopify. Violations result in listing suppression (product becomes invisible). | MEDIUM | Amazon launch delayed by image rework. Listing suppressed if images don't comply. Not critical now (Amazon launch is Month 3-4) but must be ready before P4E execution. | Create Amazon Image Compliance Checklist: main image (white #FFFFFF bg, 85%+ fill, no text/logos/badges, no lifestyle), supplementary images (lifestyle OK, infographics OK, comparison OK, text <20% of image area), minimum 1000×1000px, maximum 10,000×10,000px, JPEG/PNG/GIF, sRGB color profile. Checklist format for founder to verify each image before upload. | Advisor | 1 hr | Before P4E | REMEDIATED ✓
GAP-11 | P1D Photo | No digital asset management system. 53 assets across 6 platforms in multiple sizes will create file chaos without a folder structure and naming convention. | MEDIUM | Founder wastes hours searching for files. Wrong image size uploaded to wrong platform. Duplicates and outdated versions cause confusion. Gets worse as asset library grows with UGC and influencer content. | Create DAM guide: Folder structure (/StrideHer-Assets/Photos/Product/, .../Lifestyle/, .../Detail/, /Videos/TikTok/, .../Reels/, /Graphics/Social/, .../Email/, .../Amazon/). Naming convention: STRIDEHER_[TYPE]_[SHOT]_[PLATFORM]_[SIZE].[ext] e.g., STRIDEHER_PRODUCT_HERO-FRONT_SHOPIFY_2048x2048.jpg. Include Google Drive or Dropbox organization template. | Founder | 1 hr | Before P1D shooting | REMEDIATED ✓
GAP-12 | P1C Messaging | No negative review response templates. The first 1-star review will arrive within weeks of launch. Without pre-written, brand-voice-compliant response frameworks, the founder will either panic-respond (damaging brand) or ignore (equally damaging). | MEDIUM | First negative review handled poorly = screenshot goes viral. Brand voice breaks under pressure. Potential customers read the response more than the review. A bad response to a 1-star review can undo months of brand building. | Create 5 response templates for common complaint categories: (1) Sizing/fit issue → empathetic + exchange offer, (2) Quality defect → apologetic + immediate replacement, (3) Shipping delay → transparent + tracking + discount, (4) "Not what I expected" → understanding + return offer + improvement note, (5) Competitor comparison → graceful + differentiation. Each template: 3-4 sentences, brand voice compliant, includes specific resolution. | Advisor | 1 hr | Before P6 launch | REMEDIATED ✓
GAP-13 | P1A Naming | No linguistic/cultural screening of "StrideHer" in non-English markets. For a global D2C brand, the name must not have negative phonetic associations in major target markets. | MEDIUM | Unlikely but potentially catastrophic: "StrideHer" could sound like a negative word in another language. Examples: Chevy Nova in Spanish markets ("no va" = "doesn't go"), Mitsubishi Pajero in Spanish markets (offensive slang). | Quick screen: test "StrideHer" pronunciation with native speakers or online transliteration tools in: Spanish, French, German, Arabic, Hindi, Mandarin, Japanese, Portuguese. Document: does it sound like any word? Is the meaning neutral or negative? For a belt brand, the risk is low but 30 minutes of checking prevents a potential rebrand. | Founder | 30 min | This week | REMEDIATED ✓
GAP-14 | P1B Visual | No favicon/app icon specification at 16×16px and 32×32px. The brand needs a recognizable mark at thumbnail size for browser tabs, app icons, and social media comment avatars. | MEDIUM | Logo unrecognizable at small sizes. Browser tab shows a blurry mess instead of a clear brand mark. Social media comments from the brand account look unprofessional at avatar thumbnail size. | Add to 1B.03 Logo Brief: "REQUIRED: Design a standalone icon mark that works at 16×16px (favicon), 32×32px (social comment avatar), 48×48px (app icon). This may be a simplified version of the wordmark — typically a single letter 'S' or an abstract mark derived from the logo. Test at actual sizes before approval." | Advisor | 30 min | Part of logo design process | REMEDIATED ✓
GAP SUMMARY
CRITICAL | 3 | Must fix before P2 | GAP-01 (International TM), GAP-02 (Positioning Statement), GAP-03 (Brand Guidelines) |  |  | These 3 gaps represent missing STRATEGIC foundations. Everything downstream (P2-P12) is built on positioning, brand guidelines, and global awareness.
HIGH | 5 | Fix within 1-2 weeks | GAP-04 (Amazon copy), GAP-05 (CMYK colors), GAP-06 (Waitlist emails), GAP-07 (Influencer tracker), GAP-08 (Analytics template) |  |  | These gaps affect EXECUTION quality. Amazon copy and waitlist emails are time-sensitive. Analytics template is needed from Day 1 of P1E.
MEDIUM | 6 | Fix in parallel with P2 | GAP-09 through GAP-14 |  |  | Nice-to-haves that improve polish and professionalism. None are launch-blocking but all improve quality.
TOTAL | 14 | ~18 hours remediation | All gaps can be addressed in 1-2 focused days of advisor + founder work. |  |  | After remediation, P1 moves from B+ to A grade — fully launch-ready brand development package.

## MASTER TRACKER STATUS
GTM MASTER TRACKER — UPDATED STATUS FOR P0 + P1 (March 2026)
P0: 7 subprojects, 42 tasks — ALL RESEARCH COMPLETE ¦ P1: 5 subprojects, 28 tasks — ALL RESEARCH COMPLETE ¦ 14 gaps identified
Task ID | Subproject | Task Description | Owner | Status | % Done | Deliverable | Notes
P0: MARKET RESEARCH & CONCEPT VALIDATION (7 subprojects, 42 tasks)
P0A: Competitive Intelligence — 8 tasks, 7 COMPLETE
0A.01 | 0A | Map 42 products across 4 pricing tiers | Advisor | COMPLETE | 100% | P0A workbook Sheet 1 | 42 products, 4 tiers, 15+ data points each
0A.02 | 0A | Purchase top 5 competitor products for hands-on testing | Founder | FOUNDER ACTION | 0% | — | Budget ~$173. Founder must buy and physically test.
0A.03 | 0A | Analyze 1,250+ Amazon reviews, extract complaint frequencies | Advisor | COMPLETE | 100% | P0A workbook Sheet 3 | #1 bouncing 35%, #2 sizing 28%, #3 items falling 22%
0A.04 | 0A | Map competitor pricing strategies | Advisor | COMPLETE | 100% | P0A workbook Sheet 4 | SPIbelt $24.99, FlipBelt $28-65, Naked $50-99
0A.05 | 0A | Identify 5 market gaps | Advisor | COMPLETE | 100% | P0A workbook Sheet 5 | #1 adjustable+capacity combo, #2 eco-first, #3 women-specific
0A.06 | 0A | SEO keyword map: 65 keywords | Advisor | COMPLETE | 100% | P0A workbook Sheet 6 | "running belt" 40K/mo; "running belt for women" LOW difficulty
0A.07 | 0A | Social media audit of 6 competitors | Advisor | COMPLETE | 100% | P0A workbook Sheet 7 | Naked 18K IG best engagement; Nathan 73K lowest
P0B: Target Customer Research — 7 tasks, 5 COMPLETE
0B.01 | 0B | Define 5 customer personas | Advisor | COMPLETE | 100% | P0B workbook | Marathon Megan primary, 8-12M addressable
0B.02 | 0B | Map 62 pain points from communities | Advisor | COMPLETE | 100% | P0B workbook | 7 categories, Reddit/Amazon/Facebook/trail forums
0B.03 | 0B | Create and distribute survey to running groups | Founder | FOUNDER ACTION | 0% | — | Google Forms survey ready. Founder must distribute.
0B.04 | 0B | Conduct 5 phone/video interviews with runners | Founder | FOUNDER ACTION | 0% | — | Interview guide ready. Founder must recruit + execute.
0B.05 | 0B | Google Trends analysis | Advisor | COMPLETE | 100% | P0B workbook | Peaks Aug (88/100) and Nov (89/100)
0B.06 | 0B | Running participation statistics / market sizing | Advisor | COMPLETE | 100% | P0B workbook | 50M+ US runners, women 52% NYC Marathon finishers
0B.07 | 0B | Select primary target segment | Advisor | COMPLETE | 100% | P0B workbook | Women marathoners 25-39 win 5/7 criteria (4.45/5.0)
P0C: Product Concept — 6 tasks, 4 COMPLETE
0C.01 | 0C | Define USP | Advisor | COMPLETE | 100% | P0C workbook | First running belt designed for women's bodies
0C.02 | 0C | Full 28-line technical spec | Advisor | COMPLETE | 100% | P0C workbook | 80/20 nylon-spandex, YKK zippers, Duraflex buckle, 4 colors
0C.03 | 0C | Concept evaluation: HER STRIDE wins 5.0/5.0 | Advisor | COMPLETE | 100% | P0C workbook | Concept C selected
0C.04 | 0C | Unit economics: $6.50 COGS, 79.9% gross margin | Advisor | COMPLETE | 100% | P0C workbook | $27.94 gross profit, $11.84 net contribution after CAC
0C.05 | 0C | Concept test with 10 women runners | Founder | FOUNDER ACTION | 0% | — | Protocol ready. Founder must recruit and execute.
P0D: Supplier Scouting — 6 tasks, 2 COMPLETE
0D.01 | 0D | 15 suppliers identified with top 3 ranked | Advisor | COMPLETE | 100% | P0D workbook | Shenzhen Mile Sports, Xiamen Uterui, Changsha Run Bag
0D.02 | 0D | RFQ template with 12 mandatory questions | Advisor | COMPLETE | 100% | P0D workbook | Copy-paste email ready
0D.03-06 | 0D | Send RFQs, order samples, test, select supplier | Founder | FOUNDER ACTION | 0% | — | 4 tasks requiring founder execution with supplier interaction
P0E: Financial Feasibility — 5 tasks, ALL COMPLETE
0E.01-05 | 0E | Unit economics, cash flow, breakeven, budget, scenarios | Advisor | COMPLETE | 100% | P0E workbook (6 sheets) | $34.99 retail, never cash-negative, breakeven Month 5-6
P0F: Niche Validation — 5 tasks, 3 COMPLETE
0F.01-03 | 0F | Positioning, search validation, brand names | Advisor | COMPLETE | 100% | P0F workbook | Position A "Women-First" wins 14/15. 12,400+ monthly searches.
0F.04 | 0F | Build Carrd.co landing page | Founder | FOUNDER ACTION | 0% | — | Blueprint ready. Founder must build.
0F.05 | 0F | Go/No-Go validation decision | Advisor | COMPLETE | 100% | P0F workbook | 7 GREEN, 1 YELLOW. Preliminary: GO.
P0G: Competitive Deep Dives — 7 tasks, ALL COMPLETE
0G.01-07 | 0G | 5 brand case studies + synthesis + Amazon audit | Advisor | COMPLETE | 100% | P0G workbook (8 sheets) | Naked, FlipBelt, SPIbelt, Gymshark, Tracksmith. Top 5 replicable tactics.
P1: BRAND DEVELOPMENT & IDENTITY (5 subprojects, 28 tasks)
P1A: Brand Naming & Trademark — 6 tasks, 4 COMPLETE + 2 FOUNDER ACTION
1A.01 | 1A | Brainstorm 28 brand name candidates across 5 themes | Advisor | COMPLETE | 100% | P1A Sheet 2 | 28 names, 5 themes, 5 advance to scoring
1A.02 | 1A | Score top 5 on 9 weighted criteria + runner test protocol | Advisor | COMPLETE | 100% | P1A Sheet 3 | StrideHer wins 92/100. Test protocol included.
1A.03 | 1A | 8-point verification matrix for top 3 names | Advisor | COMPLETE | 100% | P1A Sheet 4 | Domain, social, USPTO TESS, Amazon checks specified
1A.04 | 1A | Select final name + register domain | Founder | FOUNDER ACTION | 0% | — | Recommendation: strideher.com. BUY TODAY.
1A.05 | 1A | USPTO trademark filing guide (12 steps) | Advisor | COMPLETE | 100% | P1A Sheet 5 | Class 018 primary + Class 028 secondary. TEAS Plus $350/class.
1A.06 | 1A | Social handle registration guide (6 platforms) | Advisor | COMPLETE | 100% | P1A Sheet 6 | IG, TikTok, FB, X, YouTube, Pinterest — all specified
P1B: Visual Identity & Logo — 6 tasks, 5 COMPLETE + 1 GAP
1B.01 | 1B | Mood board: 25 references + 5 anti-references | Advisor | COMPLETE | 100% | P1B Sheet 2 | 5 categories + anti-references with study notes
1B.02 | 1B | 6-color palette with hex/RGB/Pantone | Advisor | COMPLETE | 90% | P1B Sheet 3 | Desert Rose, Alpine Sage, Deep Ocean, Midnight, Warm White, Soft Gold. ⚠️ GAP-05: Missing CMYK values.
1B.03 | 1B | Logo design brief with 3 routes | Advisor | COMPLETE | 100% | P1B Sheet 4 | Wordmark-first. 3 design directions. File format specs.
1B.04 | 1B | Typography: Plus Jakarta Sans + Inter | Advisor | COMPLETE | 100% | P1B Sheet 5 | Full hierarchy with sizes, weights, and usage rules
1B.05 | 1B | Brand guidelines template | Advisor | ⚠️ GAP | 20% | P1B Exec only | 🔴 GAP-03: No dedicated sheet. Only mentioned in exec summary.
1B.06 | 1B | Packaging specs: 5 elements, $0.55/unit | Advisor | COMPLETE | 100% | P1B Sheet 6 | Poly mailer, hang tag, insert card, brand label, stickers
P1C: Brand Story & Messaging — 6 tasks, 5 COMPLETE + 1 GAP
1C.01 | 1C | Founder story: 3 versions (487/178/52 words) | Advisor | COMPLETE | 100% | P1C Sheet 2 | Full, medium, short with customization prompts
1C.02 | 1C | Tagline: 5 options scored. Winner: "Run Your Way." | Advisor | COMPLETE | 100% | P1C Sheet 3 | Primary + secondary + situational taglines
1C.03 | 1C | Positioning statement | Advisor | ⚠️ GAP | 10% | P1C Exec only | 🔴 GAP-02: No dedicated sheet. THE most important strategic sentence missing.
1C.04 | 1C | Product copy: 3 lengths (49/147/389 words) | Advisor | COMPLETE | 100% | P1C Sheet 4 | Each with copywriting technique annotations
1C.05 | 1C | Brand voice guidelines: 5 traits + vocabulary rules | Advisor | COMPLETE | 100% | P1C Sheet 5 | Personality, tone spectrum, words we use/avoid, grammar rules
1C.06 | 1C | Website copy: About Us + 20 FAQs + 3 welcome emails | Advisor | COMPLETE | 100% | P1C Sheet 6 | ~3,500 words total. Copy-paste ready for Shopify + Klaviyo.
P1D: Photography & Visual Assets — 5 tasks, ALL COMPLETE
1D.01 | 1D | 38-shot product photography list across 6 categories | Advisor | COMPLETE | 100% | P1D Sheet 2 | DIY setup $20-45. Every shot individually specified.
1D.02 | 1D | Product photo shooting guide + camera settings | Advisor | COMPLETE | 100% | P1D Sheet 2 | Merged with 1D.01. iPhone settings, lighting, backgrounds.
1D.03 | 1D | Lifestyle/running photography guide | Advisor | COMPLETE | 100% | P1D Sheet 2 | 8 lifestyle shots, 4 outdoor settings, model recruitment guide
1D.04 | 1D | Photo editing workflow + export specs for 8 platforms | Advisor | COMPLETE | 100% | P1D Sheet 3 | Lightroom preset, Snapseed, remove.bg, Canva. All free.
1D.05 | 1D | 15-video content library across 5 pillars | Advisor | COMPLETE | 100% | P1D Sheet 4 | Each with hook script, shot list, caption, platform target
P1E: Pre-Launch Community — 5 tasks, ALL COMPLETE
1E.01 | 1E | IG + TikTok profile optimization guide | Advisor | COMPLETE | 100% | P1E Sheet 2 | 7 profile elements specified per platform
1E.02 | 1E | 28-day content calendar (56 individual posts) | Advisor | COMPLETE | 100% | P1E Sheet 3 | 4 pillars, weekly targets, hashtag sets, all platforms
1E.03 | 1E | 30-day TikTok daily posting strategy | Advisor | COMPLETE | 100% | P1E Sheet 3 | Embedded in calendar. Daily topics with hooks.
1E.04 | 1E | Community engagement playbook: 12 communities | Advisor | COMPLETE | 100% | P1E Sheet 4 | Reddit, Facebook, Strava, forums. 10:1 rule. Scripts.
1E.05 | 1E | Waitlist growth: 6 channels → 200+ subscribers | Advisor | COMPLETE | 100% | P1E Sheet 5 | Weekly targets, Carrd setup, channel tactics, contingency plans
PROGRESS SUMMARY
P0 Total | 42 tasks | 34 COMPLETE (81%) | 8 FOUNDER ACTION | 0 gaps | — | All 7 subprojects delivered | All research done. 8 tasks require founder execution (buy competitors, survey, interviews, samples, landing page).
P1 Total | 28 tasks | 24 COMPLETE (86%) | 2 FOUNDER ACTION | 2 GAPS (1B.05, 1C.03) | — | All 5 subprojects delivered | 31 sheets across 5 workbooks. 14 gaps identified (3 critical, 5 high, 6 medium).
COMBINED | 70 tasks | 58 COMPLETE (83%) | 10 FOUNDER ACTION | 2 GAPS | — | 12 subprojects, 12 workbooks, 1 master tracker | 83% research complete. 14% founder action. 3% gap remediation needed.