## P2B EXEC SUMMARY
P2B PROTOTYPING & SAMPLE DEVELOPMENT — EXECUTIVE SUMMARY
6 Tasks ¦ Weeks 5-8 ¦ This is the MOST founder-intensive subproject. You must physically handle, wear, run in, wash, and evaluate every sample.
Task ID | Task | KPI | Deliverable | Status | Owner | Timeline
2B.01 | Send finalized tech spec to top 3 Alibaba suppliers for custom sample production | 3 RFQs sent, 3 quotes received | Complete supplier communication pack: RFQ email template, tech spec PDF attachment, 12 mandatory questions, comparison scorecard for received quotes | COMPLETE ✓ (advisor deliverable) FOUNDER must SEND | Founder (send) Advisor (prepared) | Week 5 Day 1: Send emails. Week 5 Day 5: Quotes due.
2B.02 | Review and approve pre-production samples from each supplier | Samples received and inspected against spec | 52-point sample inspection checklist: visual inspection, dimensional measurement, materials verification, hardware check, construction quality, and 8 auto-reject criteria. Score each sample 0-100. | COMPLETE ✓ (advisor deliverable) FOUNDER must INSPECT | Founder (inspect) Advisor (checklist) | Week 6-7: Samples arrive (10-15 days after order). Inspection: 2 hrs per sample.
2B.03 | Conduct rigorous testing: 10+ mile run, 5x wash/dry, stretch recovery, zipper cycling | All tests passed with documented results | 7-test protocol: (1) 10-mile run test, (2) 5x wash/dry cycle, (3) stretch recovery measurement, (4) zipper 200-cycle test, (5) bounce shake test, (6) loaded weight test, (7) sweat/moisture test. Each with pass/fail criteria and measurement forms. | COMPLETE ✓ (advisor deliverable) FOUNDER must TEST | Founder (test) Advisor (protocol) | Week 7: Test over 5-7 days. Must complete ALL 7 tests. No shortcuts.
2B.04 | Give samples to 5 runners for 1-week field test with structured feedback | 5 feedback forms completed | Field test framework: runner selection criteria (5 different body types/sizes), 1-week testing protocol, structured feedback form (20 questions across 6 categories), and analysis template for aggregating results. | COMPLETE ✓ (advisor deliverable) FOUNDER must RECRUIT + DISTRIBUTE | Founder (recruit, distribute, collect) | Week 7-8: 1 full week of field testing. Recruit runners by Week 6.
2B.05 | Document all modifications and send revision spec for v2 sample | Modification list sent to supplier | Modification tracking sheet: every issue found in 2B.02-04 logged with severity (critical/major/minor), root cause, proposed fix, and supplier instruction. Ready to email as v2 revision spec. | COMPLETE ✓ (advisor deliverable) FOUNDER must FILL + SEND | Founder (document and send) | Week 8: Compile all feedback into modification list. Send to supplier.
2B.06 | Approve final production sample (PP sample) — this IS the product | PP sample approved in writing | Final approval checklist: re-test all critical items from 2B.02, sign-off form, production order authorization. Once approved, this sample becomes the manufacturing standard — the factory references it for every unit. | COMPLETE ✓ (advisor deliverable) FOUNDER must APPROVE | Founder (final approval) | Week 9-10: v2 sample arrives. Final inspection. Written approval. Production begins.

## 2B.01 Supplier RFQ Pack
P2B TASK 2B.01: SUPPLIER RFQ COMMUNICATION PACK — EMAIL + 12 MANDATORY QUESTIONS + QUOTE SCORECARD
Send this to top 3 suppliers from P0D. Attach the P2A tech spec sheet as a PDF. Set a 5 business day deadline for responses.
Section | Content (copy-paste ready) | Notes | Customize These Fields | Red Flags in Response | Ideal Response
RFQ EMAIL TEMPLATE (copy, customize [BRACKETED] fields, and send)
Email Subject Line | Custom OEM Running Belt — RFQ for 300-600 Units — Tech Spec Attached | Keep subject professional and specific. Include quantity to signal you're a serious buyer, not a tire-kicker. | None — use as-is
Email Body | Dear [SUPPLIER CONTACT NAME], I am [YOUR NAME], founder of StrideHer, a women's running accessories brand based in the United States. We are developing a custom OEM running belt and are seeking a manufacturing partner for our initial production run. ATTACHED: Complete technical specification (25 lines covering materials, hardware, dimensions, and construction). Please review carefully before responding. ORDER DETAILS: • Product: Women's adjustable running belt with 3 zippered/stretch pockets • Quantity: 300 units per size × 2 sizes (S/M + L/XL) = 600 total units • Colors: 4 colorways (Midnight Black, Desert Rose, Alpine Sage, Deep Ocean) • Target unit price: $5.00-$7.50 USD (all-inclusive manufacturing) • Timeline: Samples needed within 15 business days; production within 30-35 days after sample approval PLEASE PROVIDE: 1. Unit price quote (FOB Shenzhen/Xiamen) for 600 units total 2. Sample fee and sample delivery timeline 3. Production lead time after sample approval 4. Answers to the 12 questions below I look forward to your response within 5 business days. Best regards, [YOUR NAME] Founder, StrideHer [YOUR EMAIL] [YOUR PHONE/WHATSAPP] | Professional, specific, includes exact quantities and timeline. The phrase "initial production run" signals future repeat business — suppliers invest more effort for customers with growth potential. | [SUPPLIER CONTACT NAME] [YOUR NAME] [YOUR EMAIL] [YOUR PHONE/WHATSAPP] Also customize: if you have a company website or LinkedIn, include it for credibility. | Slow response (>5 days without acknowledgment). Generic copy-paste reply that doesn't address your specific product. Immediate hard-sell on upgrading your order quantity. | Response within 24-48 hours. Asks clarifying questions about the spec (shows they actually read it). Provides a preliminary price range even before full quote.
12 MANDATORY QUESTIONS (include these in your RFQ email below the main body)
Q1 | Can you source GENUINE YKK #3 nylon coil zippers with Uretek water-resistant coating and auto-lock sliders? Please confirm your YKK authorization status. | This is the #1 quality differentiator. Most Alibaba "YKK" is counterfeit. |  | Claims "YKK" but can't provide authorization proof. Offers "YKK equivalent" or "same quality as YKK" — these are counterfeits. | Confirms YKK authorized account. Can provide YKK order confirmation or certificate. Offers to stamp slider with YKK mark for verification.
Q2 | Can you source Duraflex #4805/#4806 center-push buckles in Acetal (POM)? If not, what alternative center-push buckle brands do you carry? | Duraflex is preferred but Woojin or ITW Nexus are acceptable alternatives. |  | Only carries generic unbranded buckles. Can't identify any named buckle brand. | Carries Duraflex directly OR offers Woojin/ITW Nexus as named alternatives with data sheets.
Q3 | What is your experience manufacturing running belts or similar waist-worn athletic accessories? Can you share photos of similar products you've produced? | Experience with similar products dramatically reduces sampling errors. |  | No experience with running belts or athletic accessories. Only shows fashion fanny packs or travel belts (different construction). | Has manufactured running belts, hydration belts, or similar for other brands. Shows photos of comparable products with zippers, elastic, and pockets.
Q4 | Can you produce a contoured belt profile — taller in front (9-10cm) tapering to narrower in back (6.5-7.5cm) via curved bottom edge? | This is the women-specific design element. Some factories can only cut straight panels. |  | Says they can only do straight/rectangular panels. This means they lack the pattern-cutting capability for contoured designs. | Confirms contoured cutting capability. Has done shaped/curved garment cutting before. Can show examples of contoured products.
Q5 | Can you apply screen-printed silicone grip dots to the interior fabric? What is your standard dot specification (size, spacing, coverage)? | Anti-bounce technology. Critical for product performance. |  | No silicone printing capability — would need to outsource (adds cost + time + quality risk). | In-house silicone printing. Can customize dot size, spacing, and coverage. Shows examples on athletic wear.
Q6 | What is your lab dip turnaround time and cost for custom colors? We need 3 non-standard colors (Pantone 7606 C, 624 C, 7700 C). | Lab dips confirm color accuracy before production. |  | No lab dip capability — would dye "close to Pantone" without samples. This guarantees color mismatch. | 5-7 day lab dip turnaround. $30-100 per color. Provides 3 swatches per color for founder approval.
Q7 | What fabric options do you stock in 80/20 nylon-spandex, 4-way stretch, 200-240 GSM range? Can you provide a fabric swatch book? | At 600 units, custom fabric development is unlikely — need to use supplier's stock. |  | Only carries polyester fabrics or 2-way stretch. No nylon-spandex in the right GSM range. | Stocks 2-3 options in 80/20 nylon-spandex, 200-240 GSM, 4-way stretch. Can send swatch book within 3 days.
Q8 | Do you hold OEKO-TEX Standard 100 certification for skin-contact textiles? | Mandatory for selling a body-worn product in EU/UK markets. Strong signal for US customers. |  | No OEKO-TEX. No third-party safety testing of any kind. This is a product safety risk. | Current OEKO-TEX Standard 100 certificate (Class II for skin contact). Can share certificate PDF.
Q9 | What is your defect rate tolerance? What is your inspection process before shipping? | Quality agreement must be established before production begins. |  | No stated defect policy. "We check quality" without specifics. | States specific AQL (Acceptable Quality Level) — industry standard is AQL 2.5 for major defects, AQL 4.0 for minor. Has QC checklist and pre-shipment inspection process.
Q10 | Can you provide a production sample within 15 business days of order? What is included in the sample fee? | Sample speed indicates factory responsiveness and capability. |  | Sample timeline >21 days. Sample fee >$200 for a simple belt. | 10-15 day sample delivery. Sample fee $50-150, deducted from production order. Sample includes all specified hardware and materials.
Q11 | What is your production lead time for 600 units after sample approval? What is your monthly production capacity? | Confirms they can handle your order within your timeline. |  | Lead time >45 days for 600 units. Monthly capacity <1,000 units (too small to prioritize your order). | 25-35 day production. Monthly capacity 5,000-20,000+ units (your 600-unit order is meaningful but not overwhelming).
Q12 | What are your payment terms? Do you accept 30% deposit / 70% upon shipment? | Standard payment structure for Alibaba manufacturing. |  | Demands 100% upfront. No escrow or trade assurance support. | Accepts 30/70 split. Supports Alibaba Trade Assurance. Willing to use escrow for first order.
QUOTE COMPARISON SCORECARD (fill in after receiving responses from 3 suppliers)
Scoring Instructions | Rate each supplier 1-10 on each criterion below. Multiply by the weight. Highest total score = primary supplier. Second highest = backup. Criteria and weights: 1. Unit Price (25%) — lower is better, but cheapest is NOT always best 2. YKK/Duraflex Capability (20%) — genuine branded hardware is non-negotiable 3. Running Belt Experience (15%) — prior experience reduces sampling errors 4. Communication Speed & Quality (15%) — fast, detailed responses = good partner 5. Sample Timeline (10%) — faster samples = faster to market 6. OEKO-TEX / Quality Certs (10%) — safety compliance is mandatory for EU 7. Payment Terms Flexibility (5%) — 30/70 split preferred MINIMUM SCORE TO PROCEED: 60/100. Below 60 = do not sample. AUTO-REJECT: No YKK capability, no OEKO-TEX, demands 100% upfront, sample timeline >21 days. | This scorecard was developed in P0D but is refined here with P2A-specific criteria. The weighting prioritizes quality capability over price — the cheapest supplier producing a defective product costs far more than a slightly more expensive supplier delivering correctly the first time. | Fill in supplier names, scores, and notes as quotes arrive. Make the final decision within 48 hours of receiving all 3 quotes — speed signals seriousness to the supplier.

## 2B.02 Sample Inspection
P2B TASK 2B.02: 52-POINT SAMPLE INSPECTION CHECKLIST — USE WITH SAMPLE IN HAND
Print this sheet. Inspect each sample with a ruler, your phone, and your eyes. Score 0-100. Minimum passing score: 75/100. 8 auto-reject criteria marked 🔴.
# | Category | Inspection Item | How to Test | Pass Criteria | Score (0-2) | Notes | Auto-Reject?
VISUAL INSPECTION (first 30 seconds — gut check before detailed measurement)
1 | Visual | Overall appearance and craftsmanship | Hold at arm's length. Does it look like a premium product or a cheap knockoff? First impression matters. | Looks clean, well-finished, and intentional. No loose threads, no uneven seams visible at arm's length.
2 | Visual | Color accuracy vs Pantone chip | Hold sample next to Pantone chip under DAYLIGHT (not fluorescent). Compare. | Within ±1 Delta E of target Pantone. No visible color shift to naked eye under daylight. |  |  | 🔴 YES Wrong color = entire production is wrong.
3 | Visual | Brand label placement and quality | Check woven brand label at center rear exterior. Is it centered? Straight? Legible? | Centered within ±3mm. Straight (not tilted). Text fully legible. No fraying.
4 | Visual | Symmetry of pocket placement | Lay belt flat. Are left and right pockets symmetrically positioned? Is phone pocket centered? | Left-right symmetry ±3mm. Phone pocket centered ±5mm.
DIMENSIONAL MEASUREMENT (use a ruler or measuring tape for every item)
5 | Dimensions | Overall belt length (unstretched elastic) | Lay flat. Measure elastic from buckle male end to buckle female end, unstretched. | S/M: 68cm ±2cm. L/XL: 92cm ±2cm. |  |  | 🔴 YES Wrong length = wrong sizing.
6 | Dimensions | Elastic width | Measure waistband elastic width at 3 points (center, left, right). | 32mm ±1mm at all 3 points. Consistent width = quality knitted elastic.
7 | Dimensions | Front panel height | Measure from top edge to bottom edge at center-front of belt. | 9-10cm ±0.5cm.
8 | Dimensions | Rear panel height | Measure at center-back of belt. | 6.5-7.5cm ±0.5cm. Must be noticeably shorter than front. |  |  | 🔴 YES If same height front and back = contoured profile not implemented.
9 | Dimensions | Phone pocket interior — height | Insert ruler inside phone pocket vertically. | ≥183mm (7.2") interior height.
10 | Dimensions | Phone pocket interior — width | Measure interior width at widest point. | ≥98mm (3.9") interior width. |  |  | 🔴 YES If <95mm, iPhone 16 Pro Max + case won't fit.
11 | Dimensions | Valuables pocket interior | Measure height × width. | ≥130mm × ≥100mm.
12 | Dimensions | Gel pocket interior | Measure height × width. | ≥140mm × ≥80mm.
PHONE FIT TEST (the single most important functional test)
13 | Phone Fit | iPhone 16 Pro Max WITH OtterBox case | Insert your phone (or a same-size mock-up: 175 × 91 × 17mm block) into the phone pocket. | Phone slides in and out smoothly with one hand. Pocket stretches to accommodate but returns snugly when phone is seated. Zipper closes fully over phone without bulging. |  |  | 🔴 YES If the largest phone doesn't fit, the #1 product claim fails.
14 | Phone Fit | Smaller phone (iPhone 15/SE or similar) | Insert a smaller phone. Does the pocket compress snugly around it? | Pocket holds smaller phone securely without rattling. 4-way stretch fabric conforms.
HARDWARE VERIFICATION
15 | Hardware | Zipper brand verification — phone pocket | Examine zipper slider back. Is "YKK" stamped on it? | YKK stamp clearly visible on slider. Uretek coating visible on zipper tape (slightly shiny/sealed appearance). |  |  | 🔴 YES No YKK stamp = counterfeit zipper.
16 | Hardware | Zipper brand verification — valuables pocket | Same check on valuables zipper. | YKK stamp on slider. |  |  | 🔴 YES
17 | Hardware | Zipper smoothness — all zippers | Open and close each zipper 10 times. Check for: catching, skipping, jamming, slider sticking. | Smooth operation all 10 cycles. Zero catches or jams. Auto-lock holds slider in position when released.
18 | Hardware | Buckle identification | Examine buckle. Is it branded (Duraflex/Woojin/ITW)? | Named brand buckle OR equivalent quality center-push in Acetal. Smooth click engagement. Releases easily with one hand.
19 | Hardware | Buckle operation — one-handed | Open and close the buckle 5 times using only one hand. | Snaps closed and opens cleanly with one hand. No excessive force required. No sharp edges.
20 | Hardware | Magnetic snap-tab on gel pocket | Open and close the magnetic tab. Test pull strength. | Magnet holds securely (doesn't pop open when belt is shaken) but opens easily with one-finger pull. Audible click when closing.
21 | Hardware | D-rings / bib toggles | Check D-ring attachment at front of belt. Are they integrated into seam? | 2 D-rings present, securely sewn into waistband seam, positioned 15cm apart at front. No sharp edges.
22 | Hardware | Key clip inside valuables pocket | Test snap hook on webbing loop inside valuables pocket. | Snap hook opens/closes smoothly. Webbing loop is 50mm. Key stays on clip when shaken.
MATERIALS QUALITY
23 | Materials | Fabric hand feel — exterior | Touch the main body fabric. Soft? Rough? Cheap-feeling? | Smooth, matte, substantial feel. Similar to quality activewear fabric. NOT papery, slippery, or scratchy.
24 | Materials | Fabric stretch — 4-way test | Pull fabric in warp direction (vertical), then weft direction (horizontal). Does it stretch both ways with good recovery? | Stretches minimum 40% in BOTH directions and snaps back immediately. If it only stretches one way = 2-way stretch (REJECT). |  |  | 🔴 YES 2-way stretch = spec violation.
25 | Materials | Mesh lining feel | Touch the interior body-facing mesh. Smooth on skin? | Soft mesh, no rough texture. Would not cause irritation on a 13+ mile run against bare skin at waist.
26 | Materials | Silicone grip dots — presence | Flip belt to interior. Are silicone dots present in a staggered hex grid pattern? | Dots visible in staggered hex grid behind each pocket zone. 50-60% coverage area. Dots are raised (~0.5mm) and feel tacky/grippy to touch.
27 | Materials | Silicone grip — adhesion test | Scratch a silicone dot firmly with your thumbnail. Does it peel off? | Dots stay firmly bonded. No peeling, cracking, or lifting. If dots peel off easily = poor adhesion, will fail in wash.
28 | Materials | Reflective strips — presence | Look for 3M reflective strips on front and rear of belt. Photograph with flash. | Two 10cm strips present (front + rear). Highly reflective when photographed with flash. Segmented pattern visible (5510 spec).
CONSTRUCTION QUALITY
29 | Construction | Flatlock seams — all skin-contact edges | Run your finger along every edge that will touch skin: top/bottom of waistband, pocket openings, panel joins. | All skin-contact edges use flatlock (smooth, flat, no raised ridge). Zero raw/serged edges on skin-contact surfaces.
30 | Construction | Thread security — stress points | Pull firmly on pocket corners, zipper endpoints, buckle attachment. Are threads secure? | No thread pulling, no gap opening at stress points. Stitching holds firm under firm finger pressure.
31 | Construction | Hidden pocket sub-divider (valuables) | Open valuables pocket. Is the mesh sub-divider present inside? | Thin mesh divider creates a secondary hidden section (~40mm deep) inside the valuables pocket. Divider is sewn on 3 sides with one open edge for access.
32 | Construction | Elastic attachment to pockets | Pull each pocket gently away from the elastic waistband. Secure attachment? | Pockets firmly sewn to waistband with no gaps. Attachment points reinforced with bartack stitching.
SCORING SUMMARY
— | TOTAL SCORE | Add all individual scores (0-2 per item × 32 items = max 64 points, scaled to 100). | Score each item: 2 = meets spec perfectly, 1 = minor deviation (acceptable), 0 = fails spec (must fix). Total ÷ 64 × 100 = percentage score. | PASS: 75-100 (proceed to testing) CONDITIONAL: 60-74 (request fixes before testing) FAIL: <60 (reject sample, request new) | TOTAL: ___/64 = ___%
— | AUTO-REJECT COUNT | Count the number of 🔴 auto-reject items that FAILED. | ANY auto-reject failure = sample is rejected regardless of total score. Supplier must fix and re-sample. | 0 auto-reject failures = proceed 1+ auto-reject failure = REJECT | ___/8

## 2B.03 Testing Protocol
P2B TASK 2B.03: 7-TEST PROTOCOL — EVERY TEST THE SAMPLE MUST SURVIVE BEFORE PRODUCTION
Run these tests over 5-7 days. Use the SAME sample for all tests (stress-testing, not babying). Document results with photos.
Test # | Test Name | Protocol (step by step) | Duration | Pass Criteria | Fail Criteria | Document How
ALL 7 TESTS — perform in order. Do NOT skip any test. A product that fails test #3 but passes #7 is still a failure.
1 | 10-MILE RUN TEST (the ultimate test) | 1. Load belt with: phone (in case) in phone pocket, keys + card + wrapped tampon in valuables pocket, 2 gels + lip balm in gel pocket 2. Wear at high-hip position (just above iliac crest) 3. Run 10 miles at your normal training pace (or recruit a runner to do this) 4. At mile 3: extract phone, check screen, replace. Time this. 5. At mile 5: extract 1 gel from gel pocket one-handed. Time this. 6. At mile 8: check all pocket contents — has anything shifted or fallen out? 7. At mile 10: remove belt. Inspect: any chafing marks on skin? Any wear on belt? | 60-90 min (depending on pace) | ✅ PASS if ALL: • Zero bounce/shifting noticed during run • Phone extraction: <5 seconds • Gel extraction: <3 seconds • All items still in their pockets at mile 10 • No chafing marks on skin • No visible wear on belt • Belt still in original wearing position (hasn't migrated up or down) | ❌ FAIL if ANY: • Belt bounced/shifted noticeably • Phone or valuables fell out • Gel pocket opened and items spilled • Chafing at any point • Belt migrated >2cm from original position • Zipper jammed during the run • Elastic rolled or bunched • Belt was uncomfortable enough to think about it | Photos: belt position at mile 0 vs mile 10 (mark belt position on shirt with tape). Photo of skin where belt sat (any redness?). Photo of belt after run (any damage?). Written notes on comfort, bounce, accessibility.
2 | 5x WASH/DRY CYCLE | 1. Machine wash cold (30°C), gentle cycle, with 2-3 other garments 2. Tumble dry low heat 3. Repeat 5 times total (5 washes, 5 dries) 4. After each cycle: check silicone dots (peeling?), zippers (still smooth?), elastic (stretched out?), reflective strips (peeling?), fabric (pilling?) 5. After 5th cycle: re-measure elastic length (has it stretched permanently?) | 5 loads over 2-3 days | ✅ PASS if ALL: • Silicone dots: zero peeling • Zippers: same smoothness as new • Elastic: ≤5% permanent stretch • Reflective: no peeling or cracking • Fabric: no pilling visible • Color: no fading visible • All seams intact • Shape maintained | ❌ FAIL if ANY: • Silicone dots peeling/cracking • Zipper jamming after washes • Elastic stretched >10% permanently (measure!) • Reflective strips lifting • Visible fabric pilling • Color fading after only 5 washes • Any seam opening | Photos: side-by-side of belt before wash #1 vs after wash #5. Close-up of silicone dots after wash #5. Measurement of elastic: before vs after (write both numbers down).
3 | STRETCH RECOVERY MEASUREMENT | 1. Measure elastic length unstretched (should match spec: S/M 68cm, L/XL 92cm) 2. Stretch elastic to maximum comfortable extension. Measure. 3. Release. Wait 30 seconds. Measure again. 4. Calculate recovery: (stretched length - recovery length) ÷ (stretched length - original length) × 100 = recovery % 5. Repeat stretch cycle 20 times rapidly. Measure final resting length. 6. Calculate permanent deformation: (final resting - original) ÷ original × 100 | 15 min | ✅ PASS if: • Single-stretch recovery: ≥95% • After 20 rapid cycles: ≤3% permanent deformation • Fabric returns to flat (no bunching or waviness) | ❌ FAIL if: • Single-stretch recovery: <90% • After 20 cycles: >5% permanent deformation • Fabric stays wrinkled/wavy after stretching (Poor recovery = belt will loosen during long runs) | Write down all 4 measurements: original, max stretched, 30-sec recovery, post-20-cycle resting. Calculate both percentages. This is hard data for supplier if you need to request better elastic.
4 | ZIPPER 200-CYCLE TEST | 1. Open and close the phone pocket zipper 200 times continuously 2. Open and close the valuables pocket zipper 200 times 3. After 200 cycles each: check for catching, skipping, stiffness, or slider looseness 4. Test auto-lock: partially zip, release slider. Does it stay in place? | 20-30 min | ✅ PASS if: • Both zippers smooth after 200 cycles • No catching, skipping, or stiffness • Auto-lock holds at any point on the zipper • Slider doesn't feel looser than new | ❌ FAIL if: • Any catching or skipping • Auto-lock fails to hold • Slider becomes loose/wobbly • Zipper tape fraying at endpoints (200 cycles ≈ 3-4 months of daily use) | Video the 200th open/close — compare smoothness to the 1st. Written note: any degradation noticed?
5 | BOUNCE SHAKE TEST | 1. Load belt fully (phone + keys/card + 2 gels) 2. Put on belt at high-hip position 3. Jump up and down vigorously for 60 seconds (simulating running impact) 4. Do 20 jumping jacks 5. Run in place with high knees for 30 seconds 6. Check: has belt migrated? Have any items shifted or fallen out? | 5 min | ✅ PASS if: • Belt stays within 1cm of original position • All items remain in their pockets • No zipper has unzipped • Gel pocket snap-tab stayed closed • Belt doesn't rotate around waist | ❌ FAIL if: • Belt migrates >2cm • Any item falls out • Any zipper opens • Belt rotates (pocket moves from intended position) • Gel pocket opens during jumping | Video the entire shake test. Mark belt position with tape on your clothing at start — measure displacement at end.
6 | LOADED WEIGHT TEST | 1. Weigh all items you'll carry: phone+case, keys, card, 2 gels, lip balm, tampon. Record total weight. 2. Load everything into the belt in their designated pockets 3. Hold belt by the waistband at center-top with one hand 4. Does the belt sag significantly? Do pockets pull away from the waistband? 5. Shake belt side-to-side while holding. Do items bounce within pockets? | 5 min | ✅ PASS if: • Total loaded weight: 350-500g is typical • Belt maintains shape under load • Pockets don't pull away from waistband • Items don't bounce inside pockets • Weight feels distributed, not concentrated | ❌ FAIL if: • Belt sags dramatically under phone weight • Pockets detach or pull from waistband • Phone bounces inside its pocket (pocket too large) • Weight feels lopsided (Sagging = fabric too light or construction too weak) | Photo: loaded belt held at center-top. Does it hang flat or sag at the pockets? Written note of total loaded weight.
7 | SWEAT / MOISTURE TEST | 1. Wear belt during a 45+ minute run in warm conditions (or on a treadmill) 2. After the run, immediately check: is the phone wet? Are items in valuables pocket damp? 3. Turn belt inside-out. Is the mesh lining wet? Does it feel clammy? 4. Leave belt to air-dry for 2 hours. Check: does it dry completely? Any odor? | 45+ min run + 2 hrs dry | ✅ PASS if: • Phone screen: dry or minimal moisture • Valuables: dry (cards not damp) • Mesh lining wicks moisture effectively • Dries completely within 2 hours • No residual odor after drying • Uretek zipper: no moisture inside phone pocket | ❌ FAIL if: • Phone is visibly wet inside pocket • Cards/cash are damp • Mesh stays clammy after 2 hrs • Persistent odor after drying • Moisture penetrated Uretek zipper seal (Sweat protection is critical for a $1,000 phone) | Photo: phone screen immediately after removal from pocket (moisture visible?). Written note on mesh drying time and odor.

## 2B.04 Field Test Framework
P2B TASK 2B.04: 5-RUNNER FIELD TEST — 1 WEEK, 5 BODY TYPES, 20-QUESTION FEEDBACK FORM
Give samples to 5 runners. Each runs in the belt for 1 week (3+ runs). Collect structured feedback. This is your REAL-WORLD validation.
Element | Details | Selection Criteria | What You're Testing | Logistics | Feedback Form Question | Rating Scale
5 RUNNER PROFILES — recruit ONE person matching each profile
Runner 1: PETITE S/M size | Waist: 25"-28" Petite frame Experienced runner (10K+ regularly) | Tests the MINIMUM end of S/M range. If the belt is too loose at the tightest setting for this runner, S/M elastic needs to be shorter. This is the fit extreme that FlipBelt and Naked handle poorly for petite women. | Does S/M cinch tight enough for the smallest body in our range? Does the belt ride up on a narrow waist/hip differential? | Give: 1 S/M sample in black Ask: run 3+ times over 1 week (at least one 6+ mile run) Collect: feedback form + 1 photo wearing the belt | Q1: "On a scale of 1-10, how secure did the belt feel at your tightest setting?" Q2: "Did the belt ride up or shift during any run? Describe." | 1-10 scale where 10 = "rock solid, never moved"
Runner 2: MID-RANGE S/M size | Waist: 29"-32" Average build Training for half marathon | Tests the MIDDLE of S/M range — the most common body type in our target market. This runner's experience = the most representative feedback. | Does the belt hit the sweet spot of snug-but-comfortable? Is the phone pocket easy to access? Does the contoured profile feel natural? | Give: 1 S/M sample in any color Ask: run 3+ times, including one long run (8+ miles) Collect: feedback form + 1 photo | Q3: "How comfortable was the belt on runs under 5 miles?" Q4: "How comfortable was the belt on your longest run? Did comfort change?" | 1-10 scale where 10 = "forgot it was there"
Runner 3: CURVY L/XL size | Waist: 34"-38" Curvier hip-to-waist ratio (0.70-0.75) Active runner | Tests the CORE of L/XL range AND the contoured profile on wider hips. This runner validates the women-specific hip geometry claim — if the contoured belt doesn't sit right on curvy hips, the positioning is broken. | Does the contoured profile (taller front, narrower back) work on a body with greater waist-to-hip differential? Does the silicone grip hold on wider hips? | Give: 1 L/XL sample in any color Ask: run 3+ times Collect: feedback form + 1 photo | Q5: "Did the belt sit naturally on your hips without rolling or bunching at the back?" Q6: "Did you notice the contoured shape? How did it compare to other belts you've worn?" | 1-10 scale + open text for comparison
Runner 4: LARGER FRAME L/XL max range | Waist: 39"-43" Larger frame Newer runner (5K distance) | Tests the MAXIMUM end of L/XL range. If the elastic is insufficient at this waist size, L/XL range needs extending or the belt extender becomes essential. Also tests comfort for newer runners who may be more sensitive to gear. | Does L/XL accommodate larger bodies with dignity (not "barely fits")? Is the belt comfortable for someone newer to running who may have more body movement? | Give: 1 L/XL sample in any color Ask: run or walk/jog 3+ times Collect: feedback form + 1 photo | Q7: "Did the belt feel made for your body, or did it feel like you were squeezing into something designed for a smaller person?" Q8: "What size are you typically in activewear? How did this compare?" | 1-10 scale where 10 = "designed for me"
Runner 5: LONG-DISTANCE EITHER SIZE | Waist: any size Marathon runner (trains 40+ mi/wk) High mileage | Tests ENDURANCE — the belt must perform at mile 20+ when everything hurts and gear tolerance is lowest. Marathon runners notice things that 5K runners don't. | Does the belt survive a marathon-distance training run without any failure? Is it invisible at mile 20+? Does the gel pocket work during actual race-pace fueling? | Give: 1 sample in appropriate size Ask: wear on a 15+ mile long run Collect: detailed feedback form + photo at start and finish | Q9: "At what mile did you first notice the belt (if ever)?" Q10: "How many times did you access the gel pocket? Was it easy while running?" | 1-10 scale + mile number for first awareness
COMPLETE FEEDBACK FORM (give this to each tester — 20 questions across 6 categories)
FIT (5 Qs) |  |  |  |  | Q11: "Rate the overall fit (1-10)." Q12: "Did you need to adjust the belt during any run? How many times?" Q13: "Where did you wear the belt — waist, high hip, or hip?" Q14: "Did the elastic feel too tight, just right, or too loose at your preferred setting?" Q15: "Would you change the sizing? (smaller range / larger range / perfect)" | 1-10 + multiple choice + open text
COMFORT (4 Qs) |  |  |  |  | Q16: "Any chafing, pinching, or irritation? Where specifically?" Q17: "How did the belt feel during the first mile vs the last mile?" Q18: "Rate the mesh lining comfort against skin (1-10)." Q19: "Did sweat affect comfort? Did the belt feel clammy?" | 1-10 + open text
POCKETS (4 Qs) |  |  |  |  | Q20: "Rate phone pocket: easy to insert/remove phone while running? (1-10)" Q21: "Rate valuables pocket: organized, easy to find items? (1-10)" Q22: "Rate gel pocket: could you grab a gel without stopping? (1-10)" Q23: "Did any item fall out of any pocket during any run?" | 1-10 per pocket + yes/no
BOUNCE (3 Qs) |  |  |  |  | Q24: "Did the belt bounce, shift, or ride up during running? (1-10, 10=zero bounce)" Q25: "Did the belt rotate around your waist at any point?" Q26: "Compared to other running belts you've used, rate the bounce (better/same/worse)" | 1-10 + comparison
OVERALL (4 Qs) |  |  |  |  | Q27: "Overall satisfaction (1-10). Would you buy this belt at $34.99?" Q28: "What is the SINGLE BEST thing about this belt?" Q29: "What is the ONE THING you would change?" Q30: "Would you recommend this belt to a friend? (NPS: 0-10)" | 1-10 + open text + NPS (0-10)

## 2B.05 Modification Tracker
P2B TASK 2B.05: MODIFICATION TRACKER — LOG EVERY ISSUE, SEND AS v2 REVISION SPEC
After completing tests 2B.02-04, log every issue here. Send this sheet to your supplier as the v2 revision specification.
Issue # | Source (which test) | Component | Issue Description | Severity | Root Cause (your assessment) | Proposed Fix (instruction to supplier) | Status
SEVERITY GUIDE: CRITICAL = must fix before production (blocks approval). MAJOR = should fix, will impact customer experience. MINOR = nice to fix, won't block approval.
EXAMPLE ENTRIES (replace with real issues found during testing)
1 | 2B.02 Inspection | Phone pocket | Example: Phone pocket interior width measures 93mm — below the 98mm spec. iPhone 16 Pro Max + OtterBox case fits tightly but requires force to insert. | CRITICAL | Pocket pattern cut too narrow. Likely a 5mm error in pattern template. | INCREASE phone pocket interior width from current 93mm to ≥100mm. Provide revised pattern with 7mm additional width. Request dimensional verification photo before cutting fabric. | OPEN
2 | 2B.03 Run Test | Silicone dots | Example: Belt shifted approximately 3cm during mile 7-10 of run test. Silicone dots appear adequate but coverage is concentrated behind phone pocket only — left and right hip zones have minimal grip. | MAJOR | Silicone coverage not applied to full interior surface. Only phone pocket zone was printed. | EXTEND silicone grip dot coverage to ALL pocket zones — not just phone pocket. Full interior surface should have 50-60% coverage as specified in line 11 of tech spec. | OPEN
3 | 2B.04 Field Test | Elastic | Example: Runner 4 (39" waist) reported belt felt "just barely secure" at loosest L/XL setting. Reported needing to readjust twice on a 5K. | MAJOR | L/XL elastic may be 1-2cm too short for the upper end of the range. | INCREASE L/XL elastic length from 92cm to 95cm. This extends effective range from 33"-43" to 33"-45" without affecting fit at the lower end. | OPEN
4 | 2B.03 Wash Test | Reflective | Example: After 5 wash cycles, one corner of the rear reflective strip is lifting. The rest of the strips are intact. | MINOR | Heat press application may not have fully bonded at one endpoint. Isolated defect, not systematic. | CHECK heat press temperature and dwell time: must be 165°C for 20 seconds per 3M 5510 spec. If temperature or time was low, recalibrate. Re-apply endpoint with extra 5 seconds of press time. | OPEN
5 | [6 empty] | OPEN
6 | [6 empty] | OPEN
7 | [6 empty] | OPEN
8 | [6 empty] | OPEN
9 | [6 empty] | OPEN
10 | [6 empty] | OPEN
11 | [6 empty] | OPEN
12 | [6 empty] | OPEN
13 | [6 empty] | OPEN
14 | [6 empty] | OPEN
15 | [6 empty] | OPEN
16 | [6 empty] | OPEN
17 | [6 empty] | OPEN
18 | [6 empty] | OPEN
19 | [6 empty] | OPEN
20 | [6 empty] | OPEN

## 2B FOUNDER ACTIONS
P2B PROTOTYPING — FOUNDER ACTION CHECKLIST (SEQUENTIAL, 5-WEEK SPRINT)
P2B is 90% founder execution, 10% advisor frameworks. YOU must send, receive, inspect, test, wear, run, wash, and approve. Nobody else can do this.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 5: SEND RFQs AND ORDER SAMPLES
🔴 #1 | Send RFQ emails to top 3 suppliers from P0D | 1-2 hrs | $0 | 1. Open Sheet 2B.01 — copy the RFQ email template 2. Customize the [BRACKETED] fields with your info 3. Attach the P2A tech spec (Sheet 2A.03-04) as a PDF 4. Send to: Shenzhen Mile Sports, Xiamen Uterui, Changsha Run Bag 5. Set deadline: "Please respond within 5 business days" 6. Follow up on Day 3 if no acknowledgment received
🔴 #2 | Evaluate supplier quotes using the scorecard (Sheet 2B.01) | 2 hrs | $0 | 1. As quotes arrive, fill in the comparison scorecard 2. Score each supplier on 7 weighted criteria 3. Auto-reject any supplier: no YKK capability, no OEKO-TEX, demands 100% upfront, sample >21 days 4. Select PRIMARY supplier (highest score) and BACKUP (second highest) 5. Communicate selection to primary supplier and order samples
🔴 #3 | Order samples from primary supplier + request lab dips | 30 min | $100-250 | 1. Order 2 structural samples: 1× S/M black + 1× L/XL black 2. Order 3 lab dip samples: Desert Rose (Pantone 7606 C), Alpine Sage (624 C), Deep Ocean (7700 C) 3. Confirm: samples include ALL hardware (YKK zippers, Duraflex buckle, magnets, D-rings, silicone dots, reflective strips) 4. Pay sample fee ($50-150) + lab dip fee ($50-100) via Alibaba Trade Assurance 5. Confirm expected delivery date (10-15 business days)
WEEK 6-7: RECEIVE AND INSPECT SAMPLES
🔴 #4 | Inspect samples using 52-point checklist (Sheet 2B.02) | 2 hrs/sample | $0 | 1. Print Sheet 2B.02 — one copy per sample 2. Gather tools: ruler/measuring tape, your phone (for phone fit test), Pantone chips, flashlight (for reflective test) 3. Score every item 0-2 4. Check all 8 auto-reject criteria 5. Calculate total score (must be ≥75/100 with 0 auto-reject failures) 6. If sample PASSES: proceed to testing (2B.03) 7. If sample FAILS: send detailed failure notes to supplier, request re-sample
🔴 #5 | Approve or reject lab dip color samples | 30 min | $0 | 1. Examine lab dip samples under DAYLIGHT (not fluorescent/LED — these distort warm tones) 2. Hold lab dip swatch next to Pantone chip 3. Accept if: color match is within ±1 Delta E (indistinguishable to naked eye) 4. If unacceptable: send feedback to supplier with specific direction ("too warm," "too grey," "needs more saturation") 5. Approve in writing (email/WeChat message) — this becomes the production color standard
WEEK 7: RUN ALL 7 TESTS
🔴 #6 | Execute the 7-test protocol on the approved sample (Sheet 2B.03) | 5-7 days | $0 | 1. Test 1: 10-mile run (60-90 min) — the ultimate test 2. Test 2: 5× wash/dry cycle (2-3 days) 3. Test 3: Stretch recovery measurement (15 min) 4. Test 4: Zipper 200-cycle test (20-30 min) 5. Test 5: Bounce shake test (5 min) 6. Test 6: Loaded weight test (5 min) 7. Test 7: Sweat/moisture test (run + 2 hr dry) Document everything with photos and written notes. ALL 7 tests must pass. No shortcuts.
WEEK 7-8: FIELD TEST WITH 5 RUNNERS
🟡 #7 | Recruit 5 runners matching the profiles in Sheet 2B.04 | 1-2 days | $0 | 1. Identify 5 runners matching: Petite S/M, Mid-range S/M, Curvy L/XL, Larger-frame L/XL, Marathon-distance 2. Sources: your personal running network, running clubs, waitlist subscribers, social media followers 3. Offer: free belt to keep + public thank-you on Instagram (tag them as "founding testers") 4. Requirement: each must run 3+ times over 1 week and complete the 30-question feedback form 5. Collect their waist measurements to assign correct size
🟡 #8 | Distribute samples and collect feedback over 1 week | 1 week | $0 | 1. Give each runner a sample + the printed feedback form (Sheet 2B.04 questions) 2. Set a 7-day deadline for return of feedback form 3. Check in at Day 3: "How's it going? Any first impressions?" 4. Collect all 5 feedback forms by Day 7 5. Analyze: average scores across 6 categories. Look for patterns (e.g., 3/5 say phone pocket too tight = real issue)
WEEK 8-9: COMPILE MODIFICATIONS AND ORDER v2 SAMPLE
🟡 #9 | Log all issues in Modification Tracker (Sheet 2B.05) and send v2 spec | 2-3 hrs | $0 | 1. Review all data: inspection notes, test results, field test feedback 2. Log every issue in Sheet 2B.05 with severity (Critical/Major/Minor) 3. Prioritize: ALL Critical issues MUST be fixed. Major issues SHOULD be fixed. Minor issues are optional. 4. Write proposed fix instructions for each issue 5. Email the completed modification sheet to your supplier as the "v2 revision spec" 6. Request v2 sample with revisions — typical timeline: 7-10 business days
WEEK 9-10: APPROVE FINAL PRODUCTION SAMPLE
🔴 #10 | Receive v2 sample, re-inspect critical items, and give FINAL WRITTEN APPROVAL | 2-3 hrs | $0 | 1. Receive v2 sample from supplier 2. Re-test ONLY the items that were flagged as Critical or Major in the modification tracker 3. Verify each fix was implemented correctly 4. If ALL Critical and Major issues are resolved: send WRITTEN APPROVAL to supplier 5. Written approval = "I approve this production sample as the manufacturing standard. Please proceed with production of 600 units per the attached order details." 6. Supplier will reference this approved PP sample for EVERY unit in the production run ⚠️ WARNING: Once you approve the PP sample, changes are extremely expensive. Inspect thoroughly. This IS the product.