## P2C EXEC SUMMARY
P2C PACKAGING & UNBOXING DESIGN — EXECUTIVE SUMMARY
5 Tasks ¦ Weeks 7-9 ¦ Total packaging COGS: $0.55/unit ¦ 5 elements that turn a belt delivery into a brand experience.
Task ID | Task | KPI | Deliverable | Status | Strategic Purpose | Budget
2C.01 | Design branded poly mailer or recyclable kraft mailer with logo print | Mailer design approved + print-ready file | Complete mailer specification: dimensions, material, color, logo placement, artwork template, and sustainability messaging. Print-ready file in Canva or Adobe format. | COMPLETE ✓ | The mailer is the FIRST physical touchpoint with the customer. A branded mailer signals "this is not another Amazon generic." Recycled material reinforces StrideHer's values without adding cost. Logo on mailer = free brand impression for anyone who sees the package (mailroom, front porch, roommate). | $0.20-$0.30 /unit
2C.02 | Design product hang tag with brand story, care instructions, and premium feel | Hang tag artwork ready for print | Front: StrideHer wordmark + tagline. Back: 6-line founder micro-story + care icons. 350 GSM kraft with soft-touch matte finish and eyelet for attaching to belt buckle. | COMPLETE ✓ | The hang tag is what the customer touches FIRST when they open the package. Premium feel (thick stock, soft-touch finish) signals quality before they even try the belt. The micro-story on the back creates an emotional connection. This is the "jewelry box" effect — premium packaging justifies premium price. | $0.06-$0.10 /unit
2C.03 | Design insert card: thank you + QR code to review page + 10% off next purchase + social handles | Insert card artwork with all copy finalized | 4×6" card, 350 GSM coated, soft-touch matte one side. Front: thank you + QR code + 10% off code. Back: care instructions + social handles + community invite. All copy written and ready to paste into Canva template. | COMPLETE ✓ | The insert card is the highest-ROI packaging element. It drives 3 outcomes: (1) reviews via QR code (reviews = conversions), (2) repeat purchases via 10% off code, (3) social follows/UGC via Instagram/TikTok handles. A $0.05 card that generates a $35 repeat purchase = 70,000% ROI. This is NOT optional. | $0.04-$0.06 /unit
2C.04 | Source packaging suppliers: compare Alibaba bulk, Sticker Mule, Packlane, and belt supplier | Top 2 suppliers selected with quotes | Comparison matrix of 5 packaging supplier options across 8 criteria. Primary + backup selected. Bulk pricing confirmed. Lead times documented. | COMPLETE ✓ | Packaging sourcing is separate from belt manufacturing — your belt supplier CAN provide packaging but specialized print shops deliver better quality at equal or lower cost. Split or consolidated sourcing decision based on quotes. | Varies by supplier
2C.05 | Order packaging: 300+ mailers, 300+ hang tags, 500+ insert cards | Order placed, delivery confirmed | Complete order specification: quantities per item, artwork files uploaded, proofs approved, delivery timeline confirmed. Extra insert cards ordered for events/influencer kits. | FOUNDER ACTION | Order EXTRA insert cards (500 vs 300 belts) — the extras go in influencer packages, event giveaways, and trade show materials. Insert cards are the cheapest packaging element and the most versatile marketing tool. | $150-250 total order

## 2C.01 Poly Mailer Design
P2C TASK 2C.01: BRANDED POLY MAILER — THE FIRST THING THE CUSTOMER SEES
A branded mailer costs $0.05-$0.10 more than a plain one. That $0.10 turns "a package arrived" into "MY StrideHer arrived."
Element | Specification | Design Details | Artwork Instructions | Sustainability | Cost Estimate | Supplier Notes
MAILER OPTION COMPARISON (select ONE — recommendation: Option A for launch)
OPTION A: Recycled Poly Mailer ★ RECOMMENDED | Size: 10" × 13" (254 × 330mm) Material: 100% recycled LDPE (low-density polyethylene) Thickness: 2.5 mil (63.5 microns) Seal: Self-adhesive peel strip Color: Midnight (#1A1A1A) exterior | Front: StrideHer wordmark centered, printed in Desert Rose (#C07C7C), position at top 1/3 of mailer face. Below logo: "Run Your Way." tagline in smaller Plus Jakarta Sans. Bottom edge: small text "100% Recycled Material" with recycling symbol. Back: plain (logo on front only for cost efficiency at 1-color print). | 1. Create artwork in Canva Pro at 10×13" / 300 DPI 2. Export as print-ready PDF with 3mm bleed 3. Logo: use vector SVG from brand files 4. Color: 1-color print (Desert Rose on Midnight background) — 1-color is 40-60% cheaper than multi-color 5. Send artwork + Pantone reference (7606 C) to supplier 6. Request a printed proof before approving production run | ✅ 100% recycled LDPE — standard recycling stream (#4 plastic) ✅ No virgin plastic ✅ Lightweight = lower shipping carbon footprint ✅ "100% Recycled Material" callout reinforces brand values Future upgrade: compostable mailers from noissue or EcoEnclose (~$0.40-$0.60/unit — save for when margins support it) | $0.20-$0.30/unit at 300-500 qty 1-color print on recycled LDPE. Price drops to $0.12-$0.18 at 1,000+ qty. | Key suppliers: Alibaba (cheapest bulk), Sticker Mule (US, fast, small qty), noissue (eco-focused, higher price). At 300 qty, Alibaba or belt manufacturer is cheapest. Minimum order typically 100-500 units.
OPTION B: Recycled Kraft Mailer (alternative) | Size: 10.5" × 14.5" (to fit belt + insert card with room) Material: Recycled kraft paper, padded Thickness: 120 GSM kraft + bubble lining Seal: Self-adhesive Color: Natural kraft brown | Front: StrideHer wordmark centered in Midnight (#1A1A1A) stamp/print on natural kraft. "Run Your Way." tagline below. Kraft gives an artisanal, eco-conscious aesthetic that aligns with Tracksmith/Janji premium positioning. | Same artwork process as Option A but print color is Midnight on kraft (dark on light). Kraft mailers have a more "premium indie brand" feel vs poly mailers which feel "Amazon generic." Downside: kraft is ~$0.10-$0.15 more expensive than poly and slightly heavier (higher shipping cost). | ✅ Recycled kraft paper = highly recyclable ✅ Perceived as more "eco" than poly (even though recycled poly is comparable) ✅ Premium unboxing feel ❌ Heavier = higher shipping cost ❌ Less water-resistant than poly (risk in rain) | $0.30-$0.45/unit at 300-500 qty Higher than poly but premium feel. | Consider kraft for V2 packaging upgrade if customer feedback indicates packaging matters for the premium price positioning. For launch at $10K budget, poly mailer is the right choice.
WHAT GOES INSIDE THE MAILER (packing order matters)
Packing Order (top to bottom) | 1. Belt (folded, secured with brand sticker) 2. Hang tag (already attached to belt via buckle D-ring) 3. Insert card (on TOP of belt, face up — first thing customer sees when opening) No tissue paper (adds cost, creates waste). No plastic bags inside (contradicts sustainability). Belt arrives folded with insert card on top = clean, intentional, zero-waste. | The insert card sits on TOP so it's the first thing the customer reads when opening the mailer. This is deliberate — the 10% off code and review QR code are seen BEFORE the customer fully examines the belt. The brand sticker (1.5" circle) seals the folded belt — customer peels it off to unfurl the belt. Tactile moment. | Include a packing instruction card in your fulfillment SOP: "Place insert card face-up on top of folded belt. Ensure hang tag is visible. Seal belt fold with brand sticker. Place into mailer with insert card facing opening." | Zero-waste unboxing: no tissue, no plastic bags, no void fill. Belt fills the 10×13" mailer snugly. If there's excess space, fold belt differently — do NOT add filler. | Sticker: $0.04-$0.06/unit (1.5" circle, brand logo) | Brand sticker source: Sticker Mule (US, fast, 50 sticker min order ~$29) or Alibaba bulk (500+ for ~$0.02/unit). Order 500 stickers — extras for thank-you notes, laptop stickers at events, influencer packages.

## 2C.02-03 Hang Tag + Insert Card
P2C TASKS 2C.02-03: HANG TAG + INSERT CARD — EXACT COPY + ARTWORK SPECIFICATIONS
Every word on these two items is finalized below. Design in Canva Pro using brand fonts + colors. Both items are the size of a playing card or postcard.
Item | Dimensions + Material | Side | Complete Copy (paste into Canva) | Layout Instructions | Design References | Print Spec
HANG TAG (attaches to belt via ribbon/cord through eyelet → loops around buckle D-ring)
HANG TAG | 3.5" × 2" (89 × 51mm) 350 GSM uncoated kraft stock OR 350 GSM coated stock with soft-touch matte lamination 3mm round corners 3mm eyelet hole (top center) Strung with 6" Desert Rose or Midnight cotton cord | FRONT | StrideHer Run Your Way. The first running belt designed for women. | Layout: • StrideHer wordmark: centered, top 40% of card. Plus Jakarta Sans ExtraBold. Midnight (#1A1A1A) on Warm White (#FAF8F5) background. • "Run Your Way." tagline: centered, below wordmark. Plus Jakarta Sans Regular, smaller size. Midnight color. • Product descriptor: centered, bottom 30%. Inter Regular, smallest size. Deep Ocean (#3D5A80). • Eyelet hole: top center, 10mm from edge. Minimalist. Generous white space. The hang tag should feel like a premium fashion label, not a product info card. | Reference: Tracksmith hang tags (clean, minimal, premium kraft feel). Satisfy Running tags (bold typography, minimal info). Janji tags (eco kraft with minimal text). | 1-color print (Midnight) on kraft stock OR 2-color (Midnight + Desert Rose) on coated stock Kraft = more natural/eco feel Coated = more polished/premium feel Recommend: coated with soft-touch matte for launch. Feels expensive.
HANG TAG | (same card, flip to back) | BACK | Designed by a woman runner who couldn't find what she needed. — [CARE ICONS ROW:] 🫧 Machine wash cold 🌀 Tumble dry low 🚫 No iron ¦ No bleach strideher.com [SIZE:] S/M or L/XL [COLOR NAME:] Midnight Black | Layout: • Micro-story: centered, top 50%. Inter Regular, 8pt. Midnight color. This is the 12-word founder story — short enough to read in 3 seconds, emotional enough to remember. • Dash separator (em dash) • Care icons: centered row. Standard ISO 3758 care symbols. 6mm icon size. • URL: centered, Inter Medium, 7pt. • Size + Color: bottom 15%, Inter Regular, 7pt. LEAVE BLANK in artwork — print size/color per batch or use a hand-stamp. The micro-story is the most powerful element: "Designed by a woman runner who couldn't find what she needed." Eleven words that communicate the ENTIRE brand positioning. | Reference: Outdoor Voices tags (care symbols + short brand statement). Allbirds tags (materials story on reverse). The micro-story approach mirrors luxury fashion brands that put a single sentence on the back of their hang tags. | Same stock as front. Back may be 1-color only (Midnight) to save cost. Size/color text: either pre-printed per batch OR leave blank + hand-stamp. Hand-stamping adds a personal touch at low volume (300 units).
INSERT CARD (loose card placed on top of belt inside the mailer — first thing customer sees)
INSERT CARD | 4" × 6" (102 × 152mm) standard postcard size 350 GSM coated stock Soft-touch matte lamination (front only) Full-color printing both sides Round corners optional (3mm if yes) | FRONT | Thank you for running with us. You're one of the first. That means something. — [QR CODE — centered, 30×30mm] Scan to share your run (links to Shopify product review page) — 10% off your next order: HERSTRIDE10 strideher.com | Layout (front — the "action" side): • Thank you headline: top 25%. Plus Jakarta Sans Bold, 16pt. Midnight color on Warm White background. • Emotional subtext: "You're one of the first. That means something." Inter Regular, 10pt. This makes early customers feel like insiders, not just buyers. • QR code: CENTERED, 30×30mm minimum. Generates via Shopify Review page URL or post-purchase survey link. Black QR on white background for maximum scan reliability. • Below QR: "Scan to share your run" in Inter Regular 8pt. • Discount code: bottom 30%. "HERSTRIDE10" in Plus Jakarta Sans Bold, 14pt. Desert Rose color (#C07C7C). URL below in Inter 8pt. Hierarchy: gratitude → review CTA → repeat purchase incentive. In that order — gratitude BEFORE asking for anything. | Reference: Glossier insert cards (clean, emotional, action-driven). Dollar Shave Club (funny, memorable, clear CTA). Away luggage (premium feel, minimal text). The QR code is the #1 most important element — it drives reviews without requiring the customer to navigate to a review page manually. Scanning a QR code is 10× easier than typing a URL. | Full-color front. Soft-touch matte lamination on front surface only (saves cost vs both sides, still feels premium). QR code: test scan before approving print proof. A QR code that doesn't scan = worthless.
INSERT CARD | (same card, flip to back) | BACK | HOW TO WEAR YOUR STRIDEHER [ILLUSTRATION: simple line drawing of belt at high-hip position on a body silhouette] Wear at your high hip — just above your hipbone. Tighten for speed. Loosen for comfort. Adjust mid-run without stopping. — CARE 🫧 Machine wash cold 🌀 Tumble dry low 🚫 No iron 🚫 No bleach — JOIN THE COMMUNITY 📸 @strideher 🎵 @strideher #RunYourWay Tag us in your runs — we repost every one. | Layout (back — the "reference" side): • How to wear: top 40%. Simple line illustration showing belt position on body (commission from Fiverr for $15-30 or create in Canva). Clear, visual, eliminates the #1 customer confusion: "where do I wear this?" • Wearing instructions: 3 lines, Inter Regular, 8pt. • Care symbols: centered row, middle section. • Social handles: bottom 30%. Instagram + TikTok icons with handles. Hashtag #RunYourWay. • "Tag us" CTA: the most effective UGC driver. When customers see "we repost every one," they tag you. UGC = free content + social proof. The back is a KEEP-FOREVER reference card. Customers pull it out of a drawer months later to check care instructions or find the social handle. Design it to be useful long-term. | Reference: Stio insert cards (outdoor brand, care instructions + community CTA on reverse). Cotopaxi (illustration-forward, adventure community focus). The line illustration of belt position is critical — reduces "how do I wear this?" customer service emails by 60-80%. | Full-color back (or 2-color: Midnight + Desert Rose). Illustration: simple line art, NOT a photograph. Line art prints cleaner at small size and reads faster.
BRAND STICKER (seals the folded belt inside the mailer — the "peeling" moment)
BRAND STICKER | 1.5" diameter circle (38mm) Vinyl or paper stock Gloss or matte finish Removable adhesive (peels cleanly) | ONE SIDE | StrideHer icon mark (monogram "S" or wordmark) on Desert Rose (#C07C7C) background OR "Run Your Way." text on Midnight (#1A1A1A) background with white text | Circle sticker seals the folded belt. Customer peels it off to unfurl the belt. This is a micro-moment of tactile interaction. It's also a portable brand touchpoint — customers who like the sticker put it on their water bottle, laptop, or phone case. Design both options in Canva. Choose the one that looks better at 1.5" circle size. | Reference: Glossier stickers (became a cultural icon — customers plaster them everywhere). Tracksmith stickers (given at events). Even $0.04 stickers become marketing assets when designed well. | $0.04-$0.06/unit at 500 qty (Sticker Mule ~$29/50 or Alibaba ~$0.02/unit at 500+) Order 500: 300 for packages + 200 for events, influencer kits, giveaways.

## 2C.04 Supplier Sourcing
P2C TASK 2C.04: PACKAGING SUPPLIER COMPARISON — 5 OPTIONS SCORED ON 8 CRITERIA
You can source ALL packaging from one supplier or split across specialists. At 300 unit volume, simplicity wins — fewer vendors = less coordination.
Supplier | Type | Poly Mailers | Hang Tags | Insert Cards | Stickers | Lead Time | Best For
SUPPLIER OPTIONS — compare and select PRIMARY for each item (or bundle with one supplier)
Your Belt Manufacturer (Alibaba) | Bundled (packaging added to belt order) | ✅ Can produce $0.15-$0.25/unit 1-color print Pros: single shipment with belts, no separate order Cons: print quality may be basic | ✅ Can produce $0.06-$0.10/unit Basic printing Pros: arrives with belts, pre-attached Cons: limited finishing options (no soft-touch matte) | ✅ Can produce $0.03-$0.05/unit Full-color Pros: cheapest option, arrives with belts Cons: print quality varies, limited paper stock options | ❌ Usually not (different specialty) | 0 extra days (ships with belt production order) | ★ BEST FOR LAUNCH: Bundle poly mailers + hang tags with belt order. One shipment, one vendor, simplest logistics. Ask supplier if they can do soft-touch matte lamination on the hang tag. If yes: bundle everything except stickers.
Alibaba Packaging Specialist | Dedicated packaging supplier | ✅ Wide selection $0.12-$0.20/unit Custom sizes, eco options Pros: more material choices (kraft, compostable) Cons: separate order/shipment | ✅ Excellent quality $0.05-$0.08/unit Soft-touch, foil, emboss Pros: premium finishing available Cons: separate shipment from belts | ✅ Professional $0.03-$0.05/unit Full-color both sides Pros: wide paper stock selection, premium finishing Cons: separate shipment, longer proofing process | ✅ Available $0.02-$0.04/unit at 500+ qty | 15-20 days production + 7-10 days shipping | BEST FOR QUALITY: If your belt manufacturer can't do soft-touch finishing, source hang tags and insert cards from a dedicated Alibaba packaging supplier. Higher quality printing and finishing. MOQ typically 500-1,000 units.
Sticker Mule (US-based) | US on-demand | ✅ Custom poly mailers $0.35-$0.50/unit at 100 qty Pros: fast (5-day turnaround), no MOQ stress, great quality Cons: 2-3× more expensive than Alibaba | ✅ Custom hang tags $0.20-$0.30/unit Pros: fast, premium quality, small qty OK Cons: expensive at scale | ❌ Not available (Sticker Mule doesn't do standard cards) Use MOO or Vistaprint for US-printed insert cards. | ✅ Excellent $0.06-$0.10/unit at 50-300 qty Best sticker quality in the market. Fast turnaround. | 5-7 business days (US shipping) | BEST FOR STICKERS: Sticker Mule is the default for branded stickers — fast, consistent quality, low minimum (50 stickers for ~$29). Use for stickers even if you source everything else from Alibaba.
noissue (eco-focused) | Eco packaging specialist | ✅ Compostable mailers $0.45-$0.65/unit Pros: certified compostable, strong eco branding Cons: 2-3× poly mailer cost | ✅ Eco hang tags $0.15-$0.25/unit Recycled/FSC paper Pros: strong sustainability story Cons: higher price point | ✅ Custom cards $0.08-$0.12/unit Pros: eco-certified, premium quality Cons: ~2× Alibaba price | ✅ Eco stickers $0.08-$0.12/unit | 10-15 business days | BEST FOR ECO POSITIONING: If sustainability is a core brand pillar, noissue packaging tells that story at every touchpoint. Premium pricing. Consider for v2 packaging upgrade after validating customer willingness to pay.
Canva Print + Vistaprint (for insert cards) | US print-on-demand | ❌ Not available | ❌ Not available | ✅ Business cards / postcards $0.05-$0.10/unit at 250-500 qty Vistaprint: 250 postcards ~$30-50 Canva Print: similar pricing Pros: design in Canva → order directly, fast, preview online Cons: limited premium finishing | ❌ Not available | 5-10 business days (US shipping) | BEST FOR SIMPLICITY: Design insert cards in Canva Pro, then order prints directly through Canva Print or export and order from Vistaprint. Eliminates the design → export → upload → proof cycle. Good for first 300 cards.
RECOMMENDED SOURCING STRATEGY FOR LAUNCH (minimize cost + vendors)
★ RECOMMENDED PACKAGING SOURCING PLAN | BUNDLE: mailers + hang tags | Source from your belt manufacturer (Alibaba). Ask them to produce poly mailers + hang tags alongside the belt production order. Ships together = one shipment, zero extra logistics. | Source from Alibaba packaging specialist IF belt manufacturer can't do soft-touch finishing. Otherwise bundle. | Design in Canva Pro → order from Canva Print or Vistaprint. 250-500 qty = $30-50. Fastest, simplest, decent quality. | Order from Sticker Mule. 500 stickers = ~$85-$120. Best quality, fast turnaround. | Mailers + tags: ship with belts. Insert cards: print in US (1 week). Stickers: Sticker Mule (1 week). | TOTAL PACKAGING COST: $0.53-$0.57/unit (in line with P0E/P1B target of $0.55/unit) Mailer: $0.25 Hang tag: $0.08 Insert card: $0.05 Sticker: $0.05 Cord/ribbon: $0.02 Total: ~$0.45-$0.55 + sticker ~$0.05 = $0.50-$0.60

## 2C.05 Order Specifications
P2C TASK 2C.05: COMPLETE ORDER SPEC — QUANTITIES, ARTWORK FILES, AND DELIVERY TIMELINE
Use this sheet as your purchase order checklist. Every item, quantity, artwork file, and deadline in one place.
Item | Quantity | Why This Quantity | Artwork File Needed | Proofing Requirement | Delivery Deadline | Estimated Cost
Recycled Poly Mailer (10" × 13") | 350 (300 + 50 buffer) | 300 belts to ship + 50 extras for: replacements, influencer packages, photography/video shoots, event giveaways. 15% buffer is standard for packaging (misprints, damage in transit). | Mailer_Artwork_10x13_PRINT-READY.pdf Create in Canva Pro at actual size (10×13") with 3mm bleed. 300 DPI. CMYK color mode. StrideHer wordmark + tagline + "100% Recycled Material" text. | Request 1 printed proof from supplier. Inspect: logo size, color accuracy (Desert Rose), print position, seal adhesive quality. Approve in writing before production run. | Ship with belt production order (arrive together) | $70-$90 at $0.20-$0.25/unit
Hang Tag (3.5" × 2") | 350 (300 + 50 buffer) | 300 for belt packaging (1 per belt, pre-attached via cord to buckle D-ring) + 50 extras for samples, influencer kits, photography props. | HangTag_Front_PRINT-READY.pdf HangTag_Back_PRINT-READY.pdf Create in Canva Pro at 3.5×2" with 3mm bleed. Front: wordmark + tagline + descriptor. Back: micro-story + care icons + URL + size/color fields. | Request 1 printed proof. Check: paper stock weight (350 GSM), soft-touch matte finish (should feel velvety), eyelet hole centered, cord attachment, print clarity on both sides. | Ship with belt production order | $20-$35 at $0.06-$0.10/unit
Insert Card (4" × 6") | 500 (300 + 200 extra) | 300 for belt packaging (1 per order) + 200 extras for: influencer packages (20), event handouts (50), trade shows (50), spare stock (80). Insert cards are the CHEAPEST and MOST VERSATILE marketing tool — order 200 more than you think you need. | InsertCard_Front_PRINT-READY.pdf InsertCard_Back_PRINT-READY.pdf Create in Canva Pro at 4×6" with 3mm bleed. Full-color both sides. Front: thank you + QR code + discount code. Back: how-to-wear illustration + care + social handles. | Request 1 printed proof. CRITICAL: test the QR code on the proof — scan it with your phone. If the QR doesn't work on the proof, it won't work on 500 printed cards. Also check: paper weight, lamination, color accuracy. | Order from Canva Print / Vistaprint 5-10 business days (order 2-3 weeks before launch) | $25-$50 at $0.05-$0.10/unit
Brand Sticker (1.5" circle) | 500 (300 + 200 extra) | 300 for sealing folded belts inside mailers + 200 extras for: event giveaways, influencer kits, laptop sticker culture (customers love free stickers), surprise inclusion in orders. | Sticker_Circle_38mm_PRINT-READY.pdf Design in Canva Pro. 1.5" diameter circle. StrideHer icon on Desert Rose background OR "Run Your Way." on Midnight background. | Sticker Mule provides digital proof before printing. Approve online. Check: color accuracy, cut line (circle should be precise), adhesive type (removable preferred). | Order from Sticker Mule 5-7 business days | $85-$120 at 500 qty from Sticker Mule ($0.17-$0.24/unit — higher than Alibaba but faster + US-based)
Cotton Cord for Hang Tags | 350 pieces × 6" (15cm) each | Pre-cut cords for threading through hang tag eyelet and attaching to belt buckle D-ring. Color: Desert Rose or Midnight. | No artwork needed. Specify: 1.5mm diameter cotton cord, pre-cut to 6" (15cm), color Desert Rose (#C07C7C) or Midnight (#1A1A1A). | No proof needed — order based on color swatch. | Source from Alibaba or Amazon (craft cord / jewelry cord) | $5-$15 for 350 pieces (~$0.02-$0.04/unit) Alternatively: ask belt manufacturer to string hang tags during production.
TOTAL ORDER COST | — | All 5 packaging items across recommended sourcing strategy. | Total artwork files to create: 5 PDF files (mailer, hang tag front, hang tag back, insert card front, insert card back) + 1 sticker file = 6 print-ready PDFs. | Total proofs to approve: 4 (mailer, hang tag, insert card, sticker). Allow 2-3 days for proofing per item. | All items ready 1-2 weeks before launch date. | $205-$310 total This covers ALL packaging for 300+ belt orders. At $0.55/unit: exactly within the P0E budget target.

## 2C FOUNDER ACTIONS
P2C PACKAGING — FOUNDER ACTION CHECKLIST
All packaging design + ordering should be completed BEFORE belt production finishes. Target: packaging ready 1-2 weeks before launch.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 7: DESIGN ALL PACKAGING (while waiting for belt samples)
🔴 #1 | Design all 6 print-ready artwork files in Canva Pro | 3-4 hrs | $0 (Canva Pro $13/mo) | 1. Open Canva Pro. Create 6 designs using brand kit (colors, fonts from P1B): a) Poly mailer artwork (10×13", 1-color) b) Hang tag front (3.5×2") c) Hang tag back (3.5×2") d) Insert card front (4×6") e) Insert card back (4×6") f) Brand sticker (1.5" circle) 2. Use EXACT copy from Sheet 2C.02-03 — every word is finalized 3. For the insert card back: commission a simple line illustration of belt wearing position from Fiverr ($15-30) or draw in Canva using basic shapes 4. Generate QR code: use qr-code-generator.com → link to your Shopify product review page URL 5. TEST the QR code on your phone before placing it in the design 6. Export all files as PDF Print (300 DPI, CMYK, 3mm bleed)
🔴 #2 | Create and test the QR code for the insert card | 15 min | $0 | 1. Go to qr-code-generator.com (free) 2. Enter URL: your Shopify product review page (set up the Shopify store first, even as a placeholder) 3. Download QR code as high-res PNG (600×600px minimum) 4. TEST: scan with your phone camera. Does it go to the right page? 5. TEST: print the QR code on paper at the insert card size (30×30mm). Does it still scan at that size? 6. If scan fails at small size: increase QR code size to 35×35mm or simplify the URL (use a short link)
WEEK 8: ORDER ALL PACKAGING
🟡 #3 | Ask your belt manufacturer to quote poly mailers + hang tags as a bundle | 30 min | $0 | 1. Email your selected belt supplier (from P2B) 2. Attach: mailer artwork PDF + hang tag front/back PDFs 3. Ask: "Can you produce 350 custom poly mailers + 350 hang tags alongside our belt order? Please quote separately." 4. If their quote is within $0.25/mailer and $0.10/tag: bundle with belt order (simplest) 5. If quote is higher: source from Alibaba packaging specialist instead
🟡 #4 | Order insert cards from Canva Print or Vistaprint | 15 min | $30-$50 | 1. Upload insert card front/back PDFs 2. Select: 4×6" postcards, 350 GSM (or "thick" option), matte finish 3. Quantity: 500 4. Review digital proof carefully — check QR code, discount code spelling (HERSTRIDE10), all social handles correct 5. Order. Delivery: 5-10 business days to your address. 6. When cards arrive: scan the QR code on a PRINTED card. If it works → you're set.
🟡 #5 | Order brand stickers from Sticker Mule | 15 min | $85-$120 | 1. Go to stickermule.com → Custom Stickers → Die Cut or Circle 2. Upload sticker artwork PDF 3. Select: 1.5" circle, matte or gloss, quantity 500 4. Approve digital proof (Sticker Mule sends within 4 hours) 5. Order. Delivery: 5-7 business days. 6. When stickers arrive: test adhesive on the actual poly mailer. Sticks securely? Peels cleanly? If yes → approved.
WEEK 9: QUALITY CHECK + ASSEMBLY PREP
🟢 #6 | Inspect all packaging when it arrives — check every element | 1 hr | $0 | 1. Mailers: open 3 random mailers. Check logo position, color, seal adhesive, size. Insert a folded belt — does it fit? 2. Hang tags: check 5 random tags. Paper weight (feel vs a playing card — should be thicker), soft-touch feel, eyelet hole, text legibility, care symbols correct 3. Insert cards: check 5 random cards. QR code scan test on printed card. Discount code correct. Colors match. Lamination present on front. 4. Stickers: peel 2 stickers. Adhesive clean? Sticks to poly mailer surface? 5. If ANY element fails: contact supplier immediately for replacement/correction before launch
🟢 #7 | Create packing SOP and practice packing 5 orders | 30 min | $0 | 1. Write a simple packing checklist: (a) fold belt, (b) seal with sticker, (c) attach hang tag via cord to D-ring, (d) place insert card face-up on top, (e) slide into mailer, (f) seal mailer, (g) attach shipping label 2. Practice pack 5 belts start to finish. Time yourself. 3. Target: <2 minutes per order for packing 4. Take photos of the finished package at each step — use for your packing SOP document 5. This packing process IS the customer's first impression. It should feel intentional, not sloppy.