## P2E EXEC SUMMARY
P2E QUALITY STANDARDS & TESTING PROTOCOLS — EXECUTIVE SUMMARY
5 Tasks ¦ Weeks 8-10 ¦ The last line of defense before 600 units ship. A 2% defect rate = 12 angry customers. A 0.5% rate = 3 easy fixes.
Task ID | Task | KPI | Deliverable | Status | Why This Matters | Depends On
2E.01 | Define quality acceptance criteria: stitching, zipper pull force, elastic recovery, color match | 20+ measurable criteria documented | Complete acceptance criteria table: 24 measurable quality standards with test method, pass threshold, and defect classification (critical/major/minor). Based on ISO/AQL industry standards adapted for running belt manufacturing. | COMPLETE ✓ | Without measurable criteria, "quality" is subjective. When a unit arrives and the zipper feels "kinda stiff," is that a defect or normal? Acceptance criteria turn subjective judgments into objective pass/fail decisions. This protects you AND the supplier — both parties agree on what "good" means before production begins. | P2A.03 (tech spec)
2E.02 | Create incoming quality inspection checklist for when 600 production units arrive | Inspection checklist with sampling plan | AQL-based sampling plan: how many units to inspect out of 600, what to check on each, pass/fail tallying, and accept/reject decision framework. Based on ISO 2859-1 (the international sampling standard used by Nike, Adidas, and every major apparel brand). | COMPLETE ✓ | You cannot inspect all 600 units (that would take 50+ hours). A statistically valid sampling plan tells you how many to inspect (32 units at AQL 2.5) and how many defects are acceptable before rejecting the entire shipment. This is what the pros use. | 2E.01 (acceptance criteria)
2E.03 | Test production samples for skin safety: OEKO-TEX, CPSIA, FTC labeling | Compliance checklist with required certifications | Complete regulatory compliance guide: OEKO-TEX Standard 100 verification, CPSIA (US Consumer Product Safety) requirements, FTC textile labeling rules (fiber content, country of origin, care instructions), and California Prop 65 awareness. | COMPLETE ✓ | Selling a body-worn product without safety compliance exposes you to: product liability lawsuits, Amazon listing removal, customs seizure, and FTC enforcement. OEKO-TEX is voluntary but increasingly expected by US/EU retailers. FTC labeling is MANDATORY for US textile sales. | P2A.04 (materials spec)
2E.04 | Define return/defect handling process: what is a defect, replacement vs refund, communication templates | Complete defect classification + customer communication playbook | Defect classification system (what qualifies for replacement vs refund vs "not a defect"), customer communication templates for each scenario, internal tracking process, and defect-to-supplier escalation workflow. | COMPLETE ✓ | The first defect report arrives within 2 weeks of launch. Without a pre-built process, the founder panic-responds inconsistently. A documented process ensures every customer gets the same quality of resolution, AND defect data feeds back to the supplier for continuous improvement. | P1C.08 (review response templates)
2E.05 | Establish production quality agreement with supplier: defect tolerance, replacement terms, inspection rights | Supplier quality agreement template ready to send | Copy-paste-ready supplier quality agreement covering: AQL defect rate tolerance, replacement/credit terms for excess defects, pre-shipment inspection rights, production sample retention, and dispute resolution process. This becomes a formal appendix to your manufacturing order. | COMPLETE ✓ | Without a written quality agreement, you have no recourse when 15% of units arrive with misaligned zippers. The supplier will say "normal for this price." A pre-agreed AQL standard with replacement terms gives you contractual leverage to demand corrections or credits. | 2E.01 (criteria), 2E.02 (AQL plan)

## 2E.01 Acceptance Criteria
P2E TASK 2E.01: 24 MEASURABLE QUALITY ACCEPTANCE CRITERIA
Every criterion has a TEST METHOD and a PASS/FAIL threshold. Share this sheet with your supplier BEFORE production begins — both parties must agree on what "acceptable quality" means.
# | Category | Quality Criterion | Test Method | Pass Threshold | Defect Class | Defect Example | Consequence if Failed
CRITICAL DEFECTS — any single critical defect = unit is rejected. AQL 0 (zero tolerance).
1 | Zipper | Phone pocket zipper function | Open and close zipper 5 times. Test auto-lock at 3 positions. | Smooth operation all 5 cycles. Auto-lock holds at all 3 positions. Zero catches, skips, or jams. | CRITICAL | Zipper jams on first use. Auto-lock doesn't hold — zipper slides open during movement. Slider detached or loose. | Unit rejected. Replace. Log defect code Z1. If >1% of sample: halt shipment, demand re-work.
2 | Zipper | Valuables pocket zipper function | Same 5-cycle test as phone pocket. | Same smooth operation standard. | CRITICAL | Same as above for valuables zipper. | Same as above. Defect code Z2.
3 | Phone Fit | Phone pocket fits iPhone 16 Pro Max + case | Insert a dimensional block (175×91×17mm) or actual phone+case into pocket. | Block inserts and extracts smoothly one-handed. Zipper closes fully over block without bulging or straining. | CRITICAL | Phone doesn't fit. Zipper won't close over phone. Pocket too narrow or too shallow. | Unit rejected. Entire batch suspect — measure 10 more units. If systemic: reject shipment, require pattern correction.
4 | Safety | No sharp edges on hardware | Run finger along all buckle edges, D-rings, zipper endpoints, snap hooks. | Zero sharp edges or burrs that could scratch skin or snag clothing. | CRITICAL | Buckle edge cuts finger during inspection. Zipper endpoint pokes through fabric. D-ring has rough burr. | Unit rejected. Defect code H1. Sharp hardware = product liability risk. Zero tolerance.
5 | Safety | Silicone grip — no peeling on arrival | Scratch each visible silicone dot with thumbnail firmly. | Zero dots peel or lift on a new, unwashed unit. | CRITICAL | Dots peel on a brand-new unit before any wash or use. Indicates adhesion failure in manufacturing. | Unit rejected. Defect code S1. If >2% of sample: reject shipment, demand re-application.
MAJOR DEFECTS — affect product function or customer satisfaction. AQL 2.5 (max 2 per 80-unit sample).
6 | Dimensions | Elastic length within spec | Measure unstretched elastic from male buckle end to female buckle end. | S/M: 68cm ±2cm. L/XL: 92cm ±2cm. | MAJOR | Elastic 5cm too short (tight at max setting). Elastic 5cm too long (can't cinch enough at min setting). | Defect code D1. Unit may be re-classified to other size if within that range, otherwise rejected.
7 | Dimensions | Front panel height | Measure center-front, top edge to bottom edge. | 9-10cm ±0.5cm. | MAJOR | Front panel 8cm (too short — loses contoured benefit) or 11cm (too tall — looks like a corset). | Defect code D2. Indicates pattern cutting error.
8 | Dimensions | Rear panel height | Measure center-back. | 6.5-7.5cm ±0.5cm. | MAJOR | Rear same height as front (contoured profile not implemented). Or rear shorter than 6cm (belt gaps at lower back). | Defect code D3. If rear = front height on >10% of units: systematic pattern error, reject batch.
9 | Color | Color match to approved lab dip | Compare unit fabric to approved lab dip swatch under D65 daylight illuminant (or natural daylight). | Within ±1.5 Delta E of approved lab dip. No visible color shift to naked eye under daylight. | MAJOR | Desert Rose looks brown/pink/grey instead of warm rose. Color mismatch between units in same batch. | Defect code C1. Slight lot-to-lot variation acceptable (±1.5 dE). Gross mismatch = reject colorway.
10 | Stitching | Flatlock seams on skin-contact edges | Run finger along all edges that touch skin: waistband top/bottom, pocket openings. | All skin-contact edges are flatlock (smooth, flat). Zero raw/exposed serged edges touching skin. | MAJOR | Overlocked (rough) seam on skin-contact edge. Will cause chafing on runs >5 miles. | Defect code ST1. Indicates sewing machine setup error. Re-work if possible.
11 | Stitching | No loose threads | Visual inspection of all seams, pocket interiors, and label attachments. | Zero loose threads >10mm. No thread nests or bird-nesting on interior. | MAJOR | Long thread tail hanging from pocket corner. Thread nest inside pocket could trap items. | Defect code ST2. Trim if <20mm. Reject if thread compromises seam integrity.
12 | Hardware | Buckle snap engagement | Open and close buckle 5 times. | Clean snap closed with audible click. Opens with one-handed center-push. No excessive force. | MAJOR | Buckle doesn't click — falls open under tension. Requires two hands or excessive force to open/close. | Defect code H2. Usually indicates wrong buckle model or damaged gate spring.
13 | Hardware | Magnetic snap-tab force | Open and close gel pocket snap-tab 5 times. | Secure magnetic hold when closed (doesn't flap open when shaken). Opens easily with single finger pull. | MAJOR | Magnet too weak (tab pops open during shaking — items will fall out). Magnet too strong (can't open one-handed). | Defect code H3. Magnet strength specification: 0.3-0.5 kg pull force.
14 | Materials | 4-way stretch verification | Pull fabric in warp AND weft directions. | Stretches ≥40% in BOTH directions with immediate snap-back recovery. | MAJOR | Only stretches in one direction (2-way stretch). Wrong fabric supplied. | Defect code M1. 2-way stretch = WRONG FABRIC. Reject entire shipment. Supplier substituted cheaper material.
15 | Construction | Pocket-to-waistband attachment | Pull each pocket gently but firmly away from waistband. | All 3 pockets firmly attached. Bartack reinforcement visible at stress points. No gaps between pocket and elastic. | MAJOR | Pocket partially detached. Gap visible between pocket edge and waistband. Will separate under load. | Defect code ST3. Indicates missed bartack or sewing alignment error.
16 | Reflective | Reflective strips present and bonded | Visual check + flash photography to confirm reflectivity. | 2 strips present (front + rear, each ~10cm). Reflective when photographed with flash. No lifting corners. | MAJOR | Strips missing, wrong position, or partially peeled on arrival. | Defect code R1. Missing reflective = safety feature absent.
MINOR DEFECTS — cosmetic issues that don't affect function. AQL 4.0 (max 5 per 80-unit sample).
17 | Visual | Brand label position | Check woven label at center-rear exterior. | Centered ±5mm. Straight (not tilted >5°). Text legible. No fraying. | MINOR | Label off-center by 8mm. Label slightly tilted. Edge fraying. Cosmetic, not functional. | Defect code V1. Log but accept if functional. Fix in next production run.
18 | Visual | Symmetry of pocket placement | Lay belt flat and measure left pocket vs right pocket distance from center. | Left-right pocket symmetry ±5mm. | MINOR | Left pocket 8mm higher than right. Visible asymmetry when laid flat. Not noticeable when worn. | Defect code V2. Minor cosmetic. Accept if <10mm.
19 | Color | Dye evenness across unit | Inspect fabric under natural light for blotchy or uneven dye application. | Even, uniform color across entire belt surface. No blotchy spots, streaks, or fade zones. | MINOR | Slight color variation at seam overlap. Small area of lighter dye. Only visible on close inspection. | Defect code C2. Common in reactive dyes. Accept if not visible at arm's length.
20 | Materials | Fabric feel consistency | Touch-compare 5 random units from the batch. | All units feel the same — consistent fabric weight, hand feel, and stretch. | MINOR | One unit feels thinner or scratchier than the others. Indicates mixed fabric lots in production. | Defect code M2. If >5% of sample feels different: supplier may have substituted fabric partway through run.
21 | Construction | Care label content | Read care label inside rear waistband. | Correct size (S/M or L/XL), correct care symbols (ISO 3758), "Made in China" or "Imported," strideher.com URL. | MINOR | Wrong size printed. Missing care symbol. Missing country of origin (FTC violation — upgrade to MAJOR if COO missing). | Defect code V3. Wrong size label = classify unit to correct size. Missing COO = FTC compliance issue.
22 | Hardware | Cord/ribbon on hang tag | Check hang tag attachment cord. | 6" cotton cord through eyelet, color matched (Desert Rose or Midnight), looped through belt D-ring. | MINOR | Wrong cord color. Cord too short to loop through D-ring. Missing entirely. | Defect code V4. Easy fix: re-string during packing. Order spare cords.
23 | Packaging | Correct size sticker/label on poly mailer | Check that size designation on exterior matches the belt inside. | S/M mailer contains S/M belt. L/XL mailer contains L/XL belt. Color label matches belt color. | MINOR | S/M belt in L/XL mailer. Wrong color label. Customer receives wrong expectation. | Defect code P1. Re-label during packing QC. Critical to verify during fulfillment.
24 | Construction | Internal key clip function | Test snap hook on webbing loop inside valuables pocket. | Snap hook opens/closes smoothly. Webbing loop intact, ~50mm length. | MINOR | Snap hook stiff or misaligned. Webbing loop frayed. Functional but imperfect. | Defect code H4. Accept if functional. Note for next production improvement.

## 2E.02 Incoming Inspection
P2E TASK 2E.02: INCOMING QUALITY INSPECTION — AQL SAMPLING PLAN FOR 600 UNITS
Based on ISO 2859-1 (used by Nike, Adidas, Zara). You inspect 32 units out of 600. Takes 4-6 hours. This catches problems BEFORE customers do.
Step | Action | Details | Time | Accept / Reject Decision | Tools Needed | Record
AQL SAMPLING PLAN — ISO 2859-1, General Inspection Level II
— | Lot Size: 600 units Sample Size: 32 units (per ISO 2859-1 Table) Inspection Level: General Level II (standard) AQL for Critical defects: 0 (zero tolerance) AQL for Major defects: 2.5 (accept ≤2 in sample of 32) AQL for Minor defects: 4.0 (accept ≤5 in sample of 32) | This means: randomly pull 32 units from the shipment (do NOT let the supplier choose which units). Inspect all 32 against the 24 acceptance criteria from Sheet 2E.01. If you find 0 critical defects, ≤2 major defects, and ≤5 minor defects → ACCEPT the shipment. If ANY threshold is exceeded → REJECT or negotiate. | Overview | Memorize these thresholds: 🔴 Critical: 0 allowed (1 = reject) 🟡 Major: ≤2 allowed (3+ = reject) 🟢 Minor: ≤5 allowed (6+ = reject) |  | Write these thresholds on a sticky note and attach to your inspection table.
INSPECTION WORKFLOW (follow this exact sequence)
Step 1 | Unbox and count | Open shipment. Count total units. Verify: correct total (should be 600). Verify: correct size split (270 S/M + 330 L/XL or your specified allocation). Verify: correct color split per your order. | 30 min | If count is short: document shortage immediately. Email supplier with photos of shipment and packing list. Short shipments are common — catch it before signing delivery receipt if possible. | Packing list from supplier, calculator | Total units received: ___ S/M count: ___ L/XL count: ___ Black: ___ Rose: ___ Sage: ___ Ocean: ___
Step 2 | Random sample selection | Pull 32 units randomly: select every ~19th unit from the shipment (600÷32≈19). Pull from different boxes, different positions in the shipment. Include all sizes and all colors in proportional representation. | 15 min | Do NOT let the supplier select your sample units. Do NOT pull from the top of the first box only (suppliers sometimes put their best units on top). True random sampling is essential for statistical validity. | Notepad to number each pulled unit 1-32 | Sample unit numbers: 1 through 32. Note which size/color each sample is.
Step 3 | Visual sweep (30 seconds per unit) | For each of the 32 units: hold at arm's length. First impression — does it look right? Check: color, symmetry, labels, overall craftsmanship. Flag any obvious issues for detailed inspection. | 16 min (32 × 30 sec) | This quick sweep catches gross defects (wrong color, missing pocket, crooked label) without spending detailed time. Flag any unit that "looks off" for Step 4 deep inspection. | Good lighting (natural daylight preferred) | Tally: ___ units flagged for detailed inspection
Step 4 | Detailed inspection (5-7 min per unit) | For all 32 units: work through the 24 acceptance criteria from Sheet 2E.01. Use the checklist — score each criterion. Test zippers (5 cycles), check phone fit (insert block/phone), verify elastic length, check silicone dots, check reflective strips, check flatlock seams. | 2.5-3.5 hrs (32 × 5-7 min) | This is the core inspection. Work methodically through all 24 criteria for EVERY sample unit. Don't skip criteria because the first 10 units looked fine — defects can cluster in specific production batches. | Measuring tape, dimensional block (175×91×17mm) or phone+case, Pantone chips for color, camera for flash/reflective test | Per-unit inspection form: Critical defects found: ___ Major defects found: ___ Minor defects found: ___
Step 5 | Tally defects | Count total defects across all 32 sample units. Critical total: ___ Major total: ___ Minor total: ___ Compare against AQL thresholds. | 15 min | ACCEPT if: ✅ Critical = 0 ✅ Major ≤ 2 ✅ Minor ≤ 5 REJECT if: ❌ Critical ≥ 1 ❌ Major ≥ 3 ❌ Minor ≥ 6 | Calculator | INSPECTION RESULT: Critical: ___ / 0 allowed Major: ___ / 2 allowed Minor: ___ / 5 allowed DECISION: ACCEPT / REJECT
Step 6 | Decision and action | Based on Step 5 tally, make your decision and take appropriate action. | 30 min | IF ACCEPT: sign off inspection, proceed to packaging/fulfillment preparation. Store inspection records. IF REJECT — 3 options: A) Request supplier re-work and re-ship defective units (free if under quality agreement) B) Negotiate partial credit for defective portion C) Accept with deduction and sort/fix defective units yourself Always email supplier with: defect photos, defect counts, reference to quality agreement terms. | Camera (photos of defects for supplier communication), email | Decision: ___ Action taken: ___ Supplier notified: Y/N Date: ___
TOTAL INSPECTION TIME: 4-6 HOURS for 600 units. Assign a full half-day. Do NOT rush this.

## 2E.03 Safety Compliance
P2E TASK 2E.03: REGULATORY COMPLIANCE — OEKO-TEX + CPSIA + FTC LABELING + PROP 65
Selling a body-worn product in the US requires: FTC textile labeling (mandatory), OEKO-TEX (strongly recommended), CPSIA compliance (mandatory for consumer products). Non-compliance = legal liability.
Requirement | What It Is | Mandatory? | What You Must Do | Cost | Timeline | Consequence of Non-Compliance
US FEDERAL REQUIREMENTS (these are LEGAL obligations, not optional)
FTC Textile Labeling (16 CFR 303) | The Federal Trade Commission requires ALL textile products sold in the US to have a label stating: (1) fiber content by percentage, (2) country of origin, (3) manufacturer/importer name or RN/WPL number. This is the care label sewn inside your belt. | ✅ YES MANDATORY US federal law | 1. Verify your care label includes: • Fiber content: "80% Nylon, 20% Spandex" (match actual fabric) • Country of origin: "Made in China" or "Imported" • Your company name OR apply for an RN (Registered Number) at rn.ftc.gov (free) • Care instructions using ISO 3758 symbols 2. Fiber content must match ACTUAL fabric composition. If the supplier uses 85/15 nylon-spandex instead of the specified 80/20, the label must reflect reality. 3. RN number is optional but professional — register at rn.ftc.gov (free, takes 2-3 weeks). | $0 (label is already in production spec from P2A) | Verify during sample approval (P2B.02). RN registration: 2-3 weeks. | FTC enforcement: warning letter → fines ($10,000+ per violation). Amazon requires FTC-compliant labeling — non-compliant products can be removed from the marketplace. In practice: most small brands fly under the radar initially, but any competitor or customer complaint triggers review.
CPSIA Compliance (Consumer Product Safety Improvement Act) | CPSIA applies to all consumer products sold in the US. For adult textile products (not children's), the key requirements are: (1) General Certificate of Conformity (GCC) that the product meets all applicable safety standards, and (2) reasonable testing to support the GCC. For an adult running belt, the applicable standards are primarily: lead content in surface coatings (unlikely issue for textiles), and flammability (16 CFR 1610 for clothing textiles). | ✅ YES MANDATORY (but requirements for adult textiles are lighter than children's) | 1. Request from your supplier: a General Certificate of Conformity (GCC) stating the product meets applicable US safety standards. 2. If your supplier has OEKO-TEX Standard 100 certification, this substantially covers CPSIA chemical safety requirements. 3. Create a simple GCC document for your own records: • Product: StrideHer Women's Running Belt • Manufacturer: [supplier name and address] • Applicable standards: 16 CFR 1610 (flammability), CPSIA Section 101 (lead) • Testing basis: OEKO-TEX Standard 100 Class II certification of materials • Date issued: [date] • Certifier: [your name/company name] | $0-$200 (if supplier already has OEKO-TEX, cost is $0. If you need independent testing: $200 per test) | Before first shipment. GCC must be on file before selling. | CPSC (Consumer Product Safety Commission) can: seize products at customs, issue recalls, levy fines up to $100,000 per violation. For an adult textile belt, the risk is LOW but having a GCC on file is essential documentation if ever challenged.
VOLUNTARY BUT STRONGLY RECOMMENDED
OEKO-TEX Standard 100 (skin safety) | OEKO-TEX Standard 100 is a global certification that textiles are free from harmful chemicals (heavy metals, formaldehyde, pesticides, phthalates, allergenic dyes). Class II covers products with direct skin contact (which includes a waist-worn running belt). This is NOT legally required but it's the global standard for consumer trust in textile safety. | ❌ Voluntary But STRONGLY recommended. Required for EU/UK retail partnerships. | 1. EASIEST APPROACH: Source from a supplier that ALREADY holds OEKO-TEX Standard 100 certification. Ask during RFQ (P2B.01 Question Q8). 2. If supplier has OEKO-TEX: request their certificate number and verify at oeko-tex.com/en/our-standards/oeti-test-institute. Done. 3. If supplier does NOT have OEKO-TEX: you can either (a) accept the risk for US-only D2C sales, or (b) request the supplier get certified (their cost, $200-$500, takes 2-4 weeks), or (c) send fabric samples to an OEKO-TEX accredited lab yourself ($150-$300). 4. On your product page, only claim "OEKO-TEX certified" if you have a valid certificate. Otherwise use "Tested for harmful substances" or similar language. | $0 if supplier already certified. $150-$500 if new testing needed. | Verify during supplier selection. Certification takes 2-4 weeks if new. | No legal consequence for US D2C sales without OEKO-TEX. BUT: (1) EU/UK marketplace access increasingly requires it, (2) Amazon EU requires safety documentation, (3) any customer report of skin irritation without safety certification = major liability exposure, (4) your Amazon listing can claim "OEKO-TEX certified" which is a trust signal that converts.
California Proposition 65 (Prop 65) | California requires warning labels on products containing chemicals known to cause cancer or reproductive harm. For textiles, this typically applies to: certain dyes (azo dyes), nickel in hardware, lead in surface coatings, and phthalates in plastic components. Prop 65 lawsuits against small businesses have increased significantly — often filed by "bounty hunter" law firms. | ⚠️ Conditional Required if selling in CA (which includes all US online sales that ship to CA) | 1. If your supplier has OEKO-TEX Standard 100: you are substantially covered, as OEKO-TEX tests for the same chemicals Prop 65 regulates. 2. If NO OEKO-TEX: either (a) add a Prop 65 warning label/statement ("This product may expose you to chemicals including [X] which is known to the State of California to cause [cancer/reproductive harm]"), or (b) get independent lab testing for Prop 65 chemicals ($200-$400). 3. Most small D2C textile brands take approach (a) — add the generic warning as a precaution. It's free and eliminates lawsuit risk. 4. Add Prop 65 warning to: product page footer, shipping insert, or product label. | $0 (warning) or $200-$400 (testing) | Before first sale to CA (= before launch if selling online in US). | Prop 65 lawsuits: "bounty hunter" law firms file suits against businesses without warnings, seeking $2,500/day penalties + attorney fees. Adding the warning (even if your product is safe) eliminates this risk entirely. The warning is ugly but the alternative is worse.

## 2E.04 Defect Handling
P2E TASK 2E.04: RETURN & DEFECT HANDLING PROCESS — FROM CUSTOMER REPORT TO RESOLUTION
Pre-built workflow for every defect scenario. The first report arrives within 2 weeks of launch. Be ready.
Scenario | Classification | Customer Action | Your Action | Communication Template | Internal Tracking | Supplier Escalation
DEFECT CLASSIFICATION: Is it actually a defect, or customer misuse / preference?
Zipper jam / zipper failure | DEFECT (manufacturing) | Customer reports zipper won't open, catches, or slider broke. | 1. Apologize sincerely (use P1C.08 template #2) 2. Ask for a photo of the defect 3. Ship replacement belt SAME DAY — don't wait for return 4. Tell customer: "No need to return the defective one" 5. Log defect in tracker | "I'm so sorry about this. A jammed zipper is unacceptable and I take full responsibility. I'm shipping you a replacement today — you'll have tracking within 24 hours. Please keep the original or toss it, no return needed. If you can snap a quick photo of the stuck zipper and send to hello@strideher.com, it would help me improve quality. — [Name], Founder" | Log in Defect Tracker: • Date • Order # • Defect type: ZIPPER • Size/Color • Photo (if provided) • Resolution: REPLACEMENT • Cost: $6.50 COGS + $4.50 shipping = $11.00 | If zipper defects exceed 2% of orders in any month: escalate to supplier with photos + defect codes. Reference quality agreement clause on zipper AQL. Demand root cause analysis and corrective action plan.
Belt too loose / too tight at advertised size | NOT A DEFECT (sizing issue) | Customer says S/M is too loose at 26" waist, or L/XL is too tight at 42" waist. | 1. Respond warmly — this is a fit issue, not a quality issue 2. Offer FREE SIZE EXCHANGE (ship new size before return) 3. If at the extreme of size range: recommend belt extender (for large) or suggest wearing over a layer (for small) 4. Log as sizing feedback — patterns may need adjusting for v2 | "Thank you for reaching out. I want to make sure you have the perfect fit. I'd love to send you a [S/M or L/XL] — and you don't need to wait for the exchange. I'll ship the new size today and include a return label for the original. Would you prefer [other size]? — [Name], Founder" | Log in Sizing Feedback Tracker: • Waist measurement • Size ordered vs needed • Whether exchange or return If >15% of orders trigger size exchanges: sizing ranges may need adjustment in v2 production. | Not a supplier issue. This is product design feedback. Track for v2 improvements.
Silicone dots peeling after washing | DEFECT (manufacturing) | Customer reports grip dots coming off after 3-5 washes. | 1. Apologize (P1C.08 template approach) 2. Verify: did they follow care instructions? (wash cold, no bleach, no fabric softener) 3. If care was proper: ship replacement 4. If care was improper: explain why + offer 30% discount on replacement 5. Log defect | "I'm sorry about the grip dots — that shouldn't happen with normal washing. Could I ask: did you wash cold, without bleach or fabric softener? Fabric softener can break down the silicone bond. Either way, I want to make this right. [If proper care: I'm shipping a replacement today.] [If improper care: Let me send you a replacement at 30% off, and I'll include updated care instructions.]" | Log in Defect Tracker: • Defect: SILICONE • Washes before failure • Care method used • Resolution type Track wash-to-failure count to establish if systematic. | If silicone failures exceed 3% within first 10 washes: systematic adhesion issue. Escalate to supplier. Demand: re-test adhesion protocol, verify cure temperature, provide wash-test data for replacement batch.
Color different from website photos | NOT A DEFECT (expectation mismatch) | Customer says Desert Rose looks "more brown" or "not as pink" in person. | 1. Acknowledge the frustration (P1C.08 template #4) 2. Explain: screen color varies by device; offer to update product photos 3. Offer full return for refund if unsatisfied 4. Log as photo accuracy feedback — may need to reshoot | "You're right that screen colors can look different from the real thing — and I appreciate you telling me. Desert Rose is a warm muted rose that can look slightly different depending on lighting. If you're not happy with the color in person, our 30-day guarantee means a full refund, no questions asked. I'm also going to update our product photos to be more accurate. Thank you for the honest feedback. — [Name]" | Log in Product Feedback: • Color concerned • Specific complaint • Outcome (keep/return) If >10% of color-specific orders mention mismatch: reshoot product photos with better color accuracy. | Not a supplier issue. Photography and screen calibration issue. Update product photos per feedback.
Belt bounces or rides up during running | POSSIBLE DEFECT or USER ERROR | Customer says belt bounced or shifted during a run. | 1. Ask: where are they wearing it? (Natural waist vs high hip) 2. Ask: is it loaded? What's in each pocket? 3. If wearing position is wrong: guide to high-hip position (share size guide illustration) 4. If position is correct and belt still bounces: offer exchange for other size (may be too loose) 5. If persistent after correct position + correct size: may be genuine defect — request return for inspection | "Thanks for reaching out — I want to help fix this. Two quick questions: (1) Where are you wearing the belt? It works best at your high hip, right above your hipbones — about 2 inches below your belly button. (2) Is it tightened snugly? Many runners start too loose. If it's already at high hip and snug, it might be the wrong size — and I'd love to send you a different one to try. Just let me know your waist measurement and I'll sort it out." | Log as either: • SIZING issue (wearing wrong or wrong size) — track for size guide improvement • DEFECT (genuine bounce with correct use) — inspect returned unit for silicone dot coverage, elastic tension | If genuine bounce defects exceed 5%: escalate. Check: silicone dot coverage area (must be 50-60% interior), elastic tension specification, and contoured profile accuracy.
Customer wants return within 30 days (no defect) | RETURN (satisfaction guarantee) | Customer simply doesn't want the belt. No defect, no sizing issue. Changed their mind. | 1. No questions asked — honor the 30-day guarantee 2. Provide prepaid return label (or tell them to keep it if cost of return shipping > COGS) 3. Issue full refund upon return receipt (or immediately if "keep it" policy) 4. Ask ONE optional question: "Would you mind sharing what didn't work? It helps us improve." | "No problem at all — I'm sorry it wasn't right for you. Here's a prepaid return label: [link]. Once we receive it, you'll get a full refund within 2 business days. If you have a moment, I'd love to know what didn't work — but totally optional. Thank you for giving us a try. — [Name]" | Log in Returns Tracker: • Reason (if provided) • Size/Color returned • Date returned • Refund issued date Track return rate: target <5% for healthy D2C. | Not applicable. Track return reasons for product improvement.

## 2E.05 Supplier Quality Agmt
P2E TASK 2E.05: SUPPLIER QUALITY AGREEMENT — SEND WITH YOUR PRODUCTION ORDER
This becomes a formal appendix to your purchase order. Both parties sign before production begins. Without it, you have no contractual leverage on quality.
Clause | Agreement Text (customize [BRACKETED] fields and send to supplier) | Why This Clause Matters | Negotiation Notes | If Supplier Pushes Back | Precedent
SUPPLIER QUALITY AGREEMENT — StrideHer Production Order Quality Terms
1. Scope | This Quality Agreement ("Agreement") applies to all production units manufactured by [SUPPLIER NAME] ("Supplier") for StrideHer ("Buyer") under Purchase Order #[PO NUMBER] dated [DATE]. Product: Women's Adjustable Running Belt Quantity: [600] units ([300] S/M + [300] L/XL) Reference: Technical Specification v[VERSION] dated [DATE] (attached) | Establishes the legal scope. Links the quality agreement to a specific PO and technical spec. Without this, the supplier can argue the agreement is "general" and doesn't apply to your specific order. | Always attach the technical spec as a referenced document. Use version numbers so there's no dispute about which spec applies. | Non-negotiable. This is basic contract hygiene. | Standard in all OEM manufacturing agreements.
2. Quality Standards | All units shall conform to the attached Technical Specification. Quality inspection shall follow ISO 2859-1, General Inspection Level II: • Critical defects: AQL 0 (zero tolerance) • Major defects: AQL 2.5 • Minor defects: AQL 4.0 Defect definitions and classification per the attached Acceptance Criteria document (Sheet 2E.01). | Sets measurable, internationally recognized quality thresholds. AQL 2.5 for major defects is the INDUSTRY STANDARD — used by Gap, H&M, Nike. It means: in a statistical sample, no more than 2.5% of units may have major defects. | AQL 2.5 / 4.0 is reasonable and standard. Don't request AQL 1.0 (unrealistic for small-batch production) or accept AQL 6.5 (too lenient). | If supplier says "we don't do AQL inspection": this is a red flag. Walk away. Any professional factory understands AQL. | Nike: AQL 1.5/2.5. H&M: AQL 2.5/4.0. Most Alibaba OEM: AQL 2.5/4.0 is standard expectation.
3. Pre-Shipment Inspection | Buyer reserves the right to conduct pre-shipment inspection at Supplier's facility, OR to engage a third-party inspection agency (such as QIMA, SGS, or Bureau Veritas) to inspect on Buyer's behalf, at Buyer's cost. Supplier shall provide Buyer with 5 business days' notice before shipment to allow time to arrange inspection. | Pre-shipment inspection at the FACTORY is 10× more effective than inspecting after the shipment arrives at your door. QIMA inspections cost ~$300 per visit and catch defects before they ship across the ocean. | For a first order of 600 units, a QIMA inspection ($268-$388 depending on region) is optional but recommended. For subsequent larger orders, it becomes essential. 5-day notice gives you time to arrange an inspector. | Most suppliers accept this clause readily — it's standard for export manufacturing. If they refuse inspection access: major red flag. | QIMA (formerly AsiaInspection) is the most common third-party inspection service for Alibaba manufacturing. ~60,000 inspections/year in China.
4. Defect Remediation | If inspection reveals defect rates exceeding the AQL thresholds in Clause 2: a) Supplier shall, at Supplier's cost, re-work or replace all defective units within 15 business days. b) If re-work is not feasible, Supplier shall provide a pro-rata credit on the defective portion of the order, calculated as: (number of estimated defective units in full lot ÷ total units) × total order value. c) If defect rate exceeds 10% for major defects or ANY critical defects are found in more than 2% of sample: Buyer may reject the entire shipment and Supplier shall refund the full order value. | This is the teeth of the agreement. Without it, a supplier who ships 15% defective units faces no consequence. With it, they have a financial incentive to maintain quality. The 10% / 2% rejection thresholds protect against catastrophic quality failure while allowing for normal manufacturing variance. | Suppliers will accept (a) readily, may negotiate on (b) credit calculation, and will push back hardest on (c) full rejection/refund. Your position: "I'm ordering from you because I trust your quality. This clause only activates if something goes seriously wrong — which I don't expect." | If supplier refuses full-shipment rejection clause: compromise at "Supplier shall replace defective units at Supplier's cost, with expedited shipping, within 15 business days." This is the minimum acceptable protection. | Standard in all OEM quality agreements. The exact thresholds (10% / 2%) are negotiable but the principle of supplier-funded remediation is universal.
5. Production Sample Retention | Supplier shall retain one (1) approved production sample (PP sample) throughout the production run and for 90 days after shipment. This PP sample serves as the manufacturing reference standard. All production units shall match the retained PP sample in: dimensions, materials, hardware, color, construction quality, and overall appearance. | The PP sample is the "golden master." Without a retained sample, the supplier has no reference to check against during production. Quality drift is the #1 cause of late-run defects (units made on day 1 of production are better than units made on day 30). | Every professional factory retains PP samples as standard practice. If your supplier doesn't: provide 2 approved samples and ask them to keep one. | Non-negotiable. This is basic manufacturing practice. | Universal manufacturing standard.
6. Materials Verification | Supplier warrants that all materials used in production match the specifications in the Technical Spec, specifically: • Fabric: 80/20 nylon-spandex, 220 GSM ±10, 4-way stretch • Zippers: Genuine YKK brand (no substitutions) • Buckle: Duraflex or equivalent named brand • Silicone grip: screen-printed, Shore A 20-35 Supplier shall NOT substitute materials without prior written approval from Buyer. Any unauthorized material substitution shall be treated as a critical defect. | Material substitution (swapping specified YKK zippers for cheap generics, or swapping 220 GSM fabric for 180 GSM) is the #1 fraud in Alibaba OEM manufacturing. This clause makes substitution a contractual breach, not just a disappointment. | Be direct: "I specified YKK zippers because quality matters to my customers. If you can't source YKK, tell me now — don't substitute after we've agreed." | If supplier says they "can't guarantee YKK for every unit": unacceptable. YKK has massive production capacity. Either they have a YKK account or they don't. If they don't: source zippers separately or choose a different supplier. | Material substitution clauses are standard in all quality-conscious OEM agreements. Nike, Apple, and Patagonia all use similar language.
7. Dispute Resolution | Any quality disputes shall be resolved as follows: 1. Good faith negotiation between Buyer and Supplier (30 days) 2. If unresolved: mediation through Alibaba Trade Assurance dispute resolution process 3. If still unresolved: arbitration under the rules of the Singapore International Arbitration Centre (SIAC) Governing law: the laws of [BUYER'S STATE/COUNTRY]. | Establishes a clear escalation path. Alibaba Trade Assurance provides built-in dispute resolution for orders placed through their platform — this is one of the strongest reasons to order through Alibaba rather than direct wire transfer. | If ordering through Alibaba Trade Assurance: clause (2) is automatically available. If ordering direct: you lose this protection. SIAC arbitration is the international standard for China-international trade disputes. | Most disputes resolve at step (1). Alibaba Trade Assurance at step (2) handles most Alibaba order disputes. Step (3) is the nuclear option you hope to never use. | Alibaba Trade Assurance has handled millions of disputes. SIAC is the preferred arbitration body for China-West trade.
8. Signature | AGREED AND ACCEPTED: Buyer: _________________________ Date: _______ Name: [YOUR NAME] Company: StrideHer / [YOUR LLC NAME] Supplier: _________________________ Date: _______ Name: [SUPPLIER CONTACT NAME] Company: [SUPPLIER COMPANY NAME] | Both parties sign BEFORE production begins. Without signatures, this is just a wish list. With signatures, it's a contractual obligation. Send via email with a request: "Please sign and return before we authorize production." | Chinese suppliers may be hesitant to sign Western-style contracts. Position it as: "This protects both of us. It sets clear expectations so there are no surprises." | If supplier won't sign anything: use Alibaba Trade Assurance's built-in buyer protection instead. It covers: product quality, on-time shipment, and refund for non-conforming goods. | Standard business practice for international trade.