## P4A EXEC SUMMARY
P4A SHOPIFY STORE SETUP & CONFIGURATION — EXECUTIVE SUMMARY
7 Tasks ¦ Weeks 6-8 ¦ Cost: $1/mo (3-month trial) + $15/yr domain ¦ Your store should be LIVE and tested before inventory arrives.
Task ID | Task | KPI | Deliverable | Status | Key Decision | Cost
4A.01 | Create Shopify account: plan selection, domain connection, basic settings | Account live with custom domain | Complete Shopify setup guide: plan comparison (Basic vs Shopify vs trial), domain connection instructions (strideher.com), essential admin settings (currency, timezone, address, tax), and email forwarding setup (hello@strideher.com). | COMPLETE ✓ | SHOPIFY BASIC ($39/mo, or $1/mo for first 3 months with trial). Connect strideher.com domain ($10-15/yr from Namecheap/Google). Set up hello@strideher.com email forwarding. This is the ONLY platform recommended for a bootstrapped D2C brand — Shopify handles hosting, security, payment processing, and mobile optimization. | $1-$39/mo + $15/yr domain
4A.02 | Select and customize theme: Dawn (free) with StrideHer brand colors, fonts, and layout | Theme live with brand identity applied | Complete theme customization guide: Dawn theme selected (free, fast, mobile-first), exact color codes entered, custom fonts loaded (Plus Jakarta Sans + Inter), homepage section layout, navigation structure, and mobile optimization checklist. | COMPLETE ✓ | DAWN THEME (free) — Shopify's flagship free theme. Clean, fast (92+ Lighthouse score), mobile-optimized, and built for single-product brands. No paid theme needed. Customize with StrideHer colors (Desert Rose primary, Midnight text, Warm White backgrounds) and fonts (Plus Jakarta Sans headings, Inter body). | $0 (free theme)
4A.03 | Build product page: photos, video, description, size guide, comparison, reviews | Product page live with all P2D content | Complete product page build guide: exact section order, photo sequence (8+ images in specific order), all copy from P2D.05, size guide integration, comparison table placement, FAQ accordion, and review app setup. This page converts 60-70% of purchase decisions. | COMPLETE ✓ | Product page uses ALL content from P2D.05 (hero headline, 5 benefit sections, spec table, 10-question FAQ) + P2D.01 (size guide) + P2D.03-04 (capacity photos + comparison table). Photo order: hero shot → on-body → pocket detail → phone fit → all colors → capacity → lifestyle → bounce test video. | $0
4A.04 | Set up essential pages: Home, About, FAQ, Contact, Shipping, Returns, Privacy, Terms | 8 pages live with final copy | Complete page-by-page build guide: each of the 8 required pages with final copy (from P1C.06 website copy + P2D.02 care + new policy copy), layout instructions, and legal compliance notes for shipping/returns/privacy/terms. | COMPLETE ✓ | 8 ESSENTIAL PAGES: (1) Home (hero + product + trust signals), (2) About Us (founder story from P1C.01), (3) FAQ (20 questions from P1C.06 + P2D.05), (4) Contact (form + email + response time promise), (5) Shipping Policy, (6) Returns/Refund Policy, (7) Privacy Policy, (8) Terms of Service. The last 4 are LEGALLY REQUIRED for US e-commerce. | $0
4A.05 | Configure shipping rates: free US shipping, international rates, zones | Shipping rates live and tested | Complete shipping configuration: free US shipping (built into $34.99 price), international rate tables by zone, Shopify Shipping discount activation, carrier selection (USPS Priority for US), and shipping profile setup instructions. | COMPLETE ✓ | FREE US SHIPPING (included in $34.99 retail price — customers hate paying for shipping more than they hate a slightly higher product price). International: calculated at checkout via Shopify Shipping rates. USPS Priority Mail for US orders (~$4.50 for a running belt in a poly mailer). Shopify Shipping gives 40-60% carrier discounts. | $4-$5/order US shipping (absorbed in retail price)
4A.06 | Set up payment processing: Shopify Payments + PayPal + Shop Pay | Payments live and tested | Complete payment setup guide: Shopify Payments activation (0% transaction fee on Shopify plan), PayPal Express as secondary option, Shop Pay (accelerated checkout), Apple Pay / Google Pay mobile wallets, and tax collection configuration. | COMPLETE ✓ | SHOPIFY PAYMENTS primary (2.9% + $0.30 per transaction on Basic, no additional Shopify fees). PayPal Express as alternative. Shop Pay for returning customers (60% faster checkout = higher conversion). Enable Apple Pay + Google Pay (mobile wallets convert 2× better on mobile). Tax: auto-collect US sales tax by state. | 2.9% + $0.30 per transaction
4A.07 | Place test order through entire checkout flow | Test order successful end-to-end | Complete pre-launch testing checklist: 22-point test covering add-to-cart, variant selection, checkout flow, payment processing, order confirmation email, shipping notification, mobile checkout, and discount code testing. Nothing launches until ALL 22 tests pass. | COMPLETE ✓ | Test EVERY path a customer can take: add to cart from product page, change size/color in cart, apply discount code (HERSTRIDE10), checkout as guest + as account, pay with credit card + PayPal, verify confirmation email, verify inventory deducts, test on iPhone AND Android. A broken checkout = $0 revenue from $10K invested. | $0 (Shopify refunds test orders)

## 4A.01-02 Account + Theme
P4A TASKS 4A.01-02: SHOPIFY ACCOUNT CREATION + DAWN THEME CUSTOMIZATION
Total setup time: 2-3 hours. Follow step by step. Every Shopify setting and Dawn theme customization value is specified below.
Step | Setting / Action | Exact Value / Instruction | Where in Shopify | Why This Setting | Common Mistakes | Time
4A.01: SHOPIFY ACCOUNT CREATION + ESSENTIAL SETTINGS
1 | Create Shopify account | Go to shopify.com → "Start free trial" → enter email, password, store name. Store name: "StrideHer" (becomes your default myshopify.com URL: strideher.myshopify.com). Start with the free trial (3 days free, then $1/mo for 3 months on Basic plan = $3 total for first 3 months). | shopify.com → Sign Up | $1/mo for 3 months is the best D2C platform deal in history. After 3 months: $39/mo for Basic (sufficient until $50K+/year revenue). Shopify handles: hosting, SSL certificate, mobile optimization, payment processing, and app ecosystem. | Using a personal email. Use hello@strideher.com (set up email forwarding from Namecheap/Google Workspace). Choosing "Shopify" plan ($105/mo) when Basic ($39/mo) is sufficient for first year. | 15 min
2 | Connect custom domain | If not already registered: buy strideher.com from Namecheap ($10-15/yr). In Shopify: Settings → Domains → Connect existing domain → Enter strideher.com → Follow DNS configuration steps (change A record to Shopify's IP, CNAME record to shops.myshopify.com). Set strideher.com as PRIMARY domain. Redirect strideher.myshopify.com → strideher.com. | Settings → Domains | A custom domain is non-negotiable for brand credibility. strideher.myshopify.com signals "just started yesterday." strideher.com signals "legitimate brand." Google also ranks custom domains higher than subdomains. | Not setting the custom domain as PRIMARY (visitors see myshopify.com URL). Not enabling auto-redirect. DNS changes take up to 48 hours to propagate — do this FIRST. | 30 min (+ 48 hrs DNS)
3 | Set up email forwarding | hello@strideher.com → your personal email. Option A: Namecheap email forwarding (free with domain purchase). Settings → Email Forwarding → add hello@strideher.com → forward to [your gmail/email]. Option B: Google Workspace ($6/mo for actual @strideher.com inbox — overkill for launch but professional). All customer emails, Shopify notifications, and supplier communications use hello@strideher.com. | Namecheap dashboard (not Shopify) | Customers trust brand@domain.com. "Contact us at stridehergirl2026@gmail.com" destroys credibility. Email forwarding costs $0 and takes 5 minutes. Your customers never know it forwards to your personal inbox. | Using a Gmail address as the customer-facing contact. Not testing that forwarded emails actually arrive in your inbox. Not setting up "reply-as" so outgoing emails show hello@strideher.com (Google/Outlook allow this). | 15 min
4 | Configure store settings | Shopify Admin → Settings: • Store name: StrideHer • Store email: hello@strideher.com • Customer email: hello@strideher.com • Business address: [your address — required for taxes, not shown to customers unless you choose] • Store currency: USD • Timezone: [your timezone] • Unit system: Imperial (for US customers) • Weight unit: lb | Settings → General Settings → Store details | These settings propagate across: email templates, invoices, shipping calculations, and tax forms. Getting them right now prevents fixing them across 20 templates later. | Wrong timezone (affects order timestamps and analytics). Wrong currency (confuses international customers). Missing business address (blocks tax registration). | 10 min
5 | Enable Shopify Payments | Settings → Payments → Activate Shopify Payments. Complete identity verification (SSN, bank account, business address). This enables: credit card processing (Visa/Mastercard/Amex/Discover), Shop Pay, Apple Pay, Google Pay. Transaction fees on Basic plan: 2.9% + $0.30 per transaction. NO additional Shopify fee (vs 2% fee if using a third-party payment gateway). | Settings → Payments | Shopify Payments is MANDATORY to avoid the extra 2% transaction fee. On a $34.99 sale: Shopify Payments = $1.31 in fees. Third-party gateway = $1.31 + $0.70 Shopify fee = $2.01. That extra $0.70 × 600 units = $420 in unnecessary fees. | Not completing identity verification (payments delayed). Not enabling Shop Pay (losing 60% faster checkout for returning customers). Using a different gateway when Shopify Payments is available in your country. | 15 min
6 | Enable PayPal Express | Settings → Payments → PayPal → Activate PayPal Express Checkout. Connect your PayPal business account (create one at paypal.com/business if needed). PayPal appears as an alternative payment option at checkout: "Pay with PayPal." | Settings → Payments → Alternative payments | 12-15% of online shoppers prefer PayPal. Not offering it = losing those customers at checkout. PayPal also builds trust for first-time visitors who don't want to enter card details on a new site. | Using a personal PayPal instead of PayPal Business. Not testing the PayPal checkout flow (it redirects to PayPal then back — this can break if misconfigured). | 10 min
4A.02: DAWN THEME CUSTOMIZATION — applying the StrideHer brand identity to every pixel
7 | Install Dawn theme | Online Store → Themes → Dawn should be default. If not: Theme Library → Add Dawn → Publish. Dawn version: use the latest version (auto-updates through Shopify). | Online Store → Themes | Dawn is Shopify's flagship free theme built with Online Store 2.0. It's faster (92+ Lighthouse performance score) than 90% of paid themes. Clean, minimal, and designed for single-product or small-catalog brands — exactly StrideHer's profile. | Installing a paid theme ($150-$350) before validating the business. Paid themes add features you don't need yet and can slow page load speed. Dawn is the right choice until revenue exceeds $100K/year. | 5 min
8 | Set brand colors | Theme Editor → Theme settings → Colors: • Primary (accent): #C07C7C (Desert Rose) • Secondary: #7A9A7E (Alpine Sage) — used sparingly for badges/accents • Background: #FAF8F5 (Warm White) • Text: #1A1A1A (Midnight) • Button background: #C07C7C (Desert Rose) • Button text: #FFFFFF (White) • Sale badge: #3D5A80 (Deep Ocean) Copy hex codes EXACTLY from P1B.02 color palette. Verify each color renders correctly in the theme editor preview. | Customize → Theme settings → Colors | Brand consistency from website to packaging to social media creates trust. If your Instagram is Desert Rose but your website buttons are generic blue, the brand feels fractured. These hex codes are the same ones from P1B — now applied to the digital storefront. | Using Shopify's default blue (#5C6AC4) or generic colors. Entering hex codes without the # prefix (Shopify requires it). Not testing colors on mobile (some hex values render differently on phone screens). | 10 min
9 | Set brand typography | Theme Editor → Theme settings → Typography: • Heading font: Plus Jakarta Sans (upload as custom font OR use closest available: "Poppins" as fallback in Dawn) • Body font: Inter (available in Shopify's font library) • Heading size scale: 100% (default) • Body font size: 16px minimum (accessibility standard) Note: Shopify's font library may not include Plus Jakarta Sans. If not: use Poppins (similar geometric sans-serif) or add custom CSS to load Plus Jakarta Sans from Google Fonts. | Customize → Theme settings → Typography | Typography is the second most visible brand element after color. Plus Jakarta Sans (headings) + Inter (body) are the brand type system from P1B.04. Consistent typography across all touchpoints (website, emails, packaging, social) creates subconscious brand recognition. | Using Shopify's default fonts without customizing. Setting body text below 16px (accessibility violation — fails WCAG standards and frustrates older users). Using more than 2 fonts (slows page load, looks chaotic). | 10 min
10 | Configure header + navigation | Theme Editor → Header: • Logo: upload StrideHer wordmark SVG/PNG (max 250px wide, transparent background) • Announcement bar: "Free US Shipping on Every Order" (Desert Rose background, white text) • Main navigation menu: — Shop (links to product page) — About (links to About Us page) — Size Guide (links to /pages/size-guide) — FAQ (links to /pages/faq) — Contact (links to /pages/contact) Mobile: verify hamburger menu includes all items. Announcement bar must be visible on mobile. | Customize → Header Navigation: Online Store → Navigation → Main menu | The header is on EVERY page. It must be: clean (5-6 items max), prioritized (Shop first), and include the free shipping announcement (reduces cart abandonment by 15-25% — customers see "free shipping" before they even look at the product). The announcement bar is the highest-visibility real estate on the entire site. "Free US Shipping" is the #1 message to put there. | More than 6 nav items (overwhelming). No announcement bar (wasting prime real estate). Logo too large (pushes content below the fold on mobile). Missing mobile hamburger menu test. | 20 min
11 | Configure footer | Theme Editor → Footer: • Column 1: "StrideHer" logo + "The first running belt designed for women." tagline + social icons (IG, TikTok) • Column 2: "Shop" — product link, size guide • Column 3: "Support" — FAQ, Contact, Shipping Policy, Returns Policy • Column 4: "Legal" — Privacy Policy, Terms of Service • Email signup: "Join our community" with Klaviyo/Mailchimp form integration • Copyright: "© 2026 StrideHer. All rights reserved." | Customize → Footer Settings → Policies (auto-generates policy pages) | Footer is where cautious shoppers go to verify legitimacy. They look for: return policy, contact info, privacy policy. A missing footer = "this site might be a scam." A complete footer = "this brand is professional and trustworthy." | No return policy link (the #1 trust signal in the footer). No email signup (missing list-building opportunity on every page). Broken social links (links to empty or wrong profiles). | 15 min
12 | Configure homepage sections | Theme Editor → Homepage template: • Section 1: Image banner — hero product photo (Desert Rose belt on runner), headline "The First Running Belt Designed for Women.", CTA button "Shop Now" → product page • Section 2: Rich text — subheadline "Adjustable fit. 3 separate pockets. Zero bounce. From mile 1 to mile 26.2." • Section 3: Featured product — StrideHer belt with variant selector (size + color), price, Add to Cart • Section 4: Image with text — "Designed for Your Body" section with contoured profile photo • Section 5: Multicolumn — 3 trust icons: "Free Shipping" + "30-Day Guarantee" + "Designed by Runners" • Section 6: Video — product demo or bounce test embed • Section 7: Testimonials — field tester quotes (from P2B.04) • Section 8: Newsletter signup — "Join the community. Get 10% off your first order." | Customize → Homepage → Add/edit sections | The homepage follows the proven D2C conversion structure: hero (what is this?) → product (show me) → benefits (why should I care?) → social proof (who else uses it?) → CTA (how do I buy?). Each section answers a specific visitor question in the order they naturally ask them. 70%+ of homepage visitors will click directly to the product page — the homepage just needs to create enough interest for that click. | Too many sections (homepage shouldn't scroll for 5 minutes). No clear CTA above the fold. Hero image too slow to load (optimize to <200 KB). Product not visible without scrolling. | 30-45 min

## 4A.03 Product Page Build
P4A TASK 4A.03: PRODUCT PAGE — EXACT BUILD SEQUENCE WITH ALL CONTENT MAPPED
This page converts 60-70% of purchase decisions. Every photo, every word, every section is specified. Build it in the EXACT order below.
Order | Page Element | Content Source | Shopify Implementation | Photo / Media | Conversion Role | Mobile Notes
PRODUCT PAGE BUILD — top to bottom in the order a customer sees it
1 | Product Title | StrideHer Women's Running Belt — Adjustable Fit, 3 Pockets, Zero Bounce | Admin → Products → Title field. This title also becomes the SEO title tag unless you customize it separately (SEO section at bottom of product editor). | — | Title contains key search terms: "women's running belt," "adjustable," "3 pockets," "zero bounce." Shoppers who arrive via Google see this in search results. | Title truncates on mobile at ~60 characters. The first 60 chars must communicate the core product: "StrideHer Women's Running Belt — Adjustable Fit, 3 P..."
2 | Price + Compare-at | $34.99 Compare-at price: LEAVE BLANK. Do NOT set a fake "was $59.99, now $34.99" comparison. Customers see through it instantly and it cheapens the brand. | Admin → Products → Pricing section. Price: 34.99 Compare-at: empty Cost per item: 6.00 (for margin tracking — not shown to customers) | — | Clean pricing builds trust. Fake markdowns are the #1 signal of a cheap Amazon-clone brand. StrideHer's positioning is "premium quality at a fair price" — not "discounted from an inflated MSRP." | Price must be visible without scrolling on mobile. Verify in mobile preview.
3 | Variant Selectors | SIZE: S/M (25"-33") ¦ L/XL (33"-43") COLOR: Midnight Black ¦ Desert Rose ¦ Alpine Sage ¦ Deep Ocean Showing waist range IN the variant name eliminates size guide lookup for 80% of shoppers. | Admin → Products → Variants. Create option 1: "Size" with values "S/M (25"-33")" and "L/XL (33"-43")" Create option 2: "Color" with values for each. Set inventory tracking per variant (8 variants total). Set SKU codes: SM-BLK, SM-RSE, SM-SGE, SM-OCN, LXL-BLK, LXL-RSE, LXL-SGE, LXL-OCN. | Each color variant should have its own product photo. When customer selects "Desert Rose," the main image switches to the Desert Rose belt photo. | Variant names with waist range = instant size selection without visiting size guide. Reduces "which size?" support emails by 50%+. Color swatches with actual product photos (not colored dots) show exactly what they're getting. | Size and color selectors must be large enough to tap on mobile. Default Shopify variant buttons are fine. Don't use tiny dropdowns — buttons with visual swatches convert better.
4 | Product Photos (in this exact order) | Photo 1: Hero front (belt in selected color on white background) — P1D Shot #1 Photo 2: On-body front (runner wearing belt) — P1D Shot #6 Photo 3: 3-pocket exploded flat lay — P1D Shot #17 Photo 4: Phone fit close-up (iPhone in pocket) — P1D Shot #12 Photo 5: All 4 colors side by side — P1D Shot #3 Photo 6: Detail close-up (zipper, buckle, silicone dots) — P1D Shot #21 Photo 7: Lifestyle running action — P1D Shot #30 Photo 8: Bounce test video (embed or upload) — P1D Video #2 | Admin → Products → Media section. Upload in this exact order (Shopify displays in upload order). For video: upload directly (max 1 GB) or embed YouTube/Vimeo link. Image specs: 2048×2048px recommended (Shopify auto-optimizes). JPEG for photos, PNG for graphics with transparency. sRGB color profile. | All 8 images mapped to P1D shot list. Each image serves a specific conversion function: 1: "Is this the product I'm looking for?" 2: "How does it look when worn?" 3: "How are the pockets organized?" 4: "Will my phone fit?" 5: "Which color do I want?" 6: "Is it well-made?" 7: "What does it look like in action?" 8: "Does it actually not bounce?" | Photo sequence matters more than photo quality. A customer who sees the PHONE FIT photo at position 4 (after hero, on-body, and flat lay) has answered their top 3 questions in <30 seconds. Each photo answers the NEXT question in the buyer's decision journey. | Mobile users swipe through photos. First photo must be instantly recognizable as the product (clean hero on white). Swipe = sequential storytelling. Video thumbnail should indicate "tap to play" — not auto-play (auto-play with sound causes rage-exits on mobile).
5 | Product Description (below photos) | ALL copy from P2D.05: • Hero headline: "The First Running Belt Designed for Women." • Subheadline: "Adjustable fit. 3 separate pockets. Zero bounce." • Benefit 1: Stop Guessing Your Size • Benefit 2: Your Phone Doesn't Touch Your Gels • Benefit 3: Invisible From Mile 1 to 26.2 • Benefit 4: Built Around Your Body. Literally. • Benefit 5: The Details That Matter After Mile 10 • Specs table • 10-question FAQ | Admin → Products → Description field (rich text editor). Use Shopify's rich text editor for basic formatting. For advanced layout (multi-column benefits, FAQ accordions): use a page builder app (GemPages free tier or Dawn's built-in sections) or custom HTML in the description. FAQ: use a free Shopify FAQ app (HelpCenter FAQ, Product FAQ) for accordion-style expandable questions. | Product description photos: embed additional images between text sections using Shopify's rich text image insert. Each benefit section should have a corresponding photo to its left or right (alternating sides for visual rhythm). | The product description is for the 30-40% of shoppers who scroll past the photos. These are SERIOUS buyers who want detail before committing. The description addresses their remaining objections in order: sizing → pockets → bounce → women-specific → quality → specs → FAQ. | On mobile, the description appears BELOW the Add to Cart button (different from desktop where it's beside/below photos). This means mobile users must scroll further to read it — keep paragraphs short (3 lines max on mobile). Every section should start with a bold headline visible in the scroll.
6 | Size Guide Link/Tab | Link to /pages/size-guide (created in P2D.01). Option A: Inline link in product description "View Size Guide →" Option B: Dedicated tab below product description (use Dawn's tab sections) Option C: Popup/modal that opens within the product page (use a Shopify size chart app) | Option B or C recommended. Tab: customize Dawn's product page template to include a "Size Guide" tab alongside "Description" and "Reviews." Popup: install "Kiwi Size Chart" (free) or "EasyFit" (free) app. | Include the fit photos from P2D.01 — real runners in different body types wearing the belt with their waist measurements captioned. | The size guide must be accessible WITHOUT leaving the product page. If a shopper has to navigate away to find sizing info, 40% won't come back. Inline tab or popup keeps them on the purchase-decision page. | Size guide popup must be mobile-optimized. Test: tap the "Size Guide" link on a phone. Does the popup fill the screen without cutting off? Can you close it easily? Is the size chart readable without zooming?
7 | Reviews Section | Install a reviews app: • Judge.me (free plan = basic reviews) • Loox (free plan = photo reviews) • Stamped.io (free plan = reviews + Q&A) Recommended: Judge.me (free, integrates with Shopify, supports photo reviews, and auto-sends review request emails 7 days after delivery). | Admin → Apps → Search "Judge.me" → Install. Configure: auto-request email (7 days post-delivery), enable photo reviews, enable Q&A section, display on product page as a section below description. | At launch you'll have 0 reviews. Seed with: (1) P2B.04 field testers — ask each to leave a review, (2) first 10 customers — include a handwritten note asking for a review, (3) insert card QR code drives to review page. Target: 10 reviews within 30 days. 25+ reviews within 90 days. | Reviews are the #1 conversion factor on product pages. A product with 10+ reviews converts 2× better than one with 0 reviews. Photo reviews convert 3× better than text-only. Amazon shoppers especially expect reviews — seeding reviews before Amazon launch (P4E) is critical. | Reviews section appears below the fold on mobile. Add a "★★★★★ (X reviews)" badge near the price/Add-to-Cart area that, when tapped, scrolls to the reviews section. This gives social proof above the fold without taking up space.
ADD-TO-CART + TRUST SIGNALS (the final conversion zone)
8 | Add to Cart Button | Button text: "Add to Cart" (not "Buy Now" — Add to Cart is universally understood). Button color: Desert Rose (#C07C7C) with white text. Buy Now button (direct to checkout): enable as secondary option below Add to Cart. Shop Pay button: appears automatically if Shop Pay is enabled — "Buy with Shop Pay" for 1-click checkout. | Dawn theme automatically places Add to Cart. Customize button color in Theme Settings → Colors → Button background. Buy Now: enable in Theme Settings → Product page → Show dynamic checkout button. | Place trust signals DIRECTLY below the Add to Cart button: • "Free US Shipping" • "30-Day Money-Back Guarantee" • "Free Size Exchanges" Use small text or icons — not big graphics. These 3 lines remove the final 3 objections at the moment of decision. | The Add to Cart zone is where 80% of purchases happen — or don't. Every element in this zone must reduce friction. Free shipping removes the "hidden cost" fear. Guarantee removes "what if it doesn't fit" fear. Free exchanges removes "what if I picked the wrong size" fear. | Add to Cart button must be STICKY on mobile (stays visible as user scrolls). Dawn theme supports sticky Add to Cart in mobile view — verify it's enabled in theme settings. If the button scrolls off-screen, mobile conversion drops 30-40%.

## 4A.04 Essential Pages
P4A TASK 4A.04: 8 ESSENTIAL PAGES — EVERY PAGE YOUR STORE NEEDS WITH FINAL COPY
4 content pages (Home, About, FAQ, Contact) + 4 legal/policy pages (Shipping, Returns, Privacy, Terms). The last 4 are LEGALLY REQUIRED.
Page | URL | Content Source | Key Copy / Summary | Shopify Build | Legal Requirement? | Priority
CONTENT PAGES (brand storytelling + customer support)
Home Page | strideher.com (/) | P2D.05 hero headline + P1D photos + P1C.02 tagline | Hero banner: "The First Running Belt Designed for Women." + hero photo + "Shop Now" CTA button. Featured product section with variant selector. Trust icons: Free Shipping ¦ 30-Day Guarantee ¦ Designed by Runners. Testimonials from field testers. Newsletter signup: "Join the community. Get 10% off." | Customize → Homepage template → add sections per Sheet 4A.01-02 Step 12. | No | 🔴 #1 Build first
About Us | strideher.com /pages/about | P1C.06 About Us copy (412 words) + P1C.01 founder story + founder photo | Headline: "Every Runner Deserves Gear That Fits." Founder story (full version, 487 words from P1C.01 — customize all [BRACKETED] sections). Photo of founder (running or candid portrait). Mission statement. Ends with CTA: "Shop the belt that started it all →" | Admin → Pages → Add page → Title "About Us" → paste content from P1C.06. Add to main navigation. | No | 🟡 #2
FAQ | strideher.com /pages/faq | P1C.06 FAQ section (20 questions) + P2D.05 product FAQ (10 questions) | Combine P1C.06 website FAQ (20 questions in 5 accordion sections: Product, Sizing, Shipping, Returns, Brand) with P2D.05 product-specific FAQ (10 questions). Total: 30 questions. Organize into 6 sections. Use accordion format — each question expands on click. Do NOT show all answers at once (overwhelming). | Admin → Pages → Add page → Title "FAQ". For accordion: use Shopify's built-in collapsible content section (Dawn supports this) or install HelpCenter FAQ app (free). | No | 🟡 #3
Contact | strideher.com /pages/contact | New content (simple) | Headline: "We'd Love to Hear From You." Email: hello@strideher.com Response time: "We respond to every email within 24 hours." Contact form: name, email, subject, message. Shopify's default contact form works. Social handles: Instagram @strideher, TikTok @strideher. "Whether you have a question about sizing, want to share your run, or just want to say hi — we're here." | Admin → Pages → Add page → Title "Contact Us" → select "page.contact" template (includes built-in form). Add to main navigation under "Support" or as a standalone nav item. | No | 🟡 #4
LEGAL / POLICY PAGES (legally required for US e-commerce — Shopify auto-generates templates)
Shipping Policy | strideher.com /policies/shipping-policy | New content | FREE US SHIPPING All US orders ship free via USPS Priority Mail. Typical delivery: 2-5 business days. INTERNATIONAL SHIPPING We ship worldwide. International rates calculated at checkout. Typical delivery: 7-21 business days depending on destination. Import duties and taxes are the responsibility of the buyer. ORDER PROCESSING Orders placed before 2 PM EST ship same day (Mon-Fri). Orders after 2 PM ship next business day. TRACKING Every order includes a tracking number. You'll receive a shipping confirmation email with tracking within 24 hours of shipment. | Settings → Policies → Shipping policy (Shopify auto-generates a template — customize with your specifics). Also linked automatically in the checkout footer. | ⚠️ Recommended (not legally required but expected by customers + Amazon requires for FBA) | 🔴 #5 Complete before launch
Return & Refund Policy | strideher.com /policies/refund-policy | New content based on P2E.04 defect handling | 30-DAY RUN-IT-AND-LOVE-IT GUARANTEE Run in it, wash it, race in it. If you don't love your StrideHer belt within 30 days of delivery, return it for a full refund — no questions asked. FREE SIZE EXCHANGES Ordered the wrong size? We'll ship your new size before you return the old one. Free exchanges within 30 days. HOW TO RETURN 1. Email hello@strideher.com with your order number 2. We'll send a prepaid return shipping label within 24 hours 3. Ship the belt back in any packaging 4. Refund processed within 2 business days of receipt DEFECTIVE PRODUCT Received a defective belt? Email us with a photo. We'll ship a replacement immediately — no need to return the original. NON-RETURNABLE Belts returned after 30 days. Belts with intentional damage (cut, burned, modified). | Settings → Policies → Refund policy. This policy also appears automatically in the checkout footer — customers check it before completing purchase. | ✅ Legally required for US e-commerce. FTC requires clear refund policy disclosure before purchase. | 🔴 #6 MUST complete before first sale
Privacy Policy | strideher.com /policies/privacy-policy | Shopify template + customization | Use Shopify's auto-generated privacy policy template (Settings → Policies → Privacy policy → "Create from template"). Customize with: • Company name: StrideHer / [YOUR LLC NAME] • Contact email: hello@strideher.com • Data collected: name, email, address, payment info (via Shopify Payments — you never see full card numbers) • Email marketing: "We send marketing emails only with your consent. Unsubscribe anytime." • Cookies: Shopify uses standard cookies for cart functionality and analytics If selling to EU customers: add GDPR compliance language (Shopify template includes this). Enable cookie consent banner in Shopify settings. | Settings → Policies → Privacy policy → "Create from template" → customize. For GDPR cookie banner: Online Store → Preferences → Customer privacy → Enable EU consent banner. | ✅ Legally required. GDPR (EU), CCPA (CA), and most US states require privacy policy disclosure. | 🔴 #7 MUST complete
Terms of Service | strideher.com /policies/terms-of-service | Shopify template + customization | Use Shopify's auto-generated Terms of Service template (Settings → Policies → Terms of service → "Create from template"). Customize with: • Company name: StrideHer / [YOUR LLC NAME] • Governing law: [Your State], United States • Limitation of liability: standard Shopify template language is sufficient • Intellectual property: "StrideHer, Run Your Way, and associated logos are trademarks of [YOUR LLC NAME]." The Shopify template covers: general terms, accuracy of information, modifications to pricing, products/services, payment, refund policy reference, and governing law. | Settings → Policies → Terms of service → "Create from template" → customize. | ✅ Legally required. Protects you from liability and sets governing law for disputes. | 🔴 #8 MUST complete

## 4A.05-06 Shipping + Payments
P4A TASKS 4A.05-06: SHIPPING RATES + PAYMENT PROCESSING CONFIGURATION
Free US shipping built into $34.99 price. Shopify Payments = lowest transaction fees. Enable every payment method to maximize conversion.
Setting | Configuration | Where in Shopify | Details | Cost Impact | Why This Setting | Common Mistakes
SHIPPING CONFIGURATION (4A.05)
US Domestic Shipping | FREE SHIPPING — no minimum, no threshold, every order. Carrier: USPS Priority Mail (via Shopify Shipping). Expected transit: 2-5 business days. Your cost: ~$4.50 per order (running belt in poly mailer, ~6 oz). | Settings → Shipping and delivery → General shipping rates → US zone → Free shipping | Shopify Shipping gives 40-60% discount on USPS rates. A 6 oz poly mailer via USPS Priority at Shopify rates: ~$4.00-$5.00. You absorb this cost in your $34.99 retail price. Do NOT offer "calculated rates at checkout" for US — customers HATE discovering shipping costs at checkout. Free shipping eliminates the #1 cart abandonment reason. | -$4.50/order (absorbed in retail price) At $34.99 retail: still $30.49 after shipping cost = 87% of retail | Free shipping converts 15-25% better than paid shipping. Customers would rather pay $34.99 with free shipping than $29.99 + $4.99 shipping — even though the total is the same. Psychology beats math. | Charging for US shipping (instant cart abandonment). Setting a "free shipping above $50" threshold (you only sell 1 product at $34.99 — nobody reaches $50). Not activating Shopify Shipping discounts.
International Shipping | Calculated rates at checkout — Shopify calculates real-time based on weight + destination. Shipping zones: create zones for Canada, UK, EU, Australia, Rest of World. Expected rates: $8-$20 depending on destination. Note on product page: "We ship worldwide. International rates calculated at checkout." | Settings → Shipping and delivery → Add shipping zone for each region. Enable "Calculate shipping rates at checkout" for international zones. | Real-time calculated rates are fair and transparent. Flat-rate international shipping ($15 flat) works but may over/under-charge depending on destination. Duties/taxes note on shipping policy: "Import duties and taxes are the responsibility of the buyer." This is standard for D2C brands shipping from the US. | $8-$20/order (paid by customer) | International customers expect to pay shipping — it's less of a conversion barrier outside the US. The key is TRANSPARENCY: show the rate at checkout, not as a surprise after they've entered payment info. | Not setting up international zones at all (blocks 15-20% of potential customers). Not mentioning duties/taxes in shipping policy (leads to angry customers who get hit with import charges on delivery).
Shipping Labels | Print shipping labels directly from Shopify. Settings → Shipping and delivery → Shipping labels → select USPS. Buy + print labels from order page: Orders → [order] → "Buy shipping label" → select USPS Priority Mail → print. Printer: Dymo LabelWriter 4XL ($200) for professional labels, OR print on regular paper and tape to mailer (fine for first 100 orders). | Settings → Shipping and delivery → Shipping labels. Also: each order page has a "Buy shipping label" button. | Shopify buys the postage and charges your account. No need for a separate stamps.com or pirateship.com account — Shopify Shipping includes everything. Schedule USPS pickup: schedule.usps.com (free daily pickup from your address). No post office trips needed. | $0 setup $200 for label printer (optional — paper labels work fine) | Printing labels from Shopify is the fastest fulfillment workflow: Order → Buy Label → Print → Attach → Ship. No copying addresses, no manual postage calculation, no post office line. | Hand-writing addresses (looks unprofessional, error-prone). Using stamps.com separately (double the work). Not scheduling USPS pickup (wasting 30 min/day at the post office).
PAYMENT PROCESSING CONFIGURATION (4A.06)
Shopify Payments | PRIMARY payment processor. Enables: Visa, Mastercard, Amex, Discover, Shop Pay, Apple Pay, Google Pay. Fees: 2.9% + $0.30/transaction on Basic plan. No additional Shopify transaction fee (vs 2.0% if using third-party gateway). Payout schedule: daily automatic deposits to your bank account (2 business day delay). | Settings → Payments → Shopify Payments → Complete setup (requires: SSN, bank account, business address verification). | Shopify Payments is powered by Stripe on the backend. It's the most seamless integration — no third-party setup needed. When activated, it auto-enables: Shop Pay (returning customer 1-click checkout), Apple Pay (Safari users), Google Pay (Chrome/Android users). These accelerated checkouts convert 2× better on mobile. | 2.9% + $0.30 per transaction On $34.99 sale: $1.31 in fees Net: $33.68 | Shopify Payments is the only way to avoid the extra 2% Shopify transaction fee. On 600 units at $34.99: the 2% fee would cost $420 in unnecessary fees. Shopify Payments saves that $420. | Not completing identity verification (holds up your first payout). Not enabling Shop Pay (losing 1-click checkout). Not enabling Apple Pay / Google Pay (losing mobile wallet users).
PayPal Express | SECONDARY payment option. Appears as alternative at checkout: "Pay with PayPal." Fees: 2.9% + $0.30/transaction (same as Shopify Payments, but PayPal charges directly — NOT through Shopify). No additional Shopify fee for PayPal Express. | Settings → Payments → PayPal → Activate PayPal Express Checkout → link your PayPal Business account. | PayPal is a trust signal — especially for first-time visitors on a new brand's site. "I can use PayPal" = "If something goes wrong, PayPal protects me." About 12-15% of online shoppers prefer PayPal. Offering it captures those customers. | 2.9% + $0.30 (same as Shopify Payments) | PayPal preference is especially strong among: international shoppers (trust PayPal more than unknown US sites), older demographics (35-45), and cautious first-time buyers on new brands. | Using personal PayPal instead of PayPal Business (transaction limits, no invoicing). Not testing the PayPal redirect flow (customer clicks PayPal → goes to PayPal → returns to Shopify confirmation — this redirect can break).
Tax Collection | Enable US sales tax auto-collection. Shopify auto-calculates and collects state/local sales tax based on your business address and the customer's shipping address. Settings → Taxes → United States → Enable → Shopify manages collection. You are responsible for REMITTING collected taxes to state tax authorities (quarterly or annually depending on state). | Settings → Taxes and duties → United States → Manage. | Sales tax nexus: you have tax nexus in your home state (must collect). You MAY have nexus in other states depending on sales volume (economic nexus thresholds vary: typically $100K in sales or 200 transactions per state). For launch: enable auto-collection for your home state. Shopify handles the calculation. You remit to your state tax authority quarterly. Consider TaxJar or Avalara ($20-$50/mo) once selling in multiple states. | $0 to configure Tax amount collected from customer (not your expense) | Sales tax compliance is MANDATORY. Not collecting and remitting sales tax in your home state = tax evasion. Shopify makes collection easy — remitting is your responsibility. Set a quarterly calendar reminder: "File + remit state sales tax." | Not enabling tax collection (tax evasion — state penalties). Manually calculating tax (Shopify auto-calculates perfectly). Not remitting collected taxes (holding someone else's money — serious legal issue).
Discount Codes | Set up launch discount codes: 1. HERSTRIDE20 — 20% off, single use per customer, for waitlist founding members (from P1E.05) 2. HERSTRIDE10 — 10% off, unlimited uses, for insert card repeat purchases (from P2C.03) 3. WELCOME10 — 10% off first order, for new email subscribers (from homepage signup) All codes: minimum purchase $0, applies to entire order, active for specified date range, auto-generated unique codes optional. | Admin → Discounts → Create discount → enter code, type (percentage), value, usage limits. HERSTRIDE20: percentage=20%, limit to 1 use per customer, start/end date = launch week only. HERSTRIDE10: percentage=10%, no limit per customer, no expiry. WELCOME10: percentage=10%, limit 1 per customer, auto-apply via Klaviyo welcome email. | Track discount code performance: Admin → Discounts → each code shows usage count and total discount given. Waitlist code (HERSTRIDE20) should convert 15-25% of waitlist subscribers to Day 1 purchases. Insert card code (HERSTRIDE10) drives repeat purchases at 10-15% redemption over 90 days. Welcome code (WELCOME10) drives first purchase at 5-10% conversion from email signups. | -20% for waitlist -10% for repeat -10% for new subs Blended discount: ~$3-$5/order avg | Discount codes are customer acquisition and retention tools, not margin-destroyers. A 20% discount on a first order that creates a lifetime customer (3+ purchases) is the highest-ROI marketing spend possible. Track: total discounts given vs total additional revenue generated by those codes. | Creating permanent 20%+ discounts (trains customers to wait for sales). Not limiting HERSTRIDE20 to 1-use-per-customer (abuse by sharing code publicly). Not setting expiry dates on launch codes (they should expire after launch week).

## 4A.07 Testing Checklist
P4A TASK 4A.07: 22-POINT PRE-LAUNCH TESTING CHECKLIST — NOTHING LAUNCHES UNTIL ALL PASS
A broken checkout = $0 revenue from $10K invested. Test EVERY path. On EVERY device. With EVERY payment method. No shortcuts.
# | Test Category | Test | How to Test | Pass Criteria | Fail Action | Pass?
CHECKOUT FLOW (test the full purchase journey — start to finish)
1 | Cart | Add product to cart from product page | Go to product page → select S/M Black → click "Add to Cart." Verify cart shows correct product, size, color, and price. | Cart shows: StrideHer Belt, S/M, Midnight Black, $34.99, qty 1. | Wrong product/price/variant → fix product setup.
2 | Cart | Change variant in cart | In cart, change size from S/M to L/XL. Change color from Black to Desert Rose. | Cart updates correctly. Price unchanged. Image updates to match new variant. | Variant change doesn't update → check variant configuration.
3 | Cart | Apply discount code | In cart, enter HERSTRIDE20. Apply. | Price reduces from $34.99 to $27.99. Discount line shows "-$7.00 (HERSTRIDE20)." | Code doesn't apply or wrong amount → fix in Admin → Discounts.
4 | Checkout | Guest checkout | Click "Checkout." Do NOT log in. Enter test shipping address. Proceed. | Checkout loads. Shipping address form works. Guest checkout allowed (no account required). | Forced account creation → disable in Settings → Checkout → Customer accounts → "Accounts are optional."
5 | Checkout | Shipping method display | At shipping step, verify shipping rate shows correctly. | US address: "Free Shipping" displayed. International: calculated rate displayed. | No shipping rate shown or wrong rate → fix in Settings → Shipping.
6 | Payment | Credit card payment | Enter Shopify's test card: 4242 4242 4242 4242, any future expiry, any CVV. Submit. | Payment processes. Order confirmation page appears. Confirmation email received. | Payment fails → check Shopify Payments setup. Test mode may need enabling.
7 | Payment | PayPal payment | At payment step, select PayPal. Complete PayPal sandbox payment. | Redirects to PayPal, processes, returns to Shopify confirmation. | PayPal redirect fails → check PayPal Express configuration.
8 | Payment | Shop Pay (if available) | If testing with a real Shop Pay account, attempt Shop Pay checkout. | 1-click checkout processes. Confirmation received. | Shop Pay not appearing → check Shopify Payments activation.
9 | Confirmation | Order confirmation email | After placing test order, check email for confirmation. | Email received within 2 minutes. Shows: order number, product, price, shipping address, estimated delivery. Sent from hello@strideher.com (not noreply@shopify.com). | No email → check Settings → Notifications → Order confirmation → enabled. Wrong sender → fix notification email settings.
10 | Confirmation | Order appears in admin | Go to Shopify Admin → Orders. Verify test order appears. | Order visible with correct details: customer, product, variant, price, discount applied, payment status. | Order missing → payment didn't process correctly. Re-test.
INVENTORY + VARIANTS
11 | Inventory | Inventory deducts on purchase | Check product variant inventory count before and after test order. | S/M Black inventory decreased by 1 after order. | No deduction → enable "Track quantity" on the variant.
12 | Inventory | Out-of-stock behavior | Set one variant to 0 inventory. Try to add to cart. | Variant shows "Sold Out." Cannot be added to cart. Other variants remain available. | Out-of-stock variant still purchasable → enable "Stop selling when sold out" in variant settings.
MOBILE EXPERIENCE (70%+ of traffic)
13 | Mobile | Full checkout on iPhone | Complete the entire test order flow on an iPhone (Safari browser). | Every step works: product page → cart → checkout → payment → confirmation. No elements cut off, no buttons unreachable. | Any broken element → test in Dawn theme mobile preview and fix.
14 | Mobile | Full checkout on Android | Complete flow on an Android phone (Chrome browser). | Same as iPhone test. All elements functional. | Android-specific issues are rare with Dawn theme but test anyway.
15 | Mobile | Add to Cart button visibility | Scroll product page on mobile. Is the Add to Cart button always visible? | Sticky Add to Cart button visible at all scroll positions. | Not sticky → enable in Theme Settings → Product page → Sticky ATC.
PAGES + NAVIGATION
16 | Pages | All 8 pages load correctly | Click every page in the navigation: Home, About, FAQ, Contact, Shipping, Returns, Privacy, Terms. | All 8 pages load with correct content. No broken links. No "page not found" errors. | Broken page → check page URL in Admin → Pages.
17 | Navigation | Main menu works on desktop + mobile | Click every navigation link on desktop. Open hamburger menu on mobile and click every link. | All links navigate to correct pages on both desktop and mobile. | Broken link → fix in Online Store → Navigation → Main menu.
BRAND + DESIGN
18 | Brand | Logo displays correctly | View logo in header on desktop and mobile. | Logo crisp, correctly positioned, links to homepage when clicked. | Blurry logo → upload higher-res version (SVG preferred).
19 | Brand | Colors match brand spec | Compare website colors to P1B.02 palette. Check: button color (Desert Rose), text (Midnight), background (Warm White). | All colors match hex codes from brand guidelines. | Wrong colors → update in Theme Settings → Colors.
20 | Brand | Favicon displays in browser tab | Open strideher.com in a browser. Check the tab icon. | StrideHer favicon (from P1B.03b icon spec) visible in browser tab. | Missing/generic → upload favicon in Theme Settings → Favicon.
FINAL CHECKS
21 | SEO | Product page SEO title + description | View page source or use Shopify SEO preview. Check meta title and description. | Title: "StrideHer Women's Running Belt — Adjustable Fit, 3 Pockets, Zero Bounce." Description: 150-160 chars summarizing the product for Google search results. | Default Shopify title → customize in product editor → SEO section.
22 | Analytics | Google Analytics connected | Verify GA4 tracking is installed. | Go to GA4 real-time report → visit strideher.com → confirm your visit appears in real-time data. | No data → install Google Analytics tag via Shopify: Online Store → Preferences → Google Analytics.

## 4A FOUNDER ACTIONS
P4A SHOPIFY STORE — FOUNDER ACTION CHECKLIST
Total build time: 8-12 hours over 2-3 days. Start during shipping transit (P3C). Store must be LIVE and tested before inventory arrives.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
DAY 1: ACCOUNT + THEME (3-4 hours)
🔴 #1 | Create Shopify account, connect domain, configure settings | 1 hr | $1/mo + $15/yr | Follow Sheet 4A.01-02 Steps 1-6: create account, connect strideher.com, set up email forwarding, configure store settings (currency, timezone, address), enable Shopify Payments, enable PayPal Express.
🔴 #2 | Customize Dawn theme with brand identity | 2-3 hrs | $0 | Follow Sheet 4A.01-02 Steps 7-12: install Dawn, set brand colors (all 6 hex codes from P1B), set typography (Plus Jakarta Sans or Poppins headings, Inter body), configure header with logo + announcement bar + navigation, configure footer with links + social + email signup, build homepage sections.
DAY 2: PRODUCT PAGE + ESSENTIAL PAGES (4-5 hours)
🔴 #3 | Build the product page | 2-3 hrs | $0 | Follow Sheet 4A.03: create product in Shopify admin, set title + price + variants (8 SKUs), upload 8 photos in specified order, paste all P2D.05 copy into description, add size guide (tab or popup), install Judge.me reviews app, add trust signals below Add to Cart button. This is the MOST IMPORTANT page on the entire site. Spend the time.
🔴 #4 | Build all 8 essential pages | 2 hrs | $0 | Follow Sheet 4A.04: create Home (already done in theme), About Us (paste P1C.06), FAQ (combine P1C.06 + P2D.05, use accordion format), Contact (form + email + social), Shipping Policy, Return Policy, Privacy Policy (Shopify template), Terms of Service (Shopify template). Policy pages: use Shopify's auto-generated templates as starting points and customize with your specific terms.
DAY 3: SHIPPING + PAYMENTS + TESTING (2-3 hours)
🟡 #5 | Configure shipping rates and zones | 30 min | $0 | Follow Sheet 4A.05-06 shipping section: set free US shipping, configure international zones with calculated rates, activate Shopify Shipping labels, set up USPS as preferred carrier.
🟡 #6 | Set up discount codes | 15 min | $0 | Create 3 codes in Admin → Discounts: HERSTRIDE20 (20% for waitlist, single-use, launch week expiry), HERSTRIDE10 (10% for insert card repeat purchases, no expiry), WELCOME10 (10% for new email subscribers, single-use per customer).
🔴 #7 | Complete the 22-point testing checklist | 1-2 hrs | $0 | Follow Sheet 4A.07: place a test order through the ENTIRE flow on desktop and mobile. Test every payment method. Test every discount code. Verify every page loads. Check every variant deducts inventory. Check every email notification. ALL 22 TESTS MUST PASS. A single failing test = potential lost sale. Fix before launch.
🟢 #8 | Connect Google Analytics 4 | 15 min | $0 | 1. Create a GA4 property at analytics.google.com 2. Get your Measurement ID (G-XXXXXXXXXX) 3. Paste into Shopify: Online Store → Preferences → Google Analytics → paste ID 4. Verify: visit your store, check GA4 real-time report for your visit 5. This data becomes critical for marketing optimization in P5-P6.

## G1 Mobile UX Checklist
G1 REMEDIATION: MOBILE UX TESTING PROTOCOL — 15-POINT QA CHECKLIST
Run this checklist on iPhone (Safari) + Android (Chrome) before launch, after every theme change, and monthly. 60-70% of your traffic is mobile — if mobile is broken, most visitors never convert.
# | Test Item | How to Test | Pass Criteria | Fail Action | iPhone Safari | Android Chrome
PRODUCT PAGE (the page that generates 90% of revenue)
1 | Page load speed on 4G | Open product page on phone using 4G (not WiFi). Count seconds until content is visible and interactive. | Loads in <3 seconds on 4G. Hero image visible within 2 seconds. No white screen for >1 second. | Compress hero image (TinyPNG). Remove unnecessary apps adding JavaScript. Check Shopify theme code for render-blocking scripts. Switch to a lighter image format (WebP via Shopify auto-optimization).
2 | Hero image displays correctly | View product page on phone. Is the hero image: fully visible? Properly cropped? Not stretched or pixelated? Shows the belt clearly? | Belt is clearly visible in hero image. No awkward cropping of the product. Image is sharp (not blurry/pixelated). Aspect ratio is correct (no stretching). | Upload a mobile-optimized hero image (1080x1080 or 4:5 ratio). Shopify Dawn supports separate desktop/mobile images — use it. Test: product should be recognizable within the first screenful.
3 | Price + free shipping visible above fold | "$34.99 — Free Shipping" must be visible WITHOUT scrolling on a phone screen (above the fold). | Price and "Free Shipping" text visible immediately on load, without any scrolling. Font size large enough to read at arm's length. | Move price block higher in product page layout. Increase font size. Add a sticky "Free Shipping" banner at top of page (Dawn supports announcement bar). Consider: "$34.99 with FREE shipping" as a single merged line.
4 | Add to Cart button visible + tappable | Scroll to ATC button. Is it: (a) visible without excessive scrolling? (b) large enough to tap easily with a thumb? (c) clearly colored (Desert Rose)? | ATC button is within 2 scrolls of page top. Button is full-width on mobile (not a small centered button). Minimum tappable area: 44x44 pixels (Apple HIG guideline). Color contrasts with background. | In Dawn theme: Customize > Product page > ensure ATC button is set to "Full width." If button is below 3+ scrolls: move product description below ATC (description is important but ATC must come first on mobile).
5 | Size selector is easy to tap | Tap the S/M and L/XL variant buttons. Are they: large enough? Clearly labeled? Easy to select without accidentally tapping the wrong one? | Each variant button is at least 44px tall. Clear visual distinction between selected and unselected. "Find Your Size" link is visible near the selector. | Increase variant button padding in theme CSS. Add size recommendation helper text ("Most women sizes 0-10: S/M"). Ensure variant selector doesn't overlap with other elements on small screens.
6 | Size guide link/popup works | Tap "Find Your Size" link. Does the size guide: open correctly? Display a readable table? Close easily? | Size guide opens as popup or new page. Table is readable on mobile (not tiny text). Close button (X) is visible and tappable. Content doesn't overflow the screen. | If popup is too small: switch to a dedicated /pages/size-guide page instead. Ensure table columns don't require horizontal scrolling. Test: can you read the waist measurements without zooming?
CHECKOUT + TRUST ELEMENTS
7 | Checkout flow completes successfully | Add to cart > proceed to checkout > enter test info > verify all form fields work > reach payment page (don't submit). Time yourself. | Checkout completes in <60 seconds. All form fields accept input. Keyboard type matches field (numeric keyboard for phone number, email keyboard for email). No error messages on valid input. | Shopify checkout is managed by Shopify (limited customization). If issues: check Shopify Checkout Settings. Common mobile issue: address autocomplete not firing — ensure Google Places is enabled in checkout settings.
8 | Apple Pay / Shop Pay buttons visible + functional | On product page and in checkout: are express payment buttons (Apple Pay on iPhone, Google Pay on Android, Shop Pay) visible and functional? | Express payment buttons appear above or beside the standard checkout button. Tapping initiates the payment flow. On iPhone: Apple Pay should appear if the user has it set up. | Shopify Settings > Payments > Express checkouts > ensure Apple Pay, Google Pay, and Shop Pay are all enabled. These buttons can increase mobile conversion by 20-30% (one-tap purchase).
9 | Trust badges readable near ATC | "Free Shipping ¦ 30-Day Guarantee ¦ Free Exchanges" badges/text near the ATC button. Readable on mobile without zooming? | Trust badges are visible on mobile. Text is readable (12px minimum). Icons (if used) are clear. Positioned within 1 scroll of ATC button. | If trust badges are below the fold on mobile: move them directly under the ATC button. Use text-based badges (not image-based) for faster loading and better mobile rendering.
10 | Payment icons visible (Visa, MC, PayPal) | Payment method icons should appear in footer or near checkout. Customer should know their card is accepted before starting checkout. | At least 4 payment icons visible: Visa, Mastercard, PayPal, Apple Pay. Icons are sharp (not blurry SVGs). Visible on product page or in footer. | Dawn theme: Add payment icons in Theme > Customize > Footer > Show payment icons. Or add as a text line near ATC: "We accept: Visa, Mastercard, PayPal, Apple Pay."
NAVIGATION + GENERAL
11 | Review widget displays and scrolls | Scroll to the Judge.me review section. Do reviews load? Can you scroll through them? Can you sort/filter? | Reviews load on mobile. Individual reviews are readable (not cut off). Star rating is visible. Scrolling is smooth. "Write a Review" button works. | Judge.me settings > Widget > ensure mobile-responsive layout is enabled. If reviews don't load: check for JavaScript conflicts with other apps. Test in incognito mode.
12 | Navigation menu works on mobile | Tap the hamburger menu (three lines). Does the nav open? Can you access: Home, Shop, About, Size Guide, Contact, FAQ? | Menu opens smoothly. All pages are accessible. Menu closes when tapping outside or pressing X. No content hidden behind the menu. | Dawn theme handles mobile nav automatically. If pages are missing: Theme > Customize > Header > Menu > ensure all pages are in the navigation.
13 | Chat widget doesn't obstruct content | If Shopify Inbox chat is enabled: does the chat bubble cover the ATC button, price, or any critical content? | Chat bubble sits in bottom-right corner. Does NOT overlap: ATC button, price, variant selector, or review section. Chat opens without covering the entire screen. | Shopify Inbox > Settings > adjust position. If it overlaps ATC: consider disabling on product page and showing only on other pages. Or use a smaller chat icon.
14 | Free shipping banner readable | Announcement bar at top of page ("Free US Shipping on All Orders"). Visible on mobile? Readable? Doesn't push content too far down? | Banner is visible. Text fits on one line (no wrapping to 3 lines). Font size is readable. Banner height doesn't consume >10% of mobile viewport. | Shorten text to fit: "Free US Shipping" (vs longer version). Reduce font size if wrapping. Consider: making the banner dismissible (X to close) to recover screen space.
15 | Overall scroll experience | Scroll through the ENTIRE product page top to bottom. Is the experience smooth? Any janky jumps? Any elements overlapping? Any horizontal scroll? | Smooth vertical scroll throughout. No horizontal scrollbar at any point (common mobile bug). No elements overlapping or cut off. No flash of unstyled content. Footer is reachable. | Horizontal scroll = an element is wider than the viewport. Inspect with: Chrome DevTools > Toggle Device Toolbar > identify the overflowing element. Common culprits: wide images, tables without overflow:auto, or fixed-width elements.
WHEN TO RUN THIS CHECKLIST: (1) Before launch (mandatory). (2) After any theme customization. (3) After installing/removing a Shopify app. (4) Monthly spot-check (pick 5 random items). (5) After any Shopify theme update.

## G2 Site Speed Benchmarks
G2 REMEDIATION: SITE SPEED & CORE WEB VITALS — BENCHMARKS + MONTHLY MONITORING PROTOCOL
Google uses Core Web Vitals as a ranking factor. A site loading in 5+ seconds loses 40% of visitors before the page renders. Monitor monthly. Fix immediately if degraded.
Metric | What It Measures | Target | How to Check | If FAILING | Monthly Check | Baseline (record before launch)
CORE WEB VITALS — Google's 3 official performance metrics (affect SEO ranking)
LCP (Largest Contentful Paint) | How long until the LARGEST visible element (usually your hero image) finishes loading. This is what the visitor perceives as "the page loaded." | <2.5 seconds Good: <2.5s Needs work: 2.5-4.0s Poor: >4.0s | pagespeed.web.dev 1. Enter: strideher.com 2. Click "Analyze" 3. Switch to MOBILE tab 4. Find "Largest Contentful Paint" under Performance Also available in: Google Search Console > Core Web Vitals report (after 28 days of data) | MOST COMMON CAUSE: hero image is too large (>500KB). FIXES (in order of impact): 1. Compress hero image via TinyPNG.com (target: <200KB) 2. Serve WebP format (Shopify auto-converts if enabled in Settings > Files) 3. Enable lazy loading for below-fold images (Dawn does this by default) 4. Remove unnecessary Shopify apps (each app adds 50-200KB of JavaScript) 5. If using a custom font: ensure it's loaded via font-display: swap (Dawn handles this) 6. Check: is a video auto-playing above the fold? Move it below fold or use a thumbnail NUCLEAR FIX: if LCP >4s and nothing else works: switch to a different, lighter hero image. A faster-loading good image beats a slow-loading perfect image.
FID (First Input Delay) | How long until the page RESPONDS to the user's first interaction (tap, click, scroll). If FID is high: the page looks loaded but feels "frozen" when you try to interact. | <100ms Good: <100ms Needs work: 100-300ms Poor: >300ms | pagespeed.web.dev Same test as LCP — FID appears in the same report under "First Input Delay" (or the newer metric INP — Interaction to Next Paint). Note: FID requires real user data (28 days). For lab testing: use "Total Blocking Time" (TBT) as a proxy — target <200ms. | MOST COMMON CAUSE: JavaScript from Shopify apps blocking the main thread. FIXES: 1. Audit installed apps: Shopify > Settings > Apps. Each app adds JS that blocks interaction. Remove any app you're not actively using. 2. Check for heavy widgets: review widgets, chat widgets, and popup apps are the worst offenders. Defer their loading (most have a "load after page" setting). 3. Judge.me: Settings > Widget > enable "Lazy load reviews" (loads after page interaction, not on initial load) 4. Shopify Inbox: set to "Load after 5 seconds" in settings 5. If using Klaviyo popup: set trigger to "After 5 seconds" or "On exit intent" (not "On page load") GENERAL RULE: if you install a Shopify app and FID/TBT increases by >50ms: the app is too heavy. Find a lighter alternative or defer its loading.
CLS (Cumulative Layout Shift) | How much the page content JUMPS AROUND as it loads. Example: you're about to tap the ATC button and suddenly an image loads above it, pushing the button down — you tap the wrong thing. That's layout shift. | <0.1 Good: <0.1 Needs work: 0.1-0.25 Poor: >0.25 | pagespeed.web.dev Same report — find "Cumulative Layout Shift" under Performance. ALSO: manually test by watching the page load on mobile. Do elements visibly jump positions? If yes: CLS is likely >0.1. | MOST COMMON CAUSES: 1. Images without width/height dimensions (browser doesn't know how much space to reserve). FIX: Shopify Dawn sets image dimensions automatically — if using a custom theme, ensure all <img> tags have width and height attributes. 2. Late-loading banner/popup (announcement bar loads 2 seconds after page, pushing everything down). FIX: make announcement bar part of the initial HTML, not injected by JavaScript. 3. Font swap flash (custom font loads late, causing text to resize). FIX: use font-display: swap and preload the font file. 4. Dynamic content injection (review widget, trust badge app, upsell popup loading after the page). FIX: reserve space for these elements in the layout (set a minimum height on their container div). QUICK TEST: load the page on mobile 3 times in a row. If content jumps in the same spot each time: that's a reproducible layout shift. Inspect that element.
ADDITIONAL SPEED METRICS (not Core Web Vitals but important for UX)
PageSpeed Score (Mobile) | Google's overall performance score (0-100) combining all metrics into a single grade. Not a ranking factor directly, but a useful summary. | >70 Good: 80-100 Average: 50-79 Poor: <50 | pagespeed.web.dev → the large number at the top of the report. Alternative: Lighthouse (built into Chrome DevTools > Lighthouse tab > check "Performance" > run on Mobile). | Score <50: serious issues. Likely: multiple large images, too many apps, heavy theme customization. Score 50-70: room for improvement but not urgent. Focus on the specific failing CWV metrics. Score 70-90: good. Monitor monthly for degradation. Score 90+: excellent. Dawn theme with minimal apps typically scores 85-95 out of the box. REMEMBER: adding each Shopify app typically drops the score by 3-10 points. At 10 apps: your score may drop 30-100 points from baseline. Only install apps you actively use.
TTFB (Time to First Byte) | How long until the SERVER begins sending data to the browser. This is Shopify's infrastructure speed — mostly out of your control. | <800ms Good: <200ms Acceptable: 200-800ms Poor: >800ms | pagespeed.web.dev → "Server response time" or use webpagetest.org for detailed TTFB measurement. | TTFB is mostly controlled by Shopify's servers (which are fast globally). If TTFB is >800ms: (1) check if you're using a CDN-busting redirect (non-www to www or vice versa — should be one redirect max), (2) check if a Shopify app is doing server-side processing on every page load (rare but possible), (3) contact Shopify Support if consistently >1s. For most Shopify stores: TTFB is 100-300ms and requires no action.
Total Page Weight | The total file size of everything the browser downloads to render the page (HTML, CSS, JS, images, fonts). | <3 MB Good: <2 MB Acceptable: 2-3 MB Heavy: >3 MB | Chrome DevTools > Network tab > load page > check "transferred" total at bottom. OR: webpagetest.org > "Fully Loaded" bytes. | If >3 MB: the page is heavy. Most common culprits: 1. Images: each uncompressed product image can be 1-3 MB. FIX: compress via TinyPNG, max 500KB per image, use Shopify's auto-WebP conversion. 2. Apps: each Shopify app adds 50-300KB of JS/CSS. 10 apps = 0.5-3 MB of overhead. Audit and remove unused apps. 3. Video: auto-playing product video can be 5-20 MB. FIX: use a thumbnail + play button (loads video only on click). 4. Fonts: custom fonts add 100-300KB. Stick to 2 fonts (Plus Jakarta Sans + Inter per P21 brand board). TARGET: product page <2 MB, homepage <2.5 MB.
MONTHLY MONITORING PROTOCOL — add to P6E.01 weekly KPI review (check monthly, not weekly)
Step | Action | Time | Tool | If Degraded | Frequency | Add to P13 Week
1 | Run PageSpeed Insights on strideher.com (MOBILE tab) | 2 min | pagespeed.web.dev | If any CWV metric moved from "Good" to "Needs Improvement": investigate what changed since last month (new app installed? theme update? new images added?). | Monthly (1st Monday) | Add to Month 1+ KPI review
2 | Screenshot the results and save to Google Drive: /Reports/Speed/ | 1 min | Screenshot tool | Compare to previous month's screenshot. Are scores improving, stable, or declining? A declining trend over 2+ months = something is degrading. | Monthly | —
3 | Compare LCP, FID, CLS to baseline (recorded before launch) | 1 min | Saved baseline from Column G of this sheet | If any metric is >20% worse than baseline: the degradation is significant. Most likely cause: a recently installed app. Disable the most recently added app and re-test. | Monthly | —
4 | Check Shopify app count: remove any unused apps | 2 min | Shopify > Settings > Apps | Each app adds JS/CSS weight. If you've added 3+ apps since launch and score dropped >10 points: start removing. Rule: if you haven't opened the app in 30 days, uninstall it. | Monthly | —
5 | Test product page on YOUR phone (real-world check) | 1 min | Your phone (4G, not WiFi) | Does the page FEEL fast? If you notice lag, jank, or slowness that the numbers don't capture: trust your experience. Real users feel what you feel. | Monthly | —