## P5A EXEC SUMMARY
P5A INFLUENCER SEEDING PROGRAM — EXECUTIVE SUMMARY
6 Tasks ¦ Weeks 8-14 ¦ Cost: ~$420-$630 (30 free belts at $6-7 COGS + shipping) ¦ The highest-ROI marketing for a bootstrapped D2C brand.
Task ID | Task | KPI | Deliverable | Status | Expected Return | Cost
5A.01 | Build target influencer list: 30 micro-influencers in running/fitness on IG + TikTok | 30 qualified prospects identified + scored | Complete influencer prospecting framework: ideal influencer profile (6 criteria), where to find them (8 discovery methods), 30-person scoring template, and red/green flags for influencer selection. Micro-influencers (1K-50K followers) deliver 3-5× better engagement rate and 60% lower cost-per-impression than macro-influencers. | COMPLETE ✓ | 30 micro-influencers × 15-30% acceptance rate = 5-9 influencers posting content. Each influencer reaches 1K-50K followers with 3-8% engagement rate. Total estimated impressions: 25,000-200,000 from a single wave. Cost per 1,000 impressions: $2-$5 (vs $8-$15 for paid ads). Plus: you own the content forever as UGC for ads. | ~$210-$315 (15 belts at $6-7 COGS + ~$5 shipping each = ~$14-$21 per gifted unit)
5A.02 | Craft personalized outreach DMs/emails: product gift for honest review | Outreach templates + personalization framework | 3 outreach templates (Instagram DM, TikTok DM, email) each with a personalization framework showing exactly which elements to customize per influencer. Plus: follow-up cadence (Day 3, Day 7) and "no response" protocol. No payment offered — product gift only. This is authentic seeding, not paid sponsorship. | COMPLETE ✓ | Personalized outreach converts at 15-30%. Generic "Hi, want a free product?" converts at 2-5%. The 15 minutes spent personalizing each message (referencing a specific post, complimenting their running content, explaining WHY you chose them) is the difference between 2 partnerships from 15 DMs vs 5 partnerships. | $0 (your time: ~4 hours for 15 personalized outreach messages)
5A.03 | Send Wave 1 outreach to 15 influencers, track responses | 15 outreach messages sent, responses tracked | Complete outreach tracking spreadsheet: 15 influencer prospects with columns for: outreach date, platform, message sent, response (Y/N/pending), response date, shipping status, content posted (Y/N), content type, engagement metrics, and content URL for reposting. | COMPLETE ✓ | Wave 1 = learning wave. You discover: which platform (IG vs TikTok) gets better response rates, which message angle resonates, what follower size is most responsive, and which content format (reel, story, post, TikTok) your influencers prefer. This data optimizes Wave 2 for 2× better results. | ~$105-$158 (7-8 belts shipped to accepting influencers)
5A.04 | Ship free product to accepted influencers with branded packaging + handwritten note | Products shipped with unboxing experience | Complete influencer shipping specification: what to include in the influencer package (belt in brand packaging + personalized handwritten note + insert card + exclusive discount code for their followers), how to make it "unboxing-worthy" for content creation, and shipping method selection. | COMPLETE ✓ | The unboxing IS the first piece of content. A beautifully packaged product with a handwritten note gets filmed, photographed, and shared. A plain mailer with no personality gets opened off-camera and generates zero content. The extra $2-$3 in packaging + 5 minutes writing a note = the difference between content and silence. | ~$2-$3 extra per package for premium unboxing experience
5A.05 | Track and repost all influencer content: save, request permission, repurpose as UGC for ads | Content library built, 5+ pieces reposted | Complete content tracking and repurposing system: how to monitor for influencer posts (manual + tools), content saving workflow, permission request template, reposting etiquette, and how to repurpose influencer content as UGC ad creative (the most effective ad format in 2025-2026, converting 30-50% better than brand-produced ads). | COMPLETE ✓ | Each piece of influencer content serves TRIPLE duty: (1) organic reach to the influencer's audience (free), (2) reposted content on StrideHer's own channels (social proof), and (3) UGC ad creative for Meta/TikTok paid campaigns (highest-performing ad format). One influencer video can drive $500-$2,000 in attributed revenue over its lifetime. | $0 (content is free — influencers create it, you repurpose it)
5A.06 | Send Wave 2: 15 more influencers optimized from Wave 1 learnings | Wave 2 outreach sent with improved targeting | Wave 2 optimization framework: which Wave 1 variables to analyze (acceptance rate by platform, content quality by follower size, engagement rate by content type), how to adjust targeting for Wave 2, and a scaling decision tree for Wave 3+ if results justify continued investment. | COMPLETE ✓ | Wave 2 should perform 30-50% better than Wave 1 because you've learned: which platform converts best, which follower size creates the best content, which message angle gets the highest acceptance rate, and what type of content (review video vs running clip vs flat lay) drives the most website traffic. | ~$105-$158 (same as Wave 1)

## 5A.01 Influencer Prospecting
P5A TASK 5A.01: BUILD TARGET LIST — 30 MICRO-INFLUENCERS IN RUNNING/FITNESS NICHE
Micro-influencers (1K-50K followers) outperform macro-influencers for D2C: 3-5× engagement rate, more authentic content, and they'll accept free product instead of demanding $500-$5,000 fees.
Criteria | Ideal Profile | Why This Matters | Green Flags (pursue) | Red Flags (skip) | Where to Find Them | How to Evaluate | Priority
THE IDEAL STRIDEHER INFLUENCER — 6 criteria that predict partnership success
1. Follower Count | 1,000 - 50,000 followers. SWEET SPOT: 3,000-15,000. This range gets: high engagement rate (5-10%), genuine audience relationships, willingness to accept free product (no fee), and enough reach to drive measurable traffic. | Below 1K: reach too small for the effort. Above 50K: most demand payment ($200-$2,000+ per post) and have lower engagement rates (1-3%). The 3K-15K sweet spot maximizes: reach × engagement × cost efficiency. At $14-$21 per gifted belt: cost per 1,000 impressions = $1-$5 (vs $8-$15 for paid Meta ads). | 3K-15K followers with consistent posting (3+ posts/week). Growing follower count (gaining followers, not losing). Engagement rate >5% (comments, not just likes). | Bought followers (sudden spikes in follower count, low engagement relative to followers). Inactive accounts (last post >2 weeks ago). Engagement pods (same 10 people commenting on every post). | Instagram: search hashtags #womenrunners #runnersofinstagram #marathontraining #halfmarathon #runningmom TikTok: search "running belt" "running gear" "marathon training" Strava: local running clubs with active social members Reddit: r/running r/XXrunning power users | Check engagement rate: (avg likes + comments) ÷ followers × 100. 5%+ = excellent (pursue) 3-5% = good (pursue) 1-3% = average (maybe) <1% = fake or disengaged (skip) | ★ #1 Most important criteria
2. Audience Demographics | Women, 25-39, who run regularly. Their audience should match StrideHer's target: P0B personas (Marathon Megan, Running Rachel, Wellness Willow). US-based preferred (primary market), UK/Canada/Australia acceptable. | An influencer with 10K followers but an audience of teenage boys won't sell women's running belts. The influencer's AUDIENCE must match YOUR customer, not just the influencer themselves. | Bio mentions: runner, marathon, half marathon, running mom, women who run. Content is running-focused with female-presenting audience. Comments from women asking running questions. Location: US/UK/Canada. | Audience mostly male. Content is general fitness (not running-specific). Location: country where you don't ship. Bio is vague ("fitness enthusiast" with no running specifics). | Instagram audience insights: not available publicly, but you can estimate from: who comments (check 10 recent comments — are they women? runners?), what hashtags they use, and what brands they tag. Or ask directly after acceptance: "What % of your audience is women aged 25-40?" | Open 5 recent posts → read 10 comments each → are commenters women who run? This 10-minute manual check is more reliable than any tool. | #2
3. Content Quality | Well-lit photos, clear video, authentic voice. Does NOT need to be professional production quality — authentic "real runner" content outperforms polished studio content for D2C brands. Should look like: a real person sharing their genuine experience, not a commercial. | The content they create for StrideHer will match the quality of their existing content. If their feed is dark, blurry, low-effort: your product will look dark, blurry, low-effort. If their content is bright, energetic, authentic: your product gets that treatment. | Good lighting (natural outdoor preferred). Steady video (not excessively shaky). Clear audio if speaking. Genuine captions (not copy-pasted). Variety of content types (reels, stories, static posts, TikToks). | Every photo is heavily filtered and unrealistic. Captions are one word ("mood"). No video content (video drives 3× more engagement than photos for running content). Inconsistent quality (good posts mixed with lazy posts). | Scroll through their last 20 posts. Would you be proud to see StrideHer in 5 of those posts? If yes: pursue. If no: skip. | Visual quality + authentic voice > production value. A runner filming a shaky selfie video of their morning run in natural light creates more trust than a studio shoot. | #3
4. Running Credibility | Actually runs regularly. Content shows: running routes, race photos, training updates, gear reviews, running tips. They talk ABOUT running, not just pose in running clothes. Ideal: trains for half/full marathons, participates in local races, posts weekly training updates. | A fitness model who wears running clothes but doesn't run won't create authentic running belt content. Their review will feel staged and hollow. A real runner who USES the belt during training creates content that resonates with other runners because it's genuine. | Race bibs in photos. Strava/Garmin screenshots shared. Training plans discussed. Specific running routes mentioned. Gear reviews with real opinions (positive AND negative). Running community engagement. | Only gym content (no outdoor running). No race participation. Never mentions mileage, pace, or training. Running content is just "outfit of the day" with running shoes. No authentic running stories. | Search for: #raceday #finishline #marathontraining #runningcommunity + filter by follower count. Check Strava for influencers who share both Strava stats AND social content. | Would you trust their running belt review? Would you believe they actually ran in it? If yes: running credibility confirmed. | #4
5. Engagement Authenticity | Real comments from real followers who ask genuine questions and share genuine reactions. Not: "Great post!" "Love this!" "Fire 🔥" repeated by the same 10 accounts on every post (engagement pod signals). | Authentic engagement = authentic influence. An influencer with 5K followers and 50 genuine comments per post has MORE influence than one with 50K followers and 10 "Nice!" comments. Genuine comments look like: "What shoes are those?" "How was the race?" "I'm training for my first half too!" — QUESTIONS and CONVERSATIONS, not just emojis. | Comments include questions. Comments are varied (different people, different topics). The influencer REPLIES to comments (indicating genuine community). Comment-to-like ratio >5% (e.g., 200 likes + 12 comments = 6%). | Same commenters on every post (pod). Only emoji comments. Influencer never replies. Sudden engagement spikes on specific posts (paid engagement). Comment-to-like ratio <1%. | Read 20 comments across 3 recent posts. Count: how many are genuine (questions, reactions) vs generic ("love this!")? If >60% are genuine: engagement is authentic. | The "20 comment test" takes 5 minutes and is the most reliable authenticity check available without paid tools. | #5
6. Brand Alignment | Values and aesthetic that complement StrideHer. Body-positive, inclusive, pro-women, authentically enthusiastic about running gear. Their personal brand should feel like it BELONGS alongside StrideHer. Not required: perfect alignment. Diversity of voices (different running levels, body types, ages) is a feature, not a bug. | An influencer whose feed contradicts StrideHer's brand values (e.g., promotes extreme dieting alongside "wellness") creates brand association risk. A diverse range of influencers (different body types, running levels, ethnicities, ages) demonstrates that StrideHer is for ALL women who run. | Body-positive messaging. Celebrates personal running achievements (not just performance). Inclusive language. Shares both successes and struggles. Supports other women runners in comments. | Promotes unhealthy body image. Competitive gatekeeping ("real runners only do X"). Controversial political content (brand risk). Promotes competing running belt brands actively. | Quick check: would StrideHer's target customer (P0B personas: Marathon Megan, Running Rachel, Wellness Willow) follow this person and trust their recommendation? If yes for at least one persona: brand alignment confirmed. | Trust your instinct. If scrolling their feed makes you think "our customer would love this person" — pursue. | #6
INFLUENCER SCORING TEMPLATE — score each prospect 1-5 on each of the 6 criteria (30 max)
SCORING TEMPLATE | For each of the 30 prospects, score 1-5 on: 1. Follower Count (sweet spot = 5) 2. Audience Demographics (women runners = 5) 3. Content Quality (bright, authentic = 5) 4. Running Credibility (races, training = 5) 5. Engagement Authenticity (real comments = 5) 6. Brand Alignment (values match = 5) Maximum: 30 points. Outreach priority: ★ 25-30: Tier 1 (outreach first, highest priority) ★ 20-24: Tier 2 (outreach in Wave 1) ★ 15-19: Tier 3 (outreach in Wave 2) ★ Below 15: Skip | Scoring prevents "spray and pray" outreach (messaging everyone and hoping for the best). A scored list ensures your 15 Wave 1 outreach messages go to the 15 BEST prospects — maximizing acceptance rate, content quality, and ROI per gifted belt. | Create a Google Sheet with columns: Influencer Handle ¦ Platform ¦ Followers ¦ Score 1-6 (each criterion) ¦ Total Score ¦ Tier ¦ Outreach Status ¦ Notes Sort by Total Score descending. Wave 1 = top 15. Wave 2 = next 15.
8 DISCOVERY METHODS — where to find running micro-influencers
Discovery Methods | 1. HASHTAG SEARCH: #womenrunners #runnersofinstagram #marathontraining #runningmom #shewhodaresruns #runlikeagirl #runnergirl — sort by "Recent" to find active posters 2. COMPETITOR TAGGED: check who tags @flipbelt @spibelt @nathansports — these runners already review running belts 3. RACE HASHTAGS: #nycmarathon #bostonmarathon #chicagomarathon — find women who post race content with gear mentions 4. STRAVA CLUBS: "Women Who Run" and city-specific women's running clubs — members with social media links 5. RUNNING PODCASTS: guests on running podcasts often have engaged social followings 6. REDDIT r/running and r/XXrunning: active posters who also have Instagram/TikTok (check their profile links) 7. TIKTOK SEARCH: "running belt review" "running gear" "marathon training" — sort by recent, filter by <50K 8. LOCAL RUNNING STORES: many sponsor local runners/clubs — ask for introductions | Use ALL 8 methods to build a diverse prospect list. Don't rely on just one — hashtag search finds the most volume but competitor tagging finds the highest-intent influencers (they already review running gear). |  |  | Spend 2-3 hours on discovery across all 8 methods. Target: 50+ raw prospects → score down to 30 qualified → prioritize into Tiers 1-3.

## 5A.02-03 Outreach + Tracking
P5A TASKS 5A.02-03: OUTREACH TEMPLATES (3 PLATFORMS) + RESPONSE TRACKING SYSTEM
Personalized outreach converts at 15-30%. Generic "want a free product?" converts at 2-5%. Invest 15 minutes per message. It's worth every second.
Template | Platform | Message (customize [BRACKETED] sections for each influencer) | When to Use | Expected Response Rate | Follow-Up Cadence | Key Principles
3 OUTREACH TEMPLATES — one per platform. The [BRACKETED] sections MUST be personalized for each influencer.
TEMPLATE 1: Instagram DM | Instagram Direct Message | Hey [FIRST NAME]! 👋 I came across your post about [SPECIFIC POST — e.g., "your Chicago Marathon training recap" or "your morning run with the sunrise shot last week"] and it really resonated with me. I'm [YOUR NAME], founder of StrideHer — we just launched the first running belt designed specifically for women's bodies. I built it because I was tired of "unisex" belts that never fit right. I'd love to send you one to try on your runs — completely free, no strings attached. If you love it, I'd be grateful if you shared your honest experience. If you don't love it, I still want to hear your feedback. Would you be open to trying one? I can have it at your door in 3-5 days. — [YOUR NAME] strideher.com | Instagram is the PRIMARY outreach platform. Best for: influencers with strong IG presence, photo-heavy running content, reels showing running gear. Send DMs between 8-10 AM or 6-8 PM in the influencer's timezone (highest read rates). | 15-25% response rate for personalized DMs. (vs 3-5% for generic DMs) | Day 0: send initial DM. Day 3 (no response): follow-up: "Just bumping this in case it got lost in your DMs! No pressure either way — I genuinely think you'd love this belt." Day 7 (no response): final follow-up: "Last message from me! If the timing isn't right, totally understand. Wishing you great miles ahead." Day 7+: mark as "No Response" and move on. | 1. REFERENCE A SPECIFIC POST — this proves you actually looked at their content. Generic DMs get ignored; specific ones get read. 2. "No strings attached" — this is critical. Don't say "in exchange for a post." Say "if you love it, I'd be grateful if you shared." The subtle difference: one feels transactional, the other feels like a gift. 3. Lead with YOUR story (founder, designed for women) not just the product. Influencers connect with people, not products. 4. Make it easy: "at your door in 3-5 days" removes friction. 5. Keep under 200 words — DMs that scroll require too much commitment to read.
TEMPLATE 2: TikTok DM | TikTok Direct Message | Hey [FIRST NAME]! Loved your video about [SPECIFIC TIKTOK — e.g., "the running gear essentials you packed for your half marathon" or "your honest review of running accessories"]. So real. I'm the founder of StrideHer — the first running belt built specifically for women. 3 zippered pockets, adjustable fit, zero bounce. Would love to send you one for free to try. Honest review welcome — good or bad. No payment, no contract, just a free belt. Down? Drop me your address at hello@strideher.com and I'll ship it this week. — [YOUR NAME] | TikTok DMs are shorter and more casual than Instagram. TikTok culture is: direct, authentic, no fluff. Best for: influencers who create running gear content, "get ready to run with me" videos, running product reviews. TikTok DMs have lower read rates than IG — some influencers don't check TikTok DMs regularly. If no response on TikTok: try their IG or email instead. | 10-20% response rate. TikTok DMs are less reliable than IG DMs. Backup: find their IG or email. | Day 0: send TikTok DM. Day 5 (no response): try IG DM with Template 1 (many TikTokers are more active on IG DMs). Day 10: if no response on either platform, mark as "No Response." | TikTok DMs must be SHORT. Under 100 words. TikTok users scroll fast and read fast. "Down?" is TikTok-native language. "Would you be amenable to exploring a potential collaboration?" is not. Direct the response to EMAIL (hello@strideher.com) because TikTok DM is unreliable for ongoing conversations. Once they reply: move the conversation to email for shipping details.
TEMPLATE 3: Email (for influencers with email in bio) | Email | Subject: Free StrideHer belt for you — honest review welcome Hi [FIRST NAME], I've been following your running content on [IG/TikTok] and really enjoyed [SPECIFIC CONTENT — e.g., "your marathon training series" or "your running belt comparison reel"]. Your perspective on running gear is exactly the kind of honest, thoughtful feedback I value. I'm [YOUR NAME], founder of StrideHer (strideher.com). We just launched the first running belt designed specifically for women's bodies — adjustable fit from 25" to 43", 3 separate zippered pockets, silicone grip dots for zero bounce, and a contoured profile that follows women's hip geometry. I'd love to send you one — completely free — to test on your runs. There's no obligation to post or review, though I'd be honored if you shared your honest experience with your audience. Here's a 60-second video showing the belt: [link to product page or YouTube video] Would you be open to trying one? Just reply with your preferred size (S/M fits 25"-33", L/XL fits 33"-43") and color (Midnight Black, Desert Rose, Alpine Sage, or Deep Ocean) and I'll ship it this week. Thanks for the miles you inspire. [YOUR NAME] Founder, StrideHer hello@strideher.com strideher.com | Email is the MOST PROFESSIONAL outreach channel. Use when: • The influencer has an email in their IG/TikTok bio (they expect business inquiries) • They're a blogger or YouTuber (used to email pitches) • You want to provide more detail (link to product, size guide, etc.) Email has the lowest response rate (competition from other brands) but the highest response QUALITY (serious influencers who respond via email are more likely to create high-quality content). | 10-15% response rate. Lower volume but higher quality responses. | Day 0: send email. Day 4 (no response): follow-up: "Hi [NAME], just following up on my note below. Would love to get a StrideHer belt to you for testing. Any interest? No worries if the timing's off." Day 10: final follow-up: "Last ping! If now isn't the right time, I totally understand. Wishing you great runs ahead." Day 10+: mark as "No Response." | Email subject line must be CLEAR and COMPELLING. "Free StrideHer belt for you" tells them exactly what they get and why they should open. Include a LINK to the product (video or product page). Influencers who receive email pitches check the product before responding — make it easy. The size/color question at the end is a "micro-commitment" — it's easier to answer "I'm a S/M in Desert Rose" than "yes I want to collaborate." Once they reply with a size, they're committed.
TRACKING SPREADSHEET TEMPLATE (Google Sheet — one row per influencer, update after every touchpoint)
TRACKING FIELDS | Google Sheets | Create a Google Sheet with these columns: 1. Influencer Handle (@name) 2. Platform (IG / TikTok / Email) 3. Followers (number) 4. Score (from 5A.01 scoring, /30) 5. Tier (1 / 2 / 3) 6. Outreach Date 7. Outreach Method (DM / Email) 8. Response (Yes / No / Pending) 9. Response Date 10. Size/Color Requested 11. Shipped Date 12. Tracking Number 13. Delivered Date 14. Content Posted? (Yes / No / Pending) 15. Content URL (save the link) 16. Content Type (Reel / Story / Post / TikTok / YouTube) 17. Content Engagement (likes + comments) 18. Permission to Repost? (Yes / No / Pending) 19. Used as UGC Ad? (Yes / No) 20. Notes | This spreadsheet is the COMMAND CENTER for the entire influencer program. Update it religiously — every DM sent, every response received, every package shipped, every piece of content posted. Sort by: Tier (highest first), then by Response status (Yes > Pending > No). Color-code: Green = content posted, Yellow = shipped/pending, Red = no response. |  |  | This spreadsheet becomes the P5A version of the P1E.07 influencer tracker — but with operational fields (shipping, content, reposting) added. If you already started P1E.07: extend that sheet with columns 6-20 above.

## 5A.04-05 Ship + Repost
P5A TASKS 5A.04-05: INFLUENCER PACKAGE SHIPPING + CONTENT TRACKING & REPURPOSING
The unboxing IS the first piece of content. Make it worth filming. Then track every piece of content created and repurpose for ads.
Element | Details | How to Execute | Why This Matters | Cost | Timeline | Notes
5A.04: INFLUENCER PACKAGE — what to include + how to make it unboxing-worthy
Package Contents | Every influencer package contains: 1. StrideHer belt in their requested size/color (in standard brand packaging — poly mailer with brand sticker) 2. HANDWRITTEN NOTE (personalized — see template below) 3. Insert card (standard from P2C.03 — with QR code + care instructions) 4. Exclusive INFLUENCER DISCOUNT CODE (unique per influencer: their handle as the code, 15% off for their followers) 5. Optional: small branded extra (sticker sheet, trail mix packet, or hair tie with brand tag — costs <$2) | Package exactly as a customer would receive it PLUS the handwritten note and exclusive code. The influencer should experience the SAME unboxing a customer gets — this makes their review authentic. Create unique discount codes: Admin → Discounts → "[HANDLE]15" (e.g., "SARAH15") — 15% off, unlimited uses, tracks how many sales each influencer generates. | The package IS the content trigger. Influencers who receive a thoughtful, well-packaged product with a personal note are 3× more likely to post content than those who receive a plain brown box. The handwritten note is the most important element. It takes 3 minutes and makes the influencer feel valued as a person, not a marketing channel. | $14-$21 per package (belt COGS $6-$7 + packaging $1 + shipping $5 + extras $2) | Ship within 48 hours of acceptance. Fast shipping = fast content. Every day of delay = lower likelihood of posting. | Ship via USPS Priority Mail (2-5 days, tracking included). The tracking number also serves as a follow-up conversation starter: "Your belt should arrive tomorrow! Can't wait to hear what you think after your first run."
Handwritten Note Template | Write on a small card (3.5×5" notecard or StrideHer branded card if available): "Hi [FIRST NAME], Thank you so much for trying StrideHer! I've been following your running journey and [ONE SPECIFIC COMPLIMENT — e.g., "your Chicago Marathon finish was incredible" or "your morning runs inspire me to get out the door"]. I built this belt because I was tired of gear that wasn't made for us. I hope it makes your miles a little easier. Your exclusive code for your community: [HANDLE]15 (15% off) Run your way, [YOUR FIRST NAME]" Handwrite every note. Not typed, not printed. Handwritten. | Keep a stack of notecards and a nice pen at your packing station. Before writing each note: open the influencer's profile on your phone and find the specific compliment. This 60-second personalization step is the most important part. If your handwriting is truly illegible: print the body but handwrite the greeting and sign-off. | Handwritten notes are the ultimate authenticity signal. In an era of automated everything, a hand-written note says: "A real person packaged this, cares about me, and took the time." Influencers post photos of handwritten notes. They never post photos of packing slips. | $0.50 per notecard (bulk: $5 for 50 cards from Amazon/Staples) | 3 min per note. 15 notes = 45 min. Do all 15 notes in one batch session while packaging. | DO NOT use a handwriting robot or printed "handwritten" font. Influencers can tell. The imperfections of real handwriting ARE the point. A messy but genuine note is 10× more impactful than a perfect printed one.
5A.05: CONTENT TRACKING + REPURPOSING — turn influencer content into your most valuable marketing assets
Monitoring for Posts | Check daily for influencer content: 1. MANUAL CHECK: open each influencer's profile (IG + TikTok) daily for 2 weeks after delivery. Check: feed posts, reels, stories (stories disappear in 24 hrs — check daily), TikToks. 2. HASHTAG MONITORING: ask influencers to use #StrideHer and @strideher. Search these daily. 3. GOOGLE ALERTS: set up a Google Alert for "StrideHer" to catch blog posts or YouTube videos. 4. DM CHECK: some influencers will DM you when they post (common courtesy). | Set a daily calendar reminder: "Check influencer content — 10 min" for 2 weeks after each shipment wave. When you find content: 1. Screenshot/screen-record immediately (stories disappear) 2. Save the direct URL 3. Update your tracking spreadsheet 4. Like + comment on the post within 1 hour (engagement boosts their reach = more exposure for StrideHer) | If you don't actively monitor, you'll miss: stories (gone in 24 hrs), TikToks (can be hard to find later), and the optimal window for reposting (first 24 hours get the most engagement when you share to your own audience). | $0 | Daily for 2 weeks after each shipment wave. Total: ~2 hours per wave (10 min/day × 14 days). | Use the Instagram "Save" feature to bookmark influencer posts. This creates a curated library of all StrideHer content in one place. For TikTok: use the "Favorites" feature to save TikToks.
Permission to Repost + UGC Use | BEFORE reposting or using content as ad creative: Send a DM: "[FIRST NAME], I LOVE the content you created! Thank you so much 🙏 Quick question — would you be okay with us reposting this to our StrideHer account and potentially using it in our marketing? Full credit to you of course. Totally fine if you'd rather we didn't." Most influencers say yes (it's free exposure for them too). If they say YES: you now have licensed UGC for: • Reposting on StrideHer IG/TikTok (free content) • Using as Meta/TikTok ad creative (highest-performing ad format) • Featuring on your website product page (social proof) • Including in email marketing (testimonial content) | 1. DM permission request (template above) 2. Wait for explicit "yes" — do NOT assume permission 3. Once approved: download the full-resolution content (ask them to send original file if possible — screenshots lose quality) 4. Store in your Brand Asset folder (P1D.04 DAM system): /Influencer-UGC/[Handle]/[Date]-[ContentType] 5. Credit them in every repost: "@[handle] wearing StrideHer on her morning run 🏃‍♀️" For UGC ads: Meta allows you to run ads using influencer content with their permission. This is called "UGC ad creative" and outperforms brand-produced ads by 30-50%. | UGC (User-Generated Content) ad creative is the #1 performing ad format on Meta and TikTok in 2025-2026. A real runner's authentic video of your product converts 30-50% better than a professionally produced brand ad. The influencer seeding program's TRUE value isn't just the organic reach — it's the library of UGC content you build for paid advertising. 10 influencer videos = 10 ad creatives to test = months of ad content without a production budget. | $0 | Request permission within 24 hours of content posting. Repost within 48 hours (maximize momentum). | ALWAYS credit the influencer when reposting. Never crop out their watermark or username. The credit is both ethical and strategic — other influencers see you give credit and are more likely to accept your next outreach.

## 5A.06 Wave 2 Optimization
P5A TASK 5A.06: WAVE 2 OPTIMIZATION — LEARN FROM WAVE 1, DOUBLE RESULTS IN WAVE 2
Wave 1 is the experiment. Wave 2 is the optimized version. Analyze 5 variables, adjust, and send 15 more outreach messages.
Variable | What to Analyze from Wave 1 | How to Adjust for Wave 2 | Example | Data Source | Impact | Decision Rule
5 VARIABLES TO ANALYZE + OPTIMIZE BETWEEN WAVE 1 AND WAVE 2
1. Platform Response Rate | Of your 15 Wave 1 outreach messages: How many on IG responded? ___/___ How many on TikTok responded? ___/___ How many on Email responded? ___/___ Which platform had the highest acceptance rate? | If IG outperforms TikTok: shift Wave 2 to 80% IG, 20% TikTok. If TikTok outperforms: shift to 80% TikTok. If Email outperforms both: shift to email-first for all influencers with email in bio. | Wave 1: IG 4/8 (50%), TikTok 1/5 (20%), Email 1/2 (50%). Conclusion: IG and Email are equally effective. TikTok DMs underperform. Wave 2: 10 IG DMs + 5 Emails. Skip TikTok DMs. | Tracking spreadsheet (5A.02-03): columns 2, 7, 8. | Shifting to the best-performing platform increases Wave 2 acceptance rate by 30-50%. | If one platform has 2×+ higher response rate than another: concentrate Wave 2 on the winner. If all platforms are similar (<10% difference): maintain equal split but test a new variable (message angle).
2. Follower Size vs Content Quality | Of influencers who POSTED content: Which follower size tier created the best content? • 1K-5K: ___ • 5K-15K: ___ • 15K-50K: ___ "Best content" = highest quality video/photo + most engagement + most authentic review. | If smaller influencers (1K-5K) created better content: target more nano-influencers in Wave 2. They're hungrier, more grateful, and often more authentic. If larger influencers (15K-50K) created better content: target more established creators — their production value may be worth the reach. | Wave 1 finding: 3K-8K influencers created the most authentic content AND had the highest engagement rate. 20K+ influencers created polished but generic content that felt less personal. Wave 2: target 3K-10K sweet spot. | Tracking spreadsheet: columns 3, 16, 17. | Targeting the right follower size improves content quality AND cost-efficiency. | The "best" influencer is the one whose content YOU would share on your brand page and use as an ad. Not necessarily the one with the most followers.
3. Content Format Performance | Which content FORMAT drove the most engagement and website traffic? • Instagram Reel: ___ • Instagram Story: ___ • Instagram Feed Post: ___ • TikTok video: ___ • YouTube video: ___ • Blog post: ___ | If Reels outperform: in Wave 2 outreach, mention "we'd love to see it in a reel if you're up for it" (gentle suggestion, not a demand). If TikTok outperforms: target more TikTok-native creators. If Stories outperform: note that stories disappear in 24 hours — request that influencers also save as a Highlight. | Wave 1: Reels averaged 5,000 impressions + 200 engagements. Stories averaged 1,500 impressions but 50 link clicks. TikTok averaged 8,000 views but 0 trackable link clicks. Conclusion: Reels for awareness, Stories for website traffic. Request both in Wave 2. | Tracking spreadsheet: columns 16, 17. GA4: check referral traffic from instagram.com and tiktok.com during the content posting window. | Guiding influencers toward the highest-performing format (gently) increases the ROI of each gifted belt. | NEVER demand a specific format. Suggest: "Feel free to share however feels most natural — but we've seen Reels perform really well if you're up for it!"
4. Message Angle Effectiveness | Which ANGLE in your outreach message got the best response? Angles used: • "Designed for women" (gender-specific) • "First running belt with separate pockets" (feature-specific) • "Zero bounce" (pain-point-specific) • "I've been following your running journey" (personal connection) • "Founder story" (bootstrapped, authentic brand) | Identify which angle appeared in the outreach messages that got accepted vs rejected. If "designed for women" consistently got responses: lead with it in Wave 2. If "pain-point" (zero bounce) resonated: lead with that instead. If "personal connection" was the differentiator: double down on the personalization effort. | Wave 1: 3/4 messages leading with "designed for women" got a response. 1/4 messages leading with "zero bounce" got a response. 2/4 messages leading with personal connection got a response. Conclusion: "designed for women" is the strongest lead angle. Wave 2: lead every message with the women-specific positioning. | Compare outreach message text (saved in tracking sheet or DM history) with response outcomes. | The right message angle can double response rates from 15% to 30%. | A/B test if you have enough volume: send 8 messages with Angle A and 7 with Angle B. Whichever performs better: use exclusively in future waves.
5. Scaling Decision | After Wave 1 + Wave 2 (30 total outreach messages): Total belts gifted: ___ Total content pieces created: ___ Total impressions: ___ Trackable website visits: ___ Sales attributed (via discount codes): ___ Cost per content piece: ___ Cost per 1,000 impressions: ___ Cost per attributed sale: ___ | SCALE if: • Cost per 1,000 impressions < $5 (competitive with paid ads) • At least 50% of gifted influencers posted content • At least 1 sale per 5 gifted belts (20% conversion-to-sale rate from seeded units) CONTINUE SMALL if: • Metrics are borderline — run Wave 3 of 10 influencers to confirm trends PAUSE if: • Cost per 1,000 impressions > $10 (paid ads are more efficient) • <30% of gifted influencers posted content • 0 attributed sales from 15+ gifted belts | Wave 1+2 combined results: 15 belts gifted, 10 content pieces, 45,000 total impressions, 350 website visits, 8 sales via influencer codes. Cost: 15 × $18 = $270 Cost per content piece: $27 Cost per 1,000 impressions: $6 Cost per sale: $34 Decision: CONTINUE — CPM ($6) is competitive with paid ads ($8-$15) and the UGC content library is an additional asset worth $500+ in ad production value. | All data from tracking spreadsheet + GA4 referral traffic + Shopify discount code analytics. | The scaling decision determines whether influencer seeding becomes a permanent channel (ongoing waves every 4-6 weeks) or a launch-only tactic. | The TRUE value of influencer seeding includes: organic impressions (measurable) + UGC content library (worth $50-$100 per video in ad production value) + social proof for brand credibility (immeasurable). Factor all 3 into the scaling decision, not just CPM.

## 5A FOUNDER ACTIONS
P5A INFLUENCER SEEDING — FOUNDER ACTION CHECKLIST
Total investment: ~$420-$630 (30 gifted belts) + ~15 hours of founder time over 6 weeks. Expected return: 25K-200K impressions + 10-20 UGC content pieces + 5-15 attributed sales.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 8-9: PROSPECT + OUTREACH WAVE 1
🔴 #1 | Build influencer prospect list: 50 raw → score → 30 qualified → rank into tiers | 3-4 hrs | $0 | 1. Use all 8 discovery methods from Sheet 5A.01 to find 50+ running micro-influencers 2. Create Google Sheet with the 20-column tracking template from Sheet 5A.02-03 3. Score each prospect 1-5 on the 6 criteria from Sheet 5A.01 (total score /30) 4. Rank by score. Top 15 = Wave 1. Next 15 = Wave 2. 5. Research each Wave 1 prospect: find their specific post to reference in outreach. Note their size/color guess.
🔴 #2 | Send personalized outreach to 15 Wave 1 influencers | 4 hrs (~15 min per message) | $0 | 1. For each of the 15 Wave 1 prospects: open their profile, find the specific post/video to reference 2. Select the right template (IG DM, TikTok DM, or Email from Sheet 5A.02-03) 3. Customize ALL [BRACKETED] sections — first name, specific post reference, personal compliment 4. Send between 8-10 AM or 6-8 PM in their timezone 5. Log in tracking sheet: outreach date, platform, message sent 6. Set Day 3 and Day 7 follow-up reminders for non-responders
WEEK 9-10: SHIP + MONITOR
🔴 #3 | Ship belts to all accepting influencers | 30 min per package | $14-$21 per package | 1. When an influencer responds YES: ask for size, color, and shipping address 2. Create their unique discount code in Shopify: "[HANDLE]15" (15% off, unlimited uses) 3. Pack their belt per Sheet 5A.04-05: standard brand packaging + handwritten note (personalized!) + insert card + notecard with their exclusive discount code 4. Ship via USPS Priority Mail (tracking included) within 48 hours of acceptance 5. DM them: "Your StrideHer belt is on its way! Tracking: [number]. Can't wait to hear what you think 🏃‍♀️" 6. Update tracking sheet: shipped date, tracking number
🟡 #4 | Monitor daily for influencer content (2 weeks after shipping) | 10 min/day × 14 days | $0 | 1. Daily: check each influencer's IG + TikTok for new content featuring StrideHer 2. Check #StrideHer hashtag across platforms 3. When content is found: screenshot/screen-record immediately, save URL, like + comment within 1 hour 4. Update tracking sheet: content type, URL, engagement metrics 5. Send thank-you DM: "This is amazing! Thank you so much 🙏" 6. If no content after 14 days: send a gentle check-in (NOT a demand): "Hey [NAME]! How are your runs going in the StrideHer? I'd love to hear your honest thoughts — no pressure to post if it's not your thing."
🟡 #5 | Request repost permission + download content for UGC library | 15 min per piece | $0 | 1. For every piece of influencer content: send the permission request DM from Sheet 5A.04-05 2. Once approved: download full-resolution content (ask influencer to send original file via DM or email) 3. Save in brand asset folder: /Influencer-UGC/[Handle]/[Date]-[ContentType] 4. Repost to StrideHer IG/TikTok with full credit within 48 hours 5. Flag best pieces as "UGC Ad Candidates" for Meta/TikTok advertising (P6C) 6. Update tracking sheet: permission status, reposted, used as ad creative
WEEK 12-14: WAVE 2 + SCALING DECISION
🟡 #6 | Analyze Wave 1 results and send optimized Wave 2 | 2-3 hrs analysis + 4 hrs outreach | $105-$158 | 1. Compile Wave 1 data per Sheet 5A.06: platform response rates, follower size vs content quality, format performance, message angle effectiveness 2. Adjust Wave 2 targeting based on findings (shift platform, follower size, message angle) 3. Select 15 Wave 2 prospects from your remaining scored list (adjust scoring weights if Wave 1 revealed new criteria) 4. Send personalized outreach to all 15 using the optimized template 5. Ship, monitor, and track using the same process as Wave 1 6. After Wave 2: make the SCALE / CONTINUE / PAUSE decision per Sheet 5A.06