## P6E EXEC SUMMARY
P6E PERFORMANCE OPTIMIZATION & 90-DAY PLAN — EXECUTIVE SUMMARY
5 Tasks ¦ Weeks 16-24+ (ongoing) ¦ Cost: $0 ¦ The difference between a brand that launches and dies vs one that launches and GROWS.
Task ID | Task | KPI | Deliverable | Status | Why Optimization Matters | Timeline
6E.01 | Establish weekly KPI review cadence: traffic, conversion, AOV, CAC, ROAS, email, reviews | Weekly review ritual operational | Complete weekly review protocol: 15 KPIs tracked weekly, 30-minute Monday morning ritual, benchmarks by month, and escalation triggers (which metric declines require which action). This is the operating system of a data-driven D2C brand — the rhythm that turns raw numbers into growth decisions. | COMPLETE ✓ | Without a weekly review cadence: you discover problems 30-60 days late (when revenue drops, not when the leading indicator first moved). With a weekly review: you catch a declining conversion rate in Week 2, diagnose the cause in Week 3, fix it in Week 4 — before it destroys Month 2 revenue. Weekly reviews compress the feedback loop from months to days. | Start: Week 3 (after enough data accumulates). Continue: FOREVER. This never stops.
6E.02 | A/B test product page: hero image, headline, price display, CTA button | 3 A/B tests completed with documented winners | Complete A/B testing framework: what to test first (ranked by expected conversion lift), how to run tests on Shopify (with free tools), minimum sample size for statistical significance, and 6 specific test ideas with hypotheses. A 10% conversion rate improvement on the product page = 10% more revenue from the SAME traffic — the highest-ROI optimization available. | COMPLETE ✓ | A/B testing is the COMPOUND INTEREST of D2C optimization. A 5% improvement in conversion rate + a 5% improvement in AOV + a 5% improvement in email conversion = 15.8% total revenue increase (multiplicative, not additive). Three small optimizations create outsized impact because they multiply across every visitor, every day, forever. | Month 2-3: run first 3 tests. Each test needs 2-4 weeks and 200+ sessions per variant. Monthly thereafter.
6E.03 | Analyze first 30 days of customer data: who bought, where from, what drove them | 30-day customer analysis report completed | Complete customer data analysis: demographic profile of actual buyers (age, location, device, traffic source), purchase funnel analysis (where they enter, where they drop off, what converts them), cohort analysis (Day 1 buyers vs Week 2 buyers — different profiles?), and the critical question: "Does our actual customer match our P0B persona assumptions?" | COMPLETE ✓ | The first 30 days of real customer data is more valuable than all 7 months of pre-launch research. P0B personas were HYPOTHESES — customer data validates or invalidates them. If your P0B "Marathon Megan" was predicted as the primary buyer but actual data shows "Running Rachel" (casual 5K runner) is 60% of sales: your marketing targeting, content strategy, and ad audiences all need to shift to match REALITY. | Day 30: compile report. This is a ONE-TIME deep analysis that resets all assumptions.
6E.04 | Collect and respond to first 20+ reviews: identify patterns in praise and complaints | Review analysis completed, patterns documented | Complete review analysis framework: how to solicit reviews (P4B.04 Email 3 + Judge.me auto-requests), how to respond to every review (positive and negative — templates provided), how to identify PATTERNS (3+ mentions of same praise = marketing message, 3+ mentions of same complaint = product fix), and how to use reviews as ad creative + product page social proof. | COMPLETE ✓ | Reviews are the VOICE OF THE CUSTOMER at scale. Individual reviews are anecdotes; 20+ reviews reveal PATTERNS. The pattern in praise tells you what to amplify in marketing ("zero bounce" mentioned in 8 of 20 reviews = lead your ads with zero bounce). The pattern in complaints tells you what to fix in v2 ("gel pocket magnet too weak" in 3 reviews = must-fix for reorder). Reviews are simultaneously: social proof, product research, marketing copy, and quality control. | Target: 10 reviews by Day 30. 25+ by Day 60. Analyze patterns at 20+ reviews.
6E.05 | Create 90-day optimization plan: what to scale, what to fix, what to kill | 90-day plan documented with monthly milestones | Complete 90-day post-launch optimization plan: Month 1 focus (fix what's broken), Month 2 focus (optimize what's working), Month 3 focus (scale what's proven). With specific actions per month across 6 areas: product page, ad campaigns, email, content, product, and operations. This plan transforms the "launch sprint" into "sustainable growth operations." | COMPLETE ✓ | The 90-day plan prevents the post-launch stall — the common pattern where a founder launches with huge energy, runs hard for 2 weeks, then loses direction. "What should I focus on NOW?" becomes unanswerable without a plan. The 90-day structure answers that question for every week of the next 3 months: Month 1 = fix, Month 2 = optimize, Month 3 = scale. | Day 8 (after launch week results from P6B.05): write the plan. Execute Months 1-3.

## 6E.01-02 KPIs + AB Testing
P6E TASKS 6E.01-02: WEEKLY KPI REVIEW PROTOCOL + PRODUCT PAGE A/B TESTING FRAMEWORK
15 KPIs every Monday. 3 A/B tests per quarter. The operating system of a data-driven D2C brand.
# | KPI | Source | Week 1 | Week 2 | Week 3 | Week 4 | Benchmark / Action Trigger
WEEKLY KPI DASHBOARD — update every Monday morning (30 minutes). Same template as P4C.05, condensed for weekly rhythm.
1 | Sessions | GA4 |  |  |  |  | Month 1: 200-500/wk. Month 3: 500-1,500. Declining 2 weeks in a row → investigate: social posting frequency? Ad spend change? SEO drop?
2 | Conversion Rate (%) | Shopify Analytics |  |  |  |  | Month 1: 1.5-3%. Month 3: 2.5-4%. Below 1.5% for 2 weeks → product page issue (run Clarity recordings). Above 4% → excellent, scale traffic.
3 | Orders | Shopify |  |  |  |  | Month 1: 8-15/wk. Month 3: 15-30/wk. Flat for 3 weeks → traffic or conversion problem. Diagnose which.
4 | Revenue ($) | Shopify |  |  |  |  | Month 1: $280-$525/wk. Month 3: $525-$1,050. Compare to P0E model weekly.
5 | AOV ($) | Shopify |  |  |  |  | $32-$35 (single product). Drops below $30 → too many discounts active. Rises above $35 → customers buying 2+ (celebrate).
6 | CAC ($) | Ad spend ÷ new customers |  |  |  |  | Target: <$10. $10-$15 = acceptable during scaling. >$15 = optimize ads before spending more. $0 = organic/referral only (best case).
7 | ROAS (×) | Meta + Google Ads |  |  |  |  | Target: 3×+. 2-3× = break-even after COGS. <2× = losing money on ads, pause and diagnose. >4× = scale immediately.
8 | Email Revenue ($) | Klaviyo |  |  |  |  | Track: welcome flow + abandoned cart + post-purchase revenue. Target: 20-30% of total revenue from email. Below 15% → flows may be broken.
9 | Email List Growth | Klaviyo |  |  |  |  | Net new subscribers/week. Target: +20-50/wk from popup + organic. Declining → popup fatigue (refresh offer/design).
10 | Review Count (cumulative) | Judge.me |  |  |  |  | Target: 10 by Day 30, 25 by Day 60, 50 by Day 90. Below target → send additional review request email or increase post-purchase Email 3 frequency.
11 | Avg Review Rating | Judge.me |  |  |  |  | Target: 4.5+. Below 4.0 → product quality issue, investigate complaints. 4.0-4.5 → normal, address specific concerns in v2. 4.5+ → excellent.
12 | Social Followers (IG) | IG Insights |  |  |  |  | Track net growth. +50-100/wk = healthy. Flat → increase posting frequency or try new content format. Losing followers → content may be too salesy.
13 | Social Followers (TikTok) | TikTok Analytics |  |  |  |  | TikTok grows in bursts. 0 growth for 2 weeks then +300 overnight is normal. Don't panic at flat weeks.
14 | Inventory Remaining | Shopify |  |  |  |  | Track total units remaining. When below reorder point (P3D.01) → trigger reorder immediately. Don't wait.
15 | Customer Service Tickets | Email inbox |  |  |  |  | Track: total emails/week + top 3 topics. If sizing questions >30% of tickets → size guide needs improvement. If "where's my order" >20% → shipping communication needs work.
A/B TESTING FRAMEWORK — 6 tests ranked by expected conversion impact
TEST 1 ★ Highest Impact | HERO IMAGE: test current hero photo vs an on-body running photo as the first product image | Shopify: duplicate product page theme section. Show Version A to 50% of visitors, Version B to 50%. Use Shopify's built-in A/B testing (Shopify Plus) OR free tools: Google Optimize (sunset — use VWO or Convert free tiers) OR simply swap the image for 2 weeks, compare conversion rate period-over-period. |  |  |  |  | HYPOTHESIS: an on-body running photo as hero converts better than a product-on-white hero because visitors immediately see how it looks when WORN (answering "will this look good on me?" — the #1 product page question). MINIMUM SAMPLE: 200 sessions per variant (400 total) for 95% statistical significance at a 2% baseline conversion rate. At 500 sessions/week: test runs 2 weeks. EXPECTED LIFT: 5-15%. At 500 sessions/week with 2.5% baseline: a 10% lift = 1.25 additional sales/week = $44/week = $2,275/year from a single image swap.
TEST 2 | CTA BUTTON TEXT: "Add to Cart" vs "Get Yours — Free Shipping" | Change the Add to Cart button text in Dawn theme: Customize → Product page → Button text. Run for 2 weeks per variant. |  |  |  |  | HYPOTHESIS: "Get Yours — Free Shipping" converts better because it: (1) creates ownership language ("yours"), (2) removes the #1 purchase objection (shipping cost) directly on the button, and (3) feels more personal than generic "Add to Cart." EXPECTED LIFT: 3-8%. Small per-click impact but applies to EVERY visitor — compounds significantly over time.
TEST 3 | PRICE DISPLAY: "$34.99" vs "$34.99 — Free Shipping Included" vs "$34.99 (Save $4.99 on shipping)" | Edit the price display in product page template. Test each variant for 2 weeks. |  |  |  |  | HYPOTHESIS: explicitly calling out "Free Shipping Included" next to the price pre-answers the "how much is shipping?" objection before the customer reaches checkout. 60% of cart abandonment is caused by unexpected shipping costs — even when shipping IS free, many customers assume there will be a charge. EXPECTED LIFT: 5-12% reduction in cart abandonment rate.
TEST 4 | SOCIAL PROOF PLACEMENT: reviews badge near Add to Cart vs below the fold only | Add a "★★★★★ (X reviews)" text badge directly below the price and above the Add to Cart button. Compare to current placement (reviews section at bottom of page only). |  |  |  |  | HYPOTHESIS: a review count badge near the purchase decision zone provides social proof at the moment of decision — when the visitor's thumb is hovering over "Add to Cart." Currently, reviews are below the fold — 40% of mobile users never scroll to them. EXPECTED LIFT: 5-10%. Once you have 20+ reviews, this test becomes highly impactful.
TEST 5 | SIZE GUIDE ACCESSIBILITY: current (link in description) vs button next to size selector | Add a "📏 Size Guide" button directly next to the S/M ¦ L/XL variant selector. Compare click-through and conversion. |  |  |  |  | HYPOTHESIS: a size guide button NEXT TO the size selector reduces sizing uncertainty at the decision point. Clarity session recordings (P4C.04) consistently show visitors scrolling past the size guide link in the description. Putting it where they're already looking = more clicks = more confident size selection = fewer abandoned carts. EXPECTED LIFT: 8-15% reduction in size-related bounce + 3-5% overall conversion lift. This is the #1 finding from D2C session recordings.
TEST 6 | URGENCY MESSAGING: no urgency vs "X left in stock" vs "Selling fast — order soon" | Add low-stock messaging to the product page when any variant has <30 units remaining. Test: no message vs specific count ("Only 12 left") vs vague ("Selling fast"). |  |  |  |  | HYPOTHESIS: specific inventory counts ("Only 12 left in Desert Rose S/M") create genuine urgency without feeling manipulative — because it's TRUE (you really only have 12 left). Vague urgency ("Selling fast!") feels salesy. Specific is trustworthy. EXPECTED LIFT: 3-8% when stock is genuinely low. No effect when stock is high (don't show "247 left" — that's anti-urgency). Only activate below 30 units per variant.

## 6E.03-04 Data + Reviews
P6E TASKS 6E.03-04: 30-DAY CUSTOMER ANALYSIS + REVIEW PATTERN MINING
The first 30 days of real data is more valuable than 7 months of pre-launch research. P0B personas were hypotheses — customer data validates or invalidates them.
Analysis Area | Questions to Answer | Data Source | How to Pull the Data | What to Do With Findings | Expected Insights | Action Trigger
6E.03: 30-DAY CUSTOMER DATA ANALYSIS — complete on Day 30, update monthly thereafter
WHO Bought? | • Age range of buyers (if available from Meta Pixel or email data) • Gender split (should be ~95% women — if male purchases are significant, investigate: buying as gifts? mismatched targeting?) • Geographic distribution: which US states? Any international? • Device: mobile vs desktop purchase split • New vs returning visitor at time of purchase | GA4 → Demographics GA4 → Tech → Device Shopify → Customers Klaviyo → subscriber profiles Meta Pixel → audience insights | GA4: Reports → User Attributes → Demographics → age + gender breakdown of converters. GA4: Reports → Tech → Platform → device category of purchasers. Shopify: Customers → export → analyze by state, country. Klaviyo: Audience → demographics. | Compare to P0B personas: • "Marathon Megan" (30-35, serious runner) was predicted as 35% of buyers. Actual: ___%. • "Running Rachel" (25-30, casual) predicted 25%. Actual: ___%. • "Wellness Willow" (35-39, lifestyle) predicted 20%. Actual: ___%. If actual ≠ predicted: SHIFT your marketing targeting to match actual buyer profile. The market tells you who your customer IS — listen. | Common surprise findings for women's running products: 1. Age skews older than expected (35-44 vs predicted 25-35) — older runners spend more on gear 2. Desktop conversion rate is 2× mobile (even though 70% of traffic is mobile) — checkout optimization for mobile is critical 3. Top 3 states are often: CA, TX, NY/FL — population centers with running culture | If actual buyer profile diverges >20% from P0B assumptions: → Update Meta ad targeting to match actual demographics → Adjust content tone/imagery to resonate with actual audience → Revise P0B personas based on real data → This is NOT a failure — it's the market teaching you who your customer really is
WHERE Did They Come From? | • Traffic source breakdown: organic search, social (IG vs TikTok), email, paid ads (Meta vs Google), direct, referral • Which SOURCE drives the most revenue (not just traffic — a source with 100 visits and 5 sales beats a source with 500 visits and 2 sales) • First-touch vs last-touch attribution: did they discover you on TikTok but buy via email? | GA4 → Acquisition → Traffic acquisition GA4 → Monetization → e-commerce purchases by source Shopify → Analytics → Sales by traffic source Klaviyo → flow revenue attribution | GA4: Reports → Acquisition → Traffic acquisition → sort by "Conversions" column (not sessions). The conversion-sorted view reveals your MONEY channels vs your TRAFFIC channels. They're often different. | ALLOCATE time and budget proportional to REVENUE contribution, not traffic contribution. Example finding: TikTok drives 40% of traffic but 10% of revenue. Email drives 15% of traffic but 35% of revenue. → Action: maintain TikTok for awareness but invest MORE in email optimization (higher revenue per effort). → Action: investigate why TikTok traffic doesn't convert (wrong audience? mobile checkout issues? landing page mismatch?). | Typical D2C Month 1 source mix: • Email: 30-40% of revenue (highest converter) • Social: 15-25% (awareness driver) • Paid ads: 20-30% (scalable) • Organic: 5-10% (growing) • Direct: 10-15% (brand awareness) Email almost always over-indexes on revenue because subscribers are pre-qualified. | If any single source >50% of revenue: → Diversification risk. If that source fails (email deliverability issue, ad account suspension, algorithm change), you lose >50% of revenue overnight. → Actively invest in second and third channels to reduce dependency.
WHAT Converted Them? | • Last page visited before purchase (was it the product page? A blog post? The FAQ?) • Average pages per session for buyers (how much research before purchasing?) • Time between first visit and purchase (same session? Came back later via email?) • Discount code usage: what % used HERSTRIDE20 vs WELCOME10 vs full price? • Which EMAIL in the welcome/abandoned cart flow triggered the purchase? | GA4 → Path exploration GA4 → User explorer Shopify → discount analytics Klaviyo → flow conversion attribution | GA4: Explore → Path exploration → start with "purchase" event → look backward to see which pages they visited before buying. Klaviyo: Flows → each flow → conversion metrics → which specific email drove the purchase? | Understanding the conversion PATH reveals: • If most buyers visit the FAQ before purchasing → the FAQ is a critical trust-builder (optimize it further) • If most buyers return via abandoned cart Email 2 (social proof) → social proof is the primary conversion driver (add more to the product page) • If 60% of buyers use a discount code → price sensitivity is higher than expected (test a $29.99 price point) • If 40% buy at full price → pricing power is strong (maintain $34.99) | Common conversion path for D2C running products: Visit 1 (social/ad): browse product page → leave. Visit 2 (email): open abandoned cart email → return → read FAQ → leave. Visit 3 (email): open Email 2 (social proof) → return → buy. Average: 2-3 visits before purchase. Average: 3-7 days between first visit and purchase. | If average visits-to-purchase >4: → Consider adding a stronger incentive earlier in the journey → Or add more trust signals to the product page (reduce the number of visits needed to feel confident) If >70% buy on first visit: → Traffic is extremely well-qualified (your targeting is excellent) → Scale that traffic source aggressively
6E.04: REVIEW ANALYSIS — mine 20+ reviews for PATTERNS, not individual opinions
PRAISE Patterns (3+ mentions = marketing message) | Read every review. Tally how many times each positive theme is mentioned: • Zero bounce / stays in place: ___/20 • Adjustable fit / sizing: ___/20 • Pocket organization / separation: ___/20 • Comfort / invisible after mile X: ___/20 • Phone fit / security: ___/20 • Women-specific design: ___/20 • Hidden pocket / period products: ___/20 • Quality / craftsmanship: ___/20 The top 3 themes (by mention count) become your PRIMARY marketing messages — because customers are telling you what they value MOST in their own words. | Judge.me dashboard Shopify → Reviews Amazon reviews (when live) | Export all reviews to a spreadsheet. Create columns for each theme above. Read each review and mark which themes it mentions. Sort by frequency. Top 3 themes = your marketing copy should lead with these words (not your words — THEIR words). | If "zero bounce" is mentioned in 12 of 20 reviews: → Lead every ad, every email subject line, every social post with "zero bounce" → The product page hero headline should reference this → The Amazon listing title should include it Customer language > marketer language. "It doesn't move at all" (customer) is more persuasive than "Zero Bounce Technology" (marketer). Use their exact phrasing in your ads. | Expected top praise themes for a women's running belt: 1. "Doesn't bounce / stays in place" (the #1 pain point solved) 2. "Finally fits / adjustable" (sizing solved) 3. "Love the separate pockets" (organization) 4. "Hidden pocket" (surprise + delight) 5. "Comfortable / forget it's there" (the ultimate compliment) | When 3+ reviews mention the same praise: → IMMEDIATELY update: product page headline, Meta ad primary text, Google Search ad headline, email subject lines → The market just told you your value proposition — use their words
COMPLAINT Patterns (3+ mentions = v2 fix) | Same tally exercise for negative themes: • Sizing issue (too large/small): ___/20 • Gel pocket magnet too weak: ___/20 • Color different from photos: ___/20 • Zipper stiff / hard to use one-handed: ___/20 • Elastic loses stretch after X washes: ___/20 • Silicone dots peel after X washes: ___/20 • Phone pocket too tight for [specific model]: ___/20 • Price too high for what you get: ___/20 Any theme with 3+ mentions = MUST-FIX for v2 (add to P3D.03 modification list for reorder). | Same sources as praise + customer service emails + return reason data (Shopify → Orders → filter: refunded) | Categorize each complaint as: • PRODUCT FIX (change in v2 production): pocket dimensions, magnet strength, elastic spec • COMMUNICATION FIX (change on website/packaging): color accuracy, size guide clarity, care instructions • NO FIX NEEDED (subjective preference): "I prefer tube belts" — this isn't a defect, it's a preference mismatch Product fixes go to P3D.03 (v2 spec). Communication fixes go to P4A.03 (product page update). | RESPOND to EVERY negative review: "Thank you for the honest feedback, [NAME]. I'm sorry the [issue] didn't meet your expectations. Here's what we're doing about it: [specific action — e.g., 'we're increasing the gel pocket magnet strength in our next production run']. In the meantime, I'd love to make this right — please email hello@strideher.com and I'll personally resolve it." A thoughtful founder response to a negative review often converts the reviewer into a loyal advocate AND reassures future readers that the brand cares. | Expected top complaint themes: 1. Sizing confusion at the 33" overlap (communication fix: improve size guide) 2. Gel pocket magnet too weak (product fix: stronger magnet in v2) 3. Phone pocket tight for largest phones + thickest cases (product fix: 5mm wider in v2) 4. Color slightly different from screen (communication fix: update product photos) | When 3+ reviews mention the same complaint: → IMMEDIATELY: respond to each review acknowledging the issue → Within 1 week: update product page/FAQ to address it proactively → Within 1 month: add to P3D.03 v2 modification list → On reorder: implement the fix in production

## 6E.05 90-Day Plan
P6E TASK 6E.05: 90-DAY POST-LAUNCH OPTIMIZATION PLAN — FIX → OPTIMIZE → SCALE
Month 1: fix what's broken. Month 2: optimize what's working. Month 3: scale what's proven. Every week has a focus. Every month builds on the last.
Area | Month 1: FIX (Days 8-30) | Month 2: OPTIMIZE (Days 31-60) | Month 3: SCALE (Days 61-90) | KPI to Track | Monthly Milestone | If Behind Target
THE 90-DAY PLAN — 6 areas optimized across 3 phases. Write specific actions after reviewing launch week data (P6B.05).
PRODUCT PAGE | FIX based on Clarity recordings: • If <50% scroll to ATC button → shorten above-fold content or enable sticky ATC • If size guide gets 0 clicks → add button next to variant selector (A/B test #5) • If photos get rage-clicks (trying to zoom) → enable image zoom in Dawn theme • Update product page with actual customer language from first reviews • Fix any broken elements identified in session recordings | OPTIMIZE with A/B tests: • Run Test #1 (hero image) for 2 weeks • Run Test #2 (CTA button text) for 2 weeks • Add "★★★★★ (X reviews)" badge near ATC button (Test #4) • Update FAQ with the top 5 customer questions from Month 1 emails • Add 2-3 customer photos to the product page gallery (UGC) | SCALE proven changes: • Implement all A/B test winners permanently • Add video testimonials from ambassadors to product page • If conversion rate >3%: the product page is optimized — shift focus to driving MORE traffic • Launch the comparison blog post (P4D.03 #1) and link prominently from product page • Consider adding a "Frequently Bought Together" section if you launch accessories | Conversion rate Month 1: 1.5-3% Month 2: 2.5-3.5% Month 3: 3-4%+ | Month 1: product page bugs fixed, customer language incorporated. Month 2: 2 A/B tests completed, winners implemented. Month 3: conversion rate >3% consistently. | If conversion <1.5% in Month 1: fundamental product page issue. Watch 20 Clarity recordings. The problem will be obvious — either: visitors can't find the ATC button, the page loads too slowly, the product isn't clearly described, or the price isn't visible early enough.
AD CAMPAIGNS | FIX based on Week 1-2 ad data: • Kill any ad set with CPA >$15 after 14 days (P6C.04 framework) • Kill any creative with CTR <0.5% after 1,000 impressions • If ALL ad sets have CPA >$15: the product page is the problem, not the ads — pause ads, fix the page first • Verify: Conversions API is tracking accurately (Meta Events Manager) • Check Google Merchant Center for any product feed disapprovals | OPTIMIZE winning campaigns: • Scale the best-performing Meta ad set by 20% budget increase • Create 2 new ad creatives based on learnings (what hook worked best?) • Launch Google Search campaign (P6D.03) if not already live • Test 1 new audience on Meta (e.g., lookalike from email list vs lookalike from purchasers) • Begin cross-channel optimization: compare Meta vs Google ROAS monthly | SCALE proven channels: • If Meta ROAS >3×: increase budget 20% every 2 weeks • If Google ROAS >3×: increase budget 20% every 2 weeks • Launch Amazon PPC (P4E.04) alongside Amazon listing • Test TikTok Ads (new channel — $5/day test budget using best UGC video from Meta) • Total ad budget should be 15-25% of monthly revenue | ROAS (blended) CPA ($) Month 1: 2× ROAS Month 2: 2.5-3× Month 3: 3×+ | Month 1: first profitable ad campaign identified. Month 2: 2-3 profitable campaigns running. Month 3: $500-$800/month ad spend at 3×+ ROAS. | If ROAS <2× after 30 days across ALL campaigns: pause all ads. The issue is likely: (1) product page conversion too low, (2) ad creative not resonating, or (3) wrong audience. Fix #1 first (cheapest to test), then #2 (new creative), then #3 (new audience).
EMAIL | FIX based on Klaviyo flow performance: • If welcome flow conversion <8%: rewrite Email 1 subject line (A/B test in Klaviyo) • If abandoned cart recovery <5%: check Email 1 timing (should be 1 hour, not 24 hours) • If post-purchase Email 3 (review request) has <20% open rate: test new subject line • Ensure all flows are "Live" (not paused or draft) • Verify domain authentication still active (SPF/DKIM) | OPTIMIZE flows: • A/B test 2 subject lines per flow (Klaviyo has built-in A/B testing) • Add a 4th email to the welcome flow (Day 10: "Last chance for 10% off") if conversion is between 8-12% • Create a "winback" flow: triggered when a customer hasn't purchased in 60 days → "We miss you" + 15% off • Send 1-2 manual campaigns per month (new blog post, seasonal content, customer spotlight) | SCALE email as a revenue channel: • If email drives 25%+ of revenue: it's your #1 channel — invest in growing the list • Test a weekly newsletter (running tips + product mentions — not just promotions) • Launch a VIP segment for repeat buyers (top 10% by spend → exclusive early access) • Build a birthday/anniversary automation (requires collecting birthday at signup) • Target: email revenue = 30-40% of total revenue by Month 3 | Email revenue % of total Month 1: 20-30% Month 2: 25-35% Month 3: 30-40% | Month 1: all 3 flows live + performing above minimum thresholds. Month 2: 2 A/B tests completed, winback flow launched. Month 3: email = 30%+ of revenue, list growing 10%+ monthly. | If email revenue <15% of total: either the list is too small (scale popup + content to grow it) or the flows are underperforming (check open rates → subject lines, click rates → CTA/design, conversion → landing page).
CONTENT + SOCIAL | FIX based on content performance: • Identify which content PILLAR (P5B.01) drove the most engagement in Month 1 → increase that pillar's ratio • If TikTok views <300 average: hooks are too weak → rewrite first 3 seconds of every video • If IG engagement rate <3%: posting frequency may be too low or content is too product-heavy → shift ratio toward tips + community • Publish blog post #1 (P4D.03) if not yet live | OPTIMIZE content mix: • Double down on the content FORMAT that performed best (Reels? Carousels? TikToks?) • Repurpose top 5 performing organic posts as paid ad creative (they already proved they resonate) • Publish blog post #2 (P4D.03) • Create 2 more YouTube pillar videos (P5B.04) • Begin tracking: social → website → purchase attribution (GA4 social referrals) | SCALE content operations: • If one platform drives 3× more traffic than others: focus 60% of effort there • Consider hiring a freelance content editor ($100-$200/month) to help with video editing • Launch a user-generated content campaign: "Share your StrideHer run → we feature you + give $10 credit" • Publish blog post #3 (P4D.03) + begin monthly publishing cadence • Target: 1,000+ social followers across platforms by Month 3 | Social followers Website traffic from social Month 1: 200-500 Month 2: 400-800 Month 3: 700-1,500 | Month 1: consistent daily posting established. Month 2: top content format identified + doubled. Month 3: 1,000+ followers, social drives 15%+ of site traffic. | If social drives <5% of traffic after Month 2: social may not be the right channel for your audience. Some D2C brands thrive on social; others grow through search/email. Don't force a channel that isn't working — reallocate time to whatever IS working.
PRODUCT | FIX based on customer feedback: • Compile all product complaints from: reviews, emails, returns, parkrun conversations • If sizing exchanges >10%: improve the size guide (add more fit photos, clarify the 33" overlap) • If any defect reported 3+ times: flag as MUST-FIX for v2 (P3D.03) • Send follow-up survey to first 30 customers: "What would you change about StrideHer?" | OPTIMIZE product experience: • Finalize v2 modification list (P3D.03) based on 60 days of data • Attach v2 spec to reorder PO if reorder is triggered • Test 1 new color or limited edition based on customer demand data • Update product photos with UGC (customer-submitted photos on the product page) • Improve packaging based on unboxing feedback | SCALE product line: • If v2 reorder is placed: implement all MUST-FIX modifications • Evaluate: is there demand for a second product? (belt extender? running vest? phone armband?) • Survey ambassadors and top customers: "What other running gear do you wish existed?" • Begin v3 roadmap (P3D.03 V3 section) for production run #3 • Target: <3% return rate, >4.5 star average review | Return rate Avg review rating Month 1: <5% Month 2: <4% Month 3: <3% Rating: 4.5+ | Month 1: top 3 product improvements identified. Month 2: v2 modification list finalized. Month 3: v2 improvements implemented in reorder production. | If return rate >8%: systematic product issue. The most common: sizing confusion (communication fix) or product doesn't match photos (photography fix). Rarely is it actual product quality if P2E QC was followed.
OPERATIONS | FIX operational bottlenecks: • If shipping >24 hours consistently: add a second daily packing batch or hire part-time help • If customer response time >24 hours: set up canned responses for top 5 questions in email • If inventory tracking is off (Shopify count ≠ physical count): do a full physical count and reconcile • Streamline the packing workflow: is the station ergonomic? Are supplies always stocked? | OPTIMIZE fulfillment: • If order volume >5/day consistently: consider 3PL evaluation (ShipBob, ShipMonk — get quotes) • Automate: order confirmation → tracking email (should already be automatic via Shopify — verify) • Create FAQ template responses for the top 10 customer questions (saves 2-3 min per reply) • Set up Shopify Flow automations: auto-tag customers by source, auto-alert on low stock | SCALE operations: • If order volume >10/day: 3PL becomes cost-effective vs founder time. Get 3 quotes, compare to your current cost (time × hourly value + shipping costs). • Hire first part-time help: virtual assistant for customer service ($15-$20/hr, 5-10 hrs/week) — this frees 5-10 hours/week for growth activities • Document all processes in SOPs: packing, shipping, CS templates, social posting — this enables delegation • Target: founder spends <25% of time on operations, >75% on growth | Ship time CS response time Month 1: <24h ship, <24h response Month 2: <24h both Month 3: <18h ship, <12h response | Month 1: all operational bugs fixed. Month 2: top 10 FAQ templates created, Shopify automations set up. Month 3: either 3PL onboarded OR part-time help hired if volume justifies. | If operations consume >50% of founder time at Month 3: growth will stall because there's no time for marketing, content, partnerships, and product development. The 90-day target is to systematize operations enough that they run in <25% of your time — either through automation, delegation, or outsourcing.

## 6E FOUNDER ACTIONS
P6E PERFORMANCE OPTIMIZATION — FOUNDER ACTION CHECKLIST
This is the ONGOING operating system. Weekly reviews + monthly analyses + quarterly planning. The rhythm that turns a launch into a business.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 3+: ESTABLISH THE WEEKLY RHYTHM
🔴 #1 | Set up the Monday morning weekly KPI review ritual | 30 min/week (EVERY Monday, FOREVER) | $0 | Every Monday morning: 1. Open your KPI dashboard (Sheet 6E.01 or Google Sheets copy) 2. Pull 15 metrics from: Shopify Analytics, GA4, Klaviyo, IG Insights, TikTok Analytics, Judge.me 3. Fill in this week's column. Compare to last week. 4. Any metric declining 2 weeks in a row? → investigate cause this week. 5. Any metric exceeding target? → identify what's working and do MORE of it. 6. Takes 30 minutes. Non-negotiable. Put it in your calendar as a recurring event. This ritual IS the business operating system. Skip it and you're flying blind. Do it and you always know exactly what to focus on.
DAY 30: FIRST DEEP ANALYSIS
🔴 #2 | Complete 30-day customer data analysis (Sheet 6E.03-04) | 3-4 hrs | $0 | 1. Pull all data per Sheet 6E.03: who bought (demographics), where they came from (sources), what converted them (path analysis) 2. Compare actual buyer profile to P0B persona assumptions → document divergences 3. Analyze all 20+ reviews: tally praise themes and complaint themes 4. Identify top 3 praise patterns → update marketing copy to use customer language 5. Identify top 3 complaint patterns → add to P3D.03 v2 modification list 6. Respond to every negative review with a thoughtful, specific reply 7. Write a 1-page "30-Day Learnings" summary: what matched expectations, what surprised you, what needs to change This analysis resets ALL your assumptions. From Day 31 forward, decisions are based on DATA, not P0B hypotheses.
MONTH 2-3: A/B TESTING + OPTIMIZATION
🟡 #3 | Run 3 A/B tests on the product page over 6 weeks | 2 hrs setup + 2-4 weeks per test | $0 | 1. Start with Test #1 (hero image) — highest expected impact per Sheet 6E.01-02 2. Run for 2 weeks (minimum 200 sessions per variant) 3. Measure: conversion rate for each variant. Implement the winner permanently. 4. Run Test #5 (size guide button next to selector) — the #1 finding from D2C session recordings 5. Run Test #2 (CTA button text) or Test #3 (price display with "Free Shipping") 6. After 3 tests: your product page is meaningfully optimized. Each 5% lift compounds: 3 tests × 5% each = 15.8% cumulative conversion improvement. A 15% conversion lift on 500 weekly sessions at $34.99 = $131 additional weekly revenue = $6,800/year from 3 simple tests.
DAY 8: THE 90-DAY PLAN
🔴 #4 | Write the 90-day optimization plan using Sheet 6E.05 as the template | 2-3 hrs | $0 | 1. On Day 8 (after compiling launch week results from P6B.05): open Sheet 6E.05 2. For each of the 6 areas (product page, ads, email, content, product, operations): write specific Month 1/2/3 actions based on YOUR launch data (not generic templates) 3. The template provides the STRUCTURE — you fill in the SPECIFICS from your own experience 4. Print it. Pin it to your wall. Review it every Monday during the weekly KPI check. 5. At the end of each month: score yourself honestly. How many actions were completed? What drifted? 6. At Day 90: write the NEXT 90-day plan based on what you've learned. The 90-day plan is a living document. Revise it as data comes in. The plan from Day 8 will look very different by Day 45 — that's healthy. It means you're learning.
ONGOING: THE RHYTHM THAT BUILDS A BUSINESS
🟢 #5 | Maintain the optimization rhythm: weekly reviews + monthly analyses + quarterly planning | Weekly: 30 min Monthly: 2-3 hrs Quarterly: 4-6 hrs | $0 | THE OPTIMIZATION RHYTHM: WEEKLY (30 min Monday): KPI dashboard review. Catch problems early. Celebrate wins. MONTHLY (2-3 hrs, last day of month): deep analysis of: revenue vs target, channel performance, email metrics, review patterns, inventory status, and ad ROAS. Make one BIG decision per month (start a new channel, pause a failing one, launch a product improvement, hire help). QUARTERLY (4-6 hrs): write the next 90-day plan. Review: what worked, what didn't, what to try next. Set 3 quarterly OKRs (Objectives + Key Results). Share with a mentor or advisor for accountability. This rhythm is how $10K bootstrapped brands become $100K brands become $1M brands. The difference between brands that stall at $50K/year and brands that grow to $500K is NOT the product — it's the operating rhythm.

## G3 Launch Rescue Protocol
G3 REMEDIATION: LAUNCH FAILURE CONTINGENCY — "WHAT IF WEEK 1 HAS <5 ORDERS?"
Don't panic. Diagnose. Is it a traffic problem or a conversion problem? The answer determines the fix. 4 steps, 14-day timeline.
Step | Timeframe | Action | Diagnostic Question | If YES | If NO | Cross-Reference
ACTIVATION TRIGGER: Launch Week (Day 1-7) generates fewer than 5 orders. This protocol replaces panic with structured diagnosis.
STEP 1 DIAGNOSE: TRAFFIC or CONVER- SION? | Day 7-8 (the morning after Week 1 ends) | Pull TWO numbers from Shopify Analytics + GA4: 1. TOTAL SESSIONS this week: Shopify → Analytics → Overview → Sessions (7-day period) 2. TOTAL ORDERS this week: Shopify → Analytics → Overview → Orders Calculate: Conversion rate = Orders ÷ Sessions × 100 THIS IS THE SINGLE MOST IMPORTANT DIAGNOSTIC: IF sessions <200 AND orders <5: you have a TRAFFIC PROBLEM — people aren't finding your store. Go to Step 2A. IF sessions >200 AND orders <5: you have a CONVERSION PROBLEM — people visit but don't buy. Go to Step 2B. IF sessions <50: your marketing DIDN'T REACH ANYONE — the launch was invisible. This is an extreme traffic failure. Immediate action: verify all launch emails actually sent (Klaviyo delivery report), verify ads are running (Meta Ads Manager delivery status), verify your domain resolves correctly, and check that the store isn't accidentally password-protected. | Is Shopify showing 200+ sessions this week? (200 sessions = ~30/day = minimum viable launch traffic for a new D2C brand) | YES (200+ sessions, <5 orders): → CONVERSION problem. People are VISITING but NOT BUYING. Go to STEP 2B. Your marketing worked. Your product page didn't convert. This is FIXABLE. | NO (<200 sessions): → TRAFFIC problem. People are NOT FINDING your store. Go to STEP 2A. Your product page may be fine — nobody saw it. This is ALSO fixable, but different fixes. | Shopify → Analytics → Overview GA4 → Realtime → verify tracking is active P4C Analytics Setup (verify GA4 + Meta Pixel are firing)
STEP 2A — TRAFFIC RESCUE: people aren't finding your store
2A-i EMAIL RESCUE | Day 8 (send immediately) | YOUR EMAIL LIST IS YOUR MOST CONTROLLABLE TRAFFIC SOURCE. Pull Klaviyo data: How many people received the P6A launch email? What was the open rate? Click rate? IF open rate <20%: the subject line failed. Send a NEW email with a different subject: • "Still here? Your founding member discount expires tomorrow" • "I built this for you — and it's finally here" • "Last chance: HERSTRIDE20 for 20% off" IF open rate >20% but click rate <3%: the email body failed. Send a new email with: a product GIF/video in the hero, a single clear CTA button ("Shop Now — 20% Off"), and a testimonial from a beta tester. IF click rate >3% but no purchases: the traffic IS coming but not converting → switch to Step 2B. NUCLEAR EMAIL OPTION: send a PERSONAL email from your personal email (not Klaviyo) to your top 50 warmest contacts: "Hey [NAME], I just launched my running belt brand — would mean the world if you checked it out: [LINK]. No pressure to buy, but shares/feedback are just as valuable. 🏃‍♀️" | Did the launch email get >20% open rate AND >3% click rate? | YES: email performed well but didn't convert → traffic arrived, conversion failed → Step 2B. The email channel is working. Keep emailing (2-3× this week with urgency angles). | NO: email under- performed. <20% open: resend with new subject line to unopeners. <3% click: rewrite email body with video + testimonial. Send 2-3 emails this week (not spammy — each with genuinely different angle). | P4B Klaviyo flows + templates P6A pre-launch campaign emails P1E pre-launch community (email list size)
2A-ii SOCIAL BLITZ | Days 8-14 (7-day intensive) | INCREASE POSTING FREQUENCY TO 3× DAILY across all platforms for 7 days: MORNING (7-8 AM): Instagram Reel or TikTok — product demo, unboxing, or "packing my first orders" behind-the-scenes. MIDDAY (12-1 PM): Instagram Story carousel — 5 slides: problem → solution → social proof → offer → link. EVENING (6-7 PM): TikTok or Reel — relatable running content with belt featured naturally. EVERY POST includes: a clear CTA ("Link in bio" / "Comment BELT for the link"), the founding member discount code, and a product tag (IG Shopping / TikTok Shop if enabled). GO LIVE: do 1-2 Instagram/TikTok Lives this week. Show the belt, answer questions in real-time, offer a live-exclusive discount code. Lives get priority algorithmic distribution on both platforms. DM OUTREACH: personally DM 20-30 running accounts that follow you (not cold — accounts that already engaged with your content). "Hey! Just launched my running belt — would love your honest opinion if you're interested in trying one." | Are social posts getting >500 impressions each? Are you getting profile visits from posts? | YES (impressions high, profile visits high, but no sales): → Social is driving awareness but not conversion. Check: is the link in bio correct? Does the product page load fast on mobile? → Step 2B. | NO (impressions <200 per post): → Content isn't reaching people. Fixes: 1. Use trending audio on Reels/TikTok 2. Add 3-5 niche hashtags per post (#runninggear #marathontraining #runnersofinstagram) 3. Engage with 50 running accounts daily (comment on their posts → they visit your profile) | P5B Content Strategy (posting schedule + video concepts) P5A Influencer (DM outreach templates)
2A-iii PAID ADS CHECK | Day 8-9 (verify and fix) | IF YOU LAUNCHED WITH ADS (P6C Meta, P6D Google): Check Meta Ads Manager: • Delivery status: is the campaign "Active" and "Delivering"? If "Learning Limited" or "Not Delivering": the audience is too small or the bid is too low. • Impressions: has the ad been shown 1,000+ times? If <1,000 impressions in 7 days at $10-$15/day budget: something is wrong (ad rejected, audience too narrow, or payment method failed). • CTR (click-through rate): is it >1%? If <0.5%: the creative isn't compelling → swap to a different creative (UGC video instead of product photo, or vice versa). • Link clicks: are people clicking through to your site? If clicks >50 but orders = 0: traffic is arriving → Step 2B. IF ADS AREN'T RUNNING: check for rejections in Meta Ads Manager → fix the flagged issue (usually: missing privacy policy, prohibited content claim, or payment method failure). IF YOU HAVEN'T LAUNCHED ADS YET: don't start during the rescue period. Fix organic traffic first. Ads amplify what's already working — they don't fix fundamental traffic/conversion problems. | Are ads delivering 1,000+ impressions with >1% CTR? | YES: ads are working, traffic is arriving. If orders still <5: → Step 2B (conversion problem confirmed). Consider: increasing ad budget 50% for 7 days to accelerate the test. | NO: ads are broken. Not delivering: check rejection reasons, fix, and resubmit. Low CTR (<0.5%): swap creative. Test: UGC video, lifestyle photo, or benefit-focused carousel. Low impressions despite "Active": broaden audience (expand age range or interest targets). | P6C Meta Ads (ad sets, creatives, audiences) P6D Google Ads (PMax, Search) P4C Analytics (verify Pixel is tracking clicks → site)
STEP 2B — CONVERSION RESCUE: people visit but don't buy
2B-i PRODUCT PAGE AUDIT | Day 8 (2-hour deep audit) | IF TRAFFIC IS COMING BUT NOBODY IS BUYING: the product page is failing to convert. 10-POINT PRODUCT PAGE CONVERSION AUDIT: 1. HERO IMAGE: is it a clear, professional product photo? Or a confusing lifestyle shot where the belt is hard to see? → Swap to the clearest, most zoomed-in product-on-body photo. 2. PRICE + FREE SHIPPING: is "$34.99 — Free Shipping" immediately visible above the fold on mobile? If not: make it bigger. 3. SIZE SELECTOR: can visitors easily select S/M or L/XL? Is the "Find Your Size" link prominent? If sizing confusion is causing abandonment: add a bold "Not sure? Most women choose S/M" helper text. 4. REVIEWS: are there ANY reviews visible? If 0 reviews: the "Be the first to review" empty state kills trust. FIX: add 3-5 testimonial quotes from beta testers/P5A influencers as static text ABOVE the review widget until real reviews arrive. 5. ADD TO CART BUTTON: is it large, colored (Desert Rose), and obviously clickable? Test on mobile — can you tap it easily with your thumb? 6. TRUST SIGNALS: is "30-Day Money-Back Guarantee" visible near the ATC button? Are payment icons (Visa, MC, PayPal, Apple Pay) shown? If missing: add immediately. 7. PRODUCT DESCRIPTION: does the FIRST SENTENCE answer "what is this and why should I care?" If the first sentence is about fabric composition: rewrite. Lead with the benefit: "The first running belt designed for women's bodies — 3 separate pockets, zero bounce, adjustable fit." 8. IMAGES: are there 5+ images showing: product flat lay, on-body front, on-body side, pockets open with items, and size comparison? If <5: add more. 9. MOBILE EXPERIENCE: load the page on your phone. Does everything look correct? Can you complete a purchase in <60 seconds? Time yourself. 10. CHECKOUT: do a test purchase. Does the checkout flow smoothly? Are there any error messages or confusing steps? Is Apple Pay / Shop Pay working (one-tap checkout)? | Can a first-time visitor understand what the product is + why they should buy it within 5 seconds of landing on the page? | YES (page is clear but still not converting): → Step 2B-ii (price/offer issue) or Step 2B-iii (trust issue). The page communicates well but something else is blocking the purchase decision. | NO (page is confusing, slow, or missing key elements): → Fix the failing audit items IMMEDIATELY. Priority fixes: #1 Hero image #4 Social proof #6 Trust signals #7 First sentence These 4 fixes can be done in 1 hour and have the biggest impact. | P4A Shopify Store Setup (product page structure) P1D Photography (image assets) P2D Size Guide (sizing helper) P9A.05 Size Recommendation Tool
2B-ii PRICE & OFFER TEST | Day 9-10 (48-hour test) | IF THE PAGE LOOKS GOOD BUT PEOPLE STILL DON'T BUY: test whether PRICE is the objection. 48-HOUR PRICE/OFFER TEST: Option A — Launch Discount: if HERSTRIDE20 (20% off) was the founding member offer but expires soon, extend it by 7 days AND make it MORE prominent (banner at top of page, popup on entry, mentioned in first line of description). Option B — Free Gift: instead of discounting, add a perceived-value bonus: "Order this week and get a free StrideHer sticker pack + priority sizing exchange guarantee." Cost: $0.08 per sticker sheet. Perceived value: $5+. Option C — Price Test: temporarily reduce price to $29.99 for 48 hours. Track: does conversion rate increase significantly? If YES: $34.99 may be above the market's willingness to pay for an UNKNOWN brand (it'll work once you have reviews — price resistance drops with social proof). If NO: price isn't the issue. IMPORTANT: only test ONE variable at a time. Don't change price AND add a gift AND redesign the page simultaneously — you won't know what worked. | Does a 48-hour price reduction or bonus offer increase conversion rate by >50%? | YES (conversion jumped with lower price/better offer): → Price sensitivity is real for an unknown brand. Keep the offer active until you have 20+ reviews (social proof reduces price resistance). Then gradually return to $34.99. | NO (conversion didn't change even with a better offer): → Price is NOT the problem. The objection is DEEPER: trust, product understanding, or audience mismatch. → Step 2B-iii. | P0E Pricing Model ($34.99 validation) P6A.02 Founding Member Offer (HERSTRIDE20) P6E.02 A/B Tests (price sensitivity)
2B-iii TRUST & URGENCY | Days 10-14 (ongoing through rescue period) | IF PRICE ISN'T THE ISSUE: the visitor doesn't TRUST the brand enough to buy. For a brand-new, unknown D2C brand with 0 reviews: trust is the #1 conversion barrier. The visitor thinks: "Is this legit? Will the product actually arrive? Will it be as described?" TRUST-BUILDING EMERGENCY ACTIONS: 1. ADD FOUNDER VIDEO to product page: 60-second video of you holding the belt, explaining why you made it, and showing it on your body. A real human face = instant trust boost. Film on your phone, upload directly. Doesn't need to be polished. 2. ADD BETA TESTER QUOTES: even if Judge.me has 0 reviews, add 3-5 text quotes from P5A influencers or friends who tested the belt. Format: "★★★★★ 'Zero bounce from mile 1 to 13.1' — Sarah, half-marathon runner". Place ABOVE the fold on the product page. 3. ADD "AS SEEN ON" SECTION: if any influencer posted about it, any blog mentioned it, or any running club tried it: screenshot and display as a trust strip below the hero image. 4. ADD GUARANTEE BADGE: create a simple graphic: "30-Day Money-Back Guarantee ¦ Free Exchanges ¦ Free US Shipping" and place it directly below the ATC button. This answers: "What if it doesn't fit? What if I don't like it? Am I paying for shipping?" 5. ENABLE LIVE CHAT (P9A.04): a visitor who can chat with the founder in real-time has 3-5× higher conversion. If you can be online during peak hours (7-9 AM, 12-1 PM, 7-9 PM): enable Shopify Inbox NOW. | After implementing trust elements: does conversion rate improve over the next 5 days? | YES: trust was the barrier. The founder video + testimonials + guarantee badge resolved it. Keep ALL trust elements permanently. As real reviews accumulate, they'll replace the beta tester quotes organically. | NO: trust elements didn't move the needle. → Step 3 (fundamental re-evaluation). | P9A.04 Live Chat (Shopify Inbox) P5A Influencer (beta tester feedback quotes) P1D Photography (founder photo/ video assets) P8C Returns Policy (guarantee language)
STEP 3 — IF RESCUE FAILS: fundamental re-evaluation (Day 14)
STEP 3 RE- EVALUATE | Day 14 (end of rescue period) | IF DAY 14 ARRIVES AND TOTAL ORDERS ARE STILL <10 despite completing Steps 2A and 2B: This is RARE (the pre-launch community, email list, and social presence from P1E/P6A make near-zero traction unlikely). But if it happens: the issue may be FUNDAMENTAL, not tactical. FUNDAMENTAL DIAGNOSIS: 1. SURVEY YOUR EMAIL LIST: send a 3-question survey to everyone who clicked but didn't buy: • "What stopped you from purchasing?" (multiple choice: price too high, didn't trust the brand, didn't understand the product, already own a belt I like, wasn't the right time) • "What would make you more likely to buy?" (open text) • "How much would you pay for this product?" (price bracket selection) 2. REVIEW CLARITY RECORDINGS: watch 20 session recordings (Microsoft Clarity, free, installed in P4C). Where do visitors: scroll past without reading? Click something that doesn't work? Abandon the page? The recordings show you EXACTLY where the experience breaks. 3. ASK 5 PEOPLE IN YOUR TARGET AUDIENCE: show them the product page on their phone and ask: "Walk me through your thought process. Would you buy this? Why or why not?" Live user testing reveals what analytics cannot — the emotional reaction. 4. COMPARE TO COMPETITORS: visit FlipBelt.com, SPIbelt.com, and the top 3 Amazon running belt listings. Compare: pricing, photography, copywriting, trust signals, reviews. Where does StrideHer fall SHORT? Fix those gaps. BASED ON FINDINGS: • If price is consistently cited: test $27.99-$29.99 permanently (lower margin but sustainable if volume increases) • If product understanding is the issue: rebuild the product page with a video-first layout • If trust is the issue despite all rescue efforts: you need more TIME + reviews. Reduce ad spend to $5/day (preservation mode), focus 100% on organic content + influencer seeding to build social proof, and re-launch with a "relaunch" campaign when you have 15-20 reviews (4-8 weeks) | After surveying: is there ONE clear, fixable reason people aren't buying? | YES (one clear reason identified): → Fix that specific issue. Relaunch in 2-4 weeks with the fix implemented. This is the "pivot and persevere" moment from Lean Startup. You're not quitting. You're adjusting based on data. | NO (reasons are scattered or unclear): → Enter PRESERVATION MODE: Reduce ad spend to $5/day. Focus on: content, community, seeding, and accumulating social proof. Re-evaluate at Day 30 with more data. The business is NOT dead — it's pre-traction. Many successful D2C brands had weak launches then found their stride (pun intended) in Month 2-3. | P4C Microsoft Clarity (session recordings) P0A Competitive Intelligence (competitor page comparison) P9B.03 Survey template (adapt for non-buyers)
STEP 4 — TIMELINE SUMMARY + EMOTIONAL GUIDANCE
STEP 4 TIMELINE + MINDSET | Day 1-14 overview | RESCUE TIMELINE: Day 1-7: LAUNCH WEEK (execute P6A-B as planned) Day 7: CHECK — fewer than 5 orders? → Activate this protocol Day 8: Step 1 — Diagnose (traffic or conversion?) Day 8-10: Step 2A (traffic rescue) OR Step 2B (conversion rescue) Day 10-14: Continue rescue actions + monitor daily Day 14: Step 3 — If <10 orders total: fundamental re-evaluation Day 14-30: Either: specific fix implemented → mini-relaunch, OR preservation mode → accumulate social proof EMOTIONAL GUIDANCE (this matters as much as the tactics): • A weak launch does NOT mean the product is bad. Many iconic D2C brands (Gymshark, Glossier, Allbirds) had quiet launches before finding their channel/message/audience fit. • The data from a weak launch is MORE VALUABLE than the data from a strong one. A strong launch tells you "something worked" but not which thing. A weak launch + this protocol tells you EXACTLY what's broken and how to fix it. • Do NOT make emotional decisions: don't slash the price 50%, don't pivot to a completely different product, don't shut down the store, and don't burn through the contingency reserve on panic-ads. Follow the protocol. • The rescue protocol has a 14-day timeline for a reason: it's long enough to test meaningful changes but short enough to prevent prolonged bleeding. • After Month 1: if you have 15-20 orders, reviews are starting to come in, and you've identified what works: you're on track. The "hockey stick" growth curve in D2C typically starts Month 3-4, not Day 1. | N/A | EXPECTED OUTCOME IF RESCUE WORKS: Day 1-7: <5 orders (pre-rescue) Day 8-14: 5-15 additional orders (rescue actions take effect) Month 1 total: 15-25 orders (enough data to optimize) Month 2: 30-50 orders (normal P6E optimization resumes) Month 3+: growth trajectory normalizes per P7B model. | IF RESCUE DOESN'T FULLY WORK: Day 14: <10 orders total. Enter Step 3. Day 14-30: Preservation mode OR specific fix implemented. Day 30: re-evaluate with 30 days of data. The business has $2,000 contingency (P7B.03) to fund 2+ months of preservation-mode operations. Remember: $10K budget with $2K contingency was DESIGNED for exactly this scenario. | P7B.03 contingency reserve ($2,000) P6E.05 90-day optimization plan (resumes after rescue stabilizes) P7B.05 financial milestones (adjust timelines if rescue needed)