## P7D EXEC SUMMARY
P7D INVENTORY FINANCIAL TRACKING — EXECUTIVE SUMMARY
4 Tasks ¦ Weeks 1-Ongoing ¦ Cost: $0 ¦ Know exactly what you have, what it's worth, how fast it's moving, and when to reorder.
Task ID | Task | KPI | Deliverable | Status | Why This Matters | Timeline
7D.01 | Set up inventory tracking: Shopify inventory + spreadsheet backup with reorder alerts | Dual tracking system operational | Complete inventory tracking system: Shopify built-in inventory (auto-decrements on each sale, shows per-variant counts) PLUS a Google Sheets backup tracker with 8 SKUs, reorder point alerts, and weekly reconciliation protocol. The dual system catches discrepancies before they become stockouts or oversells. | COMPLETE ✓ | Shopify inventory is reliable but not infallible. A cancelled-then-refunded order may not restore inventory. A manual count error during receiving (P3C.04) propagates forever. The spreadsheet backup catches these gaps. A stockout costs: $0 revenue while out of stock + lost customers who buy from competitors + damaged organic ranking (Google/Amazon penalize unavailable products). Prevention cost: 10 minutes/week of reconciliation. | Day 1: set up. Weekly: reconcile. Continuous: Shopify auto-tracks.
7D.02 | Calculate landed cost per unit: product + shipping + duties + packaging + fulfillment labor | Landed cost documented per unit | Complete landed cost calculation: every cost from factory floor to customer's doorstep, resulting in a TRUE per-unit cost that includes items often forgotten (customs brokerage, freight insurance, inbound handling). The landed cost is MORE than the 7B.01 COGS ($6.00) — it's the FULL cost including freight, duties, and packaging that gets a belt from China to your shelf, ready to ship. Landed cost per unit: ~$9.50-$10.50. | COMPLETE ✓ | The difference between COGS ($6.00) and LANDED COST ($9.50-$10.50) is $3.50-$4.50 per unit — costs that exist but are often ignored in margin calculations. Founders who price based on COGS alone think they have 83% gross margin ($34.99 - $6 = $28.99). The REAL gross margin using landed cost: 70-73% ($34.99 - $9.50 = $25.49). Still excellent — but 10 points lower than the naive calculation. Knowing the truth prevents surprise losses. | Day 1: calculate. Update per production run (costs change with order size, freight rates, and duty rates).
7D.03 | Track inventory turnover rate: target selling through initial batch in 60-90 days | Turnover tracking active | Complete inventory turnover tracking: weekly units-sold run rate, projected sell-through date, days of inventory remaining, and turnover ratio calculation. The 600-unit initial batch should sell through in 4-6 months (moderate scenario). Faster = strong demand (reorder early). Slower = demand is softer (increase marketing before reordering). | COMPLETE ✓ | Inventory turnover answers: "Is my money trapped in unsold product?" At $6.00 COGS × 600 units = $3,600 sitting on your shelf. Every month that passes without selling: that $3,600 earns 0% return while your bank account shrinks from fixed costs. A healthy turnover (sell-through in 4-6 months) means your capital cycles back into cash that funds growth. A slow turnover (>8 months) means $3,600 is effectively frozen — it's the business equivalent of a savings account earning nothing while your bills grow. | Weekly: update sell rate. Monthly: calculate turnover ratio. At reorder point: trigger P3D.
7D.04 | Plan reorder timing: place next PO when 30-45 days of inventory remain | Reorder decision framework documented | Complete reorder timing framework: the reorder point calculation (inventory remaining ÷ daily sell rate = days remaining → trigger at 45 days), lead time assumptions (production 30-40 days + shipping 25-35 days = 55-75 days total), and the critical DECISION TREE: reorder same quantity? Increase? Decrease? Change spec (v2 modifications from P3D.03)? The reorder decision is the single highest-stakes financial decision in the first year — a $3,600+ commitment based on sell-through data. | COMPLETE ✓ | Reorder too early: cash tied up in inventory you don't need yet (opportunity cost). Reorder too late: stockout for 2-3 months while waiting for production + shipping (lost revenue + lost ranking + lost customers). The sweet spot: order when 45 days of inventory remain — this gives a 15-20 day buffer for production/shipping delays. At 600 units selling ~4/day: reorder trigger = 180 units remaining (45 days × 4/day). | Continuous monitoring. Trigger: when days remaining < 45. Decision: same week as trigger.

## 7D.01-02 Tracking + Cost
P7D TASKS 7D.01-02: DUAL INVENTORY TRACKING SYSTEM + TRUE LANDED COST PER UNIT
Shopify auto-tracks. Spreadsheet backs up. Reconcile weekly. Landed cost tells you the REAL margin — not the optimistic one.
SKU | Variant | Received (P3C.04) | Sold (Shopify) | Samples / Gifts | Damaged / Returns | Available Now | Reorder Point | Status
SH-BLK-SM | Midnight Black S/M | 75 |  |  |  |  | 19
SH-BLK-LX | Midnight Black L/XL | 75 |  |  |  |  | 19
SH-RSE-SM | Desert Rose S/M | 75 |  |  |  |  | 19
SH-RSE-LX | Desert Rose L/XL | 75 |  |  |  |  | 19
SH-SGE-SM | Alpine Sage S/M | 75 |  |  |  |  | 19
SH-SGE-LX | Alpine Sage L/XL | 75 |  |  |  |  | 19
SH-OCN-SM | Deep Ocean S/M | 75 |  |  |  |  | 19
SH-OCN-LX | Deep Ocean L/XL | 75 |  |  |  |  | 19
TOTAL | All Variants | 600 |  |  |  |  | 150
WEEKLY RECONCILIATION PROTOCOL — every Monday, 10 minutes. Prevents stockout disasters.
Step 1 | Open Shopify → Products → StrideHer → check inventory count for each of the 8 variants. |  |  |  | Match Shopify count to your spreadsheet "Available Now" column. If they differ by >2 units: investigate (cancelled order not restored? manual adjustment needed? theft/damage?).
Step 2 | Update spreadsheet: enter this week's sales (Shopify → Analytics → Sales by variant), samples given, and any returns received. |  |  |  | Available Now = Received - Sold - Samples/Gifts - Damaged + Returns. This should match Shopify's count. If not: Shopify count is usually correct (it's transactional). Update your spreadsheet to match Shopify, then investigate the gap.
Step 3 | Check reorder status: is any variant below its reorder point (19 units = 45 days at ~3 units/week)? |  |  |  | If ANY variant is below reorder point: check total inventory across all variants. If TOTAL is below 150 units: trigger the reorder decision (Sheet 7D.04). If only one variant is low: shift demand toward other colors via marketing (feature the in-stock colors on social + ads).
Step 4 | Log: date, total units remaining, weekly sell rate, days of inventory remaining. |  |  |  | This 4-number weekly log (date, units, sell rate, days remaining) is the most important inventory data in the business. Plot it over time: the trend tells you EXACTLY when you'll stock out if you don't reorder.
7D.02: TRUE LANDED COST PER UNIT — every cost from factory floor to your shelf, ready to ship
# | Cost Component | Per Unit ($) | Total (600 units) | Source | Notes
1 | Factory COGS (manufacturing) | $6.00 | $3,600 | Supplier invoice (P0D/P3A PO) | Includes: fabric, zippers, buckle, grip dots, stitching, QC, poly bag packaging at factory.
2 | Factory-to-port trucking (China) | $0.15 | $90 | Freight forwarder quote | Truck from factory in Yiwu/Guangzhou to nearest port (Ningbo/Shenzhen). Often included in FOB price — verify with supplier.
3 | Ocean freight (port-to-port) | $1.00 | $600 | Freight forwarder quote | Sea freight for 1-2 CBM (600 belts in cartons). LCL (less than container load) rate. Includes: bill of lading, port handling at origin.
4 | Freight insurance | $0.08 | $48 | Freight forwarder (typically 0.5-1% of cargo value) | Covers: loss or damage during ocean transit. Optional but recommended for first shipment. $3,600 cargo × 1.3% = $47.
5 | US customs duties | $0.65 | $390 | Customs broker or self-file | HS code 4202.92 (textile outer surface): duty rate ~8-12% of declared value. $3,600 × 10% = $360. Plus merchandise processing fee ($0.05/unit).
6 | Customs brokerage fee | $0.25 | $150 | Customs broker invoice | Fee for a customs broker to file entry paperwork. ~$150 flat for a single LCL shipment. Self-filing saves this but requires CBP experience.
7 | Port-to-door delivery (US drayage) | $0.42 | $250 | Freight forwarder or local trucker | Container/LCL pickup from US port (e.g., Long Beach, Newark) to your address. $200-$300 for LCL delivery.
8 | Inbound inspection + counting | $0.08 | $50 | Your labor (1-2 hours) | Time to: open cartons, count against packing list, check quality of 10% sample, organize by SKU on shelves (P3C.04).
9 | Packaging materials (US-side) | $1.25 | $750 | Packaging supplier invoices | Poly mailers, brand stickers, insert cards, tissue wrap, thank-you cards. These are purchased separately and added during fulfillment (not at the factory).
— | LANDED COST PER UNIT (on shelf, ready to ship) | $9.88 | $5,928 | Sum of items 1-9 | This is the TRUE cost of one belt sitting on your shelf, fully packaged and ready for a customer order. Compare to the naive "COGS" of $6.00 — the real cost is 65% higher.
★ | TRUE GROSS MARGIN (using landed cost) | $25.11 (71.8%) | — | $34.99 retail - $9.88 landed | Using landed cost: 71.8% gross margin. Using COGS only: 82.9%. The 11-point gap is real cost that exists whether you account for it or not. Using landed cost gives the honest picture.

## 7D.03-04 Turnover + Reorder
P7D TASKS 7D.03-04: INVENTORY TURNOVER TRACKING + REORDER DECISION FRAMEWORK
How fast is inventory moving? When do you reorder? How much? These questions determine whether you stockout (lost revenue) or overstock (trapped cash).
Element | Details | Formula / Calculation | Healthy Range | Warning Signal | Action Required | Data Source
7D.03: INVENTORY TURNOVER TRACKING — weekly monitoring of sell-through velocity
Weekly Sell Rate | Units sold in the last 7 days. Track every Monday as part of the 7D.01 reconciliation. Months 1-2 sell rate determines your inventory timeline: at 20 units/week, 600 units last 30 weeks (7.5 months). At 40 units/week: 15 weeks (3.75 months). The sell rate is the PULSE of the business. Everything flows from it: revenue forecasting, cash flow timing, reorder decisions, and marketing budget justification. | Weekly sell rate = units sold this week (Shopify → Analytics → Sales by product → this week). Smoothed rate (more reliable): average of last 4 weeks = (Week 1 + Week 2 + Week 3 + Week 4) ÷ 4. Use the smoothed rate for all projections (single-week rates are noisy — a viral TikTok can spike one week 5×). | Month 1: 8-15 units/week. Month 3: 15-30 units/week. Month 6: 25-40 units/week. These ranges align with the P0E/P7B revenue model. | Sell rate declining 3 weeks in a row: demand is softening. Sell rate flat for 4+ weeks: growth has stalled — marketing effort isn't scaling. | Declining: diagnose — is traffic down (fewer visitors)? Or is conversion down (same visitors, fewer buying)? The answer determines: increase marketing (traffic problem) or fix the product page (conversion problem). Flat: test a new marketing channel or launch a promotion to stimulate demand. | Shopify → Analytics → Sales by product → filter by date range.
Days of Inventory Remaining | The most important inventory number: how many DAYS until you're sold out at the current sell rate. This number decreases every day. Your job is to monitor it weekly and ACT when it crosses the reorder threshold (45 days). Think of it as a countdown timer: when it hits 0, revenue drops to $0 until the next production run arrives (55-75 days later). | Days remaining = total units available ÷ (weekly sell rate ÷ 7). Example: 350 units available ÷ (25 units/week ÷ 7 days) = 350 ÷ 3.57 = 98 days remaining. At 98 days: comfortable. At 60 days: start planning reorder. At 45 days: PLACE THE ORDER. At 30 days: you're late — air freight may be needed. | 60-120 days: comfortable. 45-60 days: plan reorder. <45 days: URGENT — reorder NOW. | <45 days with no PO placed: STOCKOUT RISK. Production (30-40 days) + sea freight (25-35 days) = 55-75 days lead time. If you have 45 days of inventory: the new batch arrives with 0-15 days of overlap (tight but viable). <30 days with no PO: you WILL stock out. Only option: air freight ($3-$5/unit extra, 7-10 day delivery). | <45 days: place PO immediately (P3D reorder protocol). <30 days + no PO: air freight emergency order for 100-200 units while sea freight order is in transit. Stockout cost: $0 revenue + lost Google/Amazon ranking + lost repeat customers who find alternatives. Prevention is ALWAYS cheaper. | Calculated from: Sheet 7D.01 "Available Now" ÷ smoothed weekly sell rate.
Inventory Turnover Ratio | How many times per year you sell through your entire inventory. Higher = better (capital cycling faster). Lower = worse (capital trapped in unsold product). Benchmark for D2C accessories: 4-8× per year (sell through every 1.5-3 months). StrideHer target: 2-4× in Year 1 (first year is slower due to brand-building; accelerates in Year 2). | Annual turnover ratio = (annual units sold × COGS per unit) ÷ average inventory value. Simplified monthly: units sold this month ÷ average units on hand = monthly turnover. Multiply by 12 for annualized. Example: 100 units sold in Month 3 ÷ average 400 units on hand = 0.25 monthly × 12 = 3.0× annual turnover. 3.0× means: you sell through your entire inventory 3 times per year (every 4 months). | Year 1 target: 2-4× annual turnover. Year 2 target: 4-6×. Best-in-class D2C: 6-10×. | Turnover <1.5× annual (selling through inventory less than every 8 months): capital is trapped. At $3,600 inventory: <1.5× means $3,600 sits for 8+ months earning nothing while you pay $1,089/month in fixed costs. Slow turnover = cash crunch. | <2× annual: increase marketing investment. The product exists and is proven — the problem is reach, not product-market fit. Alternatively: run a flash sale or bundle to accelerate sell-through (clear old inventory to free cash for a potentially improved v2 reorder). >6× annual: you're selling faster than you can restock. INCREASE ORDER QUANTITY on next PO to prevent stockouts. | Calculated monthly from Shopify sales data + inventory counts.
7D.04: REORDER DECISION FRAMEWORK — the highest-stakes financial decision of Year 1
Reorder Trigger | TRIGGER CONDITION: days of inventory remaining < 45. At that point: you have 45 days of stock left. Production takes 30-40 days. Shipping takes 25-35 days. Total lead time: 55-75 days. This means: if you order at 45 days remaining, you'll have a 10-30 day stockout gap (45 days stock - 55-75 days lead time = -10 to -30 days). To AVOID stockout entirely: trigger at 75 days remaining. But this requires committing capital earlier (before you have as much sales data). RECOMMENDED: trigger at 60 days. This gives a small buffer while not committing capital too early. | Daily sell rate = smoothed weekly rate ÷ 7. Days remaining = units on hand ÷ daily sell rate. Reorder trigger = days remaining ≤ 60. Example: 240 units on hand ÷ 4 units/day = 60 days → TRIGGER REORDER. | Trigger at 60 days for sea freight. Trigger at 30 days for air freight (emergency only — costs 3-5× more per unit). | Hitting the trigger with no cash for a PO: the worst scenario. You KNOW you need to reorder but can't afford it. Prevention: the 7B.03 budget includes inventory in the allocation. Also: Shopify Capital or PayPal Working Capital offer short-term advances based on sales history (available after ~3 months of consistent sales). | When triggered: 1. Confirm cash available for PO (P7B cash position) 2. Contact supplier with reorder quantity (same or adjusted) 3. Include v2 modifications if applicable (P3D.03) 4. Negotiate: larger quantity = lower per-unit cost (800 units may be $5.25/unit vs $6.00 for 600) 5. Pay deposit, confirm production timeline 6. Update cash flow forecast (P7B.02) | Weekly monitoring of days remaining in Sheet 7D.01.
Reorder Quantity Decision | HOW MUCH to reorder depends on sell-through data: SCENARIO A — Strong demand (sell-through in <4 months): Increase quantity 30-50%. 600 → 800-900 units. Lower per-unit cost. More inventory = longer runway. Risk: more capital tied up. SCENARIO B — Moderate demand (sell-through in 4-6 months): Same quantity. 600 → 600 units. Proven sell-through matches production quantity. Lowest risk. SCENARIO C — Slow demand (sell-through >6 months): Decrease quantity 20-30%. 600 → 400-500 units. Or: pause reorder until remaining inventory drops below 90 days. Use the pause period to investigate: is the issue product? Pricing? Marketing? | Decision matrix: Monthly sell rate × 6 months = reorder quantity (covers 6 months of inventory at current rate). Example: selling 80/month × 6 = 480 units → round to 500. Adjust upward if: sell rate is growing >15% month-over-month. Adjust downward if: sell rate is flat or declining. | Reorder = 4-6 months of inventory at current sell rate. Never order more than 8 months of inventory (too much capital tied up). Never order less than 3 months (too frequent reorders = too much shipping cost). | Ordering too much based on optimism (ordering 1,200 units because "I think demand will double") is the #1 inventory mistake for new D2C founders. Order based on DATA (actual sell rate × 6 months), not hope. Ordering too little is also a risk (frequent small orders = higher per-unit freight cost + more management overhead). | Use the decision matrix. Be CONSERVATIVE in quantity. It's better to order 500 and reorder again in 5 months than to order 1,200 and have $7,200 in inventory sitting for 15 months. Negotiate MOQ with supplier: "Can we do 500 units at the 600-unit price?" Many suppliers agree to maintain pricing for repeat orders. | Sell rate data from 7D.03. Cash position from 7B.04. v2 modifications from P3D.03.
Reorder SKU Mix Adjustment | The initial 600-unit order was split equally: 75 units × 8 SKUs. The reorder should be split based on ACTUAL SALES DATA. Example: if Midnight Black S/M sold 2× faster than Deep Ocean L/XL: INITIAL: 75 each (equal split) REORDER: Black S/M: 120, Black L/XL: 100, Rose S/M: 90, Rose L/XL: 80, Sage S/M: 60, Sage L/XL: 50, Ocean S/M: 50, Ocean L/XL: 50 = 600 total Allocate reorder proportional to sales velocity per SKU. Don't restock equally what doesn't sell equally. | For each SKU: (units sold ÷ total sold) × reorder quantity = units to reorder. Example: Black S/M sold 120 of 500 total = 24%. Reorder of 600 → 600 × 0.24 = 144 units Black S/M. Round to nearest 25 (factory minimum per variant is usually 25-50 units). | Each SKU's reorder % should reflect its actual sales %. | Reordering equal quantities across SKUs when demand is unequal = overstocking slow sellers and understocking fast sellers. The #2 inventory mistake after over-ordering. | Pull Shopify sales by variant for the entire period → calculate % of total per variant → apply % to reorder quantity. Consider: discontinuing the 1-2 slowest-selling SKUs to simplify operations and free capital for fast movers. | Shopify → Analytics → Sales by variant.

## 7D FOUNDER ACTIONS
P7D INVENTORY FINANCIAL TRACKING — FOUNDER ACTION CHECKLIST
Set up on Day 1. Reconcile weekly (10 min). Calculate landed cost once per production run. Monitor turnover continuously. Reorder at 60 days remaining.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
DAY 1: INITIAL SETUP
🔴 #1 | Set up dual inventory tracking: Shopify + Google Sheets backup | 30 min | $0 | 1. Verify Shopify inventory: Products → StrideHer → each variant shows correct starting count (from P3C.04 receiving) 2. Create Google Sheet: copy the template from Sheet 7D.01 (8 SKU rows with columns: received, sold, samples, damaged, available, reorder point) 3. Set reorder point for each SKU: 19 units (= 45 days at ~3 units/week initial estimate; update as actual sell rate becomes clear) 4. Add conditional formatting: "Available Now" cell turns RED when below reorder point 5. Bookmark this sheet — you'll update it every Monday for the life of the business
🔴 #2 | Calculate landed cost per unit using actual invoices | 30 min | $0 | 1. Gather: supplier invoice (COGS), freight forwarder invoice (all shipping charges), customs entry summary (duties + fees), packaging supplier receipts 2. Enter actual amounts into Sheet 7D.02 landed cost table (replacing estimates with YOUR real numbers) 3. Calculate YOUR landed cost per unit: should be $9-$11 range 4. Calculate YOUR true gross margin: $34.99 - landed cost = true gross margin per unit 5. Compare to 7B.01 model — if >10% different: update all financial models with the real number 6. This number determines your REAL profitability. Everything downstream depends on it being accurate.
ONGOING: WEEKLY + MONTHLY + AT REORDER TRIGGER
🟡 #3 | Weekly inventory reconciliation (every Monday, 10 minutes) | 10 min/week | $0 | Every Monday (alongside P6E.01 KPI review): 1. Shopify → Products → note each variant's inventory count 2. Open Google Sheet → update "Sold" column with this week's sales (by variant) 3. Update "Available Now" (= Received - Sold - Samples - Damaged + Returns) 4. Compare to Shopify count → if discrepancy >2: investigate 5. Calculate: days of inventory remaining = Available Now ÷ (weekly sell rate ÷ 7) 6. Log: date, total units, sell rate, days remaining (4-number weekly log) 7. If days remaining <60: begin reorder planning (contact supplier, check cash position)
🟡 #4 | Monthly inventory turnover calculation (part of 7B.04 review) | 15 min/month | $0 | Monthly (integrate with 7B.04 financial review): 1. Units sold this month: ___ (Shopify) 2. Average units on hand: (start of month + end of month) ÷ 2 3. Monthly turnover: units sold ÷ average on hand 4. Annualized turnover: monthly × 12. Target: 2-4× Year 1. 5. Inventory value: units on hand × landed cost ($9.88). This is the asset value on your balance sheet. 6. If annualized turnover <2×: demand is softer than modeled — increase marketing OR reduce next reorder quantity
🔴 #5 | Execute reorder when days remaining reaches 60 | Variable (1-2 hrs for PO + supplier comms) | $3,000-$6,000 (next PO) | When days of inventory remaining ≤ 60: 1. CONFIRM cash available for PO (check 7B.04 cash position — is there $3,000-$6,000 available?) 2. CALCULATE reorder quantity: monthly sell rate × 6 months, adjusted by SKU per Sheet 7D.04 3. INCLUDE v2 modifications from P3D.03 (if any — gel pocket magnet, phone pocket width, etc.) 4. CONTACT supplier: "Ready for reorder PO. Quantity: ___. Modifications: ___. Please confirm pricing and timeline." 5. PAY deposit (typically 30% via Wise) 6. UPDATE cash flow forecast (P7B.02) with the PO commitment 7. MONITOR production timeline — follow P3B QC protocol for quality checks before shipping