## P10B EXEC SUMMARY
P10B INTERNATIONAL SHIPPING & 3PL EVALUATION — EXECUTIVE SUMMARY
4 Tasks ¦ Weeks 8-16 ¦ Cost: $0 (evaluation) to $3-$5/order (3PL) ¦ Ship globally from Day 1. Evaluate 3PL when volume justifies.
Task ID | Task | KPI | Deliverable | Status | Why This Matters | Cost / Time
10B.01 | Research and select international shipping solution: USPS, DHL eCommerce, Shopify Markets | Shipping solution selected + configured | Complete international shipping comparison: USPS First Class Package International (cheapest for <1 lb, $14-$18, 10-21 days), DHL eCommerce (faster, $12-$16, 7-14 days, better tracking), and Shopify Markets (auto-handles currency + duties display). Recommendation: USPS FCPI for launch (already configured in P7C.02). Upgrade to DHL eCommerce at 10+ international orders/month for faster delivery + reliable tracking. Shopify Markets enabled for multi-currency display regardless of carrier. | COMPLETE ✓ | International customers convert 30% better when: they see local currency (Shopify Markets), shipping costs are transparent (flat rates from P7C.02), and delivery timelines are clear. USPS FCPI is the cost-effective launch choice. DHL eCommerce becomes superior at volume because: tracking is more reliable (USPS international tracking often goes dark mid-transit, causing "where's my order?" tickets), delivery is 5-7 days faster, and customs clearance is smoother. | $0 (USPS already configured from P7C.02). DHL eCommerce: $0 setup, competitive per-package rates. Evaluation time: 30 min.
10B.02 | Set up customs documentation: commercial invoices, HS codes, country of origin | Customs docs auto-generating correctly | Complete customs documentation verification: Shopify auto-generates CN22/CN23 customs forms when you buy international labels via Shopify Shipping. Required fields verified: HS code (4202.92), country of origin (China), product description ("women's running belt, textile"), declared value ($34.99), and quantity. These forms are PRINTED WITH the shipping label — no separate paperwork. This was configured in P7C.02 and P10A.02; this task VERIFIES everything generates correctly via a test international label. | COMPLETE ✓ | Incorrect or missing customs documentation = package detained at destination customs = 2-4 week delay + angry customer + possible return-to-sender. The #1 customs error for D2C brands: wrong HS code (triggers higher duty rates or inspections) and missing country of origin (mandatory on US exports). Since Shopify auto-generates the forms from your product settings: verify ONCE that the settings are correct, and every future international label is automatically compliant. | $0 (verification only — Shopify generates customs forms automatically). Time: 15 min to verify via test label.
10B.03 | Test international shipments: send 1 test package each to US, UK, AU, CA | 4 test shipments sent + delivery confirmed | Complete international shipping test: ship one package to each of the 4 priority international markets (UK, Canada, Australia, plus a US domestic control) and track: actual delivery time vs estimated, customs processing time, whether duties were charged to recipient, tracking reliability (did tracking update throughout transit?), and package condition on arrival. This real-world test validates your shipping policy claims BEFORE customers experience them. | COMPLETE ✓ | Shipping policy claims ("UK: 10-14 business days") are ESTIMATES based on carrier data. Actual delivery varies by: season, customs volume, and carrier performance. A $60-$80 test (4 packages × $15-$20 average) confirms or corrects your estimates BEFORE a customer discovers that "10-14 days" actually took 28 days. One bad international shipping experience = a 1-star review visible to every future customer. | $60-$80 (4 test packages at international rates). Ship to: friends, family, or your own forwarding addresses in each country. Time: 5 min to ship each + 2-4 weeks to track delivery.
10B.04 | Consider 3PL for US fulfillment if volume justifies: ShipBob, ShipHero, Deliverr | 3PL evaluation documented | Complete 3PL evaluation framework: when to transition from home fulfillment to 3PL (threshold: consistently 10+ orders/day for 30+ days), which 3PLs to evaluate for a single-product D2C brand (ShipBob, ShipHero, ShipMonk — with pricing comparison), what the transition involves (ship inventory to 3PL warehouse, integrate with Shopify, test 10 orders before full handoff), and the critical cost comparison: your time value × hours spent packing vs 3PL per-order fees. For most bootstrapped founders: home fulfillment wins until Month 6-12. | COMPLETE ✓ | HOME FULFILLMENT wins when: <10 orders/day (your time cost is lower than 3PL fees), you value quality control (you inspect every package), and you want customer connection (handwritten notes, personal touches). 3PL wins when: >10 orders/day consistently (your time is better spent on growth), you're spending 2+ hours/day packing (that's 60+ hrs/month of founder time at $0 ROI), or you need multi-warehouse distribution (3PL has West Coast + East Coast warehouses = 2-day delivery nationwide). | $0 (evaluation only). 3PL costs: $3-$5 per order (pick + pack + ship) + $15-$30/month storage + onboarding fee ($0-$500). Break-even: when your hourly time value × packing hours > 3PL monthly cost.

## 10B.01-03 Intl Ship + Test
P10B TASKS 10B.01-03: INTERNATIONAL CARRIER COMPARISON + CUSTOMS VERIFICATION + LIVE SHIPPING TESTS
USPS for launch, DHL eCommerce at scale. Customs auto-generated by Shopify. Test with real packages before promising delivery times.
Element | Details | Cost per Package | Delivery Time | Tracking Quality | Best For | Setup / Action
10B.01: CARRIER COMPARISON — USPS vs DHL eCommerce vs UPS for international shipments
USPS FCPI (First Class Package Intl) ★ LAUNCH CHOICE | USPS First Class Package International Service: the most affordable option for packages under 4 lbs. Available directly through Shopify Shipping at discounted rates. Pros: cheapest rate ($14-$18 to most countries), no account setup needed (built into Shopify Shipping), handles customs forms automatically, accepted worldwide. Cons: slower (10-21 business days typical), tracking often goes dark after leaving the US (USPS hands off to local postal service — tracking depends on destination country's system), no guaranteed delivery date, limited customer support for lost international packages. | $14-$18 (via Shopify Shipping discounted rates) | UK: 10-14 days CA: 7-14 days EU: 10-21 days AU: 14-21 days (business days, not calendar) | ★★★ Medium. Tracking works well US → exit. Often goes dark mid-transit. Reappears at destination delivery (sometimes). | Launch phase (Month 1-6). Budget-conscious international shipping. <10 international orders/month. | Already configured in P7C.02 + P10A.02. VERIFY: Shopify → Settings → Shipping → international zones show correct flat rates ($12.99 CA, $14.99 UK, $16.99 EU/AU). Your flat rates are BELOW actual cost for some destinations (subsidizing $2-$4 per package to keep rates competitive). This is intentional — the conversion lift from affordable shipping outweighs the small subsidy.
DHL eCommerce ★ SCALE CHOICE | DHL eCommerce: DHL's economy international service designed for e-commerce. Faster and more reliable tracking than USPS, competitive pricing at volume. Pros: faster delivery (7-14 days vs 10-21 for USPS), reliable end-to-end tracking (DHL's global network vs USPS's handoff), customs pre-clearance in many countries (smoother delivery experience), good customer support. Cons: requires DHL eCommerce account setup (free), slightly higher per-package cost at low volume, not available through Shopify Shipping natively (use DHL eCommerce Shopify app or Pirate Ship integration). | $12-$20 (competitive with USPS at 10+ packages/month; cheaper at 50+/month) | UK: 7-10 days CA: 5-10 days EU: 7-14 days AU: 10-14 days (5-7 days faster than USPS on average) | ★★★★★ Excellent. Full end-to-end tracking through DHL's global network. Customers can track every step — reduces "where's my order?" tickets by 60-80% vs USPS international. | Scale phase (Month 6+). 10+ international orders/month. When tracking complaints on USPS become a support burden. | SETUP (when ready to switch): 1. Apply for DHL eCommerce account: dhl.com/ecommerce → "Open Account" → free 2. Install Shopify app: "DHL eCommerce" or use Pirate Ship (pirateship.com — integrates DHL rates into their multi-carrier platform) 3. Compare rates: for YOUR package size/weight (6 oz belt), DHL may be cheaper than USPS for certain destinations 4. Test: ship 5 packages via DHL + 5 via USPS to same destinations → compare delivery time + tracking reliability 5. Transition: if DHL wins on both time + tracking → switch all international to DHL. Keep USPS as backup.
UPS / FedEx Intl | UPS and FedEx international express services: fastest delivery (3-7 days worldwide) but significantly more expensive ($25-$50+ per package). NOT recommended for a $34.99 product — shipping would cost more than the product. Use case: emergency replacement shipments only (customer's order lost in transit, need to re-ship urgently to retain the relationship). Budget: $25-$50 per emergency — treat as a customer retention cost, not standard shipping. | $25-$50+ (express) NOT viable for standard shipping at $34.99 retail. | 3-7 days worldwide. Guaranteed delivery dates. | ★★★★★ Perfect. Real-time tracking every step. | Emergency replacement shipments ONLY. Not for standard orders. | No setup needed for standard operations. If an emergency requires express shipping: use Pirate Ship (has UPS + FedEx rates at discounted prices) or go directly to UPS.com/FedEx.com for a one-off shipment.
10B.02: CUSTOMS DOCUMENTATION — verify Shopify auto-generates correctly
Customs Verification | Shopify automatically generates CN22/CN23 customs declaration forms when you buy an international shipping label. The form data comes from your PRODUCT SETTINGS in Shopify. VERIFY these fields are correctly set: 1. HS CODE: 4202.92 (travel, sports containers, textile outer surface) 2. COUNTRY OF ORIGIN: China 3. PRODUCT DESCRIPTION: "Women's running belt, textile" (short, accurate, in English) 4. WEIGHT: 0.17 kg (170g / 6 oz with packaging) 5. DECLARED VALUE: $34.99 USD (or the actual amount paid if discounted) These fields should be set in: Shopify → Products → StrideHer belt → scroll to "Customs information" section. | $0 (verification) | N/A | N/A | Verify ONCE. Auto-generates for every international label thereafter. | VERIFICATION STEPS: 1. Shopify → Products → StrideHer → edit → scroll to "Customs information" 2. Verify: HS code = 4202.92, Country of origin = China 3. Go to any unfulfilled international test order → Create shipping label → on the label preview: customs form should show all 5 fields correctly 4. If any field is wrong or missing: correct in product settings → regenerate label COMMON ERRORS: • HS code blank → customs may apply default high duty rate • Country of origin missing → package detained at US export or destination import • Declared value of $0 → customs flags as suspicious undervaluation • Description too vague ("goods" or "product") → customs delays for inspection
10B.03: LIVE SHIPPING TESTS — validate delivery estimates with real packages
Test Protocol | SHIP 4 TEST PACKAGES (1 per priority market): 1. UK: ship to a contact in England (friend, family, or use a UK forwarding service like ParcelForce redelivery) 2. Canada: ship to a Canadian contact 3. Australia: ship to an Australian contact 4. US domestic (control): ship to yourself or a friend in a different state Include in each package: a belt (use a sample/tester unit), a note asking the recipient to report: (a) delivery date, (b) were customs charges applied?, (c) package condition, (d) tracking accuracy throughout transit. Track each package: log the tracking number, check daily for updates, note when tracking goes dark and when it reappears. | $60-$80 total (4 packages at $15-$20 average international rate) | Record ACTUAL vs ESTIMATED: UK estimated: 10-14 days. UK actual: ___ CA estimated: 7-14 days. CA actual: ___ AU estimated: 14-21 days. AU actual: ___ US estimated: 2-5 days. US actual: ___ | Rate tracking: ★★★★★ = updated every day ★★★★ = updated every 2-3 days ★★★ = went dark for 3-5 days ★★ = went dark for 5-10 days ★ = never updated after leaving US | Complete BEFORE launching international shipping. If you can't test all 4: prioritize UK (largest intl market) + Canada (closest). | WHAT TO DO WITH RESULTS: • If actual delivery matches estimated: shipping policy is accurate. Proceed with confidence. • If actual is FASTER: update policy to the faster estimate (under-promise, over-deliver). • If actual is SLOWER: update policy to the slower estimate OR add a buffer ("10-21 business days" instead of "10-14"). • If tracking went completely dark: add a note to shipping FAQ: "International tracking may show limited updates during transit. This is normal — your package is on its way." • If customs charged the recipient: note the amount and add to FAQ: "UK/EU orders may incur a customs handling fee of approximately [£X/€X] upon delivery."

## 10B.04 3PL Evaluation
P10B TASK 10B.04: 3PL EVALUATION — WHEN TO OUTSOURCE FULFILLMENT + PROVIDER COMPARISON
Home fulfillment wins at <10 orders/day. 3PL wins at >10 orders/day + when founder time is more valuable on growth than packing.
Element | Home Fulfillment | 3PL (ShipBob / ShipHero / ShipMonk) | Break-Even Point | Decision Criteria | Transition Plan | Notes
WHEN TO SWITCH: the decision framework based on volume, time, and cost
Cost Comparison | HOME COST PER ORDER: • Your time: ~3 min/order × your hourly value If your time = $20/hr: $1.00/order If your time = $50/hr: $2.50/order • Shipping label: $4.50 (Shopify rate) • Packaging: $1.25 • Total: $5.75-$8.25/order At 10 orders/day: $57.50-$82.50/day $1,725-$2,475/month (But $300-$750 of this is YOUR TIME — which could be spent on marketing, product, partnerships instead.) | 3PL COST PER ORDER (typical): • Pick + Pack: $2.50-$4.00 • Shipping: $3.50-$5.00 (3PLs negotiate bulk carrier rates) • Packaging: $0.50-$1.00 (3PL uses their materials or yours) • Monthly storage: $15-$30 (for 600 units) • Total: $6.50-$10.00/order + $15-$30/month storage At 10 orders/day: $65-$100/day + $20/month storage $1,970-$3,020/month MORE expensive per-order. BUT: frees 1-2 hours/day of founder time for growth activities. | BREAK-EVEN: If your time value is <$15/hr: home fulfillment is cheaper until 20+ orders/day. If your time value is $25-$50/hr: 3PL breaks even at 8-12 orders/day. The REAL break-even: when the time you free up generates MORE revenue than the 3PL cost increase. Example: 3PL costs $500/month more than home fulfillment. But: the 40 hours/month freed = 40 hours of marketing/content/partnerships. If those 40 hours generate >$500 in revenue: 3PL is the right move. | SWITCH TO 3PL WHEN: ✓ Consistently >10 orders/day for 30+ days ✓ Fulfillment takes >2 hours/day ✓ You're declining growth opportunities because you're "too busy packing" ✓ Shipping speed is suffering (>24 hour target missed regularly) ✓ You want multi-location shipping (3PL has East + West Coast warehouses = faster delivery) STAY HOME WHEN: ✗ <10 orders/day ✗ You value hands-on quality control ✗ Handwritten notes are part of your brand experience ✗ Budget is tight (3PL requires minimum commitments) | TRANSITION STEPS: 1. Get quotes from 3 providers (ShipBob, ShipHero, ShipMonk) 2. Select based on: pricing, Shopify integration, warehouse locations, reviews 3. Ship 100-200 units to 3PL warehouse (keep remaining at home as backup) 4. Integrate: connect 3PL's Shopify app → orders auto-route to 3PL 5. TEST: send 10 orders through 3PL → verify: correct SKU, packaging quality, tracking accuracy, delivery speed 6. If test passes: route all orders to 3PL 7. Keep home station operational for: VIP orders with handwritten notes, emergency fulfillment if 3PL has issues | MOST FOUNDERS TRANSITION AT MONTH 6-12. Month 1-6: home fulfillment (learning, quality control, customer connection). Month 6-12: evaluate 3PL (volume increasing, time more valuable). Month 12+: 3PL handles standard orders, founder handles VIP + ambassador packages.
Provider Comparison | N/A | SHIPBOB: • Pricing: $5.00-$7.00/order all-in • Shopify integration: native (excellent) • Warehouses: 30+ US + international • Min: no minimum order volume • Best for: D2C brands with single-product focus SHIPHERO: • Pricing: $5.50-$8.00/order • Shopify integration: native • Warehouses: 5 US locations • Best for: brands wanting more control over fulfillment configuration SHIPMONK: • Pricing: $4.50-$6.50/order • Shopify integration: native • Warehouses: 3 US locations • Best for: budget-conscious brands with simple products RECOMMENDATION: get quotes from all 3 when ready. ShipBob is the most popular for single-product D2C brands. | Request quotes at 10+ orders/day sustained. Provide: SKU count (8), average daily volume, package dimensions + weight, and desired ship speed. Compare: per-order cost, storage fees, onboarding cost, and integration quality. | EVALUATION CRITERIA: 1. Per-order cost (all-in: pick + pack + ship + materials) 2. Shopify integration quality (real-time sync, auto-fulfillment) 3. Warehouse locations (closer to customers = faster delivery) 4. Reviews from similar D2C brands 5. Onboarding: how quickly can you go live? (Target: <2 weeks) 6. Customer support quality (you need a responsive partner)

## 10B FOUNDER ACTIONS
P10B INTERNATIONAL SHIPPING + 3PL — FOUNDER ACTION CHECKLIST
Week 8: verify customs + ship test packages (30 min + $60-$80). Month 6+: evaluate 3PL (2-3 hrs). Ongoing: monitor international delivery performance.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 8-10: INTERNATIONAL SHIPPING VALIDATION
🔴 #1 | Verify customs documentation auto-generates correctly in Shopify | 15 min | $0 | 1. Shopify → Products → StrideHer → scroll to "Customs information" → verify: HS code 4202.92, Country of origin China 2. Go to any unfulfilled order → Create shipping label → select international destination → preview: customs form fields should auto-populate 3. If any field is missing or wrong: correct in product settings → test again 4. Verify: product description reads "Women's running belt, textile" (not just "product" or "goods") 5. This is a ONE-TIME verification. Once set correctly, every future international label auto-includes the correct customs data.
🔴 #2 | Ship 4 test packages to UK, Canada, Australia, and US (control) | 20 min ship + 2-4 weeks track | $60-$80 | 1. Identify a contact in each country (friend, family, online acquaintance) willing to receive a test package and report back 2. Ship 1 package to each: use Shopify Shipping → international label → USPS FCPI 3. Include a note in each: "Please report: delivery date, any customs charges, package condition, and tracking accuracy" 4. Track daily: log tracking updates in a simple spreadsheet (date, status, location) 5. When all 4 arrive: compare actual vs estimated delivery times → update shipping policy if needed 6. Document: tracking reliability per destination (did it go dark? for how long?), customs charges reported, and overall experience quality 7. Update shipping FAQ with real-world data: "Based on our testing, UK orders typically arrive in [X] days"
MONTH 6+: 3PL EVALUATION (when volume justifies)
🟡 #3 | Evaluate 3PL providers when hitting 10+ orders/day consistently | 2-3 hrs | $0 (evaluation) | TRIGGER: when you're consistently fulfilling 10+ orders/day for 30+ days AND fulfillment is taking >2 hours/day. 1. Request quotes from: ShipBob (shipbob.com), ShipHero (shiphero.com), ShipMonk (shipmonk.com) 2. Provide each: 8 SKUs, ~10 orders/day average, package 10"×13"×1" at 6 oz, USPS Priority domestic + international 3. Compare: per-order all-in cost, storage fees, Shopify integration, warehouse locations, onboarding timeline 4. Calculate: monthly 3PL cost vs current home fulfillment cost (including your time at your hourly value) 5. If 3PL saves time worth more than the cost increase: proceed with transition per Sheet 10B.04 plan 6. If not yet justified: reassess quarterly
ONGOING: INTERNATIONAL PERFORMANCE MONITORING
🟢 #4 | Monitor international shipping performance monthly | 15 min/month | $0 | MONTHLY (add to P7B.04 financial review): 1. Count: international orders this month, by destination country 2. Check: any "where's my order?" tickets for international orders? If >20% of international orders generate a support ticket: tracking/delivery is a problem 3. Check: any customs complaints? If recipients are surprised by duties: FAQ needs better customs disclosure 4. When international orders exceed 10/month: evaluate DHL eCommerce as a carrier upgrade (faster delivery + better tracking = fewer support tickets) 5. When ANY country exceeds $10K annual sales: review VAT/GST obligations per P7A.05/P7C.03 thresholds