## P10C EXEC SUMMARY
P10C INVENTORY MANAGEMENT OPERATIONS — EXECUTIVE SUMMARY
4 Tasks ¦ Weeks 4-Ongoing ¦ Cost: $0 ¦ The operational backbone: SKU system, weekly counts, safety stock, and reorder calendar.
Task ID | Task | KPI | Deliverable | Status | Why This Matters | Cost / Time
10C.01 | Implement SKU naming system: COLOR-SIZE-VERSION | SKU system live in Shopify | Complete SKU naming convention: [COLOR 3-letter]-[SIZE 2-letter]-[VERSION] format applied to all 8 variants. BLK-SM-V1, RSE-LX-V1, etc. This system scales: when v2 launches, variants become BLK-SM-V2 — every historical record distinguishes between production runs. SKUs are set in Shopify → Products → Variants → SKU field, used in: inventory tracking (P7D), supplier POs (P3A), customs forms, and internal reporting. | COMPLETE ✓ | Without a SKU system: "the black one, medium" works for 1 product with 8 variants. It breaks at 2 products with 16 variants. A formal SKU system creates: machine-readable inventory tracking, clear PO specifications (supplier knows EXACTLY which variant you're ordering), version tracking across production runs (v1 vs v2 quality comparison), and professional communication with suppliers/3PLs. | $0 (naming convention). Time: 15 min to enter SKUs in Shopify.
10C.02 | Set up weekly inventory count: physical count reconciled with Shopify every Sunday | Weekly reconciliation operational | Cross-reference P7D.01 — the dual tracking system (Shopify + Google Sheets backup) is already established. This task OPERATIONALIZES it: Sunday evening physical count of all 8 SKU positions → compare to Shopify count → investigate discrepancies → update if needed → log weekly totals. The 10-minute weekly ritual that prevents stockouts, oversells, and inventory shrinkage from going undetected. | COMPLETE ✓ | Inventory discrepancies compound over time. A single miscounted variant (Shopify says 72, you actually have 70) seems harmless. But over 8 variants × 4 months: discrepancies accumulate to 10-15 units. Those 10-15 "phantom" units trigger: overselling (customer buys, you can't ship = refund + 1-star review), incorrect reorder timing (you think you have more than you do), and financial reporting errors (inventory value is wrong on your balance sheet). | $0. Time: 10 min every Sunday evening.
10C.03 | Define safety stock levels: minimum inventory per SKU while reorder is in transit | Safety stock levels set for all 8 SKUs | Complete safety stock calculation: the minimum units you MUST have on hand when a reorder PO is placed, to cover sales during the production + shipping lead time (55-75 days). Safety stock = daily sell rate × lead time days × safety factor (1.2-1.5). At 4 units/day sell rate and 65-day lead time with 1.3 safety factor: safety stock = 4 × 65 × 1.3 = 338 units. This means: trigger reorder when total inventory hits 338 units (not when it hits 0). Per-SKU: 338 ÷ 8 = ~42 units per SKU. | COMPLETE ✓ | Without safety stock: you place a reorder when inventory "feels low" → production takes 40 days + shipping 30 days → you stock out for 2-4 weeks → $0 revenue + lost customers + damaged search rankings. With safety stock: you place a reorder at 338 units remaining → new stock arrives just as the last units sell → zero downtime. The safety factor (1.3×) adds a buffer for: production delays, shipping delays, and demand spikes. Stockout prevention is the single most important operational metric. | $0 (calculation only). Time: 15 min to calculate + set reorder alerts in your P7D tracker.
10C.04 | Create reorder calendar aligned with production lead times + seasonal demand | Reorder calendar documented | Complete reorder planning calendar: maps your inventory sell-through trajectory against the production + shipping lead time, with seasonal adjustments for demand peaks (August-September peak running season, January new-year-resolution runners, March-April spring race season). The calendar answers: "When EXACTLY should I place my next PO?" based on: current inventory, current sell rate, production lead time, and seasonal forecast. It also identifies the CRITICAL ORDER WINDOW — the 2-week period where placing the PO avoids stockout. Miss this window → stockout is mathematically inevitable. | COMPLETE ✓ | Seasonal demand planning prevents two costly mistakes: (1) UNDER-ORDERING before a peak season (August marathon training season = 30-50% demand spike — if you order the same quantity as off-season, you stock out during your most profitable months), and (2) OVER-ORDERING before a slow season (November-December = 20-30% demand dip for running gear — ordering based on October's peak rate leaves excess inventory eating cash). The reorder calendar aligns ORDER TIMING with DEMAND FORECAST. | $0 (planning document). Time: 1 hour to create. Update: monthly with actual sell rate data.

## 10C.01-04 Inventory Ops
P10C TASKS 10C.01-04: SKU SYSTEM + WEEKLY COUNTS + SAFETY STOCK + REORDER CALENDAR
Naming convention for 8 variants. 10-min Sunday count. Safety stock = 338 units. Reorder when total inventory hits the trigger.
SKU | Color | Size | Version | Shopify Count | Physical Count | Discrepancy | Safety Stock (per SKU)
SH-BLK-SM-V1 | Midnight Black | S/M | V1 |  |  |  | 42
SH-BLK-LX-V1 | Midnight Black | L/XL | V1 |  |  |  | 42
SH-RSE-SM-V1 | Desert Rose | S/M | V1 |  |  |  | 42
SH-RSE-LX-V1 | Desert Rose | L/XL | V1 |  |  |  | 42
SH-SGE-SM-V1 | Alpine Sage | S/M | V1 |  |  |  | 42
SH-SGE-LX-V1 | Alpine Sage | L/XL | V1 |  |  |  | 42
SH-OCN-SM-V1 | Deep Ocean | S/M | V1 |  |  |  | 42
SH-OCN-LX-V1 | Deep Ocean | L/XL | V1 |  |  |  | 42
TOTAL | All | All | — |  |  |  | 338
SAFETY STOCK CALCULATION — the math behind the 338-unit reorder trigger
Input | Value | Source | Formula / Notes
Input | Value | Source | Formula
Average daily sell rate | 4 units/day | P7D.03 smoothed weekly rate ÷ 7 (adjust monthly with actual data) | Shopify sales ÷ days selling
Production lead time | 35 days | P3A supplier quote (30-40 day range, use midpoint) | Factory confirmation on PO
Shipping lead time | 30 days | P3C sea freight (25-35 days, use midpoint) | Freight forwarder estimate
Total lead time | 65 days | Production + shipping | 35 + 30 = 65 days
Base reorder point | 260 units | Daily rate × total lead time | 4 × 65 = 260
Safety factor | 1.3× (30% buffer) | Accounts for: production delays, shipping delays, demand spikes | Industry standard for single-source supply chain
SAFETY STOCK / REORDER POINT | 338 units | Base × safety factor | 260 × 1.3 = 338 units total
Per-SKU reorder point | 42 units | Total ÷ 8 SKUs (adjust proportional to actual sales mix per P7D.04) | 338 ÷ 8 = 42.25 → round to 42
10C.04: REORDER CALENDAR — seasonal demand adjustments + critical order windows
Month | Season | Demand Factor | Monthly Units (est.) | Inventory Remaining (projected) | Action | Reorder Quantity | Notes
Jan | New Year resolution | 1.2× | 144 | 456 | Monitor. Demand spike from NYR runners. If sell rate exceeds forecast: consider air freight for emergency restock. | — | January is the #2 demand month for fitness products. Marketing: "New year, new gear" campaign.
Feb | Winter training | 1.0× | 120 | 336 | ⚠️ APPROACHING REORDER POINT (338). If not already ordered: place PO NOW. | 600-800 (if triggered) | February is a natural reorder month for Aug-Sep launch brands (6 months of sales data available).
Mar | Spring race prep | 1.1× | 132 | 204 | If PO placed in Feb: production in progress. Monitor factory timeline. | — | Spring marathon season begins. Half marathon training = peak belt demand.
Apr | Race season | 1.2× | 144 | 60 | New inventory should be arriving or in transit. If delayed: consider air freight for critical SKUs. | — | Boston Marathon, spring 10Ks. Social content: race day belt content.
May | Post-race plateau | 0.9× | 108 | 552* | *New inventory arrived (assume 600-unit reorder). Monitor sell-through of new batch. | — | Post-spring-race dip. Focus on: content, community, reviews. Less on acquisition.
Jun | Summer buildup | 1.0× | 120 | 432 | Steady state. Begin planning for Aug-Sep peak season. | — | Summer running begins. Heat-related content (belt in hot weather).
Jul | Summer peak start | 1.1× | 132 | 300 | If Aug-Sep is your peak: consider a smaller top-up order for fast-selling SKUs. | 200-400 (top-up if needed) | July orders arrive just in time for Aug-Sep peak.
Aug | PEAK SEASON | 1.4× | 168 | 132 | ★ HIGHEST demand month. Marathon training season + back-to-routine. Ensure full inventory. | — | Marketing budget: maximum this month. All channels at full spend.
Sep | Peak continues | 1.3× | 156 | -24 ⚠️ | If inventory hits 0: emergency air freight ($3-$5/unit extra). This is why July top-up order is critical. | Emergency 200 air (if stockout) | September stockout is the #1 preventable disaster for running gear brands.
Oct | Fall transition | 1.1× | 132 | 444* | *Assume next regular reorder arrived. Sell-through into holiday gifting potential. | 600-800 (regular reorder) | Fall races + early holiday gifting ("gifts for runners" marketing angle begins).
Nov | Holiday gifting | 1.0× | 120 | 324 | Gift-focused marketing: "The perfect gift for the runner in your life." Bundle offers. | — | Black Friday / Cyber Monday: consider a 20% site-wide sale (1 day only — don't devalue the brand).
Dec | Holiday + winter | 0.8× | 96 | 228 | Lowest demand for running gear. Use this month for: planning, product development (v2 spec), and rest. | — | Year-end: compile annual financial review (P7B), write next year's plan.

## P10D Packaging Optimization
P10D PACKAGING OPTIMIZATION — COST ANALYSIS + UNBOXING FEEDBACK + ECO OPTIONS
4 Tasks ¦ Weeks 10-Ongoing ¦ Analyze costs, improve based on feedback, explore eco-friendly, and source branded elements.
Task | Details | Current Cost | Optimization | Impact | Timeline | Action
10D.01: PACKAGING COST ANALYSIS — target <$1.50/order all-in
Per-Order Cost Breakdown | CURRENT PACKAGING COST PER ORDER: • Poly mailer (10×13"): $0.25 • Brand sticker (seal): $0.10 • Insert card (QR + care): $0.15 • Tissue wrap: $0.15 • Thank-you card (first 20 orders only): $0.10 • Total standard order: $0.65 • Total with thank-you card: $0.75 TARGET: <$1.50/order (current: $0.65-$0.75 ✓ — well under target). This is EXCELLENT cost control from P2C. The packaging is effective, branded, and cheap. No optimization needed on cost — optimize on EXPERIENCE instead. | $0.65-$0.75 per order (well under $1.50 target) | Cost optimization is NOT needed — $0.65 is already efficient. Focus optimization on EXPERIENCE improvements that don't significantly increase cost: 1. Upgrade tissue wrap to branded tissue ($0.05 extra = $0.20 total) — subtle but premium 2. Add a small sticker sheet ($0.08 extra) — customers stick them on water bottles/laptops = free brand exposure 3. Replace generic thank-you card with a permanent "care card" ($0.10) that goes in every order, not just the first 20 Total upgraded cost: $0.88/order — still well under $1.50. | Current $0.65/order × 50 orders/month = $32.50/month packaging cost. Upgraded $0.88/order × 50 = $44/month. Difference: $11.50/month for a noticeably more premium unboxing experience. ROI: if the upgraded packaging generates 1 additional social post per month from an excited customer: the $11.50 is covered by $20-$50 in equivalent ad spend for that organic reach. | Month 3-4: evaluate feedback from first 100 customers. Month 4-5: implement upgrades on next packaging reorder. | DECISION FRAMEWORK: If unboxing generates social posts (customers photograph the packaging): the current experience is WORKING — don't change it. If no unboxing content appears: upgrade packaging elements to make it more "share-worthy." If customers specifically praise the packaging in reviews: maintain and emphasize it. If customers don't mention packaging at all: it's invisible — which is fine (the product matters more than the box).
10D.02: UNBOXING EXPERIENCE FEEDBACK — what impressed, what felt cheap, what was missing
Feedback Collection | COLLECT UNBOXING FEEDBACK from 3 sources: 1. REVIEWS: search all reviews for packaging mentions. "Loved the personal note" → keep notes. "Packaging was basic" → consider upgrade. "Beautiful packaging" → it's working. 2. SOCIAL MEDIA: search #StrideHer for unboxing photos/videos. Do customers photograph the packaging? The sticker? The note? If yes: the unboxing IS content-worthy. If no unboxing content exists: the packaging isn't remarkable enough to share. 3. QUARTERLY SURVEY (P9B.03): add a packaging question: "How was your unboxing experience? (1-5)" + "What would make it better?" This direct feedback reveals: what customers remember (the personal note), what they don't notice (the tissue wrap), and what they wish existed (a carrying bag, a sticker sheet, a branded ribbon). | $0 | Based on feedback themes: IF "loved the handwritten note" is common → keep notes for longer (not just first 20 orders — consider: first 50, or all VIP/ambassador orders permanently) IF "packaging was plain" → upgrade: branded tissue, sticker sheet, nicer mailer IF "wished there was a carrying bag" → evaluate: adding a small branded drawstring bag (cost: $0.50-$1.00/unit). This becomes the product's "home" and gets seen at every race/gym → mobile brand billboard IF no packaging feedback at all → packaging is adequate. Focus effort elsewhere. | The handwritten note is consistently the #1 mentioned packaging element across D2C brands. It costs $0.10 (card) + 2 min (writing) and generates: social posts, 5-star reviews mentioning "personal touch," and emotional brand attachment. The ROI on a handwritten note is 50-100× its cost. | Collect: Month 3+ (need 50+ orders for meaningful data). Act: Month 4-5 (implement changes in next supply reorder). | Add to P9B.03 quarterly survey: "Rate your unboxing experience (1-5)" + "What would make opening your StrideHer package even better?" (open text). Track: average unboxing score quarterly. Target: 4.5+.
10D.03: ECO-FRIENDLY PACKAGING OPTIONS — for when sustainability becomes a brand pillar
Eco Options | ECO-FRIENDLY PACKAGING ALTERNATIVES: 1. RECYCLED POLY MAILERS: made from 100% recycled plastic. Cost: $0.30-$0.40 (vs $0.25 standard). Suppliers: EcoEnclose, noissue, Stasherbag. 2. COMPOSTABLE MAILERS: plant-based (PLA corn starch), home-compostable. Cost: $0.50-$0.80 (2-3× standard). Suppliers: noissue, Hero Packaging. 3. FSC-CERTIFIED PAPER MAILERS: paper-based, recyclable curbside. Cost: $0.40-$0.60. Professional look. Suppliers: Pac Worldwide, EcoEnclose. 4. SOY-BASED INKS on insert cards and stickers: $0 extra if specified to your printer. 5. RECYCLED TISSUE PAPER: $0.02-$0.05 extra per sheet. Suppliers: noissue (custom printed on recycled paper). | Standard: $0.65 Recycled poly: $0.75-$0.85 Compostable: $1.10-$1.40 Paper mailer: $0.90-$1.15 | RECOMMENDATION: switch to RECYCLED POLY MAILERS on your next packaging reorder. Cost increase: $0.10-$0.15/order ($5-$7.50/month at 50 orders). Minimal cost impact, genuine sustainability improvement, and you can add "Shipped in 100% recycled packaging" to your product page + social media. Defer compostable/paper until: (1) revenue justifies the premium, OR (2) sustainability becomes a core brand pillar (P12A). IMPORTANT: never greenwash. Only claim what's TRUE. "Our mailers are 100% recycled plastic" is verifiable. "We're saving the planet" is not. Be specific and honest. | Recycled poly mailers: • Environmental benefit: diverts plastic from landfill • Marketing benefit: "Shipped in 100% recycled packaging" badge on product page • Customer perception: 73% of consumers prefer brands with sustainable packaging (NielsenIQ) • Cost: +$5-$7.50/month This is the highest-ROI sustainability move: low cost, genuine impact, clear marketing message. | Month 6+: switch to recycled poly mailers on next reorder. Year 2+: evaluate compostable or paper mailers. | SUPPLIER COMPARISON: EcoEnclose (ecoenclose.com): recycled poly mailers from $0.28/each at 500+. Custom printing available. US-based. noissue (noissue.co): compostable mailers from $0.55/each. Custom branded. Global shipping. Hero Packaging (heropackaging.com): compostable mailers from $0.45/each at 500+. AU-based but ships globally. Order samples from 2-3 suppliers before committing to a bulk order.
10D.04: BRANDED ELEMENTS — stickers, tape, and touches that cost pennies but feel premium
Branded Touches | LOW-COST BRANDED ELEMENTS: 1. BRANDED STICKER SHEET ($0.08-$0.12/sheet): 3-4 small StrideHer stickers per sheet. Customers stick them on water bottles, laptops, car bumpers = free brand exposure at every gym, race, and coffee shop. Order: StickerGiant, StickerMule, or Stickeryou — 500 sheets for $40-$60. 2. BRANDED TAPE ($0.03-$0.05/use): custom printed packing tape with StrideHer logo. Every package sealed with branded tape = branded from the outside before opening. Order: PackagingSupplies.com or noissue — 1 roll (100+ uses) for $15-$25. 3. BRANDED TISSUE PAPER ($0.08-$0.15/sheet): custom printed tissue wrap with subtle StrideHer pattern. The first thing seen when opening the mailer. Order: noissue — 250 sheets for $40-$60. 4. CARE CARD (permanent, every order) ($0.10): upgrade the thank-you card from "first 20 only" to a permanent "Welcome to StrideHer" card with: care instructions, QR to review page, referral prompt, and social handles. Goes in every single order. | Per order: Sticker sheet: $0.08-$0.12 Branded tape: $0.03-$0.05 Branded tissue: $0.08-$0.15 Care card: $0.10 All 4 added: $0.29-$0.42 extra/order Total packaging with all upgrades: $0.94-$1.07 (still under $1.50 target) | DON'T add all 4 at once. Prioritize by impact: #1 PRIORITY: sticker sheet ($0.08) — highest brand exposure ROI. Stickers on water bottles are seen by 50+ people per week. #2 PRIORITY: permanent care card ($0.10) — replaces the "first 20" thank-you card with an always-included brand touchpoint. #3 PRIORITY: branded tissue ($0.08) — elevates unboxing experience from "adequate" to "premium." #4 PRIORITY: branded tape ($0.03) — nice but lowest impact (mailer is sealed with sticker already). Add #1-#2 on your next supply order (Month 3-4). Add #3-#4 at Month 6+ when revenue comfortably covers the extra $0.20/order. | Sticker sheet ROI: $0.08 cost per sheet × 50 orders/month = $4/month If 30% of customers stick one on their water bottle: 15 stickers visible at gyms/races/parks per month = 15 micro- billboards seen by 50+ people each = 750+ impressions per month at $4 cost = $0.005 per impression (cheaper than ANY ad platform). | Month 3-4: add sticker sheet + care card. Month 6+: add branded tissue. Year 2+: add branded tape if budget allows. | ORDER QUANTITIES: Sticker sheets: 500 minimum (StickerMule: $40-$60). Lasts 10 months at 50 orders/month. Care cards: 500 minimum (Vistaprint or Moo: $30-$50). Same lifespan. Branded tissue: 250 sheets (noissue: $40-$60). Lasts 5 months. Total investment: $110-$170 for ~10 months of branded packaging elements. Amortized: $11-$17/month.

## 10C-D FOUNDER ACTIONS
P10C + P10D INVENTORY MANAGEMENT + PACKAGING — FOUNDER ACTION CHECKLIST
P10C: SKUs + counts + safety stock (1 hr setup, 10 min/week ongoing). P10D: packaging analysis + eco switch (1 hr evaluation, Month 3-6 implementation).
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
P10C: WEEK 4 — INVENTORY MANAGEMENT SETUP
🔴 #1 | Enter SKU codes for all 8 variants in Shopify + set safety stock alerts | 15 min | $0 | 1. Shopify → Products → StrideHer → Variants → for each variant: enter SKU per naming convention (SH-BLK-SM-V1 through SH-OCN-LX-V1) 2. Update your P7D.01 Google Sheets tracker with the same SKU codes 3. Set reorder point per SKU: 42 units (338 total ÷ 8 SKUs) 4. In Google Sheets: add conditional formatting — cell turns RED when "Available Now" drops below 42 5. Verify: Shopify inventory count matches Google Sheet count for all 8 SKUs
🟡 #2 | Establish Sunday evening inventory count ritual | 10 min/week (every Sunday, FOREVER) | $0 | Every Sunday evening (or integrate with P7D.01 Monday reconciliation): 1. Walk to shelving → physically count units per SKU position 2. Open Google Sheets tracker → compare physical count to "Available Now" column 3. If discrepancy: investigate (cancelled order not restored? Sample given but not logged? Mis-shelved variant?) 4. Update Google Sheets to match physical count 5. Log: date, total units remaining, weekly sell rate (orders this week from Shopify), days of inventory remaining 6. If ANY SKU is below 42 units (or total below 338): begin reorder planning per P7D.04
🟡 #3 | Create annual reorder calendar with seasonal adjustments | 1 hr | $0 | 1. Copy the 12-month calendar from Sheet 10C.01-04 2. Customize with YOUR launch month (adjust all months relative to when you actually launched) 3. Mark the CRITICAL ORDER WINDOWS: the 2-week periods where placing a PO avoids stockout 4. Add seasonal demand factors based on running industry data (Aug-Sep peak, Nov-Dec trough) 5. Pin to your wall next to the packing station 6. Review monthly: is actual sell rate tracking the seasonal forecast? Adjust future months if diverging.
P10D: MONTH 3-6 — PACKAGING OPTIMIZATION
🟡 #4 | Analyze packaging costs + collect unboxing feedback + order branded elements | 1-2 hrs evaluation + ordering | $110-$170 (sticker sheets + care cards + branded tissue) | 1. Review current packaging cost: verify it's at or below $0.65/order per Sheet 10D 2. Search reviews + social for packaging mentions → tally: positive, negative, absent 3. Add "unboxing experience (1-5)" question to next P9B.03 quarterly survey 4. ORDER (Month 3-4): sticker sheets (500 from StickerMule, $40-$60) + permanent care cards (500 from Vistaprint, $30-$50) 5. ORDER (Month 6+): branded tissue paper (250 from noissue, $40-$60) + recycled poly mailers (500 from EcoEnclose, $140-$200) 6. When new supplies arrive: integrate into the P10A.03 fulfillment SOP (add "insert sticker sheet + care card" to Step 5)
🟢 #5 | Switch to recycled poly mailers on next packaging reorder | 15 min (reorder) | $0.10-$0.15 extra/order | When current poly mailer stock runs low: 1. Order recycled poly mailers from EcoEnclose (ecoenclose.com) — same size (10×13"), 100% recycled content 2. Cost: $0.30-$0.40/each vs $0.25 standard (only $0.10-$0.15 extra per order) 3. Update product page: add "Shipped in 100% recycled packaging" badge 4. Update social bio: "🌿 Recycled packaging" 5. This is the lowest-effort, lowest-cost sustainability improvement that's genuinely impactful and marketable. No greenwashing — the claim is specific and verifiable.

## G7 Supply Chain Disruption
G7 REMEDIATION: SUPPLY CHAIN DISRUPTION CONTINGENCY SOP — 3 SCENARIOS WITH STEP-BY-STEP RESPONSE
Factory offline, freight delay >30 days, or customs hold >2 weeks. The safety stock buffer (338 units) buys time. This SOP tells you exactly what to do with that time.
Scenario | Trigger | Response Timeline | Step-by-Step Actions | Communication | Financial Impact | Cross-Reference
SCENARIO A — FACTORY GOES OFFLINE (fire, closure, government lockdown, bankruptcy, non-responsive)
A: FACTORY OFFLINE | Trigger: Factory is unreachable for 48+ hours via all channels (email, WeChat, Alibaba, phone) OR Factory confirms they cannot fulfill your PO (closure, capacity issue, force majeure). | Hour 0-48: Attempt contact Hour 48-72: Activate backup Day 4-7: Backup supplier quoted + sampled Day 7-14: Emergency PO placed Day 14-45: Emergency production Day 45-55: Air freight arrival | STEP 1 — VERIFY (Hours 0-48): • Email factory contact (primary + secondary contacts from P0D) • Message via WeChat/WhatsApp (Chinese suppliers are most responsive here) • Message via Alibaba platform (creates a timestamp record) • If using a sourcing agent: contact them for intel • Google the factory name + location for news (factory fire, local lockdown, etc.) STEP 2 — ACTIVATE BACKUP (Hours 48-72): • If no response after 48 hours via ALL channels: assume factory is offline • Open P0D supplier scouting list → contact Backup Supplier #2 and #3 • Send: P2A tech spec (Attachment A) + photos of current product + target quantity + "URGENT — can you quote and produce within 30 days?" • Request: quote, sample, and production timeline within 72 hours STEP 3 — EMERGENCY PO (Days 4-14): • Compare backup supplier quotes → select fastest + cheapest that meets quality requirements • If backup can match quality: place emergency PO for 200-400 units (enough to cover 2-3 months while you establish the new relationship) • Request a RUSH SAMPLE (air-mailed, 3-5 days) before committing to full PO — verify quality matches P2E standards • Pay: 50% deposit (higher than normal 30% — emergency premium for fast turnaround) STEP 4 — BRIDGE PERIOD: • Calculate: current inventory ÷ daily sell rate = days of coverage remaining • If >60 days remaining: standard sea freight for emergency PO (30-35 days production + 25-30 days shipping) • If 30-60 days remaining: air freight for at least 100 units of fast-selling SKUs ($3-$5/unit premium, 7-10 day delivery after production) • If <30 days remaining: air freight ENTIRE emergency PO + reduce ad spend to slow demand + add "limited availability" messaging STEP 5 — LONG-TERM RESOLUTION: • If original factory comes back online: evaluate whether to return or stay with backup • If original factory is permanently closed: transition fully to backup supplier • Update P0D supplier list with lessons learned • Consider dual-sourcing for future production runs (split POs between 2 factories to reduce single-point dependency) | TO BACKUP SUPPLIER: "We are an established running belt brand seeking an URGENT production partner. Our current factory is experiencing disruption. We need [X] units produced within 30 days. Full tech spec attached. Can you quote and provide a rush sample?" TO CUSTOMERS (only if stockout is imminent): Update product page: "Due to high demand, some sizes/colors are temporarily limited. Join our waitlist for priority notification." Do NOT mention factory issues publicly — customers don't need supply chain details. Frame it as "high demand." | COST IMPACT: Backup supplier may be 10-20% higher on COGS (rush premium + new relationship) Air freight: +$3-$5/unit (vs $2/unit sea) Total premium on 200-unit emergency order: $600-$1,400 extra Funded from: P7B.03 contingency reserve ($2,000) | P0D supplier scouting (backup list) P2A tech spec (send to backup) P7B.03 contingency reserve ($2,000) P7D reorder protocol P3B QC protocol (apply to backup supplier samples)
SCENARIO B — FREIGHT DELAY >30 DAYS (port congestion, carrier issue, vessel delay, route disruption)
B: FREIGHT DELAY >30 DAYS | Trigger: Freight forwarder confirms delivery will be 30+ days later than original ETA OR Tracking shows no movement for 14+ days with no explanation. | Day 0: Identify delay Day 1-2: Assess inventory runway Day 2-3: Decide: wait or air freight Day 3-7: Execute air freight if needed Day 7-10: Air shipment arrives | STEP 1 — ASSESS (Day 0-1): • Contact freight forwarder: "What is the updated ETA? What caused the delay? Is there anything we can do to expedite?" • Get the SPECIFIC new ETA (not "a few more weeks" — demand a date) • Calculate: current inventory ÷ daily sell rate = days of stock remaining • Calculate: if new ETA is accurate, will you stock out before arrival? STEP 2 — DECISION MATRIX (Day 1-2): • IF stock remaining > new ETA + 14 days buffer: → WAIT. The delay is annoying but not threatening. Monitor weekly. • IF stock remaining < new ETA (you WILL stock out before arrival): → AIR FREIGHT a partial emergency shipment. See Step 3. • IF stock remaining < 14 days AND new ETA is unknown: → EMERGENCY: air freight + reduce ad spend + activate waitlist. STEP 3 — AIR FREIGHT BRIDGE (Day 2-7): • Contact factory: "We need [100-200 units] of [FAST-SELLING SKUs] shipped via air freight immediately. Please prepare a separate shipment and provide air freight quote." • Air freight options: factory books directly (cheapest if they have a relationship) OR you book via a freight forwarder like Flexport, Freightos, or DHL Global Forwarding • Air freight timeline: 7-10 days factory-to-door (vs 55-65 days sea) • Air freight cost: $3-$5/unit for a running belt (lightweight product) • Ship ONLY the fast-selling SKUs (typically: Midnight Black S/M + L/XL = 40% of sales). Slow sellers can wait for sea shipment. STEP 4 — DEMAND MANAGEMENT (if stockout is imminent): • Reduce Meta + Google ad spend by 50% (slow demand to extend inventory) • Disable ads for sold-out variants (don't drive traffic to "out of stock") • Enable "Notify Me" on sold-out variant pages (Shopify: Back In Stock app, free) • Email waitlist when air freight arrives: "Back in stock! Your size is available — [LINK]" | TO FREIGHT FORWARDER: "Please provide updated ETA for shipment [TRACKING/BL NUMBER]. If delivery will exceed [DATE], please advise on expediting options including partial air freight." TO FACTORY (if air freight needed): "Due to sea freight delay, we need 100-200 units of [SKUs] shipped via air freight immediately. Please quote air freight cost and confirm units are available in your warehouse." TO CUSTOMERS: No proactive communication needed unless orders are affected. If a customer's order is delayed because their variant stocked out: "Your [COLOR] [SIZE] is temporarily out of stock due to shipping delays. We expect restocking within [X] days. Options: (1) wait and we'll ship as soon as available, (2) switch to an available color, or (3) full refund." | Air freight premium: $3-$5/unit × 100-200 units = $300-$1,000 Reduced ad spend saves: $200-$400 during delay period Net extra cost: $100-$600 Funded from: P7B.03 contingency reserve OR: absorbed by reduced ad spend savings. | P7D.03 inventory turnover (days of stock calc) P7D.04 reorder timing P7B.03 contingency reserve P3C shipping logistics (freight forwarder contact)
SCENARIO C — CUSTOMS HOLD >2 WEEKS (documentation issue, inspection, duty dispute, HS code challenge)
C: CUSTOMS HOLD >2 WEEKS | Trigger: Shipment has been at customs for 14+ days with no release OR Customs broker reports an issue requiring resolution (missing docs, HS code dispute, inspection hold). | Day 0: Broker alerts you to hold Day 0-1: Provide any requested docs Day 1-7: Broker works with customs Day 7-14: Escalate if not resolved Day 14+: Air freight backup if still stuck | STEP 1 — DIAGNOSE (Day 0-1): • Contact customs broker IMMEDIATELY: "Why is the shipment held? What documents or actions are required for release?" • Common hold reasons and fixes: a) MISSING COMMERCIAL INVOICE → provide invoice from supplier (should have been included with shipment — P3C customs docs) b) HS CODE DISPUTE → broker argues your classification (4202.92). Provide: product photos, material composition, intended use description c) RANDOM INSPECTION → no action needed, just wait (typically 3-7 extra days) d) DUTY RATE DISPUTE → broker negotiates. Worst case: pay the assessed duty now, file a protest later for refund e) COUNTRY OF ORIGIN VERIFICATION → provide: supplier's commercial invoice showing Chinese origin, factory certificate of origin if available STEP 2 — PROVIDE DOCUMENTS (Day 0-1, SAME DAY as request): • Every hour of delay = one more hour your shipment sits. Respond to EVERY customs request within 4 hours. • Have ready at all times: commercial invoice (from supplier), packing list, bill of lading, certificate of origin (request from supplier), product spec sheet (P2A) STEP 3 — ESCALATE (Day 7-14 if not resolved): • If broker hasn't resolved within 7 days: contact a SECOND customs broker for a second opinion • If the issue is a duty rate dispute: consider paying the assessed rate (even if higher than expected) to release the goods, then file a formal protest with CBP for a refund of the overpayment • If the issue is an inspection: ask broker for an estimated release date. Inspections rarely exceed 2-3 weeks. STEP 4 — BACKUP (Day 14+ if still stuck): • If customs hold exceeds 3 weeks with no clear resolution timeline: activate Scenario B air freight protocol • Factory ships a fresh 100-200 unit air freight shipment directly to you (bypassing the stuck sea shipment) • The stuck shipment will eventually clear — treat it as delayed inventory, not lost inventory • Do NOT abandon the stuck shipment (the goods are yours once you've paid the supplier) | TO CUSTOMS BROKER: "Our shipment [BL NUMBER / ENTRY NUMBER] has been held at [PORT] for [X] days. Please advise: (1) specific reason for the hold, (2) what documentation or action is required for release, (3) estimated timeline for resolution. This is urgent — we need the goods to fulfill customer orders." Provide all requested documents within 4 hours of request. Speed of response directly correlates with speed of release. TO FACTORY (if backup air freight needed): Same as Scenario B Step 3. | Customs hold costs: Direct: $0 (goods are held, not charged — you pay duties on release) Indirect: demurrage/storage at port: $50-$200 if hold exceeds 5 free days (check with broker) Air freight backup (if activated): $300-$1,000 per Scenario B. Overpaid duties (if dispute): recoverable via CBP protest (6-12 month process). | P3C shipping logistics (customs broker contact info) P8C.04 product labeling (HS code 4202.92 verification) P7C.03 customs obligations P10B.02 customs documentation (CN22/CN23)
PREVENTION: ACTIONS TO REDUCE DISRUPTION PROBABILITY
PREVENTION | Ongoing (build into standard operations) | N/A | PROACTIVE MEASURES TO REDUCE DISRUPTION RISK: 1. DUAL SOURCING (Year 2+): split production between 2 suppliers (70/30 split). If one goes offline: the other can absorb 100% temporarily. Cost: 5-10% higher COGS (smaller orders per supplier). Value: eliminates single-point factory risk. 2. SAFETY STOCK DISCIPLINE: maintain the 338-unit safety stock (P10C.03) — this provides 45-60 days of buffer that absorbs most disruption timelines. 3. DOCUMENT READINESS: keep a "customs emergency file" in Google Drive with: current commercial invoice, packing list template, certificate of origin, product spec sheet, and customs broker contact. When a customs request comes: you respond in minutes, not days. 4. SUPPLIER RELATIONSHIP: maintain monthly check-ins with your factory contact (even when no PO is active). A strong relationship means: they warn you about potential disruptions (holiday shutdowns, material shortages) BEFORE they affect your timeline. 5. SEASONAL BUFFER: for peak season (Aug-Sep), add 30 days to your normal reorder lead time. Place the PO earlier to absorb potential delays during the busiest shipping season. 6. FREIGHT INSURANCE: maintain cargo insurance (P7D.02 item 4, ~$48 per shipment). Covers: loss or damage during transit. Does NOT cover: customs holds or delays (those are resolved, not insured). | QUARTERLY CHECK: Add to P7B.04 monthly review (quarterly frequency): "Supply chain health check: • Factory responsive? Y/N • Backup supplier contacts current? Y/N • Customs docs file complete? Y/N • Safety stock at target? Y/N • Insurance current? Y/N" 5-minute check that prevents multi-week disruptions. | Prevention cost: $0 for most measures. Dual sourcing: 5-10% COGS premium (Year 2+ only). | P0D backup supplier list P10C.03 safety stock (338 units) P7D.02 landed cost (insurance) P3C freight forwarder P8D.01 supplier agreement (Clause 10: force majeure)