## READ THIS FIRST
P13 FOUNDER QUICK-START SEQUENCING GUIDE — READ THIS BEFORE OPENING ANY OTHER FILE
This is your execution GPS. 16 weeks from today to launch and beyond. Every action is extracted from the 57 GTM workbooks and sequenced in the order you should do them.
HOW TO USE THIS GUIDE
This guide extracts the CRITICAL-PATH actions from all 57 StrideHer GTM workbooks into a single week-by-week calendar. It tells you exactly what to do each week and which workbook has the detailed instructions.
| THE 4 PHASES | Duration | Total Hours | What Gets Done | Key Milestone
🔴 | PHASE 1: FOUNDATION (Weeks -4 to -1, pre-launch) | 4 weeks | 40-50 hrs | LLC, bank account, supplier PO, Shopify store, brand assets, email list, content batch, legal pages, trademark filing | Store is live (password-protected), inventory ordered, 200+ email waitlist built
🟡 | PHASE 2: PRE-LAUNCH (Weeks -2 to 0) | 2 weeks | 20-25 hrs | Pre-launch campaign, community building, influencer seeding, ad account setup, fulfillment station, final QA | Inventory received + inspected, 500+ waitlist, ads ready to activate, station tested
🟢 | PHASE 3: LAUNCH (Weeks 1 to 4) | 4 weeks | 25-30 hrs | Launch day execution, first orders, ad optimization, review collection, support operations, weekly KPI tracking | 50+ orders, 10+ reviews, ads optimized, fulfillment rhythm established
🔵 | PHASE 4: OPTIMIZE (Weeks 5 to 12) | 8 weeks | 30-40 hrs | Amazon launch, A/B testing, monthly financial review, referral program, VIP segment, social commerce, 2nd content batch | Breakeven trajectory confirmed, 100+ orders, 50+ reviews, multi-channel revenue
RULES
1. DO TASKS IN ORDER. The sequence matters — each week builds on the previous. Skipping ahead creates dependencies that break.
2. EACH TASK REFERENCES A WORKBOOK. Open that workbook for the full step-by-step. This guide tells you WHAT and WHEN. The workbooks tell you HOW.
3. 🔴 = MUST DO THIS WEEK (blocking). 🟡 = SHOULD DO (important but 3-day flex). 🟢 = CAN FLEX (do when time allows within the phase).
4. TIME ESTIMATES ARE REAL. If a task says "2 hrs" it means 2 hrs of focused work. Budget accordingly. The full plan requires 8-12 hrs/week alongside other commitments.
5. CHECK OFF AS YOU GO. Print this sheet or copy to Google Sheets. Check each task as complete. If you fall behind: skip 🟢 tasks, never skip 🔴 tasks.

## PHASE 1 Foundation
PHASE 1: FOUNDATION — WEEKS -4 TO -1 (4 weeks before launch)
Build the legal, financial, product, and digital infrastructure. By the end of Phase 1: your store is live (password-protected), inventory is ordered, and your waitlist is growing.
P | Task | Time | Cost | Source Workbook | Depends On | Done? | Notes
WEEK -4: LEGAL + FINANCIAL FOUNDATION
🔴 | Form Wyoming LLC + apply for EIN | 1-2 hrs +wait | $100-$300 | P8A → Sheet 8A.01-02 P7A → Sheet 7A.01 | Nothing — start here |  | EIN takes 4-6 weeks for non-US applicants. Apply NOW. Everything else can proceed in parallel.
🔴 | Choose registered agent (Northwest RA recommended) | 30 min | $125/yr | P8A → Sheet 8A.01-02 | With LLC filing |  | The registered agent provides the US address you need for banking, Shopify, and legal correspondence.
🔴 | File trademark application for "StrideHer" (USPTO TEAS Plus) | 30-45 min | $250 | P8B → Sheet 8B.01-02 | LLC name needed for owner field |  | File early — 8-12 months to register. Your rights begin on the FILING date. Use ™ symbol immediately.
🟡 | Set up Wave accounting + chart of accounts | 30 min | $0 | P7A → Sheet 7A.03-04 | LLC name |  | Free accounting software. 24 expense categories pre-defined in P7A.04.
🟡 | Build unit economics model with YOUR actual costs | 1-2 hrs | $0 | P7B → Sheet 7B.01 | Supplier quotes (can estimate, refine later) |  | The model that tells you if the business math works. $34.99 retail, ~$6 COGS, ~$17.48 contribution margin.
🟡 | Build 12-month cash flow forecast (3 scenarios) | 2-3 hrs | $0 | P7B → Sheet 7B.02-03 | Unit economics model |  | Conservative, moderate, optimistic. Find your cash danger zone. Allocate $10K budget per P7B.03.
🟢 | Add © notice to website footer + Terms of Use prep | 5 min | $0 | P8B → Sheet 8B.03-04 | Website exists (do after P4A) |  | Copyright is automatic. The notice strengthens enforcement.
🟢 | Enable 2FA on ALL business accounts (as you create them) | 5 min per account | $0 | P8C → Sheet G5 | Each account created |  | Prevents 99% of breaches. Do for: email, Shopify (Week -3), Klaviyo, Meta, bank. Non-negotiable.
WEEK -3: PRODUCT + SUPPLIER + STORE FOUNDATION
🔴 | Contact top 3 suppliers from P0D + send RFQ with P2A tech spec | 2-3 hrs | $0 | P0D → Sheet 0D.03 P2A → Sheet 2A.01 P8D → Sheet 8D.01 | Tech spec finalized (P2A) |  | Send the supplier agreement (P8D.01) alongside your RFQ. Request: quote, sample, and timeline.
🔴 | Open business bank account (Mercury — accepts EIN without SSN) | 30 min +wait | $0 | P7A → Sheet 7A.02 | EIN received (or in progress) |  | Mercury can sometimes onboard with EIN application receipt before the actual EIN letter arrives. Try.
🔴 | Set up Shopify store (Basic plan) + install Dawn theme | 2-3 hrs | $29/mo | P4A → Sheet 4A.01-02 | Bank account (for Shopify Payments) |  | Password-protect immediately. Build the store while password is up. Don't go live until Week 0.
🔴 | Configure Shopify Payments + PayPal | 30 min | $0 | P7C → Sheet 7C.01 | Shopify store + bank account |  | Multi-currency auto-detect for UK (£), CA ($CAD), EU (€), AU ($AUD). PayPal for the 10-15% who prefer it.
🟡 | Build product page: photos, copy, variants, pricing | 3-4 hrs | $0 | P4A → Sheet 4A.03-04 P1D → Photography P2D → Size Guide | Shopify store + product photos |  | Lead with the benefit: "The first running belt designed for women's bodies." 5+ images. Size guide linked.
🟡 | Set up Klaviyo + create Welcome Flow (3 emails) | 1-2 hrs | $0 | P4B → Sheet 4B.01-02 | Shopify store (integration) |  | Welcome Flow triggers on email signup. 3 emails ready. This captures every visitor who gives their email.
🟡 | Install GA4 + Meta Pixel + Microsoft Clarity | 1 hr | $0 | P4C → Sheet 4C.01-03 | Shopify store |  | Analytics from Day 1. Without this: you're flying blind. GA4 for traffic, Pixel for ads, Clarity for recordings.
🟢 | Set up Wise account for supplier payments | 15 min | $0 | P7C → Sheet 7C.01 | Bank account |  | Saves 2-4% FX on every supplier payment vs bank wires. Connect to business bank.
WEEK -2: CONTENT + COMMUNITY + INVENTORY ORDER
🔴 | Approve supplier sample + place first PO (600 units) | 1 hr (decision) | $3,600 (30% deposit now) | P3A → Sheet 3A.01-03 P2B → Prototyping | Sample received + approved |  | The biggest financial commitment. Pay 30% deposit via Wise. 70% before shipping. 35-day production start.
🔴 | Create 4 legal pages: Privacy, Terms, Returns, Shipping | 2-3 hrs | $0 | P8C → Sheet 8C.01-02 | Shopify store |  | Required by Shopify, Meta Ads, and Google. Use Shopify's generator + customize per P8C templates.
🔴 | Set up Instagram + TikTok business accounts | 30 min | $0 | P5B → Sheet 5B.01 | Brand assets (P1B logo, colors) |  | Bio: "Gear for women who run. Every pace. Every body. Every mile. 🏃‍♀️" Link to coming-soon or waitlist.
🟡 | Batch-create first 20 content pieces (photos + short videos) | 4-5 hrs | $0-$50 | P5B → Sheet 5B.04 P1D → Photography | Product sample in hand |  | 20 pieces = 2-3 weeks of content. Flat lays, on-body, packing, BTS. Film on your phone. Canva for graphics.
🟡 | Launch email waitlist: "Coming Soon" landing page or popup | 1 hr | $0 | P1E → Sheet 1E.01-03 P6A → Sheet 6A.01 | Klaviyo + Shopify store |  | Goal: 200+ signups before launch. Share link on social, DM running friends, post in running groups.
🟡 | Begin posting on social (3-5×/week) to build pre-launch audience | Ongoing 30 min/day | $0 | P5B → Sheet 5B.03-04 | Social accounts + content batch |  | Start building the audience NOW. Don't wait for launch. Running tips, founder story, product teases.
🟢 | Configure international shipping zones (UK, CA, EU, AU) | 30 min | $0 | P7C → Sheet 7C.02 P10B → Sheet 10B.01 | Shopify store |  | Flat rates: UK $14.99, CA $12.99, EU $16.99, AU $16.99. Free US shipping.
🟢 | Set up SEO foundations: meta titles, descriptions, blog structure | 1 hr | $0 | P4D → Sheet 4D.01-02 | Shopify store + product page |  | Target: "women's running belt" (primary), "running belt for marathon" (secondary). Optimize product page title + meta.
WEEK -1: FINAL PREP + FULFILLMENT STATION + PRE-LAUNCH CAMPAIGN
🔴 | Build home fulfillment station: table, shelving, labels, supplies | 1-2 hrs | $50-$250 | P10A → Sheet 10A.01-02 | Inventory arriving soon |  | Table + shelving + labeled SKU positions + supplies within arm's reach. Photo the setup for reference.
🔴 | Configure Shopify Shipping: label format, USPS rates, pickup schedule | 30 min | $0 | P10A → Sheet 10A.01-02 | Shopify store |  | Buy labels in Shopify (20-40% discount vs USPS retail). Set up daily USPS home pickup (free).
🔴 | Write fulfillment SOP (the delegation document) | 1 hr | $0 | P10A → Sheet 10A.03-04 | Fulfillment station ready |  | 10 steps, 90 sec/order. Print and post at your station. This is the doc you hand a future VA on Day 1.
🔴 | Ship 5-10 influencer seeding packages (P5A Wave 1) | 1-2 hrs | $30-$60 (product + shipping) | P5A → Sheet 5A.01-04 P8D → Sheet 8D.02 | Product samples in hand |  | Include gifting agreement card. Target: nano/micro running influencers. Goal: 3-5 post about StrideHer pre-launch.
🟡 | Set up Meta Ads account + create first 3 ad sets (DON'T launch yet) | 1-2 hrs | $0 (setup only) | P6C → Sheet 6C.01-03 | Meta Pixel installed (P4C) |  | Build the ads now. Save as drafts. Activate on Launch Day. 3 audiences: interest-based, LAL, broad.
🟡 | Set up Google Ads account + create PMax campaign (DON'T launch yet) | 1 hr | $0 (setup only) | P6D → Sheet 6D.01-02 | GA4 + product feed ready |  | Google Shopping via PMax. Draft the campaign. Activate Week 2 (after Meta data is flowing).
🟡 | Install Judge.me + configure Day 14 auto-review-request email | 30 min | $0 | P9B → Sheet 9B.01-02 | Shopify store |  | Ready to collect reviews from Day 1 orders. Auto-request fires 14 days after delivery.
🟢 | Create return tracker Google Sheet + exchange-first protocol | 30 min | $0 | P9D → Sheet 9D.01-02 | Returns policy published (P8C) |  | Track every return by reason category. Patterns → product improvements.
🟢 | Install cookie consent banner (GDPR compliance) | 15 min | $0 | P8C → Sheet 8C.01-02 | Shopify store |  | Pandectes free app or Shopify built-in. Show to EU visitors only.

## PHASE 2 Pre-Launch
PHASE 2: PRE-LAUNCH — WEEKS -1 TO 0 (final countdown)
Inventory arrives. Station tested. Community primed. Ads ready. This is the "ignition sequence" — everything is GO or NO-GO before you flip the switch.
P | Task | Time | Cost | Source Workbook | Depends On | Done? | Notes
WEEK 0-MINUS: INVENTORY ARRIVAL + FINAL QA + PRE-LAUNCH EMAILS
🔴 | Receive inventory: unbox, count against packing list, inspect 10% sample | 2-3 hrs | $0 | P3C → Sheet 3C.04 P3B → Sheet 3B.01-03 | PO shipped + arrived |  | Count EVERY carton. Inspect 60 units (10% of 600). Check: zippers, stitching, grip dots, buckle, sizing. Log any defects.
🔴 | Stock fulfillment shelving: organize by SKU, verify counts match Shopify | 1 hr | $0 | P10A → Sheet 10A.01 P7D → Sheet 7D.01 | Inventory received + inspected |  | 75 units per SKU position. Update Shopify inventory counts. Update Google Sheets backup tracker.
🔴 | Process 3 test orders: full workflow from Shopify → pack → label → "ship" | 30 min | $15 (3 labels) | P10A → Sheet 10A.03-04 | Fulfillment station stocked |  | Ship to yourself or friends. Time yourself: target 90 sec/order. Fix any workflow gaps BEFORE real orders.
🔴 | Send pre-launch email sequence: 7 emails over 14 days | 30 min to schedule | $0 | P6A → Sheet 6A.01-04 | Klaviyo + email list (200+ subs) |  | Day -14 through Day 0. Building anticipation: founder story, product reveal, sizing guide, countdown, founding member offer (HERSTRIDE20).
🔴 | QA checklist: verify EVERYTHING works before removing password | 1-2 hrs | $0 | P6A → Sheet 6A.06 | ALL above completed |  | The 27-point QA checklist from P6A: checkout works, emails trigger, tracking sends, payment processes, mobile looks good, legal pages linked, size guide works, analytics firing.
🟡 | Prepare Launch Day social content: 5-7 posts + stories scheduled | 1-2 hrs | $0 | P6B → Sheet 6B.04 P5B → Content | Content batch (P5B Week -2) |  | Schedule via Later or manually. Launch day: 3 feed posts + 10 stories throughout the day.
🟡 | Write first 20 handwritten thank-you notes (ready to include in orders) | 30 min | $5 (cards) | P6B → Sheet 6B.03 | Note cards purchased |  | "Thank you for being one of our first customers. Your order means the world. — [NAME], Founder." Personal. Not scripted.
🟡 | Brief ambassadors/influencers on launch date + ask them to post | 30 min | $0 | P5A → Sheet 5A.04 P5E → Sheet 5E.03 | Influencer packages delivered (Week -1) |  | DM each: "We launch [DATE]! Would mean everything if you posted that day. Here's a discount code for your followers: HERSTRIDE20."
🟢 | Set up Shopify Inbox live chat on product page | 15 min | $0 | P9A → Sheet 9A.04 | Shopify store |  | Enable ONLY if you can respond within 5 min during business hours. After-hours: auto-reply with FAQ links.
🟢 | Test international shipping: verify customs form auto-generates correctly | 15 min | $0 | P10B → Sheet 10B.02 | Shopify Shipping configured |  | Create a test international label → verify: HS code 4202.92, "Made in China," declared value $34.99.

## PHASE 3 Launch
PHASE 3: LAUNCH — WEEKS 1-4 (go live and establish rhythm)
Remove the password. First orders. First reviews. First ad data. First support tickets. Establish the daily/weekly operating rhythm that carries the business forward.
P | Task | Time | Cost | Source Workbook | Depends On | Done? | Notes
WEEK 1: LAUNCH DAY + FIRST ORDERS
🔴 | LAUNCH DAY: remove password, send launch email, activate Meta ads, post social blitz | 2-3 hrs (launch day) | $10-$15/day ads start | P6B → Sheet 6B.01-04 P6A → Sheet 6A.05 P6C → Sheet 6C.01 | QA passed (Phase 2) |  | The hour-by-hour ops manual from P6B. Morning: remove password + send email. Midday: activate ads. Afternoon: social blitz. Evening: check orders + respond to every comment.
🔴 | Fulfill all orders same-day (2 PM batch) or next-morning (9 AM batch) | 15-45 min per batch | $4-$5.50 per label | P10A → Sheet 10A.03-04 | Orders received |  | Follow the 10-step SOP. Include handwritten notes for first 20 orders. Ship via Shopify Shipping labels.
🔴 | Respond to every support email + chat within 4 hours | 30-60 min /day | $0 | P9A → Sheet 9A.01-02 (20 templates) | Support email set up |  | Use the 20 templates from P9A. Sizing questions = #1 (40% of tickets). Personalize each response.
🟡 | Monitor Meta Ads: check delivery, CTR, cost daily for first 7 days | 15 min/day | $0 | P6C → Sheet 6C.04-05 | Ads launched |  | If an ad set spends $20 with 0 purchases: pause and replace creative. If CTR <0.5%: swap image/video.
🟡 | Post daily on IG + TikTok for first 7 days (then settle to 4-5×/week) | 30 min/day | $0 | P5B → Sheet 5B.03-04 | Content batch |  | Launch week posting is DAILY. Order packing videos, "first order!" celebrations, founder journal. Authentic > polished.
🟡 | Begin charitable giving: sponsor 1-2 women's race entries | 30 min | $25-$50 | P12B → Sheet P12B-C | Revenue starting |  | Start the purpose from Day 1. Share the story on social: "StrideHer sponsored [NAME]'s first 5K entry." Costs $25.
🟢 | If <5 orders by Day 7: activate Launch Rescue Protocol | 2-3 hrs (if needed) | $0 | P6E → Sheet G3 Launch Rescue | Day 7 data |  | Don't panic. Diagnose: traffic problem or conversion problem? Follow the 4-step rescue decision tree.
WEEK 2: OPTIMIZATION + GOOGLE ADS
🔴 | Weekly KPI review #1: pull all 15 metrics from P6E.01 dashboard | 30 min | $0 | P6E → Sheet 6E.01 | Week 1 data available |  | Sessions, orders, conversion rate, revenue, AOV, CAC, ad ROAS, email subscribers, social followers. THE weekly ritual from now on.
🔴 | Activate Google Ads (PMax Shopping campaign) at $13/day | 30 min | $13/day | P6D → Sheet 6D.01-02 | Meta Ads running 1+ week |  | Google captures search intent that Meta misses. Start PMax with product feed. Let it run 7 days before optimizing.
🟡 | Respond to first reviews (within 48 hours of each) | 10 min per review | $0 | P9B → Sheet 9B.03-04 | Reviews arrive (Judge.me) |  | Use star-specific templates. Reference SPECIFIC details from each review. Your response is read by 500+ future visitors.
🟡 | Reconcile inventory: physical count vs Shopify (Sunday evening) | 10 min | $0 | P7D → Sheet 7D.01 P10C → Sheet 10C.01-04 | Fulfillment active |  | First of the weekly counts. Log: date, total units, sell rate, days remaining. THE inventory ritual from now on.
WEEKS 3-4: RHYTHM ESTABLISHMENT
🔴 | Weekly KPI reviews #2 + #3 | 30 min each | $0 | P6E → Sheet 6E.01 | Ongoing |  | Compare to Week 1. Trends forming: which ad is winning? Which SKU sells fastest? What's the conversion rate stabilizing at?
🔴 | Continue daily fulfillment + support operations | 30-60 min/day | Ongoing | P10A, P9A | Ongoing |  | This is now your DAILY ROUTINE: 9 AM batch → support emails → midday support → 2 PM batch → evening support.
🟡 | Begin P6E A/B testing: run first test (product page title or image) | 1 hr setup | $0 | P6E → Sheet 6E.02 | 100+ sessions of data |  | Test ONE variable. Run for 7 days minimum. The first test sets the optimization cadence.
🟡 | Send 2nd wave of influencer seeding packages (5-10 more) | 1-2 hrs | $30-$60 | P5A → Sheet 5A.04 | Wave 1 results visible |  | Based on Wave 1 results: more of what worked, less of what didn't. Include content usage agreement card.
🟢 | Attend 1 local parkrun wearing the belt + hand out 5 discount cards | 2 hrs | $5 cards | P5C → Sheet 5C.01-03 | Belt in hand |  | The grassroots play. Wear it. Talk about it. Hand out "PARKRUN15" discount cards to interested runners.

## PHASE 4 Optimize
PHASE 4: OPTIMIZE — WEEKS 5-12 (scale what works, fix what doesn't, expand channels)
Amazon launch, financial reviews, retention systems, social commerce, content scaling. The business transitions from "launched" to "operating."
P | Task | Time | Cost | Source Workbook | Depends On | Done? | Notes
WEEK 5-6: AMAZON + FINANCIAL REVIEW + RETENTION
🔴 | End of Month 1: first monthly financial review (P&L, cash, unit economics, CAC, inventory) | 2-3 hrs | $0 | P7B → Sheet 7B.04-05 | Month 1 data complete |  | The monthly financial ritual. 5 reports. Write: "This month I learned: ___. Next month I will: ___. Biggest risk: ___."
🔴 | Monthly return summary #1: total returns, rate, top reasons, product issues | 30 min | $0 | P9D → Sheet 9D.03-04 | Month 1 returns logged |  | Feed findings into P3D.03 v2 spec. If "wrong size" >50% of returns: size guide needs immediate improvement.
🔴 | Launch Amazon listing (if 30+ days of Shopify data + trademark filed) | 1-2 days | $40/mo + Vine + PPC | P4E → Sheet 4E.01 P11B → Sheet 11B.01 | 30+ Shopify sales + TM filed |  | FBA: ship 100-200 units to Amazon warehouse. Vine: 30 units for reviews. PPC: $10-$15/day. This captures search buyers Shopify misses.
🟡 | Set up TikTok Shop + Instagram Shopping | 2-3 hrs | $0 | P11B → Sheet 11B.04-05 | 1,000+ TikTok followers + Shopify catalog |  | Zero-friction purchase: content IS the store. Tag products in existing and future posts. 5% TikTok commission, 0% IG.
🟡 | Create VIP customer segment in Klaviyo + VIP welcome flow | 45 min | $0 | P9C → Sheet 9C.01-03 | 2+ repeat customers OR founding members |  | Criteria: 2+ orders OR $60+ spent OR founding member. Exclusive 15% VIP code, early access, quarterly founder updates.
🟡 | Create 2-belt bundle offer on Shopify ("Buy 2, Save $10") | 30 min | $0 | P11A → Sheet 11A.03-05 | Product page live |  | Highest-margin growth lever available NOW. "One for training, one for race day." $59.99 for 2 (vs $69.98). $18.99 pure incremental profit.
🟢 | Verify referral program (Smile.io) is fully operational | 15 min | $0 | P9C → Sheet 9C.01 | Smile.io installed (P5E) |  | 6-point verification: popup, Email 3, confirmation page, customer account, tracking. All must pass.
WEEKS 7-8: CONTENT SCALING + WHOLESALE PREP
🔴 | Weekly KPI reviews #5-#6 (continuing the ritual) | 30 min each | $0 | P6E → Sheet 6E.01 | Ongoing |  | By now you have 6 weeks of data. Trends are clear. Which ad wins? Which channel converts? Which SKU leads?
🔴 | End of Month 2: second monthly financial review | 2-3 hrs | $0 | P7B → Sheet 7B.04-05 | Month 2 data |  | Compare to Month 1. Revenue growing? Margin stable? CAC declining? On track for breakeven?
🟡 | Batch-create second content batch (20 more pieces) | 4-5 hrs | $0 | P5B → Sheet 5B.04 | First batch depleted |  | Include customer UGC (repost with permission), race day content, behind-the-scenes of growth, and product-focused videos.
🟡 | Create wholesale one-sheet PDF in Canva | 1-2 hrs | $0 | P11B → Sheet 11B.01-03 | 50+ reviews + proven PMF |  | Hero image, 3 selling points, wholesale pricing ($17.50), MOQ 12, terms. Email to 5 specialty running stores.
🟡 | Send first quarterly customer survey (NPS + feedback) | 1 hr | $0 | P9B → Sheet 9B.03-04 P9C → Sheet 9C.04-05 | 50+ customers |  | 6 questions. NPS, product love, "change one thing," wish product, discovery channel, repurchase intent. Target: NPS 30+.
🟢 | Enhance size guide with fit photos from early customers | 1 hr | $0 | P9A → Sheet 9A.05 | Customer photos collected |  | Ask 5 customers for a photo wearing the belt. Real bodies > models. Each photo reduces returns.
WEEKS 9-12: SCALE + MULTI-CHANNEL + OPTIMIZATION
🔴 | Monthly financial reviews #3 (Month 3 is the breakeven trajectory checkpoint) | 2-3 hrs | $0 | P7B → Sheet 7B.04-05 | Month 3 data |  | If trending toward Month 5-6 breakeven: on track. If not: diagnose (revenue too low? costs too high?) and adjust per P7B framework.
🔴 | Create Day 45 cross-sell email flow in Klaviyo | 30 min | $0 | P9C → Sheet 9C.01-03 | 45+ days since first orders |  | Targets customers who bought once, 45 days ago, haven't reordered. "Your StrideHer needs a running buddy 🏃‍♀️🏃‍♀️"
🟡 | Apply to 2-3 race expo vendor opportunities | 1-2 hrs | $0 (application) | P11B → Sheet 11B.04-05 | 50+ reviews + proven product |  | Target half/full marathon expos within driving distance. Booth: $300-$800. Applications open 3-6 months before events.
🟡 | Mine reviews for marketing language (at 20+ reviews milestone) | 30 min | $0 | P6E → Sheet 6E.04 P9B → Reviews | 20+ reviews accumulated |  | Top 3 praise themes = your primary ad copy. Customer words > your words. Update Meta/Google ad creative.
🟡 | Begin building 2-3 running media relationships | 30 min/month | $0 | P12C → Sheet P12B-C | Brand has traction + story to tell |  | Follow editors at Women's Running, Runner's World. Comment on articles. Share their content. Plant seeds for Month 6-9 pitch.
🟡 | Compile operations manual (SOPs from P9A, P10A, P9D into Google Drive folder) | 2-3 hrs | $0 | P11D → Sheet P11D | All SOPs written across P9-P10 |  | The DELEGATION ENGINE. One folder with every SOP. When you hire a VA: hand them this folder on Day 1.
🟢 | Run 2-week time audit: track where your hours go | Track for 2 weeks | $0 | P11D → Sheet P11D | Week 9+ |  | Categorize: fulfillment, support, content, marketing, ops, admin. Highest hours × highest delegability = first hire role.
🟢 | Analyze international sales data: which countries are growing? | 30 min | $0 | P11C → Sheet 11C.01-02 | 3+ months of international orders |  | Shopify → Analytics → Sales by Country. UK, CA, AU should be top 3. If UK leads: prioritize UK localization.
🟢 | Write 3-year vision + annual milestone calendar | 2 hrs | $0 | P12C → Sheet P12B-C | 3 months of real data + reflection time |  | Year 1: foundation. Year 2: expansion. Year 3: authority. Pin above your packing station. Read every morning.

## ONGOING RITUALS
RECURRING RITUALS — THE RHYTHMS THAT RUN THE BUSINESS AFTER WEEK 12
Daily, weekly, monthly, and quarterly tasks that continue FOREVER. Print this. Make it habit. The business is the sum of these rituals.
Frequency | Ritual | Time | Source Workbook | When Exactly | Purpose
DAILY (every business day)
DAILY | Fulfillment batch #1: process overnight + morning orders | 15-30 min | P10A SOP | 9:00 AM | Ship orders. Follow the 10-step SOP. Same-day for pre-2PM orders.
DAILY | Support check #1: respond to emails + chat | 15-20 min | P9A Templates | 9:30 AM | Use templates. <4 hour response target. Label each email by category.
DAILY | Support check #2 + fulfillment batch #2 | 15-30 min | P10A + P9A | 2:00 PM | Ship afternoon orders. Respond to midday emails.
DAILY | Support check #3: clear inbox to zero | 10 min | P9A | 6:00 PM | Final check. Everything responded to. Inbox zero.
WEEKLY (every Monday)
WEEKLY | KPI review: pull 15 metrics from P6E.01 dashboard | 30 min | P6E KPIs | Monday AM | Sessions, orders, conversion, revenue, AOV, CAC, ad ROAS, email subs, social followers, reviews, inventory.
WEEKLY | Inventory reconciliation: physical count vs Shopify | 10 min | P7D / P10C | Sunday PM or Monday AM | Count each SKU. Compare to Shopify. Log: date, total units, sell rate, days remaining. Check reorder point.
WEEKLY | Ad optimization: review Meta + Google performance, adjust | 20 min | P6C / P6D | Monday AM (after KPIs) | Kill underperformers, scale winners, test new creative if needed.
WEEKLY | Social engagement: respond to comments, DMs, engage with 20 accounts | 20 min | P5B | Throughout week | Community building. Comment on running accounts. Respond to every comment on your posts.
MONTHLY (last day of each month)
MONTHLY | Financial review: P&L, cash position, unit economics actual vs model, CAC by channel, inventory value | 2-3 hrs | P7B.04 | Last day of month | The 5-report financial ritual. Write 3 sentences: learned, will do, biggest risk.
MONTHLY | Return summary: total returns, rate, reasons, product issues → v2 spec | 30 min | P9D.04 | Last day of month | Feed return patterns into product improvements. Target: <5% → <3% return rate trajectory.
MONTHLY | Margin tracker: actual vs projected per order type | 30 min | P7C.04 | Last day of month | Blended margin target: 48-55%. Check for discount creep, shipping cost increases, return rate changes.
MONTHLY | FTC disclosure spot-check: search #StrideHer, verify influencer disclosure | 5 min | P8D.03 | Any Monday | Search 10 recent influencer/ambassador posts. Verify #gifted or #ad present. DM reminders if missing.
MONTHLY | Review response: respond to ALL new reviews within 48 hours | Varies | P9B.04 | Ongoing (check 2×/week) | Star-specific templates. Reference specific details. Your response is read by 500+ future visitors.
QUARTERLY (every 90 days)
QUARTERLY | Customer survey: NPS + product feedback + feature requests | 1 hr | P9B.03 / P9C.04 | End of Q | 6 questions, 2-3 min for customer. Calculate NPS. Tally "change one thing" themes. Feed into v2 spec.
QUARTERLY | NPS + LTV calculation: track trends, calculate LTV:CAC ratio | 30 min | P9C.04-05 | After survey results | NPS target: 50+. LTV:CAC target: 3:1+. The two numbers that predict your future.
QUARTERLY | International tax threshold check: UK, EU, CA, AU cumulative sales | 15 min | P7C.03 | End of Q | Check: is any market approaching registration thresholds? If at 50%: start planning. If at 75%: register.
QUARTERLY | Channel scorecard: evaluate each channel via triple-fail test | 15 min | P11B G8 | End of Q | Revenue contribution + profitability + trend. Triple-fail = rescue. All pass = invest more.
QUARTERLY | Supply chain health check: factory responsive? backup contacts current? insurance active? | 15 min | P10CD G7 | End of Q | 5-point check. Prevents multi-week disruptions.
ANNUALLY
ANNUALLY | Wyoming LLC renewal + registered agent renewal + insurance renewal + US tax filing | 1-2 hrs | P8A.04 $400-$800 | LLC anniversary | Annual compliance. $60 WY tax + $125-$200 agent + $300-$500 insurance + $200-$500 CPA for Form 5472.
ANNUALLY | Impact report: environmental + community + product impact published on strideher.com/impact | 2-3 hrs | P12B.04 | Year-end | Accountability + marketing + differentiation. The report itself is shareable content.
ANNUALLY | Lessons document: what worked, what didn't, what to do differently, advice | 2-3 hrs | P12C.04 | Year-end | Publish as blog series + LinkedIn articles. The capstone that compounds.
ANNUALLY | 3-year vision revision: update with actual data + refined projections | 1 hr | P12C.01 | Year-end | The compass check. Are you still heading where you want to go? Adjust course if needed.