## Critical Path Dependencies
P18 DEPENDENCY MAP — WHAT MUST COMPLETE BEFORE WHAT
40 critical dependencies mapped. If you skip a predecessor: the dependent task WILL fail. Follow this sequence or follow P13 (which already incorporates these dependencies).
# | THIS TASK... | ...REQUIRES THIS FIRST | Why (what breaks if you skip) | Category | Earliest Start | Blocking Level | P13 Week
LEGAL + FINANCIAL FOUNDATION (must be first — everything else depends on these)
1 | Open business bank account (Mercury) | Form LLC + receive EIN | Mercury requires a US business entity (LLC) and EIN to open an account. Without it: no business banking, no Shopify Payments, no payment processing. | Legal | Week -4 (apply EIN) Week -3 (open bank) | 🔴 HARD BLOCKER | W-4 → W-3
2 | Enable Shopify Payments | Business bank account active | Shopify Payments deposits funds to your business bank. Without a connected bank: you can accept orders but can't receive money. | Financial | Week -3 | 🔴 HARD BLOCKER | W-3
3 | File trademark (USPTO) | LLC formed (owner = LLC name) | The trademark must be owned by the legal entity (LLC), not a person. Filing under your personal name then transferring later costs $100+ and creates complications. | Legal | Week -4 | 🟡 SOFT (can file later but delay = delay Brand Registry) | W-4
4 | Amazon Brand Registry | Trademark application filed (serial number) | Brand Registry requires a trademark serial number from USPTO. Without it: no A+ Content, no brand analytics, no counterfeit protection on Amazon. | Legal → Amazon | Month 3-4 (after TM filed in W-4) | 🟡 SOFT (Amazon works without BR but with limitations) | W-4 → M3
5 | Pay supplier (PO deposit via Wise) | Business bank + Wise account | Wise transfers from your business bank in USD to supplier in CNY. Without Wise: use bank wire at 3-5% FX markup (wastes $100+ per PO). | Financial | Week -3 | 🟡 SOFT (can use bank wire but more expensive) | W-3
PRODUCT + MANUFACTURING CHAIN
6 | Request supplier quote (RFQ) | P2A tech spec finalized | The supplier quotes based on YOUR specification. Without a finalized spec: the quote is meaningless (changing spec later = requote + potential price increase + delay). | Product | Week -3 | 🔴 HARD BLOCKER | W-3
7 | Place production PO (600 units) | Supplier sample approved + agreement signed | Never place a PO before: (1) you've seen and approved a physical sample, (2) the supplier has signed the P8D.01 agreement (IP ownership clause protects your designs). Skipping sample approval = gambling $3,600 on unverified quality. | Manufacturing | Week -2 | 🔴 HARD BLOCKER | W-2
8 | Pre-shipment inspection | Production completed (supplier notifies) | Inspect BEFORE paying the 70% balance and BEFORE shipping. Defects caught at factory = fixed at supplier's cost. Defects caught at your door = your problem. | Quality | ~4-5 weeks after PO | 🟡 SOFT (can skip but risks quality issues) | Pre-arrival
9 | Receive + stock inventory | Shipment arrives at your address | Can't fulfill orders without inventory. The fulfillment station (P10A) must be ready BEFORE inventory arrives, or you're assembling a packing station while orders pile up. | Operations | Week 0 (~8-10 weeks after PO) | 🔴 HARD BLOCKER | W0
10 | Fulfill customer orders | Inventory received + Shopify Shipping configured + fulfillment station built | All 3 must be ready: product on shelf, labels purchasable, and station organized. Missing ANY = delays on first orders = bad first impression. | Operations | Launch Day | 🔴 HARD BLOCKER | W1
DIGITAL INFRASTRUCTURE CHAIN
11 | Build Shopify product page | Shopify store created + product photos ready + copy written | The product page needs: 5+ images (P1D), description (P14 copy deck), pricing, variants configured, and size guide linked. Incomplete pages = low conversion. | E-Commerce | Week -3 | 🔴 HARD BLOCKER | W-3
12 | Set up Klaviyo email flows | Shopify store active (Klaviyo integrates via Shopify) | Klaviyo pulls customer data from Shopify. Without Shopify connected: Klaviyo can't trigger flows based on purchase, cart abandonment, or browsing behavior. | Email | Week -3 (after Shopify) | 🔴 HARD BLOCKER | W-3
13 | Install GA4 + Meta Pixel | Shopify store active (tracking scripts go in the theme) | Analytics must be installed BEFORE any traffic arrives. If you launch without Pixel: the first 2 weeks of ad data is LOST (Pixel needs to learn from conversions). Every day without Pixel = wasted learning. | Analytics | Week -3 (immediately after store) | 🔴 HARD BLOCKER | W-3
14 | Create Meta ad campaigns | Meta Pixel installed + 7+ days of Pixel data + product page live | Meta Ads need: (1) Pixel installed and firing, (2) a product page to send traffic to, (3) ideally 7 days of Pixel data for the algorithm to have baseline behavior data. Launching ads with a fresh Pixel = higher CPMs and slower optimization. | Advertising | Week -1 (create drafts) Week 1 (activate) | 🟡 SOFT (can launch with fresh Pixel but performance is slower) | W-1 → W1
15 | Launch Google Ads (PMax) | GA4 installed + product feed in Google Merchant Center + 7+ days of Meta data | Google PMax works best with: (1) GA4 conversion data, (2) an active product feed, and (3) learnings from Meta (which audiences convert). Launching Google before Meta = less data to optimize with. | Advertising | Week 2 (after 7 days of Meta data) | 🟡 SOFT (can launch simultaneously but Meta-first is optimal) | W2
CONTENT + MARKETING CHAIN
16 | Post on social media | Social accounts created + brand assets (logo, colors) ready + content batch produced | You need: accounts, visual identity, and content IN HAND before posting. Creating content daily under pressure = burnout + low quality. Batch production (P5B.04) solves this. | Content | Week -2 (after accounts + first batch) | 🟡 SOFT (can post before batch but quality suffers) | W-2
17 | Ship influencer packages | Product samples in hand + gifting agreement (P8D.02) ready | Can't seed influencers without product. Can't legally use their content without the gifting agreement. Both must be ready before the first package ships. | Influencer | Week -1 (samples arrived) | 🔴 HARD BLOCKER | W-1
18 | Launch email waitlist | Shopify + Klaviyo configured + landing page or popup built | The waitlist needs somewhere to CAPTURE emails (Shopify popup or landing page) and somewhere to STORE them (Klaviyo list). Without both: signups go nowhere. | Community | Week -2 | 🟡 SOFT (can use Google Form as fallback) | W-2
19 | Send pre-launch email sequence | Email list has 100+ subscribers + 7 pre-launch emails written | Sending a pre-launch sequence to 20 subscribers generates ~3 sales. Sending to 200 generates ~30. The email list size determines launch impact. Build the list for 2-4 weeks before the sequence starts. | Launch | Week -1 (after 2+ weeks of list building) | 🟡 SOFT (can send to any size list but impact scales with size) | W-1
LAUNCH + POST-LAUNCH CHAIN
20 | Remove store password (LAUNCH) | QA checklist passed (P6A.06): checkout works, emails trigger, tracking sends, analytics fire, legal pages linked, mobile tested | Going live with a broken checkout, missing legal pages, or non-functioning analytics = wasted launch momentum. The 27-point QA checklist must PASS before removing the password. | Launch | Week 0 (after QA passes) | 🔴 HARD BLOCKER | W0
21 | Activate Meta ads | Store live (password removed) + ads in draft status | Ads cannot point to a password-protected store. The store must be LIVE and the product page accessible before activating any ad campaign. | Launch | Launch Day (after password removed) | 🔴 HARD BLOCKER | W1
22 | Weekly KPI review (P6E.01) | 7 days of live data in GA4 + Shopify + Meta Ads | The KPI review requires: sessions data, order data, ad performance data. You need 7 full days of LIVE data before the first meaningful review. | Operations | Week 2 (end of W1 data) | 🔴 HARD BLOCKER | W2
23 | Monthly financial review (P7B.04) | 30 days of revenue + expense data in Wave/Shopify | The P&L review requires a full month of data. Doing it with 2 weeks of data = misleading (you extrapolate half the month). Wait for the full 30 days. | Financial | End of M1 | 🔴 HARD BLOCKER | M1 end
24 | First A/B test (P6E.02) | 100+ sessions of baseline data on the current product page | A/B tests require STATISTICAL SIGNIFICANCE. With <100 sessions per variant: the results are noise, not signal. Wait for sufficient traffic before testing. | Optimization | Week 3-4 (after 200+ total sessions) | 🟡 SOFT (can test earlier but results are unreliable) | W3-4
25 | Judge.me auto-review-request | 14 days after first delivered order | The Day 14 auto-request triggers based on delivery date. If your first order ships Day 1 and delivers Day 4: the review request fires Day 18. You can't accelerate this — the timing is customer-experience-driven. | Reviews | ~Day 18 (14 days after first delivery) | Automatic (no action needed — Judge.me handles it) | W3
GROWTH + SCALING CHAIN
26 | Launch Amazon listing | 30+ days Shopify sales data + trademark filed + 200 units available for FBA | Amazon works best with: proven product (30 days of Shopify sales confirms PMF), trademark (for Brand Registry), and dedicated inventory (don't deplete Shopify stock for FBA). Launching Amazon Day 1 = splitting focus + inventory too early. | Expansion | Month 3-4 | 🟡 SOFT (can launch earlier but Month 3-4 is optimal) | M3-4
27 | Apply for Amazon Brand Registry | Trademark serial number received from USPTO | Brand Registry = the single requirement is a USPTO serial number (not full registration — the serial number from filing is sufficient). Without BR: no A+ Content, no brand tools, no counterfeit protection. | Amazon | After TM filing (Week -4) | 🟡 SOFT (Amazon works without BR) | After W-4
28 | Create VIP segment in Klaviyo | 2+ repeat customers OR founding members exist | The VIP segment requires customers who QUALIFY (2+ orders, $60+ spent, or founding member tag). With 0 qualifying customers: the segment is empty and the VIP flow never triggers. | Retention | Month 2-3 (when repeat purchases begin) | Automatic (segment populates as customers qualify) | M2-3
29 | Send Day 45 cross-sell email | 45 days after first orders + Klaviyo flow built | The cross-sell flow triggers 45 days after purchase. It can't fire if: (1) the flow doesn't exist in Klaviyo, or (2) 45 days haven't passed. Build the flow in Week 5-6 so it's ready when the first customers hit Day 45. | Retention | Week 5-6 (build flow) Day 45+ (first fires) | 🟡 SOFT (build before first trigger) | W5-6
30 | Hire first VA | Operations manual compiled (P11D.04) + time audit completed (P11D.01) | Hiring without SOPs = chaos. The VA needs: documented processes, templates, and access credentials on Day 1. Without the operations manual: you spend 2 weeks training instead of 2 days onboarding. | Team | Month 6-10 (after SOPs compiled in Month 4-6) | 🟡 SOFT (can hire without SOPs but onboarding is 5x harder) | M6-10
INTERNATIONAL + ADVANCED CHAIN
31 | UK 3PL activation | UK orders >20/month for 3+ months | A UK 3PL with <20 orders/month costs more in monthly minimums than it saves in per-order efficiency. The threshold is volume-dependent — don't activate prematurely. | International | Month 12-18 (when UK volume justifies) | 🟡 SOFT (continue US shipping until volume justifies) | M12-18
32 | Launch Amazon UK | US Amazon generating $3K+/month + UK Shopify shows organic demand | Amazon UK listing without proven US Amazon performance = spreading too thin. Amazon UK without UK Shopify demand = no evidence the UK market wants your product. | International | Month 9-12 | 🟡 SOFT | M9-12
33 | Switch to 3PL (US) | Consistently 10+ orders/day for 30 days + 3PL quotes obtained | Premature 3PL = paying monthly minimums that exceed home fulfillment costs. The break-even is 10 orders/day. Below that: home fulfillment wins on cost. | Operations | Month 8-14 | 🟡 SOFT | M8-14
34 | Register for IOSS (EU VAT) | EU Shopify sales approaching EUR 10K annual | IOSS registration below EUR 10K = unnecessary compliance burden. Above EUR 10K = mandatory. Monitor quarterly per P7C.03. | Tax | When EU sales approach EUR 10K | 🟡 SOFT (not needed until threshold approached) | Quarterly check
35 | Product #2 launch | 11A.01 data analysis complete + VIP pre-sell validates demand (20+ pre-orders) | Never develop product #2 without: (1) customer data telling you WHAT to build, and (2) pre-sell validation confirming demand. The #1 product expansion mistake: building what YOU want, not what customers want. | Product | Month 12-15 | 🟡 SOFT (data-driven not timeline- driven) | M12-15
SUMMARY: 13 HARD BLOCKERS (skip = task fails) + 20 SOFT DEPENDENCIES (skip = suboptimal but possible) + 2 AUTOMATIC (system handles)