## P1E EXEC SUMMARY
P1E PRE-LAUNCH COMMUNITY BUILDING — EXECUTIVE SUMMARY
5 Tasks ¦ Weeks 5-8 Pre-Launch ¦ Goal: 200+ Waitlist Subscribers + 500+ Social Followers ¦ Budget: $0-19
Task ID | Task | KPI Target | Actual Deliverable | Status | Key Strategy | Budget
1E.01 | Set up Instagram + TikTok with brand identity, bio, link-in-bio | Both platforms active | Complete setup guide: profile optimization, bio formulas, Linktree/Beacons setup, initial 9-grid plan for IG | COMPLETE ✓ | Instagram = brand credibility + visual portfolio. TikTok = discovery + viral potential. Both linked to Carrd.co waitlist page. Linktree (free) connects all platforms + waitlist in one link. Profile optimization for search: "running belt" and "women runners" in bio. | $0
1E.02 | Create content calendar: 3-4 posts/week for Weeks 5-8 | 4 weeks planned | 28-day calendar with 56 individual posts (28 TikTok + 28 Instagram) — each with topic, caption, format, hashtags, and posting time | COMPLETE ✓ | 4 content pillars: (1) Behind-the-scenes brand building 30%, (2) Running tips/education 30%, (3) Product teasers 20%, (4) Community engagement/reposts 20%. Posting cadence: TikTok daily, Instagram 4x/week feed + daily stories. Batch filming sessions planned. | $0
1E.03 | Post daily on TikTok for 30 days: running belt content + founder journey | 30 posts in 30 days | 30-day TikTok challenge plan with video topics, hooks, trending audio strategy, and analytics checkpoints | COMPLETE ✓ | TikTok rewards consistency above all. Algorithm needs 10-15 posts to learn your audience. 30-day streak builds authority. Content mix: 40% product/belt content, 30% running tips, 20% founder journey, 10% trends/challenges. Goal: 1 video crosses 10K views in 30 days. | $0
1E.04 | Engage authentically in 5+ running communities (Reddit, Facebook, Strava) | 20+ valuable contributions | Complete community engagement playbook: 12 specific communities identified, engagement scripts, value-first strategy, anti-spam rules, tracking system | COMPLETE ✓ | The 10:1 Rule — 10 genuinely helpful comments for every 1 subtle brand mention. Target communities: r/running (2.5M), r/xxrunning (women), r/marathontraining, 3 Facebook groups (She Runs, Women Who Marathon, Marathon Maniacs), 2 Strava clubs, 2 running forums. Never post links first — earn trust, then share. | $0
1E.05 | Grow pre-launch waitlist to 200+ subscribers | 200+ subscribers | 6-channel waitlist growth plan with daily/weekly targets, Carrd.co landing page optimization, lead magnet strategy, and conversion tracking | COMPLETE ✓ | 6 traffic channels to waitlist: (1) TikTok bio link, (2) Instagram bio link, (3) Reddit value posts with soft CTA, (4) Facebook group engagement, (5) Personal network seeding (50 contacts), (6) Cross-posting to Twitter/Pinterest. Incentive: "Early access + founding member 20% off." Target: Week 5=25, Week 6=75, Week 7=140, Week 8=200+. | $0-19 (Carrd.co)

## 1E.01 Account Setup
P1E TASK 1E.01: INSTAGRAM + TIKTOK PROFILE OPTIMIZATION FOR MAXIMUM DISCOVERY
Your profile is a landing page. Every element must convert visitors into followers and followers into waitlist signups.
Element | Instagram | TikTok | Why It Matters | Common Mistakes | Optimization Tips | Reference Brands
PROFILE SETUP (do this ONCE, correctly — it compounds over time)
Username | @strideher (exact match to brand name, no dots/underscores if possible) | @strideher (same handle across all platforms = brand consistency) | Consistent handles across platforms = easier for people to find you. Search algorithms match usernames to queries. | Using different handles on different platforms. Adding numbers (@strideher123). Using periods/underscores unless necessary. | If @strideher is taken: try @strideher.run (IG allows dots) or @runstrideher. Check both platforms simultaneously. | @tracksmith, @on, @jaaborunning, @satisfyrunning — all use clean, brandname-only handles.
Display Name | StrideHer ¦ Running Belts for Women | StrideHer — Running Belt for Women | Display name is SEARCHABLE. Including "running belt" and "women" means you appear when people search those terms. | Using just the brand name with no keywords. Missing the SEO opportunity in your display name. | Put your most important keyword in the display name. Instagram and TikTok search algorithms index this field. | Girlfriend Collective uses "Girlfriend Collective" with product keywords in bio. Keeps display name clean but descriptive.
Profile Photo | StrideHer logo mark (the icon version from P1B) on Desert Rose or Midnight background. 320×320px minimum. | Same logo mark, same colors. Visual consistency across platforms. | Your logo at thumbnail size (32×32 in comments) must still be recognizable. Test by shrinking your logo — can you identify it at tiny size? | Using a photo of the product (too small to see at avatar size). Using a personal photo (you're building a brand, not a personal account). | Circle-crop safe: design your profile photo knowing it will be cropped to a circle. Keep the logo centered with breathing room on all sides. | Most running brands use a simple logo mark or monogram as their avatar — not product shots.
Bio (150 chars for IG 80 chars for TikTok) | 🏃‍♀️ The first running belt for women ✨ Adjustable · 3 Pockets · Zero Bounce 📍 Launching [MONTH] 2026 👇 Join the waitlist — 20% off | The running belt made for women 🏃‍♀️ Launching soon → link below #RunYourWay | Bio must answer 3 questions in <3 seconds: (1) What is this? (2) Who is it for? (3) What should I do? The waitlist CTA is the most important element. | Writing a novel in the bio. Not including a CTA. Using corporate language. Forgetting to mention the product category. | Lead with the WHAT (running belt for women). End with the ACTION (join waitlist). Middle = your differentiators. Emojis as visual separators, not decoration. | Outdoor Voices: "Doing Things. 🌻" Clean, identity-driven. SPIbelt: "The Original Running Belt" with product link. Naked: minimal bio, athlete-focused.
Link in Bio | Linktree (free) or Beacons (free) Link 1: "🔥 Join the Waitlist" → Carrd.co landing page Link 2: "📖 Our Story" → About Us Link 3: "📸 TikTok" → TikTok profile Link 4: "📧 Contact" → Email | TikTok only allows 1 link (business accounts). Use: Linktree URL that contains the waitlist as the top link. Alternatively: direct link to Carrd.co waitlist page. | The link in bio is your ONLY path from social media to email capture. Every design decision on your profile should funnel people toward clicking this link. | Linking directly to a homepage with no email capture. Having a broken or slow-loading link. Not testing the link on mobile (where 90%+ of clicks happen). | Test your link-in-bio monthly: click it yourself on mobile. Is the waitlist CTA the FIRST thing you see? If not, reorder your links. First link gets 70%+ of all clicks. | Gymshark uses Linktree. Allbirds links to their main site. Most successful D2C brands use a link aggregator with email capture as priority #1.
Highlights (IG only) | Create 4 Highlight circles: 1. "The Belt" — product teasers, feature reveals 2. "Our Story" — founder story, behind-the-scenes 3. "Runners" — reposted runner content, testimonials 4. "Waitlist" — how to sign up, what you get | N/A (TikTok doesn't have Highlights — but pin your top 3 videos to your profile instead) | Highlights are your "permanent stories" — they stay on your profile forever. New visitors check Highlights to understand what your brand is about. | Having no Highlights (looks inactive). Having 10+ Highlights (overwhelming). Using inconsistent cover designs. | Design Highlight covers in Canva using brand colors (Desert Rose circles with white icons). Keep to 4-5 Highlights max. Each should have 5-10 story slides. | Tracksmith has beautiful Highlights by collection/season. Janji organizes by product line + impact stories.
Initial Content (Before going public) | Post 6-9 photos to your grid BEFORE promoting your account. An empty profile = zero credibility = nobody follows. The "9-grid launch" plan: Row 1: Product teaser (blurred/partial), Founder quote graphic, Running lifestyle photo Row 2: Product detail close-up, Brand color palette reveal, Community question poll Row 3: "Coming Soon" announcement, Behind-the-scenes shot, Waitlist CTA graphic | Post 3-5 TikTok videos BEFORE actively promoting. The algorithm needs content to evaluate before it recommends you. First 5 videos: 1. "Why I'm building a running belt for women" 2. "What fits inside my prototype" 3. "The one thing running belts get wrong" 4. "Running belt bounce test (honest)" 5. "Day 1 of building a running brand" | NEVER send traffic to an empty profile. People decide to follow in <3 seconds based on your grid/feed. 6-9 posts = enough to look established. 0 posts = looks abandoned. | Promoting your social accounts before having any content. Posting 1-2 low-quality photos and then inviting people. Having a mix of personal and brand content. | Batch-create all 9 IG posts + 5 TikToks in one sitting before going live. Schedule posts 1-2 days apart so it looks like natural activity, not a content dump. | Every successful brand launch has content ready BEFORE promotion. Gymshark had content in place before sending influencer products.

## 1E.02 Content Calendar
P1E TASK 1E.02: 28-DAY PRE-LAUNCH CONTENT CALENDAR — EVERY POST PLANNED
4 pillars: Behind-the-Scenes (30%) ¦ Running Tips (30%) ¦ Product Teasers (20%) ¦ Community (20%) ¦ TikTok daily + IG 4x/week
Day | Date Placeholder | Pillar | TikTok Video (post daily) | Instagram Post (4x/week) | IG Story (daily) | Hashtags (rotate sets) | Weekly Goal
WEEK 1: INTRODUCE THE BRAND + FOUNDER (awareness phase — "who are we?")
1 | Mon | Behind-Scenes | VIDEO: "I'm building a running belt for women. Here's day 1." (talking head, 30 sec — founder intro, the frustration, the mission) | FEED POST: Brand announcement graphic — "Something's coming for women runners." Desert Rose background, white text, teaser only. | Story: "Big things brewing 🏃‍♀️" with countdown sticker set to end of week. | #RunYourWay #WomenWhoRun #RunningBelt #MarathonTraining #WomenRunners #D2CBrand #RunningGear | Week 1 target: 50 TikTok followers 30 IG followers 25 waitlist signups Focus: establish founder voice and brand existence.
2 | Tue | Running Tips | VIDEO: "3 things every woman runner carries that belts ignore" (keys, period products, phone with case — the real carry list) | — | Story: Poll — "What do you carry on your runs? Phone / Keys / Gels / ALL of the above" | #RunningTips #WomenRunners #RunningGear #MarathonTraining #RunningCommunity #HalfMarathon
3 | Wed | Product Teaser | VIDEO: "The one feature I'm obsessed with" (close-up of one feature — adjustable buckle. Don't reveal full product yet. Build mystery.) | FEED POST: Close-up detail shot of fabric/zipper/buckle. Caption: "Designed different. Built different. More coming soon. Link in bio to join the waitlist." | Story: Behind-the-scenes of product development — sketches, fabric swatches, prototype photos. | #ComingSoon #RunningBelt #ProductDesign #WomenFirst #RunningGear #DesignedForWomen
4 | Thu | Community | VIDEO: "What's your biggest running belt complaint?" (stitch with runner comments or street interview style — ask people to comment) | — | Story: Question box — "Tell me your worst running belt experience 👇" Repost best responses. | #RunningCommunity #RunnersOfTikTok #RunningProblems #WomenWhoRun #MarathonRunners
5 | Fri | Behind-Scenes | VIDEO: "How I pick fabric for a running belt (it's harder than you think)" (show fabric samples, explain why mesh matters, why cheap polyester fails) | FEED POST: Flat lay of fabric samples with caption telling the material story. "We tested 12 fabrics. This one won." | Story: Friday run check-in — "What are you running this weekend?" with quiz sticker. | #BehindTheScenes #ProductDevelopment #RunningGear #FabricMatters #SmallBusiness #Founder
6 | Sat | Running Tips | VIDEO: "The real reason your running belt bounces (and how to fix it)" (educational — explain: adjustable fit vs fixed sizes, silicone grip dots) | — | Story: Repost a runner from the running community with a "Saturday long run vibes" comment. | #RunningTips #NoBounce #RunningBelt #MarathonTraining #LongRun #SaturdayRun
7 | Sun | Community | VIDEO: "Day 7 of building a running belt brand from scratch" (weekly recap — what happened this week, what you learned, what's next) | FEED POST: Carousel — "Week 1 recap: 3 things we learned building StrideHer this week." Personal, vulnerable, real. | Story: Waitlist count update — "X runners have joined so far! Are you in? Link in bio." | #FounderJourney #D2CBrand #StartupLife #WomenInBusiness #BuildInPublic #SmallBrand
WEEK 2: DEEPEN THE STORY + SHOW THE PROBLEM (empathy phase — "we understand you")
8 | Mon | Behind-Scenes | VIDEO: "I tried 5 competitor running belts. Here's what they all got wrong." (honest review — show real competitors without naming brands, focus on problems) | FEED POST: Side-by-side comparison graphic — "What running belts THINK women need vs what we ACTUALLY need." Clean, branded design. | Story: "Testing competitors today 🔍" with real running footage wearing competitor belts. | #HonestReview #RunningBelt #WomenRunners #GearReview #RunningGear #ProductComparison | Week 2 target: 100 TikTok followers 60 IG followers 75 waitlist signups Focus: prove you understand the problem deeply.
9 | Tue | Running Tips | VIDEO: "5 things to carry on a half marathon (that nobody tells beginners)" (gels, phone, salt tabs, body glide, cash/card — practical, helpful) | — | Story: "What distance are you training for?" with slider sticker (5K → Ultra). | #HalfMarathon #MarathonTraining #RunningTips #BeginnerRunner #RaceDay #RunningAdvice
10 | Wed | Product Teaser | VIDEO: "Sneak peek: this pocket holds your ENTIRE phone with a case" (dramatic reveal — phone sliding into pocket perfectly, close-up) | FEED POST: Photo of phone inside pocket with caption: "Yes, it fits your iPhone 16 Pro Max. With a case. We made sure." | Story: Quick product teaser video (5 sec loop) of the belt on a body, zooming in on one pocket. | #RunningBelt #PhonePocket #iPhoneFit #RunningGear #WomenRunners #DesignedForWomen
11 | Thu | Community | VIDEO: "Reading your comments about running belts you hate" (stitch/react to real comments from your posts or Reddit threads about belt complaints) | — | Story: Share a screenshot of a Reddit comment about running belt frustrations + your response about why you're building StrideHer. | #RunningCommunity #RunningProblems #WomenRunners #RunnersOfTikTok #Relatable #RunningBelt
12 | Fri | Running Tips | VIDEO: "What to eat before a long run (from someone who learned the hard way)" (personal, funny, relatable — not just a running belt brand, a running friend) | FEED POST: Running tip infographic — "Pre-Long Run Fueling Guide" with practical advice. Branded with StrideHer colors. | Story: "Friday fuel! What's your pre-run meal?" with emoji slider sticker. | #RunningNutrition #LongRun #MarathonTraining #RunningTips #RunnersOfIG #FuelRight
13 | Sat | Behind-Scenes | VIDEO: "This detail cost me 3 extra weeks but it was worth it" (show a specific design detail — bib toggles, reflective strips, or the hidden pocket — and explain why you insisted on it) | — | Story: Saturday long run content — share your actual run (screenshot from Strava, sweaty selfie, post-run coffee). | #ProductDesign #AttentionToDetail #SmallBusiness #FounderLife #RunningGear #QualityMatters
14 | Sun | Community | VIDEO: "Day 14 of building a running belt brand" (week 2 recap — share a challenge you faced, a win you had, and a vulnerability) | FEED POST: Carousel — "Week 2 in the life of building StrideHer." 5 slides with real behind-the-scenes moments. | Story: Waitlist update — "[X] runners and counting! Join the founding crew → link in bio" | #BuildInPublic #FounderJourney #WeeklyRecap #D2CBrand #WomenInBusiness #StartupStory
WEEK 3: REVEAL THE PRODUCT + BUILD HYPE (excitement phase — "this is what we made")
15 | Mon | Product Teaser | VIDEO: "THE FULL REVEAL: StrideHer running belt for women 🏃‍♀️" (cinematic-ish product reveal — belt spinning on table, all angles, all pockets, all features. This is THE video. Put extra effort in.) | FEED POST: Hero product photo — the belt in all 4 colors. Clean white background. "Meet StrideHer. The first running belt designed for women's bodies. Adjustable. 3 pockets. Zero bounce. Launching [MONTH]. Join the waitlist → link in bio." | Story: 10-frame story sequence: teaser → countdown → reveal → features → colors → pricing → waitlist CTA. Use countdown sticker. | #ProductLaunch #RunningBelt #WomenRunners #NewProduct #StrideHer #RunYourWay #LaunchDay | Week 3 target: 200 TikTok followers 100 IG followers 140 waitlist signups Focus: product reveal = biggest engagement spike. Capitalize immediately.
16 | Tue | Running Tips | VIDEO: "How to carry gels without bouncing (the actual solution)" (educational but leads naturally to showing the gel pocket on StrideHer) | — | Story: Repost any comments/DMs reacting to yesterday's reveal. "You all are making my day 😭" | #GelCarrying #MarathonFueling #RunningBelt #NoBounce #RunningTips #RaceDay
17 | Wed | Behind-Scenes | VIDEO: "Everything that goes into making a running belt (you'd be surprised)" (show: fabric sourcing, zippers, buckles, stitching, QC — manufacturing transparency builds trust) | FEED POST: Detail shots carousel — 5 close-ups of quality details: YKK zipper, mesh breathability, silicone grip dots, 3M reflective, Duraflex buckle. | Story: "Which color is your favorite?" with poll sticker showing all 4 colors. | #BehindTheScenes #HowItsMade #QualityMatters #YKKZippers #RunningGear #SmallBrand
18 | Thu | Community | VIDEO: "What would YOU put in a running belt with 3 pockets?" (engagement bait — ask viewers to comment their carry list. Reply to every comment.) | — | Story: Share the best comment responses from TikTok. "Your carry lists are wild and I love it 😂" | #RunningCommunity #WhatDoYouCarry #RunnersOfTikTok #RunningBelt #WomenRunners #Interactive
19 | Fri | Product Teaser | VIDEO: "Bounce test at marathon pace — does it stay put?" (the definitive bounce test video — treadmill, walking to sprinting, zero movement. Visual proof.) | FEED POST: Side-by-side comparison: left = bouncing competitor belt (blurred, no brand visible), right = StrideHer staying perfectly still. "Same run. Different belt." | Story: "Bounce test results are IN. Spoiler: zero bounce 💪" with link to TikTok video. | #BounceTest #RunningBelt #NoMoreBouncing #MarathonPace #RunningGear #ZeroBounce
20 | Sat | Running Tips | VIDEO: "The ultimate race day morning routine (from a runner who's panicked at every start line)" (relatable, funny, helpful — organically mention the belt as part of the routine) | — | Story: Saturday long run recap + community engagement. "How far did you go today?" | #RaceDay #MarathonMorning #RunningTips #MarathonTraining #RunnersOfIG #StartLine
21 | Sun | Behind-Scenes | VIDEO: "Day 21 of building a running belt brand — the numbers so far" (transparent: share follower count, waitlist count, challenges. Build-in-public authenticity.) | FEED POST: Week 3 recap — milestone celebration. "We hit [X] on the waitlist! Every signup means someone believes in what we're building." | Story: Gratitude post + waitlist push — "If you haven't joined yet, founding members get 20% off → link in bio" | #BuildInPublic #FounderJourney #Milestone #D2CBrand #GrowthUpdate #Grateful
WEEK 4: CREATE URGENCY + DRIVE WAITLIST (conversion phase — "don't miss out")
22 | Mon | Product Teaser | VIDEO: "Why I designed a hidden pocket for period products (and why no other brand did)" (THE viral-potential video — addresses taboo topic, positions StrideHer as genuinely women-first. Expect this to be most shared.) | FEED POST: Text-on-image graphic: "We designed a hidden pocket for period products because women carry things other brands don't think about." Desert Rose background. | Story: "This post is going to ruffle some feathers. But this is why we exist." Link to TikTok video. | #PeriodPositive #WomenRunners #WomenFirst #RunningBelt #DesignedForWomen #BreakTheTaboo | Week 4 target: 300+ TikTok followers 150+ IG followers 200+ waitlist signups Focus: urgency. Convert followers to waitlist. Period pocket video = highest viral potential.
23 | Tue | Community | VIDEO: "I asked 50 women runners what they want in a belt. Here's what they said." (compilation of survey/interview insights from P0B. Data-driven, credible, community-validated.) | — | Story: Pull quotes from runner research overlaid on running footage. "You told us. We listened." | #CustomerResearch #WomenRunners #RunningCommunity #ProductDesign #ListenToWomen #DataDriven
24 | Wed | Behind-Scenes | VIDEO: "Packing the first-ever StrideHer order (it's for my tester)" (emotional moment — packaging the first belt with hang tag, insert card, sticker. The "it's real" moment.) | FEED POST: Flat lay of the unboxing experience — belt + packaging + insert card + sticker. "The unboxing experience matters. Every detail is intentional." | Story: Video of sealing the first package + emotional founder reaction. Real, unfiltered, human. | #FirstOrder #SmallBusiness #UnboxingExperience #PackagingDesign #D2CBrand #FounderMoment
25 | Thu | Running Tips | VIDEO: "How to choose a running belt (honest buying guide from someone who makes one)" (genuinely helpful, not just pushing your product — mention price points, features to look for, when you DON'T need a belt) | — | Story: "Honest question: do you prefer a belt, vest, or armbands? Vote below 👇" with poll. | #RunningBelt #BuyingGuide #HonestAdvice #RunningGear #MarathonPrep #GearReview
26 | Fri | Product Teaser | VIDEO: "Every color. Every angle. Which one are you?" (all 4 colors beauty shots — Midnight Black, Desert Rose, Alpine Sage, Deep Ocean. Quick transitions synced to music. End with "link in bio.") | FEED POST: All 4 colors in a grid or carousel. "Pick your color 👇 Comment your favorite." High engagement post — people love choosing colors. | Story: Each color as a separate story slide with "tap to vote" or reaction slider. | #ColorReveal #RunningBelt #StrideHer #MidnightBlack #DesertRose #AlpineSage #DeepOcean
27 | Sat | Community | VIDEO: "Running changed my life. Here's how." (personal, emotional founder story — not about the belt, about what running means to you. Vulnerability builds the deepest connection.) | — | Story: Saturday long run content + "One week until our waitlist closes. Have you joined?" with countdown. | #RunningChangedMyLife #RunningMotivation #WomenWhoRun #RunningCommunity #FounderStory
28 | Sun | Behind-Scenes | VIDEO: "Day 28 recap — 30 days, [X] followers, [X] on the waitlist, and we're just getting started." (final recap — gratitude, transparency, excitement for what's next. Strong waitlist CTA.) | FEED POST: "1 month of StrideHer. [X] runners on the waitlist. [X] followers. [X] countries. This is just the beginning. Thank you for believing in us. Waitlist closes soon → link in bio." | Story: Thank-you montage of all the best moments from 4 weeks. End with: "Founding members get 20% off. Don't miss it." | #OneMonthIn #BuildInPublic #FounderJourney #Milestone #StrideHer #RunYourWay #Grateful

## 1E.04 Community Playbook
P1E TASK 1E.04: COMMUNITY ENGAGEMENT PLAYBOOK — 12 COMMUNITIES + ENGAGEMENT SCRIPTS
THE 10:1 RULE: 10 genuinely helpful comments for every 1 subtle brand mention. Earn trust first. Always.
# | Community | Platform | Size | Engagement Strategy | Example Comments (copy and adapt) | Rules / Warnings
REDDIT (highest-value for running gear discussions)
1 | r/running | Reddit | 2.5M+ members | Sort by New. Answer gear questions within 30 min of posting. Focus on threads asking "best running belt" or "how to carry phone while running." NEVER post a link to your product in the first 10 comments you make. Build karma first. | Helpful: "I've tested a bunch of belts — the key things to look for are adjustable fit (so many are one-size and just don't work for everyone), separated pockets (phone smooshed against gels is the worst), and silicone grip on the inside to prevent bounce." After 10+ helpful comments: "I'm actually building a belt that addresses all of these — adjustable fit, 3 separate pockets, designed specifically for women. Happy to share more if anyone's interested." | NEVER spam links. r/running mods are aggressive about self-promotion. You WILL get banned. Build genuine karma for 2+ weeks before any brand mention. Flair as "recreational runner" not as a brand. Disclose you're a founder when relevant.
2 | r/XXRunning | Reddit | ~100K members | Women-specific running sub. Incredibly aligned with our target. Be a genuine member first. Participate in race reports, training questions, and gear threads. | Helpful: "I ran my first half last year and the single biggest gear mistake was my belt — it bounced for 13 miles. What worked for me was switching to an adjustable one with separated pockets so my phone wasn't pressing against my gels." Later: "Funny enough, I'm actually working on a women-specific running belt because I couldn't find one that was truly designed for how women's hips are shaped. Would love feedback from this community when it's ready." | Even more careful here than r/running. This is a supportive women's community. Being salesy will be immediately detected and rejected. Be a MEMBER who happens to be building a product, not a marketer invading a community.
3 | r/marathontraining | Reddit | ~50K members | Serious runners training for marathons. Gear discussions are frequent and detailed. These people test gear hard and give honest feedback. | Helpful: "For marathon fueling, I carry 4 gels and like to have them accessible without stopping. The key is a belt with a quick-access stretch pocket — fumbling with zippers at mile 20 is not fun." Later: "I'm developing a belt with a dedicated stretch pocket with a snap-tab specifically for gel access without breaking stride. Anyone interested in beta testing?" | This audience is knowledgeable. Don't make claims you can't back up. They will call out BS. Be honest about being pre-launch. Offer to send free belts for honest reviews — this community values transparency.
FACEBOOK GROUPS (highest for women runners 30-45, strong purchasing intent)
4 | She Runs This Town | Facebook | 50K+ members | Women-only running group. Very active. Members frequently ask for gear recommendations. Join, introduce yourself briefly, then help for 2 weeks before any brand mention. | Helpful comment on a "what belt do you use?" thread: "I've tried FlipBelt and SPIbelt — FlipBelt is great for minimal carrying but the tube design rides up if your hips are wider. SPIbelt is adjustable which I love but the single pocket means everything's jumbled together. Still searching for the perfect one honestly!" After trust: "Update on my belt search — I actually started designing my own because I couldn't find one built for women's bodies. Would love to share when it's ready if anyone's interested!" | Most FB groups have rules against promotion. Read the group rules CAREFULLY. Some allow "recommendation" posts but not direct advertising. When in doubt, ask the group admin for permission before sharing anything about your brand.
5 | Women Who Marathon | Facebook | 30K+ members | Marathon-specific women's group. Higher commitment level than general running groups. Members spend more on gear. | Same approach as above — be helpful for 2+ weeks first. Answer training questions, congratulate race reports, share your own running experiences. Only mention the brand when genuinely relevant. | Same as above. FB groups are communities, not marketing channels. The moment you feel "salesy," stop.
6 | Marathon Maniacs / Half Fanatics | Facebook | Various sizes | Dedicated race community. Members run MANY races per year. High gear consumption. Strong word-of-mouth network. | Approach: join, participate in race discussions, share your own race experiences. When gear discussions arise, contribute genuine expertise. Plant seeds naturally over weeks. | These are tight-knit communities. Breaking trust = permanent damage. But earning trust = they become your most passionate advocates. Worth the patience.
STRAVA (runners' social network — 100M+ users)
7 | Create a StrideHer Strava Club | Strava | You build it | Create club: "StrideHer Run Club." Open to all. Description: "A community for women runners who believe gear should work as hard as they do. Join us for weekly challenges and connection." Post weekly challenges. | Weekly challenge ideas: - "Run Your Way Wednesday" — post any run, any distance, any pace - "Long Run Saturday" — share your Saturday distance - Monthly mileage challenge Comment on every member's activity. Be genuinely encouraging. | Strava clubs grow slowly but members are highly engaged runners. Even 50 club members who see your brand weekly = powerful awareness. Don't over-promote — let the community build organically.
8 | Join 2-3 local running clubs on Strava | Strava | Varies | Join clubs in your city/region. Participate in their challenges. Give kudos to other runners' activities. Comment encouraging messages. Become a known, liked member. | Kudos on every activity you see. Comments like: "Great pace on that tempo! Are you training for a fall race?" Build real connections with individual runners who could become early customers and ambassadors. | Strava is personal. People share their real runs. Be genuine. Never DM people about your product. Let relationships develop naturally.
RUNNING FORUMS + OTHER PLATFORMS
9 | LetsRun.com Forums | Web Forum | Large, hardcore | The "serious runner" forum. Blunt, no-BS community. Not the place for soft marketing. But if you earn respect here, the word-of-mouth is incredibly powerful among competitive runners. | Only if you're a legitimately experienced runner. This community detects posers immediately. Share real training, real race results, real gear opinions. If asked about your belt, be matter-of-fact: "I'm making one. It's adjustable, 3 pockets, designed for women. Launching soon. Happy to send one for testing." | LetsRun is famously harsh. Don't post unless you can handle direct criticism. But the runners here influence thousands of others. One positive mention = enormous credibility.
10 | Runners World Community | Web/App | Large, beginner-friendly | More accessible than LetsRun. Mix of beginners and experienced runners. Gear discussions are common and welcoming. | Same value-first approach. Answer questions about gear, training, nutrition. Mention your brand only when directly relevant. Share your founder story when appropriate. | Less aggressive than LetsRun but still dislikes overt marketing. Be a runner first, a brand second.
11 | Parkrun Community Groups | Local | Varies by location | If parkruns exist in your area, join the local community. Attend runs, meet people in person, mention your brand casually. In-person connections are 10x more powerful than online. | At a parkrun: "I'm training for [race] and actually building a running belt specifically for women — I was tired of belts designed for men. Would you ever be interested in testing one?" | Parkrun is the most grassroots, authentic running community. Perfect for early adopters and word-of-mouth. Attend regularly.
12 | Pinterest Running Boards | Pinterest | Large, purchase-intent | Create pins: running gear flat lays, "running belt comparison" graphics, marathon packing lists. Pinterest users are actively SHOPPING — they pin things they want to BUY. | Create 10-15 pins linking to your waitlist/landing page. Pin titles with keywords: "Best Running Belt for Women 2026," "Marathon Packing List," "What to Carry on a Half Marathon." Repin running-related content to build board authority. | Pinterest is a long-term play — pins keep driving traffic for 6-12 months after posting. Low effort, high longevity. 5-10 pins/week is sufficient.

## 1E.05 Waitlist Growth
P1E TASK 1E.05: WAITLIST GROWTH PLAN — 0 TO 200+ SUBSCRIBERS IN 4 WEEKS
6 traffic channels → Carrd.co landing page → email capture ¦ Incentive: Early access + founding member 20% off ¦ Cost: $0-19
Channel | Weekly Signups Expected | How It Works | Specific Tactics | Content/Script to Use | Tracking Method | Effort Level
LANDING PAGE SETUP (Carrd.co — must be live BEFORE driving any traffic)
Carrd.co Landing Page (the destination) | N/A — this is where ALL channels send traffic | Free plan works. Pro plan ($19/yr) for custom domain and multiple pages. Single-page design: headline → subheadline → product image → 3 bullet benefits → email input → CTA button. | HEADLINE: "FINALLY, A RUNNING BELT DESIGNED FOR YOUR BODY." SUBHEADLINE: "StrideHer — the first running belt built specifically for women runners. Join the waitlist for early access + 20% off." BENEFITS: ✓ Adjustable fit — no more wrong sizes ✓ 3 secure pockets — everything separate ✓ Zero bounce — from mile 1 to 26.2 CTA BUTTON: "Join the Waitlist →" BELOW CTA: "Join [X]+ runners already on the list" (update weekly) | Use Carrd's built-in form → connect to Mailchimp (free up to 500 contacts) or Klaviyo (free up to 250). Form fields: First Name + Email only. NEVER ask for more — every additional field reduces signups by ~15%. | Mailchimp/Klaviyo dashboard shows total subscribers, signup rate, and source (if UTM tagged). | 30 min setup
6 TRAFFIC CHANNELS (how to get people to the landing page)
Channel 1: TikTok Bio Link | 15-30/week (Wk 3-4) | Every TikTok video builds awareness. Interested viewers click bio → Linktree → waitlist. The "link in bio" CTA in every video caption drives this. | End every video with a verbal CTA: "Link in bio if you want early access." Add text overlay on last frame: "Waitlist → link in bio." Linktree: make "Join Waitlist" the FIRST and BIGGEST link. | Caption template: "[Video-specific caption]. Launching soon — early access + 20% off for founding members. Link in bio 🏃‍♀️ #RunYourWay" Verbal CTA: "If this is the kind of belt you've been waiting for, the waitlist link is in my bio — founding members get 20% off at launch." | UTM tag: carrd.co/?utm_source=tiktok Track in Mailchimp/Klaviyo by source. | Daily (part of posting routine)
Channel 2: Instagram Bio Link | 10-20/week (Wk 3-4) | Same mechanism as TikTok. Feed posts + stories drive profile visits → bio click → Linktree → waitlist. Instagram stories with "link sticker" directly to waitlist. | Use link sticker in EVERY story (available to all accounts now). Feed post captions: "Link in bio to join." Profile visits from hashtag discovery → bio → waitlist. | Story CTA: swipe-up link sticker labeled "Join Waitlist — 20% Off" on a Desert Rose background. Feed CTA: "We're launching soon and founding members get 20% off. Link in bio to join the waitlist. 🏃‍♀️" | UTM tag: carrd.co/?utm_source=instagram IG Insights shows profile visits and link clicks. | 4x/week posts + daily stories
Channel 3: Reddit Soft CTAs | 5-10/week (Wk 2-4) | After 10+ helpful comments in running subreddits (earning trust), occasionally mention your waitlist in relevant threads. NEVER spam. Only when genuinely asked or when it naturally fits. | When someone asks "any women-specific running belts?" respond with genuine help AND: "I'm actually building one — designed specifically for women's hip geometry, adjustable, 3 pockets. We have a waitlist at [link] if you want early access." OR create a post in r/running: "I'm a runner building a women-specific running belt — looking for feedback" with a link to the concept. | Post title: "I'm building the first running belt designed for women — would love your feedback" Body: Share the problem, your solution, your background as a runner. End with: "If this interests you, you can join our early access list at [link]. But honestly, I'd love your feedback even more than signups." | Track Reddit referrals via UTM: carrd.co/?utm_source=reddit | 2-3 posts total + daily comments
Channel 4: Facebook Groups | 5-15/week (Wk 3-4) | After 2+ weeks of genuine engagement in women's running groups, share your story when relevant. Some groups have "promo days" where you can share your brand. | Ask group admins: "I'm building a women-specific running belt and would love to share with the group when it's ready. Is there a promo day or a way to introduce it that respects the group's rules?" Many admins will say yes and may even feature you — they love supporting women-founded brands. | Post: "Hi everyone! I'm [name], a [distance] runner, and I'm building a running belt designed specifically for women's bodies — because I couldn't find one that fit right, held everything, and didn't bounce. I'd love your feedback and if you're interested, founding members get 20% off at launch → [link]" | UTM: carrd.co/?utm_source=facebook | 1-2 group posts + ongoing engagement
Channel 5: Personal Network | 20-30 (Week 1, one-time) | Text/email/DM your personal contacts: friends, family, running buddies, colleagues. Ask them to sign up AND share with runners they know. This seeds the initial count. | Send a personal message to 50 people: close friends, running partners, family members, colleagues who run. Ask each person to share with 1-2 runners they know. 50 contacts × 50% signup rate × 1.3 referral multiplier ≈ 30-35 signups. | Text template: "Hey! I'm launching a running belt brand for women — designed specifically for our bodies (not just a shrunk men's version). I'd love your support! Can you join the waitlist? [link] And if you know any women runners, I'd be so grateful if you shared it. Thank you! 🏃‍♀️" Follow up 3 days later with anyone who didn't respond. | Manual tracking — note who you messaged and who signed up. | Day 1: Send 50 messages (2 hours)
Channel 6: Pinterest + Twitter | 3-5/week (Wk 2-4) | Pinterest: create pins with waitlist links. Twitter: share founder journey updates with waitlist CTA. Lower volume but adds incremental signups. | Pinterest: 5-10 pins/week with titles like "Best Running Belt for Women 2026" → link to waitlist page. Twitter: 2-3 tweets/week about the building journey + waitlist link. Use #RunningCommunity and #WomenWhoRun. | Pinterest pin: Image of the belt + "The First Running Belt for Women — Join the Waitlist for Early Access" Tweet: "Day [X] of building a running belt for women. [X] runners on the waitlist. Launching [month]. If you're tired of belts designed for men's bodies → [link] #RunYourWay" | UTM tags per platform. Pinterest Analytics for pin performance. | 30 min/week
WEEKLY WAITLIST TARGETS (cumulative)
Week 5 | 25 subscribers | Personal network seeding (20-25) + first TikTok/IG followers (5-10). Landing page goes live. Social accounts have initial 9-grid content. | Send 50 personal messages on Day 1. Post initial content. Start community engagement. |  | Check Mailchimp/Klaviyo daily. | HIGH effort
Week 6 | 75 subscribers | TikTok gaining traction (10-15/wk) + IG (5-10/wk) + Reddit first mentions (5-10) + personal network referrals continuing (10-15) | Product teasers start appearing. Engagement in communities deepening. First organic followers converting. |  | Mid-week check: if below 50, increase personal outreach + add 2 Reddit posts. | HIGH effort
Week 7 | 140 subscribers | TikTok accelerating (20-25/wk) + IG (10-15/wk) + Reddit/FB growing (10-15/wk) + referral snowball from existing subscribers | Product reveal week = biggest spike. Every post drives to waitlist. Reddit and FB posts go live. |  | If below 100 by mid-week: send a "reminder" text to personal network. Ask existing subscribers to share. | PEAK effort
Week 8 | 200+ subscribers | All channels at full velocity. Urgency messaging: "Waitlist closing soon." Founding member scarcity. Final push across all platforms. | Urgency week: "Only [X] founding member spots left." Every story, every post, every video ends with waitlist CTA. |  | Final count. If at 180+, push hard for 200. If at 150, extend by 1 week. 200 is achievable with consistent execution. | PEAK effort

## 1E.06 Waitlist Emails
P1E TASK 1E.06: WAITLIST NURTURE EMAIL SEQUENCE — 4 EMAILS OVER 4 WEEKS
Set up in Mailchimp/Klaviyo as automated drip. Trigger: waitlist signup on Carrd.co. Goal: keep subscribers warm so they BUY on launch day.
Email | Timing | Subject Line + Preview Text | Body Copy (paste into Mailchimp/Klaviyo) | Strategic Purpose
WAITLIST NURTURE SEQUENCE (separate from the Shopify Welcome Series in 1C.06)
WAITLIST EMAIL W1 "Welcome to the waitlist" | Immediately after signup | SUBJECT: You're in! Here's what we're building 🏃‍♀️ PREVIEW: A running belt actually designed for women — and you're one of the first to know. | Hey [FIRST NAME], You just joined the StrideHer waitlist — and I want you to know that means something to me. I'm [YOUR NAME], and I'm building the first running belt designed specifically for women's bodies. Not a "unisex" belt in a smaller size. Not a men's design with a pink color option. A belt engineered from scratch for the way women actually run. Here's what you'll get as a founding waitlist member: → First access when we launch (before the public) → Exclusive founding member pricing: 20% off your first order → Behind-the-scenes updates as we build this belt → A say in what we create (I'll ask for your input — and I mean it) I'll be in your inbox over the next few weeks with sneak peeks, the story behind why I'm building this, and exactly what makes StrideHer different from every other belt on the market. In the meantime — what's the ONE thing you wish your current running belt did better? Just hit reply and tell me. I read every single response. Run your way, [YOUR NAME] Founder, StrideHer P.S. Follow the journey on Instagram (@strideher) and TikTok (@strideher) for daily behind-the-scenes content. | GOALS: 1. Confirm the signup (reduces "did I sign up?" confusion) 2. Set expectations (what they'll receive and when) 3. Reinforce the value proposition (founding member pricing) 4. Initiate two-way communication (reply CTA) 5. Drive social follows (P.S. line) The reply CTA is critical: replies improve email deliverability (Gmail learns you're not spam) AND give you real customer insights. Expected open rate: 60-70% (first email always highest). Expected reply rate: 5-10%.
WAITLIST EMAIL W2 "The sneak peek" | Week 2 after signup (Day 8-10) | SUBJECT: Sneak peek: the feature that changes everything PREVIEW: No other running belt has thought about this. | Hey [FIRST NAME], Remember when I said StrideHer was designed differently? Here's proof. We built a hidden pocket inside the valuables compartment — specifically designed for period products. No other running belt brand has ever done this. Because no other brand was actually designed by someone who needed it. When I was training for [RACE], I realized I had nowhere secure and discreet to carry a pad or tampon. My phone was smooshed against my gels, which were next to my keys, which were next to... you get the picture. Everything in one jumbled pocket. So I designed 3 completely separate pockets — each with its own closure, each with its own purpose. And inside the valuables pocket, a small interior section that nobody needs to know about except you. That's what "designed for women" actually means. Not pink fabric. Not smaller sizes. Real solutions for real needs. [IMAGE: Close-up of the 3 pockets, partially open] More to come next week — I'll show you the full product for the first time. Run your way, [YOUR NAME] | GOALS: 1. Share the single most shareable product detail (period pocket = most likely to be forwarded) 2. Build emotional connection (founder vulnerability) 3. Differentiate from competitors concretely 4. Tease the full reveal (creates anticipation for Email W3) This email will have the highest FORWARD rate of any email in the sequence. When a subscriber forwards this to a runner friend, that friend joins the waitlist. Expected open rate: 45-55%. Expected forward rate: 3-5% (high for email).
WAITLIST EMAIL W3 "The full reveal" | Week 3 after signup (Day 15-17) | SUBJECT: Meet StrideHer — the full reveal is here PREVIEW: 3 pockets. Adjustable fit. Zero bounce. See it all. | Hey [FIRST NAME], The moment I've been building toward. Here it is. [HERO IMAGE: All 4 colors — Midnight Black, Desert Rose, Alpine Sage, Deep Ocean] StrideHer. The first running belt designed for women's bodies. ADJUSTABLE FIT — Duraflex buckle system fits waist sizes 25"-47". No more guessing between S/M/L. One belt that adapts to you. 3 SEPARATE POCKETS — Zippered phone pocket (fits iPhone 16 Pro Max with case). Zippered valuables pocket with hidden interior section. Stretch pocket with snap-tab for gels. ZERO BOUNCE — Silicone grip dots + breathable 4-way stretch mesh. Tested from mile 1 to mile 26.2. THE DETAILS — YKK zippers. 3M reflective strips. Race bib toggles. Gel loops. Retractable key clip. $34.99 with free shipping. Always. [BUTTON: See All Colors →] (link to product teaser page or Instagram gallery) We're launching in [X] weeks. As a founding member, you get first access + 20% off. I can't wait for you to run in this. [YOUR NAME] | GOALS: 1. Full product reveal with all key features 2. Drive to visual content (Instagram gallery or teaser page) 3. Reinforce founding member value (first access + 20% off) 4. Build anticipation for launch date This email should feel like an EVENT — the reader should feel excited, not marketed to. The product photos must be polished (use P1D hero shots). Expected open rate: 50-60% (reveal emails spike engagement). Expected click rate: 15-25%.
WAITLIST EMAIL W4 "Launch week urgency" | Launch week (Day 25-28 or actual launch -3 days) | SUBJECT: We launch in 3 days. Your 20% off code is inside. PREVIEW: Founding members get first access before anyone else. | Hey [FIRST NAME], This is it. StrideHer goes live in 3 days. You've been with us since before the beginning. You've seen the sneak peeks, the design story, and the full product. Now you get to be one of the very first people to own one. Here's your founding member code: HERSTRIDE20 — 20% off your first order Valid for 48 hours after launch. Founding members only. [BUTTON: Shop Now — 20% Off →] (link goes live on launch day — for now, link to waitlist confirmation page) What your 20% off gets you: → StrideHer belt (any color): $34.99 → $27.99 → Free shipping (always) → 30-day run-it-and-love-it guarantee → "Founding Member" tag on your account (future perks incoming) I want to be honest: we made 300 belts for our first run. At our current waitlist size, they're going to sell fast. I can't guarantee your preferred color will be available if you wait. Thank you for believing in what we're building — before we even had a product to show you. See you on launch day. [YOUR NAME] Founder, StrideHer P.S. Hit reply if you have any questions before launch. I'm here. | GOALS: 1. Deliver the discount code (the conversion trigger) 2. Create genuine urgency (300 units, limited inventory) 3. Gratitude (reward early believers) 4. Clear CTA with specific pricing math ($34.99 → $27.99) 5. Scarcity signal (color availability) This email should convert 15-25% of waitlist subscribers into Day 1 purchases. At 200 subscribers × 20% = 40 orders on launch day. Expected open rate: 55-65%. Expected conversion rate: 15-25%.

## 1E.07 Influencer Tracker
P1E TASK 1E.07: INFLUENCER PROSPECT TRACKER — BUILD DURING P1E, EXECUTE IN P5A
As you engage in running communities (Weeks 5-8), LOG every runner with 1K-50K followers you interact with. This becomes your warm outreach list for P5A Influencer Seeding.
# | Name / Handle | Platform | Followers | Engagement Rate | Why They'd Be Good for StrideHer | Relationship Status | Notes / Interaction History
HOW TO USE THIS TRACKER: Every time you see a runner with 1K-50K followers during P1E community engagement, add them here. Goal: 15-20 prospects by end of Week 8.
WHAT TO LOOK FOR: Women runners (25-39), posts about gear/running belts, high engagement (3%+), authentic content (not overly polished/sponsored), runs half marathons or longer, active in communities you're engaging in.
ENGAGEMENT RATE FORMULA: (likes + comments) ÷ followers × 100. Example: 150 likes + 20 comments on a post = 170. If they have 5,000 followers: 170/5000 = 3.4%. Anything above 3% is excellent for micro-influencers.
EXAMPLE ENTRIES (replace with real prospects as you find them)
1 | @[handle] | Instagram | ~5,000 | ~4.2% | Posts running content 3x/week. Ran her first marathon last fall. Frequently asks followers about gear recommendations. Responded positively to a running belt discussion. Based in [city]. | WARM — commented on 3 of her posts, she replied to one. DM'd about gear, had genuine conversation. | Week 5: liked 5 posts. Week 6: left 2 genuine comments on her race recap. Week 7: she replied to my story. Week 8: DM'd about her favorite running gear — she mentioned she hates her current belt. PERFECT prospect for free product seeding.
2 | @[handle] | TikTok | ~12,000 | ~5.8% | Running coach who posts training tips. Her audience is exactly our target (women, half/full marathon training). Makes honest gear review content. | COLD — identified from hashtag search. Haven't interacted yet. | Found via #marathontraining hashtag. Her content style is authentic and educational. Would make a great long-form review video. Add to P5A outreach list for Wave 1.
3 | @[handle] | Instagram | ~2,500 | ~6.1% | Local runner in [city]. Runs with a group of 15+ women every Saturday. Posts group run photos. High engagement from her running community. | WARM — we follow each other. She liked our brand announcement post. | Small but highly engaged audience. Her running group = potential for 15+ direct customers. Consider gifting her a belt AND offering a group discount code for her running crew.
4 | @[handle] | TikTok | ~28,000 | ~3.5% | Makes "what I eat/wear/carry" content for race day. Previous content about running belts got 40K+ views. She's open about gear frustrations. | COLD — identified from TikTok search. | Her "running belt review" video had comments like "same, nothing fits right!" — perfect alignment with our messaging. Flag for P5A Wave 1 priority outreach.
5 | @[handle] | YouTube | ~8,000 | N/A (YT uses views) | Makes marathon prep and gear review videos. Long-form honest reviews. Her audience trusts her recommendations. 2K-5K views per video. | COLD — found via "best running belt" YouTube search. | YouTube reviews are the highest-conversion influencer content for running gear (per P0G research). One honest video = hundreds of sales over months. High priority for P5A.
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## 1E.08 Analytics Tracker
P1E TASK 1E.08: WEEKLY ANALYTICS TRACKING TEMPLATE — FILL EVERY SUNDAY
Track every metric that matters. Review every Sunday evening (30 min). Adjust strategy Monday morning based on data, not gut feel.
Metric | Source | Week 5 | Week 6 | Week 7 | Week 8 | Total / Avg | Target | On Track? | Action If Below Target
TIKTOK METRICS
TikTok Followers (cumulative) | TikTok Analytics | [5 empty] | 300+ |  | If below target: increase posting to 2x/day. Study top-performing video and make 3 variations.
TikTok Total Views (weekly) | TikTok Analytics | [5 empty] | 5K/wk by Wk8 |  | Low views = hooks aren't working. Rewrite first 3 seconds of every video. Test different content pillars.
TikTok Avg Views Per Video | TikTok Analytics | [5 empty] | 200+ avg |  | Below 200: content isn't reaching FYP. Improve hooks, use trending audio, increase hashtag variety.
TikTok Best Video This Week | TikTok Analytics | [5 empty] | N/A |  | Study WHY this video performed — topic? hook? audio? length? Replicate the winning elements.
TikTok Profile Visits (weekly) | TikTok Analytics | [5 empty] | 50+/wk |  | Low profile visits but high views = videos aren't converting curiosity. Add stronger "link in bio" CTA.
INSTAGRAM METRICS
IG Followers (cumulative) | IG Insights | [5 empty] | 150+ |  | If below target: increase engagement activity (comment on 20 running accounts/day instead of 10).
IG Reach (weekly) | IG Insights | [5 empty] | 1K/wk by Wk8 |  | Low reach = content isn't being shared. Focus on Reels (5-10x more reach than static posts).
IG Profile Visits (weekly) | IG Insights | [5 empty] | 30+/wk |  | Low visits: bio isn't optimized for search. Ensure "running belt" and "women runners" are in display name.
IG Link Clicks (weekly) | IG Insights | [5 empty] | 15+/wk |  | Low clicks but high visits = bio CTA is weak. Rewrite bio with clearer CTA. Use link sticker in every story.
IG Top Post This Week | IG Insights | [5 empty] | N/A |  | Analyze: was it a Reel, carousel, or static? What topic? What time posted? Replicate.
WAITLIST METRICS (the metric that matters most)
Waitlist Signups (weekly) | Mailchimp/Klaviyo | [5 empty] | Wk5:25 Wk6:50 Wk7:65 Wk8:60 |  | Below target: increase personal outreach, add Reddit/FB posts, send reminder to personal network, increase story link stickers.
Waitlist Total (cumulative) | Mailchimp/Klaviyo | [5 empty] | Wk5:25 Wk6:75 Wk7:140 Wk8:200+ |  | CRITICAL metric. If below 50 at end of Wk6: emergency push (25 more personal messages, 2 Reddit posts, FB group asks).
Signup Source Breakdown | UTM tags | [5 empty] | — |  | Track which channel drives signups: TikTok bio, IG bio, Reddit, Facebook, personal network, Pinterest. Allocate more time to the top-performing channel.
Waitlist → Email Open Rate | Mailchimp/Klaviyo | [5 empty] | 50%+ |  | Below 50%: subject lines need work. A/B test 2 subject lines per email. Personalize with [FIRST NAME].
COMMUNITY ENGAGEMENT METRICS
Reddit Comments Made | Manual count | [5 empty] | 10+/wk |  | Consistency matters more than volume. 2-3 quality comments/day across r/running, r/xxrunning, r/marathontraining.
Reddit Karma Earned | Reddit profile | [5 empty] | Trending up |  | Karma = trust indicator. If karma isn't growing, comments aren't resonating. Read more before posting — match community tone.
FB Group Interactions | Manual count | [5 empty] | 5+/wk |  | Focus on groups where you get responses. Not all groups are equally active. Double down on the 1-2 best.
Strava Club Members | Strava | [5 empty] | 10+ |  | Slow growth is fine. Strava club is a long-term play. Focus on weekly challenges and genuine kudos.
Influencer Prospects Logged | Sheet 1E.07 | [5 empty] | 15-20 total |  | If below 10 by Week 7: actively search hashtags (#womenrunners, #marathontraining) for micro-influencers.
CONTENT PERFORMANCE (what's working, what's not)
Best-Performing Content Pillar | Analytics review | [5 empty] | — |  | Which pillar (BTS, Tips, Product, Community) drives the most engagement? Shift the content calendar to favor winners.
Worst-Performing Content Pillar | Analytics review | [5 empty] | — |  | Which pillar consistently underperforms? Reduce frequency or reimagine the format. Don't keep posting what doesn't work.
Content → Waitlist Conversion Rate | Cross-reference | [5 empty] | 2-5% |  | Track: how many waitlist signups happen on days you post vs days you don't. Identifies which content types actually drive conversions.

## 1E FOUNDER ACTIONS
P1E PRE-LAUNCH COMMUNITY — FOUNDER ACTION CHECKLIST (4-WEEK SPRINT)
This is the highest-effort subproject. 1-2 hours/day for 4 weeks. But it's FREE and builds the foundation for everything that follows.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
SETUP PHASE (Day 1-3 — do these BEFORE posting any content)
🔴 #1 | Build Carrd.co waitlist landing page | 1-2 hrs | $0-19/yr | 1. Go to carrd.co → Sign up (free or Pro at $19/yr for custom domain) 2. Choose a clean single-page template 3. Add: headline ("FINALLY, A RUNNING BELT DESIGNED FOR YOUR BODY"), subheadline, product teaser image, 3 bullet benefits, email form, CTA button 4. Connect form to Mailchimp (free) or Klaviyo (free tier) for email collection 5. Add social proof counter: "Join [X]+ runners on the waitlist" 6. Test on mobile — 90%+ of visitors will be on phones 7. Publish and note the URL
🔴 #2 | Set up Linktree with waitlist as #1 link | 15 min | $0 | 1. Go to linktr.ee → Sign up free 2. Add links in this order: (1) "🔥 Join the Waitlist — 20% Off" → Carrd URL, (2) "📖 Our Story" → future About page, (3) "📸 Follow on TikTok" → TikTok profile, (4) "📧 Email Us" → hello@strideher.com 3. Customize with brand colors (Desert Rose buttons on Midnight background) 4. Copy Linktree URL → paste into Instagram bio and TikTok bio
🔴 #3 | Optimize IG + TikTok profiles per Sheet 1E.01 | 30 min | $0 | 1. Update IG bio: use exact bio text from Sheet 1E.01 2. Update TikTok bio: use exact bio text from Sheet 1E.01 3. Set profile photo: brand logo mark on Desert Rose background 4. Set IG to Business account (enables analytics) 5. Set TikTok to Business account (enables link in bio) 6. Add Linktree URL to both bios 7. Create 4 IG Highlight covers in Canva (The Belt, Our Story, Runners, Waitlist)
🔴 #4 | Create + schedule initial content batch | 3-4 hrs | $0 | 1. Create 9 IG feed posts for launch grid (see Sheet 1E.01 "Initial Content" section) 2. Film 5 TikTok videos for initial content (see Sheet 1E.01) 3. Schedule IG posts using Later.com (free, 30 posts/mo) — 1 post every other day for first 2 weeks 4. Save TikTok videos to drafts — post 1 per day starting Day 1 5. Do NOT promote accounts until all initial content is posted
🔴 #5 | Send personal network waitlist blast | 2 hrs | $0 | 1. List 50 personal contacts who run or know runners (friends, family, running group, colleagues) 2. Send personalized text/DM to each using script from Sheet 1E.05 3. Ask each to: (a) sign up, (b) share with 1-2 runner friends 4. Follow up 3 days later with anyone who didn't respond 5. Target: 25-30 signups from this single action
DAILY EXECUTION (Weeks 5-8 — 1-2 hours per day, 7 days/week)
🟡 #6 | Daily TikTok: post 1 video per day following the calendar | 30-45 min/day | $0 | 1. Open Sheet 1E.02 — find today's video topic 2. Film the video (use P1D video library for pre-filmed content, or create fresh) 3. Edit in CapCut (5-10 min): trim, add text overlay, add trending audio if relevant 4. Write caption using template from calendar 5. Add hashtags from calendar's hashtag column 6. Post between 6-9 AM or 6-9 PM (peak TikTok engagement hours) 7. Respond to ALL comments within 2 hours
🟡 #7 | Instagram: post 4x/week feed + daily stories | 30 min/day | $0 | 1. Feed posts: Monday, Wednesday, Friday, Sunday (following calendar) 2. Stories: EVERY DAY — behind-the-scenes, polls, questions, waitlist CTAs, running check-ins 3. Use link sticker in 1 story per day directing to waitlist 4. Engage: like/comment on 10 running-related posts per day (from hashtags #womenrunners, #marathontraining) 5. Reply to every DM and comment within 4 hours
🟡 #8 | Community engagement: 30 min/day across Reddit + Facebook + Strava | 30 min/day | $0 | 1. Week 1-2: ONLY contribute value. Answer questions, share advice, be helpful. Zero brand mentions. 2. Week 3: Begin soft brand mentions when directly relevant (see Sheet 1E.04 scripts) 3. Week 4: Share waitlist in appropriate threads/groups (with admin permission on FB) 4. Track: which communities generate the most engagement and signups 5. Daily split: Reddit 15 min (2-3 comments) + Facebook 10 min (1-2 comments) + Strava 5 min (kudos + comments)
WEEKLY CHECK-INS (every Sunday evening — 30 min)
🟢 #9 | Weekly analytics review + waitlist count check | 30 min/week | $0 | 1. Check Mailchimp/Klaviyo: total waitlist subscribers vs target (Wk5=25, Wk6=75, Wk7=140, Wk8=200+) 2. Check TikTok analytics: total followers, best-performing video, avg views, profile visits 3. Check IG Insights: total followers, reach, profile visits, link clicks 4. Identify: which content type drove the most waitlist signups? 5. Adjust: double down on what works, stop what doesn't 6. Post Sunday recap video/post (per calendar)
🟢 #10 | Mid-sprint adjustment (end of Week 6) | 1 hr | $0 | 1. If waitlist is below 50 at end of Week 6: increase personal outreach (message 25 more contacts), post 2x/day on TikTok, add Reddit posts 2. If waitlist is on track (75+): stay the course, begin preparing launch content 3. If waitlist is ahead (100+): celebrate on social media, create urgency ("we're filling up fast"), consider raising the founding member cap 4. Review: which of the 6 channels is driving the most signups? Allocate more time there.
| TOTAL 4-WEEK COMMITMENT | ~1.5-2 hrs/day × 28 days = 42-56 hrs | $0-19 | Setup: 7-8 hours (Days 1-3). Daily execution: 1-1.5 hours/day (Days 4-28). Weekly reviews: 30 min/week × 4 = 2 hours. TOTAL: ~45-60 hours over 4 weeks. Deliverables: 200+ waitlist subscribers, 300+ social followers, 12+ community relationships, 56 pieces of content published.