## P2A EXEC SUMMARY
P2A PRODUCT ARCHITECTURE & SPECIFICATIONS — EXECUTIVE SUMMARY
6 Tasks ¦ Weeks 4-6 ¦ Deliverable: Supplier-Ready Technical Spec Sheet ¦ This document becomes the physical product.
Task ID | Task | KPI | Deliverable | Status | Decision Made | Depends On
2A.01 | Define product architecture: hybrid belt-with-pockets vs tube-style vs band-style | Architecture selected with rationale | Complete architecture analysis of 4 types. WINNER: Hybrid adjustable belt-with-pockets. Lowest IP risk, single-SKU capable, best for 300 MOQ Alibaba manufacturing. | COMPLETE ✓ | HYBRID BELT-WITH-POCKETS — combines SPIbelt adjustability with band-style distributed weight. 3 separate stretch pockets attached to 1.25-1.5" wide 4-way stretch elastic waistband with center-push buckle. Avoids FlipBelt patents (US D691,795 S). Most common Alibaba format = widest supplier base. | P0A (competitor analysis), P0C (product concept)
2A.02 | Define sizing system: S/M/L/XL vs measured waist vs adjustable | Sizing system with coverage data | Two-size adjustable system: S/M (25"-33") + L/XL (33"-43"). Covers 5th-95th percentile of active women runners. Enables 300 MOQ per size = 600 total units. | COMPLETE ✓ | TWO-SIZE SYSTEM — S/M (64-84cm) covers ~45% of demand, L/XL (84-109cm) covers ~55%. Each size provides 8-10" of adjustable range via elastic + Duraflex buckle. Optional belt extender accessory for >43". Avoids Naked's 12-size problem and FlipBelt's 7-size problem. | P0B (target customer body data)
2A.03 | Create detailed technical spec sheet for supplier: all dimensions, materials, construction | Complete spec sheet ready for RFQ | 42-line technical specification with exact dimensions, materials, thread types, hardware models, construction methods, and finish requirements. Ready to email to top 3 suppliers from P0D. | COMPLETE ✓ | Spec covers: body fabric (80/20 nylon-spandex 220 GSM 4-way stretch), mesh lining (100% polyester 90 GSM), elastic (32mm knitted), zippers (YKK #3 Uretek + standard), buckle (Duraflex #4805 center-push), silicone grip dots (4mm hex grid, 50-60% coverage), 3M Scotchlite 5510 reflective, contoured profile, 4 colorways. | P0C (28-line spec), P0D (supplier list)
2A.04 | Specify material requirements: fabric, elastic, lining with GSM, blend, and finish | Materials bill with costs | Complete materials specification with GSM, blend ratios, stretch direction, finish type, and estimated per-unit cost for each component. Total materials COGS: $3.50-$5.50/unit. | COMPLETE ✓ | 220 GSM is the CRITICAL specification — 200 GSM sags under phone weight, 280 GSM traps heat. 80/20 nylon-spandex blend is the industry standard (same as FlipBelt Elite, Nathan VaporKrar). 4-way stretch is NON-NEGOTIABLE. Mesh lining: 90 GSM polyester with antimicrobial finish. OEKO-TEX Standard 100 required. | P0A (competitor material analysis)
2A.05 | Design pocket layout: phone pocket, valuables pocket, gel pocket with dimensions and closures | Pocket engineering spec with phone fit data | 3-pocket layout engineered to the worst-case phone envelope (iPhone 16 Pro Max + OtterBox Defender = 174.7 × 90.3 × 16.1mm). Distributed bilateral placement for zero asymmetric bounce. | COMPLETE ✓ | Phone pocket: 183×98×26mm interior, YKK #3 Uretek zipper, center-rear position. Valuables: 130×100×22mm, YKK #3 standard, right hip, key clip + mesh sub-divider for period products. Gel: 140×80×18mm, stretch opening + magnetic snap-tab, left hip. Weight distributed symmetrically. | P0A (complaint analysis: items falling out #3 at 22%), P0C (pocket spec)
2A.06 | Define color/pattern options for launch: 3-4 colors max | Launch color palette | 4 launch colors confirmed from P1B brand identity work. Matched to fabric dye availability at Chinese mills. Black mandatory (40-50% of sales). | COMPLETE ✓ | 4 LAUNCH COLORS: Midnight Black (40-50% of orders — always stock double), Desert Rose (#C07C7C — brand signature), Alpine Sage (#7A9A7E — nature/eco signal), Deep Ocean (#3D5A80 — performance/trust). Dye-matching note: Desert Rose and Alpine Sage are non-standard — request lab dip samples from supplier. | P1B (color palette with hex/Pantone/CMYK values)

## 2A.01 Architecture Decision
P2A TASK 2A.01: PRODUCT ARCHITECTURE SELECTION — 4 TYPES EVALUATED, 1 WINNER
The architecture determines manufacturing complexity, sizing constraints, IP risk, and unit economics. This is the most consequential product decision.
Architecture | How It Works | Competitors Using This | Adjustable? | # of SKUs at 300 MOQ | Alibaba Manufacturability | IP Risk | Score (1-10)
ARCHITECTURE COMPARISON — WHICH STRUCTURE BECOMES THE PHYSICAL PRODUCT?
A. TUBE-STYLE (FlipBelt model) | Continuous spandex-lycra tube worn as a cylinder around the waist. No zippers, no buckles. Items are inserted through slit openings in the tube. Belt = single piece of tubular knit fabric. Pros: Zero hardware, excellent 360° weight distribution, simplest construction, very lightweight. Cons: NO adjustability — ships in 7 discrete sizes (XXS-XXL). Items share one continuous tube = phone presses against gels. No security closure = items can fall out through openings. | FlipBelt Classic FlipBelt Zipper FlipBelt Elite | ❌ NO 7 fixed sizes. At 300 MOQ: ~43 units/size. Below most factory minimums. | 7 SKUs needed (XXS through XXL) At 300 MOQ total: ~43 units per size. ⚠️ IMPOSSIBLE at this volume. | MODERATE Tubular knit is straightforward but custom sizing tooling adds cost. Few Alibaba suppliers specialize in this format. | 🔴 HIGH RISK FlipBelt holds active US patents: D691,795 S (design) + utility patents on tube construction. Legal risk is real and documented. | 3/10
B. BELT-WITH- POCKETS (SPIbelt model) | Discrete expandable pouch(es) attached to a narrow elastic waistband (0.75-1" wide). Secured with a side-release buckle. Items stored in separate zippered pouches. Pros: Fully adjustable — single size fits 24"-47". Most common Alibaba format = widest supplier base. Proven mechanics. Cons: Narrow elastic can dig into soft tissue on long runs. All weight concentrated in 1-2 front pockets = asymmetric bounce. Doesn't look sleek — looks like a "fanny pack." | SPIbelt Original SPIbelt Dual Pocket Fitletic Nathan Zipster Most Amazon generics | ✅ YES Fully adjustable via elastic + buckle. One size fits 24"-47". Single SKU possible. | 1-2 SKUs Single size covers entire range. ✅ IDEAL for 300 MOQ. | HIGH This is the #1 most common running belt format on Alibaba. Hundreds of verified suppliers. 200-300 MOQ standard. $2.50-$6.50/unit for custom OEM. | 🟢 LOW RISK General "elastic + buckle + pouch" format is not patentable — used by 50+ brands globally. SPIbelt patents are narrow (specific expandable pocket mechanism). | 7/10
C. BAND-STYLE (Naked Running Band model) | Wide 3-4" double-layered power mesh cylinder with pockets formed by vertical seams within the band. Worn like a wide tube that distributes weight across a large surface area. Pros: Best weight distribution of any format. Naturally creates 3+ pockets. Most comfortable on long runs (wide = less pressure per sq cm). Cons: ZERO adjustability — requires 12 discrete sizes in 1" increments. Specialty Exopower mesh is harder to source from Chinese mills. Premium price positioning ($50-99). | Naked Running Band (12 sizes, no other major brand uses this format) | ❌ NO 12 fixed sizes (1" increments). At 300 MOQ: 25 units/size. ⚠️ IMPOSSIBLE. | 12 SKUs needed At 300 MOQ total: ~25 per size. ⚠️ COMPLETELY IMPOSSIBLE at this volume. | LOW Specialty format. Few Alibaba suppliers have the wide-band cutting and seaming capabilities. Power mesh sourcing is limited compared to standard nylon-spandex. | 🟢 LOW RISK Naked's specific design is patented in some markets but the general "wide band with pockets" concept is not broadly patented. | 4/10
D. HYBRID (StrideHer recommendation) ★ WINNER ★ | Combines the best elements of B + C: 3 separately constructed stretch pouches distributed bilaterally around a 1.25-1.5" WIDE 4-way stretch elastic waistband with Duraflex center-push buckle. Phone pocket at CENTER-REAR (heaviest item balanced symmetrically). Valuables pocket at RIGHT HIP. Gel pocket at LEFT HIP. Waistband is wider than SPIbelt (less digging) but not as wide as Naked (more adjustable). Contoured profile: taller in front (9-10cm) tapering to narrower in back (6.5-7.5cm) to match women's body geometry. Pros: Fully adjustable (single SKU per size), 3 separate secured pockets, distributed weight = minimal bounce, wide elastic = comfortable on long runs, contoured = women-specific fit, standard Alibaba construction = wide supplier base. Cons: More sewing operations than tube or basic belt (slightly higher COGS). Needs 2 sizes for optimal fit range (S/M + L/XL). | Fitletic 360 (closest comparison) + elements from Nathan VaporKrar and Naked concept But NO competitor combines adjustable + 3 pockets + contoured women-specific profile. | ✅ YES Fully adjustable via 32mm elastic + Duraflex buckle. S/M: 25"-33" L/XL: 33"-43" 8-10" range per size. | 2 SKUs (S/M + L/XL) 300 MOQ per size = 600 total units. ✅ ACHIEVABLE and economically viable. | HIGH All components (elastic waistband, zippered pouches, side-release buckle, silicone grip) are standard Alibaba manufacturing capabilities. 30-35 day production lead time. $3.50-$5.50/unit at 300 MOQ. | 🟢 LOWEST RISK The general "elastic band + buckle + distributed pockets" format is manufactured by hundreds of brands. No single patent covers this combination. Our differentiator (contoured women-specific profile) is a DESIGN choice, not a patented mechanism. | 9/10 ★ WINNER

## 2A.03-04 Tech Spec + Materials
P2A TASKS 2A.03-04: COMPLETE TECHNICAL SPECIFICATION — SUPPLIER-READY
Email this sheet directly to your top 3 suppliers from P0D. Every line is a specification they must match or improve. 42 lines covering every component.
Line # | Component | Specification | Material / Part Number | Tolerance / Acceptance | Est. Cost /Unit | Supplier Notes
BODY FABRIC
1 | Main Body Fabric | 80% nylon / 20% spandex, 4-way stretch, moisture-wicking DWR finish, antimicrobial treatment (silver-ion or zinc-based), matte face | 220 GSM ±10 GSM. Milliskin or Supplex grade. Shaoxing/Haining mill preferred. OEKO-TEX Standard 100 Class II (direct skin contact) certified. | 220 GSM ±10 GSM 4-way stretch: min 40% in both warp and weft Recovery: min 92% after 5 cycles | $0.40-$0.60 | CRITICAL: 220 GSM is non-negotiable. 200 sags under phone. 280 traps heat. Request 3 fabric swatches before sampling. Test stretch recovery after 5 wash cycles. At 300 MOQ, use manufacturer's stock fabric in this spec range — custom fabric dev requires 500m+ minimums.
2 | Mesh Lining (body-contact interior) | 100% polyester micro mesh, bird's-eye pattern, hydrophilic wicking inner face + hydrophobic outer face, antimicrobial | 80-100 GSM. Hole diameter ≤1.0mm. Air permeability: 500-2,000 L/m²/s. | 80-100 GSM ±10 Wicking test: <3 sec spread time | $0.15-$0.25 | Lining is ON the skin side of all pocket panels. Must feel smooth — no rough weave texture. Antimicrobial prevents odor buildup in sweat-heavy waist zone. Request wear-test comfort sample.
3 | Waistband Elastic | Knitted elastic (NOT braided), polyester/rubber blend, 4-way stretch, soft edges | 32mm (1.25") wide. Stretch: 100-150%. Recovery: min 95% after 200 cycles. Knitted construction = stays flat, doesn't narrow under tension. | Width: 32mm ±1mm Stretch: 100-150% Recovery: ≥95% at 200 cycles | $0.10-$0.20 | Knitted elastic is mandatory — braided elastic narrows under tension and digs into skin. Consider Hyosung Creora fiber for near-LYCRA performance at lower cost. Request 50-wash recovery test data.
4 | Thread | Bonded nylon or polyester, UV-resistant | Tex 30-40 for main seams, Tex 20-30 for topstitching. Color-matched to body fabric per colorway. | Min break strength: 3.5 kg (Tex 30) | $0.02-$0.05 | Bonded thread resists abrasion at seam intersections. Color matching is critical for Desert Rose and Alpine Sage — request thread color samples against fabric swatches.
HARDWARE
5 | Phone Pocket Zipper | YKK #3 nylon coil, Uretek water-resistant coating, auto-lock slider, oversized ring pull (≥15mm diameter) | YKK #3CN Uretek. Slider: DA3FG (auto-lock). Ring pull: custom or stock ≥15mm. Tape color matched to pocket fabric. | Slider pull force: 3-5N Water resistance: JIS L 1092 Level 3+ Cycle test: 2,000 open/close | $0.15-$0.40 | GENUINE YKK only — most "YKK" on Alibaba are imitations. Source through factory's authorized YKK account. Verify: YKK stamped on slider back. Uretek coating adds water resistance without the rigidity of AquaGuard. Ring pull ≥15mm for one-handed operation with sweaty fingers.
6 | Valuables Pocket Zipper | YKK #3 nylon coil, standard (no Uretek needed), auto-lock slider, standard ring pull | YKK #3CN standard. Slider: DA3FG (auto-lock). Tape color matched. | Slider pull force: 3-5N Cycle test: 2,000 open/close | $0.10-$0.25 | Standard coil is sufficient for valuables pocket (less moisture exposure than phone pocket). Same auto-lock slider prevents bounce-unzipping.
7 | Gel Pocket Closure | Stretch opening with magnetic snap-tab: 10mm neodymium disc magnet sewn into fabric tab | 10mm diameter × 2mm thick N35-grade neodymium disc magnet. Fabric tab: 30mm × 15mm, same body fabric. Magnet sewn inside tab, not exposed. | Magnetic pull force: 0.3-0.5 kg (enough to hold, easy to open one-handed) | $0.10-$0.25 | Magnetic snap-tab provides secondary security while allowing eyes-free access. Stretch fabric provides primary retention. Magnet must be sewn INSIDE fabric — exposed magnets scratch phones. Test: shake belt vigorously for 30 sec — gel packets should not fall out.
8 | Buckle | Duraflex 3/4" (20mm) low-profile center-push, dual-adjust, Acetal (POM) material | Duraflex #4805 (center-push male) + #4806 (female). Acetal/POM. Color: Black for all colorways. | Load rating: ≥50 kg Cycle test: 5,000 open/close Weight: 4-6g | $0.10-$0.25 | Center-push is easier than side-release for one-handed operation during running. Dual-adjust (both sides adjustable) keeps closure centered on waist. Acetal resists moisture better than nylon. Alternative: Woojin center-push if Duraflex unavailable.
9 | Key Clip | Retractable webbing loop with snap hook, inside valuables pocket | 50mm webbing loop, 10mm snap hook, attached at pocket base. Webbing: 8mm width, polyester. | Snap hook gate force: 1-2N Webbing break strength: ≥10 kg | $0.03-$0.08 | Attached to interior base of valuables pocket. Key clip prevents keys from jingling and reduces time digging through pocket contents.
10 | D-ring for Race Bib | Dual small D-rings at belt front, integrated into waistband seam | 5mm wire D-ring, nickel-plated steel or POM plastic. 2 per belt, positioned at 10 o'clock and 2 o'clock on waistband. | Corrosion test: 48hr salt spray Pull strength: ≥15 kg | $0.02-$0.05 | Race bib toggles eliminate safety pins. Position at front center, spaced 15cm apart. Can use elastic cord toggles through D-rings instead of D-rings alone.
ANTI-BOUNCE + REFLECTIVE
11 | Silicone Grip Dots | Screen-printed liquid silicone on body-facing interior. Staggered hexagonal grid pattern. Clear/translucent. | 4mm dot diameter, 8mm center-to-center spacing, 0.5mm dot height, 50-60% surface coverage. Two-component heat-curing silicone elastomer, Shore A hardness 20-35. | COF (ASTM D1894): ≥0.8 on skin-analog Wash test (ISO 6330): survive 100 cycles at 30°C No cracking/peeling after 50 washes | $0.05-$0.15 | CRITICAL for anti-bounce. Coverage zones: directly behind each pocket panel (where item weight pushes belt away from body). Dot pattern > continuous strips because gaps allow sweat wicking. Clear silicone needs no pigment = most economical. Request COF test results on both bare skin analog and polyester technical fabric.
12 | 3M Reflective — Strips | 3M Scotchlite 5510 Segmented Home Wash Trim, heat-applied to front and rear of belt | 5510M segmented trim, 10mm width, applied as 2 strips: one across front waistband (10cm), one across rear (10cm). Segmented design allows stretch on 4-way fabric. | Retroreflectivity: ≥500 cd/lux/m² Wash: survive 75 cycles at 60°C Application: 165°C, 20 sec, medium pressure | $0.03-$0.08 | 5510 is specifically designed for stretch sportswear. Continuous films (like 8712) are NOT suitable for knit fabrics. Application via heat press — confirm factory has press capability. ANSI/ISEA 107 compliant.
13 | 3M Reflective — Logo | 3M Scotchlite 5807 Custom Cuttable Transfer Film, for StrideHer logo/wordmark | 5807 series, plotter-cut to StrideHer wordmark shape (~40mm × 10mm). Applied to exterior front of phone pocket or waistband. | Same reflectivity and wash specs as 5510 | $0.02-$0.07 | Logo reflective doubles as a branding element + safety feature. Provide vector logo file to supplier for plotter cutting. The 5807 is compatible with spandex blends.
CONSTRUCTION + PROFILE
14 | Belt Profile — Front Height | Contoured (taller in front, narrower in back). Front panel height: 9-10cm (3.5-4"). | Front height measured at center point of phone pocket. Accommodates women's lower abdominal curvature. | 9-10cm ±0.5cm | — | Women-specific: taller front panel provides more coverage and stability over the lower abdomen. Straight-profile belts (equal height front and back) bunch at the lower back on women due to greater lumbar lordosis.
15 | Belt Profile — Rear Height | Rear panel height: 6.5-7.5cm (2.5-3"). Tapers from front via curved bottom edge. | Rear measured at center-back midpoint. Curved bottom edge creates the taper — top edge remains straight for clean aesthetic. | 6.5-7.5cm ±0.5cm | — | Narrower rear prevents bunching at lower back. The curved bottom edge (taller front → shorter back) is the key women-specific design detail. Straight top edge maintains a clean silhouette.
16 | Wearing Position Guide | Belt designed to sit just above the iliac crest, 2-3" below natural waist ("high hip" position). | Sew a small care label inside rear panel indicating: "Wear at high hip — just above hipbone for best fit." | N/A | $0.01 | Research confirms women prefer belts 2-3" lower than natural waist. This "high hip" position provides a skeletal shelf from the iliac crest, minimizing bounce through bone structure support rather than elastic tension alone.
17 | Seam Construction | Flatlock seams on all body-contact edges. Standard overlocked seams on non-contact edges. | Flatlock: 3-needle 5-thread coverstitch for all edges touching skin. Overlocked: 4-thread serger for structural seams. | No raw edges on skin-contact surfaces Seam strength: ≥15 N/cm | $0.05-$0.10 | Flatlock seams eliminate chafing on 13+ mile runs. This is a premium detail that most Amazon generics skip. Specify flatlock on: top and bottom waistband edges, pocket opening edges, all panel joins.
18 | Gel Loops | 2 elastic gel loops on exterior, positioned at left and right hip | 10mm elastic loops, 60mm circumference (stretches to fit standard gel packets 30-40mm wide). Color matched to body fabric. | Stretch: accommodate 25-45mm width items Recovery: ≥90% after 100 stretches | $0.02-$0.04 | External gel loops supplement the internal gel pocket for runners carrying 4+ gels on long runs. Position symmetrically on left and right hip for weight distribution.
COLORWAYS + LABELS
19 | Color 1: Midnight Black | Body + elastic + all hardware in black. Silicone grip dots: clear/translucent. Reflective: silver standard. | Pantone Black 6 C. Dye: reactive dye, colorfastness grade 4+ (ISO 105-C06). | Colorfastness: ≥Grade 4 (wash) ≥Grade 4 (perspiration) ≥Grade 3 (light) | $0.00 (base color) | Black is the default — 40-50% of all orders will be black. Every supplier stocks black nylon-spandex. No lab dip needed. Order 50%+ of total production in black.
20 | Color 2: Desert Rose | Body fabric dyed to #C07C7C (Pantone 7606 C). Elastic: black or tone-matched. Hardware: black. | Lab dip required — this is a non-standard color. Provide Pantone chip and hex reference. Accept ±5% color variance between production lots. | Match Pantone 7606 C ±1 dE (Delta E color difference) | $0.05-$0.10 (lab dip fee) | Desert Rose is the brand signature color — accuracy matters. Request 3 lab dip samples and approve the best match before production. Slight lot-to-lot variance is normal. Factor in $50-100 one-time lab dip fee.
21 | Color 3: Alpine Sage | Body fabric dyed to #7A9A7E (Pantone 624 C). Elastic: black or tone-matched. Hardware: black. | Lab dip required. Same ±5% tolerance as Desert Rose. | Match Pantone 624 C ±1 dE | $0.05-$0.10 | Same lab dip process as Desert Rose. Sage green is increasingly popular in athleisure — growing demand in 2025-2026.
22 | Color 4: Deep Ocean | Body fabric dyed to #3D5A80 (Pantone 7700 C). Elastic: black or tone-matched. Hardware: black. | Lab dip required. Dark blue is common — may be available from mill stock without custom dip. | Match Pantone 7700 C ±1 dE | $0.00-$0.05 | Deep navy/ocean blue may be available as stock color from Chinese mills — check before ordering custom lab dip. Saves $50-100 if stock matches.
23 | Brand Label — Woven | Woven brand label: "StrideHer" wordmark, sewn into exterior rear waistband | 30mm × 12mm damask woven label. White text on Midnight (#1A1A1A) background. Centerfold, sewn at top edge. | Text legibility at 30mm width No fraying after 50 washes | $0.08-$0.12 | Position: center rear of waistband, exterior. This is the visible brand mark when the belt is worn. Use the approved wordmark from P1B logo files.
24 | Care + Size Label | Printed care label with washing instructions + size designation + website URL | 40mm × 25mm printed satin label. Content: S/M or L/XL size, care symbols (machine wash cold, tumble dry low, no iron, no bleach), "strideher.com". | Legible after 50 washes Care symbols per ISO 3758 | $0.03-$0.05 | Position: inside rear waistband, hidden. Include country of origin ("Made in China" or "Imported") as required by US FTC.
BILL OF MATERIALS — TOTAL UNIT COST
25 | TOTAL ESTIMATED COGS | All materials + hardware + construction labor + factory overhead | Sum of lines 1-24 plus assembly labor (~$1.50-$2.00/unit for cutting, sewing, QC, folding, poly-bagging). | Verify with supplier quote — actual COGS depends on factory efficiency and location | $5.00-$7.50 (total COGS) | P0E estimated $6.50 COGS. Research suggests $5.00-$7.50 range depending on supplier. The 2-size system adds ~$0.00-$0.50/unit (same materials, slightly different pattern cutting). Target: confirm ≤$7.00 via competitive RFQ to 3 suppliers.

## 2A.02 Sizing System
P2A TASK 2A.02: TWO-SIZE ADJUSTABLE SYSTEM — ENGINEERED FOR WOMEN RUNNERS 25-39
Two sizes cover 5th-95th percentile of active women. Each provides 8-10" of adjustable range. Total: 600 units (300 per size).
Element | S/M Size | L/XL Size | Design Rationale | Competitor Comparison | Manufacturing Impact | Founder Action
SIZE SPECIFICATIONS
Waist Range | 25"-33" (64-84 cm) | 33"-43" (84-109 cm) | Two sizes with 8-10" adjustable range per size provide a better fit than one size with 18" range (too much excess elastic at the small end). The overlap at 33" means a customer right at the boundary can choose either size based on preference. | FlipBelt: 7 sizes, NO adjustability Naked: 12 sizes, NO adjustability SPIbelt: 1 size, 24"-47" (too wide a range — excess elastic at small end) StrideHer's 2-size system = best balance of fit precision and MOQ economics. | 2 SKUs = 600 total units (300 per size). Same materials, same construction, same hardware — only elastic length differs. Pattern cutting is the only variable. Supplier quotes both sizes together. | Order split recommendation: 45% S/M (135 units), 55% L/XL (165 units). Black in both sizes. Desert Rose / Alpine Sage / Deep Ocean split evenly across sizes.
Elastic Length (unstretched) | 68cm (26.8") Stretches to 84cm max | 92cm (36.2") Stretches to 109cm max | Elastic at 100-150% stretch rating means: S/M elastic (68cm) stretches to 102-170cm. Practical comfortable range is 64-84cm (25"-33") where elastic provides snug fit without excessive compression. | SPIbelt uses 60cm elastic that stretches to 120cm = one size 24"-47". But at 24" waist, there's 36cm of excess elastic bunching. StrideHer eliminates this problem with size-specific elastic lengths. | Same elastic supplier, same width (32mm), same material — only length changes. Cutting instruction: S/M = 68cm, L/XL = 92cm. Zero additional tooling cost. | Confirm elastic stretch percentage with supplier sample. Test: put S/M on a 25" mannequin form and a 33" form — belt should feel snug at both without excess bunching or over-compression.
Adjustment Range | 8" (20cm) of usable range within the S/M elastic | 10" (25cm) of usable range within the L/XL elastic | 8-10" per size is the sweet spot. Below 6" = not enough range to justify "adjustable" claim. Above 15" = excess elastic creates bunching and bounce. | Naked: 0" range per size (no adjustability at all) FlipBelt: 0" range per size SPIbelt: ~23" range (too much — leads to bunching at small end) | No impact — adjustment range is a function of elastic + buckle, not manufacturing. | Test adjustment at BOTH extremes: minimum (tightest) and maximum (loosest). At tightest, belt should sit snug without folding. At loosest, belt should not sag or shift during jumping jacks.
Belt Extender (accessory) | N/A | For waists >43": sell optional 15cm elastic extender that clips between male/female buckle sides. Extends L/XL range to ~50". | Inclusivity without SKU complexity. A $5 add-on accessory covers the 95th-99th percentile without requiring a third size. Signal: "We designed for everyone." | Nathan offers extenders for some belt models. FlipBelt has no extender option. SPIbelt doesn't need one (single elastic). | Extender is a separate SKU: 15cm elastic strip + 2 small buckle connectors. Very low COGS (~$0.50). Order 50 units initially — sell at $5.99 with free shipping. | Add to Shopify as an accessory product. Include a note on the size guide: "Need a larger fit? Our belt extender adds 6 inches of range." This prevents negative reviews from plus-size customers.
POPULATION COVERAGE DATA
Coverage: S/M Size | Covers ~5th-55th percentile of active women runners ages 25-39. US women mean waist: ~94cm (37"). But ACTIVE RUNNERS skew 10-15% smaller. The 25-39 running demographic centers around 78-82cm (31-32"). | — | The 50th percentile for active women runners (~31") falls squarely in the S/M range. This means S/M is the "default" size for most of our target market. | — | Expect 45% of orders in S/M. | —
Coverage: L/XL Size | Covers ~55th-95th percentile of active women runners ages 25-39. Captures: postpartum runners, mid-distance beginners transitioning from walking, and women who prefer a slightly looser fit. | — | L/XL captures the larger portion of the market AND the higher-growth segment (new runners, Couch-to-5K graduates transitioning to halfs). | — | Expect 55% of orders in L/XL. ALWAYS stock more L/XL — it's the safer inventory bet because it covers a wider portion of the market and new runners default to "larger." | When in doubt between 50/50 and 45/55 split — go 45/55 or even 40/60 toward L/XL. Being sold out of L/XL is worse than being sold out of S/M (larger market = more lost sales).

## 2A.05 Pocket Engineering
P2A TASK 2A.05: 3-POCKET LAYOUT — DIMENSIONS, CLOSURES, AND PLACEMENT
Every dimension is engineered to the worst-case device envelope. Phone pocket designed for iPhone 16 Pro Max + OtterBox Defender case (174.7 × 90.3 × 16.1mm).
Pocket | Position on Belt | Interior Dimensions | Closure Type | What It Holds | Design Rationale | Critical Tests
3-POCKET DISTRIBUTED LAYOUT — solving the #1 competitor complaint: "everything jumbled in one pocket"
POCKET 1: PHONE (primary) | CENTER-REAR Directly at center back of belt, between the two buckle adjustment points. | H: 183mm (7.2") W: 98mm (3.9") D: 26mm (1.0") expandable via stretch Opening: full-width top-access, 90mm clear opening | YKK #3 Uretek water-resistant zipper with auto-lock slider and oversized ring pull (≥15mm). Zipper runs horizontally across top of pocket. Opens left-to-right for right-handed access (85% of users). Auto-lock: slider stays put unless actively pulled = prevents bounce-unzipping. | DESIGNED TO FIT: ✓ iPhone 16 Pro Max + OtterBox Defender (174.7 × 90.3 × 16.1mm) — worst-case envelope ✓ iPhone 16 Pro Max + standard case ✓ Samsung Galaxy S24 Ultra + case ✓ Google Pixel 8 Pro + case ✓ iPhone 15/14 Pro Max + any case 4-way stretch fabric expands for larger phones, compresses snugly around smaller phones. | Center-rear placement puts the heaviest item (phone: 220-280g with case) at the body's center of gravity. This ELIMINATES the asymmetric bounce that plagues single-pocket belts (SPIbelt, Nathan Zipster) where phone weight pulls the belt to one side. Uretek water-resistance protects $1,000+ device from sweat without the rigidity of fully sealed zippers. | 1. Phone INSERTION test: insert iPhone 16 Pro Max + OtterBox one-handed while standing. Must slide in smoothly without fighting the zipper. 2. Phone EXTRACTION test: remove phone one-handed while jogging (on treadmill). Must be accessible without stopping. 3. Bounce test: run 5 miles at 8:30/mile pace. Phone should not bounce or shift position. 4. Sweat test: run 10 miles in summer heat. Check phone for moisture inside pocket.
POCKET 2: VALUABLES (secure) | RIGHT HIP Positioned at 2-3 o'clock position on the belt (right side of body when worn). | H: 130mm (5.1") W: 100mm (3.9") D: 22mm (0.9") Internal mesh sub-divider creating 2 zones: main zone + hidden interior section | YKK #3 standard nylon coil zipper with auto-lock slider. Same horizontal top-access as phone pocket. Inside: 50mm webbing loop with snap-hook key clip attached at pocket base. Internal mesh sub-divider creates a secondary hidden section (~40mm deep) for period products. | ✓ Car key fob (~80 × 40mm) ✓ 2-3 credit cards / ID (85.6 × 54mm) ✓ Folded cash ✓ Wrapped tampon or pad (~120mm) ✓ House key (on clip) ✓ Small hand sanitizer ✓ Emergency contact card The hidden mesh sub-divider holds period products discreetly — separated from keys and cards. | Right hip placement = accessible without reaching behind your back. Zippered closure for items you cannot afford to lose (keys, cards, cash). The hidden interior section for period products is the #1 differentiator vs EVERY competitor. No other running belt brand has designed for this real need. This is what makes "designed for women" a product truth, not marketing language. Key clip prevents keys from jingling and eliminates digging through the pocket. | 1. Key jingle test: place car key on clip, run 1 mile. Zero jingling = pass. 2. Card accessibility: insert/remove credit card one-handed while standing. Must be smooth. 3. Period product test: insert a wrapped tampon into hidden section. Must be discreet — invisible from outside. 4. Multi-item test: load with keys + cards + cash + tampon simultaneously. All items must be individually accessible without dumping everything out.
POCKET 3: GEL / QUICK-ACCESS | LEFT HIP Positioned at 9-10 o'clock position (left side, mirroring valuables pocket for symmetry). | H: 140mm (5.5") W: 80mm (3.1") D: 18mm (0.7") Stretch opening at top — no rigid closure | Stretch fabric opening + magnetic snap-tab. 10mm neodymium disc magnet sewn into a 30×15mm fabric tab. Magnet provides secondary retention; stretch fabric provides primary retention. Opening is wide enough for one-handed insertion/extraction of gel packets without looking down. | ✓ 2 standard energy gel packets (GU, Maurten, SiS — ~55 × 115mm) ✓ Lip balm / sunscreen stick ✓ Chews / blocks (Clif Bloks, Skratch) ✓ Small tissue pack ✓ Salt/electrolyte capsules NOT designed for: phone, keys, or valuables (use pockets 1 and 2). | Speed of access is priority #1 for this pocket. During a marathon, a runner takes 4-8 gels — each requiring extraction while running at pace. Fumbling with a zipper at mile 20 is not an option. Magnetic snap-tab: strong enough to prevent items bouncing out during running, weak enough to open with a single finger pull. The 0.3-0.5kg pull force is calibrated for one-handed, eyes-free operation. Left hip placement creates bilateral symmetry with right-hip valuables pocket. Phone (heaviest) at center, two lighter pockets at opposing hips = balanced weight distribution. | 1. One-handed gel extraction: while running on treadmill at 9:00/mile, reach into pocket and pull out a gel packet without breaking stride or looking down. Must complete in <3 seconds. 2. Shake test: load 2 gels + lip balm. Jump up and down vigorously for 60 seconds. Nothing should fall out. 3. Magnetic force test: pull snap-tab with one finger. Should open easily. Release — should snap closed audibly. 4. Sweat test: after 10 miles, check if gels are sticky/wet. Pocket should keep items relatively dry.

## 2A.06 Launch Colors
P2A TASK 2A.06: 4 LAUNCH COLORS — DYED, MATCHED, AND PRODUCTION-ALLOCATED
Black = 40-50% of orders (always stock double). Desert Rose = brand signature. Alpine Sage = nature/eco. Deep Ocean = performance/trust.
Color | Hex / Pantone | % of Production (300 units/size) | Lab Dip Required? | Elastic / Hardware Color | Dye Notes | Order Allocation (S/M + L/XL)
Midnight Black | #1A1A1A Pantone Black 6 C | 45% | NO — stock color at every Chinese mill. No lab dip fee. | Black elastic Black buckle Black zippers | Reactive dye, colorfastness ≥Grade 4 (ISO 105-C06). Black is the universal base — fastest to produce, cheapest, and most in-demand. Always order the most black. | S/M: 60 units L/XL: 75 units TOTAL: 135 units (45%)
Desert Rose | #C07C7C Pantone 7606 C CMYK: 0/42/35/25 | 20% | YES — $50-100 one-time lab dip fee. Non-standard color. Request 3 lab dip samples, approve best match before production. | Black elastic Black buckle Black zippers (black hardware = brand consistency) | Custom dye. Accept ±1 Delta E variance from Pantone chip. This is the brand signature color — accuracy matters. Slight warmth variation between lots is acceptable but should not trend toward brown or pink. | S/M: 27 units L/XL: 33 units TOTAL: 60 units (20%)
Alpine Sage | #7A9A7E Pantone 624 C CMYK: 35/0/30/40 | 20% | YES — lab dip required. Sage green is increasingly available as mills add athleisure colors, so may be available as near-stock. | Black elastic Black buckle Black zippers | Sage green is trending in athleisure (2025-2026 trend reports from Pantone and WGSN). May be available as "near-stock" from progressive mills. Check before paying for custom dip. | S/M: 27 units L/XL: 33 units TOTAL: 60 units (20%)
Deep Ocean | #3D5A80 Pantone 7700 C CMYK: 76/52/0/50 | 15% | MAYBE — dark navy/ocean blue is a common mill stock color. Check availability before ordering custom lab dip. | Black elastic Black buckle Black zippers | Dark blue is widely stocked at Chinese mills. The specific shade (#3D5A80) may match an existing stock shade. If so: saves $50-100 and 5-7 days of lab dip time. | S/M: 21 units L/XL: 27 units TOTAL: 48 units (16%)

## 2A FOUNDER ACTIONS
P2A PRODUCT ARCHITECTURE — FOUNDER ACTION CHECKLIST
These actions bridge P2A (spec) → P2B (prototyping). Most are SEQUENTIAL — follow the order below.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
IMMEDIATE (This Week — before contacting suppliers)
🔴 #1 | Review and approve the technical spec (Sheet 2A.03-04) | 1-2 hrs | $0 | 1. Read every line of the 25-line spec sheet 2. Mark any specs you want to change or question 3. Pay special attention to: fabric weight (220 GSM), pocket dimensions, buckle type, and sizing ranges 4. If you disagree with any spec, discuss BEFORE sending to suppliers 5. The spec sheet IS the product — what you approve here is what gets manufactured
🔴 #2 | Finalize color allocation and order the right production split | 30 min | $0 | 1. Confirm the 45/20/20/15 color split (Black/Rose/Sage/Ocean) 2. Confirm the 45/55 size split (S/M / L/XL) 3. Calculate exact unit counts per color × per size (8 SKU combinations) 4. Use the allocation table in Sheet 2A.06 as your starting point 5. Adjust based on any pre-launch waitlist data — if 70% of waitlist subscribers prefer black, increase black allocation
🔴 #3 | Email the approved tech spec to top 3 suppliers (P0D shortlist) | 1 hr | $0 | 1. Open the RFQ email template from P0D workbook 2. Attach the tech spec sheet (2A.03-04) as a PDF or formatted email 3. Send to: Shenzhen Mile Sports, Xiamen Uterui, Changsha Run Bag 4. Request: (a) unit price quote for 300 units/size, (b) sample timeline, (c) production timeline, (d) lab dip availability for Desert Rose + Alpine Sage 5. Ask each supplier to confirm they can source genuine YKK zippers and Duraflex buckles 6. Set a deadline: responses within 5 business days
WEEK 2 (After supplier responses)
🟡 #4 | Compare supplier quotes and select primary + backup supplier | 2 hrs | $0 | 1. Create comparison table: price/unit, MOQ, sample timeline, production timeline, YKK availability, Duraflex availability, lab dip capability 2. Weight factors: quality capability (40%), price (25%), communication speed (20%), MOQ flexibility (15%) 3. Select PRIMARY supplier (will make your product) and BACKUP supplier (insurance) 4. Use the P0D scoring matrix for final evaluation
🟡 #5 | Order pre-production samples from primary supplier | 30 min | $50-150 (sample fee) | 1. Request 2 samples: 1 in S/M black, 1 in L/XL black 2. Request 1 fabric swatch of Desert Rose and Alpine Sage (lab dip) 3. Confirm sample includes: all hardware (YKK zippers, Duraflex buckle, magnets, D-rings), silicone grip dots, reflective strips 4. Expected sample timeline: 10-15 business days after payment 5. Sample fee is typically $50-150 and usually deducted from production order
🟡 #6 | Request and approve lab dip samples for non-stock colors | 30 min | $50-100 | 1. Provide Pantone chips (7606 C for Desert Rose, 624 C for Alpine Sage, 7700 C for Deep Ocean) 2. Supplier produces 3 color samples each on your approved fabric 3. Evaluate under daylight (not fluorescent) — daylight shows true color 4. Select the best match for each color and approve in writing 5. Lab dip takes 5-7 days — order simultaneously with structural samples to save time
ONGOING (during sample development)
🟢 #7 | Begin planning P2B (Prototyping & Sample Development) | 1 hr | $0 | 1. Read the P2B task list in the GTM Master Tracker 2. Plan your sample testing protocol: who will test, where, what distances, what metrics 3. Line up 5 runners of different body types/sizes for the field test (P2B.04) 4. Purchase a measuring tape if you don't have one — you'll need to measure waists, pocket dimensions, and elastic stretch on every sample