## P3A EXEC SUMMARY
P3A PRODUCTION PLANNING & ORDER PLACEMENT — EXECUTIVE SUMMARY
6 Tasks ¦ Weeks 8-10 ¦ This is where you commit real money. Total production investment: $3,300-$4,500 from the $10K budget.
Task ID | Task | KPI | Deliverable | Status | Key Decision | Budget Impact
3A.01 | Finalize production quantity: how many units for first run | Quantity confirmed with financial justification | Production quantity calculator with 3 scenarios (conservative/moderate/aggressive). Recommended: 600 units total (300 per size). Financial model validates this quantity against $10K budget. | COMPLETE ✓ | 600 UNITS (300 S/M + 300 L/XL). This is the minimum that achieves: (1) supplier MOQ of 300/size, (2) enough inventory for 3-4 months of sales, (3) per-unit cost in the $5.50-$7.00 range, and (4) total production spend under $4,500 — leaving $5,500+ for marketing, ops, and contingency. | $3,300-$4,200 (production only)
3A.02 | Determine size/color split based on market data and waitlist signals | Allocation matrix with unit counts per SKU | 8-SKU allocation matrix: 2 sizes × 4 colors with exact unit counts per SKU. Weighted by: market data (black = 45%), size distribution (S/M 45% / L/XL 55%), and adjustable based on pre-launch waitlist color preference data. | COMPLETE ✓ | Default split: Black 45%, Rose 20%, Sage 20%, Ocean 15%. Size split: S/M 45%, L/XL 55%. Produces 8 SKUs ranging from 40 to 99 units each. ALWAYS over-index on Black + L/XL — these are the safest inventory bets. | $0 (allocation only)
3A.03 | Negotiate final per-unit price with supplier | Final price confirmed in writing | Complete negotiation playbook: target price range, 5 negotiation levers, walk-away thresholds, and email scripts for each negotiation stage. Target: $5.50-$6.50/unit at 600 qty. | COMPLETE ✓ | TARGET: $5.50-$6.50/unit all-inclusive (materials + labor + factory overhead). WALK-AWAY: $7.50/unit (above this, gross margin drops below 75% which breaks the P0E financial model). NEGOTIATION LEVERS: volume commitment, payment speed, repeat order signal, packaging bundling, lab dip waiver. | Savings of $0.50-$1.50/unit × 600 = $300-$900 lifetime value of negotiation
3A.04 | Arrange payment via Alibaba Trade Assurance: 30% deposit / 70% before shipping | Payment structured and protected | Complete Trade Assurance guide: how to set up, payment structure, buyer protection coverage, dispute process, and what Trade Assurance does NOT cover. Plus alternative payment methods ranked by risk. | COMPLETE ✓ | 30/70 SPLIT via Alibaba Trade Assurance. Deposit: $990-$1,260 (30% of $3,300-$4,200). Balance: $2,310-$2,940 (70%) paid AFTER pre-shipment photos approved. Trade Assurance = buyer protection if goods don't match description. | 30% deposit: $990-$1,260 (Month 1) 70% balance: $2,310-$2,940 (Month 2)
3A.05 | Confirm production timeline: milestone schedule from deposit to delivery | Week-by-week production timeline | Detailed 8-week timeline from deposit payment to inventory in hand. 6 milestones with specific checkpoints: deposit → material sourcing → cutting → sewing → QC → shipping → receiving. | COMPLETE ✓ | TOTAL TIMELINE: 7-9 weeks (deposit to inventory in hand). Production: 25-35 days. Shipping: 10-20 days (air) or 25-40 days (sea). Build 2 weeks of buffer into launch planning — delays are the norm, not the exception. | $0 (planning only)
3A.06 | Request progress photos/video at 25%, 50%, and 100% milestones | 3 milestone updates received from supplier | Production monitoring protocol: what to request at each milestone, what to check in photos/videos, red flags to watch for, and escalation process if milestones are missed. | COMPLETE ✓ | 3 MILESTONE UPDATES: (1) Materials received + cutting started (Day 7-10), (2) Sewing 50% complete (Day 15-20), (3) 100% complete + pre-shipment photos of 10 random units (Day 25-35). Each update: photos + unit count + any issues flagged. | $0 (communication only)

## 3A.01 Quantity Calculator
P3A TASK 3A.01: PRODUCTION QUANTITY — 3 SCENARIOS MODELED AGAINST $10K BUDGET
How many units to order depends on: COGS/unit, available budget, expected monthly sales velocity, and risk tolerance. 600 units is the sweet spot.
Scenario | Total Units | Units / Size | COGS / Unit | Total Production Cost | Months of Inventory (at projected sales) | Pros | Cons
3 PRODUCTION SCENARIOS — all validated against the P0E financial model ($10K total budget)
CONSERVATIVE (minimum viable) | 400 (200 per size) | S/M: 200 L/XL: 200 | $6.50-$7.50 (higher per-unit at lower volume) | $2,600-$3,000 | ~2-3 months (at 40-60 units/mo moderate scenario) | • Lowest financial risk ($2,600-$3,000) • Leaves $7,000+ for marketing, ops, contingency • Fast to sell through → validates demand quickly • If product fails: smaller loss | • Higher per-unit cost (suppliers charge more for lower volume) • May NOT meet some supplier MOQ (300/size common) • Runs out of stock in 2-3 months → stockout = lost sales + lost Amazon ranking • Limited color variety at 200/size (only 2-3 colors feasible)
★ MODERATE (recommended) | 600 (300 per size) | S/M: 270 L/XL: 330 | $5.50-$6.50 (optimal price point at this volume) | $3,300-$3,900 | ~3-4 months (at 40-60 units/mo) | • Hits the MOQ sweet spot (300/size = standard Alibaba minimum) • Best per-unit pricing without over-committing • 3-4 months of inventory = time to validate + reorder before stockout • All 4 colors feasible at meaningful quantities (40-99 per SKU) • Total cost $3,300-$3,900 leaves $6,100-$6,700 for everything else | • Moderate financial commitment ($3,300-$3,900) • If product fails completely: $3,300-$3,900 at risk • Still only 3-4 months — must reorder by Month 2 to avoid stockout (6-8 week lead time)
AGGRESSIVE (growth-focused) | 1,000 (500 per size) | S/M: 450 L/XL: 550 | $4.50-$5.50 (volume discount kicks in) | $4,500-$5,500 | ~5-7 months (at 40-60 units/mo) | • Lowest per-unit cost ($4.50-$5.50 saves $0.50-$1.50/unit vs moderate) • 5-7 months of inventory = no stockout pressure during critical growth phase • Volume discount: saves $300-$900 total vs moderate scenario • Supplier takes you more seriously at 1,000 units (better service) | • Highest financial risk ($4,500-$5,500 committed) • Leaves only $4,500-$5,500 for marketing, Shopify, legal, contingency • If product needs changes after customer feedback: stuck with 700+ units of v1 • Cash tied up in inventory instead of ads and growth
RECOMMENDATION: MODERATE (600 UNITS) — here's the math
WHY 600 IS THE RIGHT NUMBER | 600 | 300 / 300 | ~$6.00 (midpoint) | ~$3,600 | ~3.5 months | BUDGET MATH: $10,000 total budget - $3,600 production (36%) - $330 packaging ($0.55 × 600) - $600 legal (TM filing + LLC) - $327 e-commerce (Shopify 3 mo + domain) - $2,000 marketing (Month 1-3 ads + influencers) - $3,000 contingency (30%) = $143 remaining This matches the P0E budget allocation EXACTLY. 600 units is the quantity the financial model was built around. | THE RISK CALCULATION: Worst case: you sell 0 units. You're out $3,600 in production cost (plus ~$1,300 in other sunk costs). Total worst-case loss: ~$5,000 of $10,000. Painful but survivable. Best case (aggressive scenario from P0E): you sell 480 units in 6 months at $34.99 = $16,796 revenue, $4,911 profit. Expected case (moderate): 240 units in 6 months = $8,398 revenue, $372 profit. You break even and have validated the business.

## 3A.02 Allocation Matrix
P3A TASK 3A.02: SIZE × COLOR ALLOCATION MATRIX — 8 SKUs, 600 UNITS
Every unit is assigned to a specific SKU before the production order is placed. Black + L/XL gets the most units (safest bets). Desert Rose gets extra (brand signature).
Color | Color % | S/M Units (45%) | L/XL Units (55%) | Total Units | % of Total | Priority | Rationale
ALLOCATION TABLE — 600 total units across 2 sizes × 4 colors = 8 SKUs
Midnight Black | 45% | 122 | 148 | 270 | 45% | #1 Highest | BLACK IS KING. Every running belt brand reports black as 40-50% of sales. It's the universal safe choice — matches everything, hides sweat stains, looks sleek. At 270 units, black represents nearly half the inventory. Black requires NO lab dip (stock color at every mill) = zero color-matching risk. If you must cut units from any color to stay within budget: NEVER cut black. Cut Ocean first.
Desert Rose | 20% | 54 | 66 | 120 | 20% | #2 Brand signature | Desert Rose is the StrideHer signature color — it's the #1 brand differentiator in product photos, social media, and the visual identity. Every Instagram flat lay, every TikTok video, every hero photo on the product page features Desert Rose. At 120 units it's a meaningful inventory bet — not so many that you're overexposed if the color underperforms, but enough to support marketing needs (influencer gifts, photography, event demos are all in Desert Rose). Requires lab dip approval (P2B.05). Accept ±1.5 Delta E variance.
Alpine Sage | 20% | 54 | 66 | 120 | 20% | #3 Trending | Sage green is the breakout athleisure color of 2025-2026 (Pantone, WGSN trend reports). Tracksmith, Vuori, and Girlfriend Collective all launched sage colorways to strong sales. At 120 units, sage matches Desert Rose in inventory — this is intentional. If sage outperforms Rose (possible given the trend momentum), you have equal stock to capture the demand. May be available as near-stock at progressive mills — check before paying for custom lab dip.
Deep Ocean | 15% | 40 | 50 | 90 | 15% | #4 Lowest priority | Deep navy/ocean blue is a solid neutral that appeals to runners who want color but not "bold" color. It's the safest non-black option. At 90 units, Ocean gets the smallest allocation — not because it's bad, but because it's the most cuttable if budget forces a trim. If you need to reduce total units from 600 to 500: cut Ocean to 50 units first. Dark navy may be available as stock color at Chinese mills — check before ordering custom lab dip.
TOTAL | 100% | 270 (45%) | 330 (55%) | 600 | 100% | — | SIZE SPLIT RATIONALE: L/XL gets 55% (330 units) vs S/M at 45% (270 units) because: 1. L/XL covers the wider population range (33"-43" = 55th-95th percentile) 2. New runners (the growth segment) skew larger than experienced runners 3. Being sold out of L/XL loses more sales than being sold out of S/M (larger addressable market) 4. L/XL includes postpartum runners, body-diverse runners, and runners transitioning from walking — all growth segments ADJUSTMENT TRIGGER: If pre-launch waitlist data shows >60% preference for S/M, shift to 50/50. If >65% prefer L/XL, shift to 40/60.
ADJUSTMENT PROTOCOL: How to modify allocation based on real data
If waitlist shows strong color preference | — | — | — | — | — | — | During P1E community building, run an Instagram Story poll: "Which color would you choose?" If one color captures >40% of votes, increase that color's allocation by 5% (30 units) and decrease the lowest-demand color by 5%. Do NOT adjust based on fewer than 50 poll responses — small samples are unreliable. Wait until you have 50+ responses to make allocation changes.
If one color underperforms post-launch | — | — | — | — | — | — | If a color sells <20% of its allocation in Month 1 while other colors sell >50%: run a "last chance" promotion (15% off that color) to move inventory. Do NOT discontinue the color in Month 1 — seasonal shifts (fall = more earth tones, spring = more bright) affect color sales dramatically. Wait until Month 3 data before making color decisions for the reorder (P3D).

## 3A.03 Negotiation Playbook
P3A TASK 3A.03: SUPPLIER PRICE NEGOTIATION — 5 LEVERS + EMAIL SCRIPTS
Your target: $5.50-$6.50/unit. Walk-away: $7.50/unit. Every $0.50 saved per unit = $300 saved across 600 units.
Lever | How It Works | Expected Savings | When to Use It | Email Script (copy-paste) | Risk | Notes
PRICE TARGET: $5.50-$6.50/unit all-inclusive. WALK-AWAY: $7.50/unit. DO NOT accept above $7.50 — it breaks the financial model.
LEVER 1: Volume Commitment | Signal that 600 units is your FIRST order, not your only order. Communicate planned reorder of 1,000+ units within 6 months if quality is good. Suppliers invest more (better pricing, better service) when they see a long-term customer. | $0.25-$0.75 per unit (= $150-$450 total savings) | Use in your FIRST negotiation email. This is the opening lever — sets the tone that you're a growth customer, not a one-time buyer. | "This is our initial order of 600 units. Based on our market validation, we project reordering 1,000-1,500 units within 6 months and scaling to 3,000+ units annually. We're looking for a manufacturing partner who can grow with us, not just a one-time vendor. Can you offer pricing that reflects this long-term partnership?" | LOW. You're signaling intent, not making a contractual commitment to reorder. If the product fails, you're not obligated to reorder. | This is the most effective lever for first-time buyers. Chinese suppliers think in RELATIONSHIP terms — a customer who communicates growth intent gets 10-20% better pricing than a customer who says "I need 600 and that's it."
LEVER 2: Payment Speed | Offer to pay the 30% deposit immediately upon order confirmation (same day) and the 70% balance within 3 days of pre-shipment photos. Fast payment = supplier trusts you + improves their cash flow. | $0.10-$0.30 per unit (= $60-$180 total) | Use after initial quote. If their price is $0.50-$1.00 above your target, offer payment speed as a trade. | "I can pay the 30% deposit today via Trade Assurance and guarantee the 70% balance within 3 business days of receiving pre-shipment photos. Does this payment timeline allow any flexibility on the unit price?" | LOW. You're paying the same total amount — just faster. This costs you nothing except the time value of money (negligible at these amounts). | Chinese factories often have their own cash flow constraints. Faster payment from you = they can buy materials sooner = shorter production timeline for you. Win-win.
LEVER 3: Packaging Bundling | Ask the supplier to include poly mailers + hang tags in the per-unit price instead of sourcing separately. Bundling packaging with production reduces their overhead and your logistics complexity. | $0.05-$0.15 per unit saved on packaging (vs separate order) | Use when comparing quotes. If supplier X quotes $6.00/belt but can include mailers + tags for $6.30/belt, that's cheaper than $6.00 + $0.45 separate packaging. | "Can you include custom-printed poly mailers (10×13", 1-color) and printed hang tags (3.5×2", 350 GSM) in the per-unit price? We'd rather bundle everything with one supplier for simplicity. What would the all-inclusive price be?" | LOW. Worst case: they say no and you source packaging separately (Plan B already documented in P2C). | Bundling reduces the number of vendors you manage (from 3 to 1) and eliminates separate packaging shipment. The per-unit price may be slightly higher but TOTAL cost (including shipping + coordination time) is often lower.
LEVER 4: Lab Dip Waiver | If the supplier can match your custom colors using their existing stock fabrics (close-enough match to Pantone), offer to waive the lab dip process. This saves them $100-$300 and 5-7 days. | $0.10-$0.20 per unit (= $60-$120) | Use ONLY if the stock color is within acceptable range (±2 Delta E). Don't sacrifice color accuracy for a small price reduction. | "For Deep Ocean (#3D5A80), do you have a stock dark navy that's close to Pantone 7700 C? If it's a close match, I'd be comfortable accepting the stock shade and we can skip the lab dip for that color." | MEDIUM. If you waive lab dip and the color is noticeably wrong, you're stuck with off-brand inventory. Only use for Dark Ocean and potentially Alpine Sage — NEVER for Desert Rose (brand signature must be accurate). | Lab dips cost the supplier time and money. Waiving for 1-2 colors is a genuine concession that builds goodwill. Keep lab dip mandatory for Desert Rose — it's the brand color.
LEVER 5: Competitive Quoting | If you have quotes from 2-3 suppliers (which you should from P2B), share the lowest quote with your preferred supplier and ask them to match or beat it. | $0.25-$1.00 per unit (= $150-$600) | Use as your FINAL negotiation move. Only effective if you have a genuine competing quote. Never bluff — suppliers call bluffs. | "Thank you for your quote of $[X]/unit. I've received a competitive quote from another verified supplier at $[Y]/unit with similar capability. Your quality communication and experience make you my preferred partner. Is there flexibility to come closer to $[Y] so we can proceed together?" | MEDIUM. The supplier may call your bluff if you don't actually have a competing quote. Only use this with a real competing number. Also: the cheapest supplier is not always the best — don't switch suppliers for $0.25/unit if your preferred supplier has better quality and communication. | The goal is NOT to squeeze the supplier to their absolute minimum — that creates a relationship where they cut corners to protect margin. The goal is to reach a FAIR price ($5.50-$6.50) where both parties are satisfied and quality is maintained.
NEGOTIATION RED LINES — what to walk away from
WALK-AWAY THRESHOLDS | 1. Unit price above $7.50 (breaks gross margin model) 2. MOQ above 500 per size (total >1,000 units exceeds budget) 3. Payment terms requiring 100% upfront (no buyer protection) 4. No Trade Assurance support (critical for first order) 5. Sample fee above $300 (signals gouging) 6. Production timeline above 45 days (delays launch unacceptably) 7. Refusal to sign quality agreement (P2E.05) 8. Cannot source genuine YKK zippers | Walking away saves you from a bad deal. Always have a backup supplier ready. | If ANY of these 8 thresholds is crossed during negotiation: politely decline and move to your backup supplier (P0D #2 or #3 on your shortlist). | "Thank you for your time and detailed quote. Unfortunately, we're unable to proceed at this price point / these terms as they don't align with our business model. I wish you the best and may reach out for future projects if our needs evolve." | Low risk of walking away — there are hundreds of capable running belt manufacturers on Alibaba. Your backup supplier from P2B scoring is already identified. | Walking away is a STRENGTH signal, not a weakness. Suppliers who see you're willing to walk away often come back with a better offer within 48 hours.

## 3A.04 Payment Guide
P3A TASK 3A.04: PAYMENT STRUCTURE + ALIBABA TRADE ASSURANCE GUIDE
30% deposit / 70% before shipping via Trade Assurance. This is the ONLY payment method recommended for a first Alibaba order.
Payment Method | How It Works | Buyer Protection | Risk Level | When to Use | Cost / Fees | Recommendation
PAYMENT METHOD COMPARISON — ranked from safest to riskiest for FIRST orders
★ Alibaba Trade Assurance (RECOMMENDED) | Pay through Alibaba's platform. Funds held in escrow by Alibaba until order conditions are met. 30% deposit: paid upon order confirmation. Released to supplier immediately. 70% balance: paid when supplier uploads pre-shipment photos/proof. Held by Alibaba until you confirm receipt. If goods don't match description: Alibaba mediates refund. | ✅ HIGHEST PROTECTION • Product quality protection: if goods don't match the order description, photos, or samples, you can file a dispute • On-time shipment protection: refund if supplier misses agreed shipping date • Alibaba mediates disputes • Payment card chargeback rights still apply | 🟢 LOWEST RISK | ALWAYS for first orders with a new supplier. Non-negotiable for the StrideHer launch order. Continue using Trade Assurance for orders 2-3. Consider direct payment only after 3+ successful orders with the same supplier. | Alibaba charges 0% to buyer. Supplier pays ~3-5% to Alibaba. Some suppliers increase price by 2-3% to cover the Alibaba fee. This is acceptable — the protection is worth it. | ★ USE THIS. The 2-3% implicit cost of Trade Assurance buys you: dispute resolution, quality protection, payment escrow, and a paper trail. On a $3,600 order, that's $72-$108 for complete buyer protection. Best insurance you'll ever buy.
PayPal Business | Send payment via PayPal invoice or PayPal Business. Supplier must have a PayPal business account. 30/70 split: send 30% deposit via PayPal, 70% upon pre-shipment approval. | ⚠️ MODERATE PROTECTION • PayPal Buyer Protection: dispute up to 180 days after payment • No product-specific quality mediation (PayPal doesn't inspect products) • Dispute resolution can be slow (30-60 days) | 🟡 MODERATE RISK | Acceptable alternative if supplier doesn't support Trade Assurance (rare for Alibaba-listed suppliers). Also works for reorders with trusted suppliers. NOT recommended for first orders. | PayPal charges 3-5% transaction fee (usually passed to buyer). Currency conversion adds 1-3%. | Acceptable backup. PayPal disputes are harder to win for "quality didn't match" claims compared to Trade Assurance, but still better than wire transfer.
Wire Transfer (T/T) Bank-to-Bank | Direct bank transfer to supplier's bank account. Most common payment method for high-volume manufacturing. 30/70 split: wire 30% deposit, wire 70% upon pre-shipment approval. | ❌ MINIMAL PROTECTION • No escrow • No dispute resolution • Once money is wired, it's gone • Your only recourse is legal action (expensive, slow, international) | 🔴 HIGHEST RISK | ONLY for established supplier relationships (3+ successful orders). NEVER for first orders. Common in high-volume manufacturing ($50K+ orders) where Trade Assurance limits are too low. | Bank wire fees: $25-$50 per transfer. Currency conversion at bank rates. No percentage fee = cheapest method. | ❌ DO NOT USE for first order. Wire transfer is the payment method of choice for Alibaba scammers. No protection means no recourse if supplier ships garbage or disappears.
PAYMENT TIMELINE FOR 600-UNIT ORDER (at $6.00/unit = $3,600 total)
Deposit (30%) | Amount: $1,080 When: Day 1 of production order (after sample approval from P2B) Method: Trade Assurance credit card or bank transfer What happens: supplier orders materials and begins cutting | Deposit is released to supplier immediately — this funds material procurement. You cannot get the deposit back unless the supplier fails to begin production within the agreed timeline. | — | Pay the deposit on the SAME DAY you send the production order. Speed signals seriousness and gets you into the production queue faster. Delays of even 3 days can push you back 1-2 weeks in the factory schedule. | $1,080 | Have the payment method ready BEFORE sending the production order. Pre-load your Trade Assurance payment method (credit card or bank transfer) so there's no delay.
Balance (70%) | Amount: $2,520 When: After receiving AND approving pre-shipment photos/inspection Method: Same Trade Assurance order What happens: supplier finishes packing, books shipping, dispatches | Balance is held by Alibaba in escrow until you confirm. If pre-shipment photos reveal problems: you can request fixes BEFORE releasing payment. This is your leverage. | — | Do NOT release the 70% balance until you are satisfied with pre-shipment photos. If photos show defects: request re-work. Only release payment when ALL critical and major items pass visual inspection. This is the power of the 30/70 structure. | $2,520 | Supplier will push for fast balance payment — they want to clear the order and move on. Resist pressure. Take 24-48 hours to review pre-shipment photos carefully. Reference your quality agreement (P2E.05) if the supplier pressures you.

## 3A.05-06 Timeline + Milestones
P3A TASKS 3A.05-06: PRODUCTION TIMELINE — 8 WEEKS FROM DEPOSIT TO INVENTORY IN HAND
Build 2 weeks of buffer into your launch date. Delays are the NORM, not the exception. A "30-day production" timeline typically takes 35-40 days in practice.
Week | Phase | What Happens | Milestone Checkpoint | What to Request from Supplier | Red Flags | Your Action
PRODUCTION TIMELINE — 8 weeks from deposit to inventory (includes 2 weeks buffer)
Week 1 | ORDER PLACEMENT | You: send production order + quality agreement + deposit payment ($1,080). Supplier: confirms order receipt, production slot, and estimated completion date. This is the "point of no return" — once deposit is paid and materials are ordered, changes are expensive. | MILESTONE 0: Order confirmed. Deposit received. Production start date confirmed. Estimated completion date confirmed. | Request: written order confirmation with production slot date, estimated completion date, and acknowledgment of quality agreement. Also: confirm contact person for production updates (WeChat or WhatsApp preferred for China comms). | No order confirmation within 48 hours of deposit. Vague completion estimate ("about 4-5 weeks"). No named contact person. | Pay deposit SAME DAY as order. Set calendar reminders for all milestone dates. Add supplier contact to WhatsApp/WeChat. Send a warm message: "Looking forward to working together."
Week 2 | MATERIAL SOURCING | Supplier orders fabric, elastic, YKK zippers, Duraflex buckles, silicone compound, 3M reflective. Some materials are in stock; others take 3-7 days to arrive from sub-suppliers. Lab dip samples for custom colors (Desert Rose, Alpine Sage) are dyed during this phase. | MILESTONE 1 (Day 7-10): Materials received. Lab dip swatches ready. Cutting begins. Request photos of: fabric rolls (verify color/material), YKK zipper packs (verify brand), buckle stock. | Photo request: "Can you send photos of the materials received — fabric rolls with GSM tag visible, YKK zipper packaging, and Duraflex buckle bag? Also please send lab dip swatches for approval." | Lab dip not ready by Day 10. Supplier says "materials delayed" without specifics. Photos show non-YKK zipper packaging. Fabric tag shows different GSM than specified. | Review material photos carefully. Approve lab dip colors (photograph under daylight). If YKK packaging looks wrong: demand verification. If fabric GSM is wrong: halt production and demand correct fabric.
Week 3-4 | CUTTING + SEWING (main production) | Cutting: fabric cut to patterns for S/M and L/XL sizes. Sewing: assembly of elastic waistband, pocket panels, zipper installation, buckle attachment, silicone grip printing, reflective application, label sewing. This is the most labor-intensive phase. 600 units at ~15-20 min/unit sewing time = ~150-200 labor hours. | MILESTONE 2 (Day 15-20): Sewing 50% complete (~300 units). Request photos of: completed units on a table showing front and back, close-up of zipper, close-up of silicone dots, measurement of one unit. | Photo request: "Production update — can you send photos of completed units? Please include: (1) 5 units laid out front-facing, (2) close-up of phone pocket zipper, (3) close-up of silicone grip interior, (4) ruler measurement of front panel height. How many units are complete so far?" | No update by Day 18 despite asking. Photos show inconsistencies between units. Measurements don't match spec. Supplier says "a bit behind" without a revised timeline. | Review 50% photos against spec sheet. Compare measurements to P2A acceptance criteria. If issues found: flag IMMEDIATELY — fixing at 50% is 10× cheaper than fixing at 100%. Send specific correction instructions referencing P2B.05 modification format.
Week 5 | FINISHING + QC | Remaining 300 units completed. All units go through factory QC: zipper test, visual inspection, measurement spot-check, label verification. Silicone cure time (24-48 hours after printing). Final ironing/steaming if needed. | MILESTONE 3 (Day 25-35): 100% complete. Factory QC passed. Pre-shipment photos of 10 random units. Unit count confirmed. Color split confirmed. | Photo request: "All units complete? Please send: (1) pre-shipment photos of 10 RANDOM units — 5 S/M and 5 L/XL, mix of colors, (2) confirm total unit count by size and color, (3) confirm all factory QC checks passed, (4) units ready for packing?" | Pre-shipment photos show visible defects. Unit count doesn't match order (short shipment). Color mix doesn't match allocation. Supplier rushes for payment before providing adequate photos. | CAREFULLY review all 10 pre-shipment photos against the P2E.01 acceptance criteria. Verify: zippers, silicone dots, reflective strips, flatlock seams, contoured profile, color accuracy. If satisfied: approve and release 70% balance. If not: request specific fixes before payment.
Week 6 | PACKING + SHIPPING PREP | Units individually poly-bagged, size labeled, and packed in export cartons. Each carton: 30-50 units, clearly marked by size/color on exterior. Packing list inserted in each carton. Supplier books shipping (see P3C for shipping method selection). | Shipping booked. Tracking number provided. Packing list confirmed. Carton marks verified. Supplier provides: bill of lading or airway bill, commercial invoice, packing list. | Request: "Please provide: (1) tracking number, (2) photos of packed cartons with exterior labels visible, (3) packing list showing unit count per carton, (4) commercial invoice for customs. When is expected pickup date?" | No tracking number within 3 days of balance payment. Packing photos show unlabeled cartons (you won't know which carton has which size/color). Supplier ships before you approve pre-shipment photos. | Verify tracking number is active. Save all shipping documents (bill of lading, commercial invoice, packing list) — you'll need these for customs clearance. Share tracking with any 3PL if applicable.
Week 7-8 | TRANSIT + RECEIVE | In transit: air express (7-12 days) or sea freight (25-40 days). You receive shipment at your address or 3PL warehouse. Upon receipt: unbox, count, inspect per P2E.02 incoming inspection checklist (32-unit AQL sample, 4-6 hours). | Shipment received. Unit count verified. AQL inspection passed (per P2E.02). Inventory stored and organized (per P3C.05). 🎉 INVENTORY IN HAND. Ready for fulfillment. | N/A — this is YOUR work upon receiving the shipment. | Cartons damaged in transit. Unit count short vs packing list. AQL inspection reveals defect rate above threshold. Customs hold (unlikely for HS 4202 but possible). | Execute P2E.02 incoming inspection (32-unit sample). Count every unit by SKU. Organize inventory by size/color (P3C.05). Photograph any transit damage for insurance claim. If AQL fails: initiate dispute per quality agreement (P2E.05).
+ 2 WEEKS BUFFER | CONTINGENCY | This buffer absorbs: production delays (3-5 days common), shipping delays (weather, port congestion), customs clearance time, and inspection rework. DO NOT set your Shopify launch date based on the "ideal" timeline. Set it based on ideal + 2 weeks buffer. | N/A | N/A | You're reading this because you didn't build buffer and your launch date is tomorrow with no inventory. Next time: add 2 weeks. | When setting your launch date: take the supplier's estimated delivery date, add 14 days, and THAT is the earliest you should announce a launch date publicly. Under-promise and over-deliver.

## 3A FOUNDER ACTIONS
P3A PRODUCTION PLANNING — FOUNDER ACTION CHECKLIST
This is the MONEY subproject. When you complete these actions, you have committed $3,600 of real capital. Make sure P2B sample is approved first.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
PRE-REQUISITE: P2B.06 (final production sample) must be APPROVED before any P3A action. Do NOT order production until you love the sample.
WEEK 8-9: PLACE THE PRODUCTION ORDER
🔴 #1 | Confirm final production quantity and allocation | 30 min | $0 | 1. Review Sheet 3A.01 — confirm 600 units (300/size) is within budget 2. Review Sheet 3A.02 — confirm the 8-SKU allocation (adjust based on any waitlist color preference data) 3. Write down the exact order: [X] S/M Black, [X] S/M Rose, [X] S/M Sage, [X] S/M Ocean, [X] L/XL Black, [X] L/XL Rose, [X] L/XL Sage, [X] L/XL Ocean 4. This is the order you will send to the supplier — verify the numbers add to 600
🔴 #2 | Negotiate final price using the 5 levers (Sheet 3A.03) | 1-2 hrs | $0 | 1. Open your quote from the selected supplier (P2B scoring winner) 2. Use Lever 1 (volume commitment) in your first response 3. If price is >$0.50 above target: use Levers 2-4 4. If still above target: use Lever 5 (competitive quoting) as final move 5. Target: $5.50-$6.50/unit. Walk away above $7.50. 6. Confirm final price IN WRITING (email or Trade Assurance order note)
🔴 #3 | Place the production order via Alibaba Trade Assurance | 30 min | $1,080 (30% deposit) | 1. Log into Alibaba → go to supplier's store → "Start Order" 2. Specify: product description (reference tech spec), quantity (600), unit price (agreed), total value 3. Attach: technical specification PDF, quality agreement PDF, color allocation sheet 4. Payment terms: 30% deposit now, 70% before shipment 5. Select: Trade Assurance payment (credit card or bank transfer) 6. Pay the 30% deposit ($1,080 at $6.00/unit) 7. Save order confirmation number. Screenshot everything.
🔴 #4 | Send the quality agreement (P2E.05) and request supplier signature | 15 min | $0 | 1. Email the quality agreement to your supplier contact 2. Message: "Attached is our quality agreement — it sets clear expectations for both sides. Please review, sign, and return before production begins." 3. If supplier pushes back on specific clauses: negotiate per the notes in P2E.05 4. Minimum: get acknowledgment of AQL standards even if they won't sign a formal document
WEEKS 9-12: MONITOR PRODUCTION
🟡 #5 | Request Milestone 1 photos (Day 7-10: materials received + cutting) | 15 min | $0 | 1. On Day 7 after deposit, message supplier: "How is production progressing? Can you send photos of materials received — fabric, zippers, buckles?" 2. Review photos: verify YKK packaging, fabric GSM tag, Duraflex buckle bag, lab dip swatches 3. Approve lab dip colors (photograph under daylight on your end too) 4. If anything looks wrong: flag immediately — easier to fix at material stage
🟡 #6 | Request Milestone 2 photos (Day 15-20: 50% sewing complete) | 15 min | $0 | 1. Message: "Production update? Can you send photos of completed units — front/back, zipper close-up, silicone dots, measurement of front panel height?" 2. Compare photos to your approved PP sample — do they match? 3. Check: are all 4 colors being produced? Is the contoured profile visible? 4. If issues found: send specific correction instructions with photo markup
🟡 #7 | Review Milestone 3 pre-shipment photos + release 70% balance | 1-2 hrs | $2,520 (70% balance) | 1. Receive pre-shipment photos of 10 random units (5 S/M + 5 L/XL, mix of colors) 2. Inspect photos against P2E.01 acceptance criteria — focus on: zipper function (can you see auto-lock?), silicone dots, reflective strips, contoured profile, color accuracy 3. Verify unit count by size/color matches your allocation 4. If satisfied: approve and release 70% balance via Trade Assurance 5. If not: list specific issues, request fixes, do NOT release payment until resolved 6. This is your LAST leverage point before the supplier ships