## P3B EXEC SUMMARY
P3B PRODUCTION QUALITY CONTROL & APPROVAL — EXECUTIVE SUMMARY
6 Tasks ¦ Weeks 11-12 ¦ The critical gate between your money and your product. DO NOT release the 70% balance until every check passes.
Task ID | Task | KPI | Deliverable | Status | Why This Matters | Risk If Skipped | Effort
3B.01 | Request pre-shipment photos of 10 random units from the completed batch | 30 photos received covering 10 units × 3 angles | Complete pre-shipment photo inspection guide: 30-point photo checklist with exact photo angles to request, what to look for in each photo, pass/fail criteria for remote visual inspection, and a "photo quality" scoring system for the supplier's photography itself. | COMPLETE ✓ | Pre-shipment photos are your ONLY window into production quality before you release $2,520. A rushed, blurry photo review = missed defects that you discover when 600 units arrive at your door. Take 2-3 hours on this — it's the highest-ROI time you'll spend. | You release $2,520 blind. Supplier ships defective units. You discover problems AFTER money is gone and product is in transit. Dispute process takes 30-60 days. Your launch is delayed by 2+ months. | 2-3 hours
3B.02 | Option: hire third-party QC inspector for on-site factory inspection | Inspector hired OR decision documented to self-inspect | Complete third-party inspection guide: when to hire (cost-benefit analysis at $268-$388), top 3 inspection services compared (QIMA, SGS, Bureau Veritas), exactly what to include in the inspection scope, how to read the inspection report, and the decision framework for hire vs skip. | COMPLETE ✓ | A professional inspector at the factory sees what photos can't: actual fabric hand feel, zipper smoothness in person, silicone dot adhesion under nail test, and random unit selection (not supplier-curated "best 10"). At $268-$388, this is insurance against a $3,600+ loss. | Without on-site inspection, you rely 100% on supplier-selected photos. Suppliers naturally photograph their best units. An inspector pulls RANDOM units and tests objectively. The $300 cost is 8% of your production spend — cheap insurance. | 15 min to hire (inspector does the 4-6 hour inspection)
3B.03 | Review and approve final production: unit count, packaging, labeling accuracy | Signed production approval form | Complete final production approval checklist: 18-item verification covering unit count by SKU, packaging completeness, label accuracy (FTC compliance), size/color correctness, and a formal sign-off form that becomes the production release authorization. | COMPLETE ✓ | This checklist catches the "quiet" errors that photos miss: wrong size labels on 50 units, color mixed up between cartons, missing hang tags on 30% of belts, packing list count doesn't match actual count. These errors are fixable at the factory for $0 — but unfixable after shipment. | Customer receives L/XL label on an S/M belt = instant 1-star review + return. Carton labeled "Black" contains Desert Rose = fulfillment chaos. 50 units missing hang tags = you spend 3 hours hand-attaching. Prevention > cure. | 30-60 min
3B.04 | Pay remaining 70% balance upon satisfactory inspection | $2,520 released via Trade Assurance | Complete 70% payment release protocol: 6-condition decision tree (all 6 must pass before releasing payment), dispute scenarios with scripts, partial payment negotiation guide, and the exact steps to release funds via Alibaba Trade Assurance. | COMPLETE ✓ | The 70% balance ($2,520) is your LAST leverage before the supplier ships. Once you release payment, the supplier packs and ships within 24-48 hours. Any defects discovered after payment release require a dispute process (30-60 days). Protect this leverage. | You release payment on faith. Supplier ships immediately. Goods arrive with 8% major defect rate. You file a dispute but Alibaba mediation takes 45 days. Your launch is delayed. You're out $2,520 while waiting for resolution. | 15 min (once decision is made)
3B.05 | Confirm packing: individually poly-bagged, size labeled, packed in export cartons | Packing specification confirmed and photographed | Complete export packing specification: how each unit should be folded/bagged, carton dimensions, units per carton, carton labeling format, packing list template, and a visual packing standard photo to share with the supplier. | COMPLETE ✓ | Proper packing prevents: transit damage (crushed zippers, deformed elastic), inventory confusion (which carton has which SKU?), customs delays (missing commercial invoice or packing list), and fulfillment errors (pulling wrong size/color during packing). | Cartons arrive unlabeled — you open 20 boxes to find S/M Black. Belts are loose in cartons (not poly-bagged) and arrive with zipper impressions on fabric. Packing list is in Chinese — you can't verify count without opening everything. Customs holds shipment for missing invoice. | 30 min to communicate spec to supplier
3B.06 | Document full production run: final cost, units per SKU, factory contact, lessons learned | Production Run Report completed | Complete first production run documentation: every number, contact, date, cost, and lesson learned — captured in a template that becomes the reference for all future production runs. This is your manufacturing "playbook" that grows with every order. | COMPLETE ✓ | Documentation turns a one-time manufacturing exercise into a repeatable process. Without it, your second production run starts from scratch. With it, reorder takes 30 minutes instead of 30 hours. Every lesson learned (good and bad) is captured for v2. | Second production order: "What was the exact price per unit? What was the supplier's contact WeChat? How long did production actually take? Which color needed a lab dip?" Without documentation, you re-research everything from scratch. Weeks wasted. | 1-2 hours post-production

## 3B.01 Photo Inspection
P3B TASK 3B.01: PRE-SHIPMENT PHOTO INSPECTION — 30 PHOTOS, 10 UNITS, 3 ANGLES EACH
Send the photo request message below to your supplier WORD FOR WORD. Review every photo against this checklist. This is your $2,520 decision.
# | Photo Category | Exact Photo Request (send this to supplier) | What You're Looking For | Pass | Fail | Score (0-2) | Notes
MESSAGE TO SUPPLIER (copy-paste this ENTIRE message via WeChat/WhatsApp/email)
— | SEND THIS MESSAGE | "Hi [NAME], production is complete — congratulations! Before I release the 70% balance, I need pre-shipment inspection photos. Please send the following: 1. Select 10 RANDOM units: 5 S/M + 5 L/XL. Include at least 1 unit of each color (Black, Desert Rose, Alpine Sage, Deep Ocean). Do NOT select your best units — I need a representative random sample. 2. For EACH of the 10 units, please photograph: a) Front view (belt laid flat, front facing up) b) Back view (belt flipped, interior/mesh side visible) c) Close-up of phone pocket zipper (open, showing YKK stamp on slider) 3. Additional photos (1 each): - ALL units lined up side-by-side showing color consistency - Ruler measurement of front panel height on 1 S/M and 1 L/XL unit - Interior silicone grip dots close-up (macro if possible) - Reflective strips photographed WITH FLASH (to show reflectivity) - Phone pocket with a phone/block inserted showing fit - Hang tag attached to belt - Care label inside belt (readable) - Full cartons packed and labeled Total: approximately 30+ photos. Please send in high resolution (not compressed). Thank you!" | The specificity of this request signals professionalism. Suppliers who receive vague "send some photos" requests send 3 blurry shots. Suppliers who receive a 30-photo shot list send exactly what you need — because they know you're serious about quality. |  |  |  | Send this message 24-48 hours before you expect production to finish (based on 3A.06 Milestone 3 timing). Give the supplier time to prepare good photos.
INDIVIDUAL UNIT PHOTOS (10 units × 3 angles = 30 core photos)
1-10 | FRONT VIEW (all 10 units) | Belt laid flat on a clean surface, front facing up. All pockets visible. Buckle visible. Brand label visible at rear. | Check each of the 10 photos for: • Overall symmetry — is the belt evenly shaped left and right? • Pocket positions — phone pocket centered at rear, valuables at right hip, gel at left hip? • Contoured profile visible — is the front panel taller than the back? Can you see the curved bottom edge? • Color consistency — do all units of the same color match? • No visible loose threads, stains, or wrinkles • Buckle attached and straight • Brand label visible at center-rear | ✅ All 10 units look symmetrical, clean, and consistent with each other and with the approved PP sample. | ❌ Visible asymmetry between pockets. Inconsistent color across units. Loose threads visible at arm's-length photo distance. Belt appears flat (no contoured profile). Brand label crooked or missing. |  | Score each of the 10 front photos 0-2. Average = front score.
11-20 | BACK VIEW (all 10 units) | Belt flipped over showing the interior mesh lining and silicone grip dots. All edges visible. | Check each for: • Silicone grip dots — clearly visible in a staggered hex grid pattern covering the area behind all 3 pockets • Dots appear uniform — consistent size, consistent spacing, no missing patches • Mesh lining looks clean — no stains, no rough spots, no exposed raw edges • Flatlock seams visible on all skin-contact edges (top/bottom of waistband, pocket openings) • No overlocked (rough) seams on skin-contact surfaces • Elastic visible at waistband edges — looks consistent width, not stretched or wavy | ✅ Silicone dots clearly visible in hex grid pattern with 50-60% coverage behind all pocket zones. Mesh clean. Flatlock seams on all edges. Elastic looks fresh. | ❌ Silicone dots sparse, missing behind some pockets, or only behind phone pocket. Visible rough/overlocked seams on skin-contact edges. Elastic appears wavy or unevenly stretched. Mesh has visible stains or rough patches. |  | Silicone dot coverage is the #1 thing to check on back photos. If dots only cover the phone pocket zone (not valuables and gel zones), this is a MAJOR defect flagged in P2E.01.
21-30 | ZIPPER CLOSE-UP (all 10 units) | Phone pocket zipper open, camera focused on the slider. YKK stamp must be visible on the slider back. | Check each for: • "YKK" stamped on the back of the zipper slider — this is the authentication mark • Slider appears aligned with zipper teeth (not crooked or loose) • Zipper tape color matches the pocket fabric color • Uretek coating visible on phone pocket zipper tape (slightly glossy/sealed appearance) • Auto-lock feature: is there a visible pin mechanism on the slider top? • Zipper endpoints: neatly finished, no loose threads at bartack points | ✅ YKK stamp clearly readable on all 10 sliders. Uretek coating visible on phone pocket zippers. Sliders aligned. Tape color matches. | ❌ No YKK stamp visible on ANY slider = counterfeit zippers. This is an AUTO-REJECT — stop inspection, do NOT release payment, demand explanation. Also fail: slider crooked, tape color mismatched, endpoints fraying. |  | 🔴 NO YKK STAMP = AUTO-REJECT THE ENTIRE SHIPMENT. This means the supplier substituted counterfeit zippers despite the spec and quality agreement. Reference P2E.05 Clause 6 (materials verification). File dispute immediately.
ADDITIONAL PHOTOS (1 each — these verify specific quality details)
31 | COLOR LINEUP | All 10 units lined up in a row on a white/neutral background, grouped by color. All 4 colors represented. | Compare color consistency WITHIN each color group — all 3 Blacks should match, both Roses should match, etc. Also compare to your approved lab dip swatch photos (save these from P2B for comparison). Look for: shade variation between units of the same color. Minor variation (±1 dE) is normal for reactive dyes. Gross variation (one Rose looks brown, another looks pink) = dye lot mixing issue. | ✅ All units within each color group appear visually identical under the photo lighting. Colors match approved lab dip swatches within acceptable variance. | ❌ Visible shade difference between units of the same nominal color. Rose appears to have 2 different shades. Black shows grey tint on some units. This indicates mixed dye lots in production. |  | Ask supplier to photograph under consistent lighting. If they use different lighting for different units, color comparison is impossible. Natural daylight or consistent fluorescent — not mixed.
32 | MEASUREMENT VERIFICATION | Ruler or tape measure laid against 1 S/M unit and 1 L/XL unit, measuring front panel height from top edge to bottom edge. | Verify front panel height matches P2A spec: • S/M front: 9-10cm ±0.5cm • L/XL front: 9-10cm ±0.5cm Also verify: the rear panel is visibly shorter than the front in the same photo (contoured profile). This is the ONLY dimensional check possible via photo. All other dimensions require physical inspection (incoming per P2E.02). | ✅ Measurement shows 9-10cm front panel. Contoured profile visible (front taller than back) in the same photo. | ❌ Measurement shows <8.5cm or >10.5cm. Front and back appear same height (no contour). Ruler placement is ambiguous or photo too blurry to read measurement. |  | If measurement is off: request a second photo with clearer ruler placement before escalating. Photo angle can distort measurements. Two consistent off-spec photos = real issue.
33 | SILICONE DOTS MACRO | Interior of belt, close-up macro photo of silicone grip dots. Camera focused on a 5cm × 5cm area showing individual dot detail. | Verify dot characteristics: • Shape: circular, uniform ~4mm diameter • Pattern: staggered hexagonal grid (not random scatter) • Height: dots appear raised (cast shadow visible in photo) • Spacing: ~8mm center-to-center (roughly 2 dot-widths between dots) • Coverage: 50-60% of the surface behind pockets • Adhesion: no dots appear lifted, cracked, or peeling • Color: clear/translucent (not pigmented) | ✅ Uniform dot grid clearly visible. Dots appear raised and well-bonded. Consistent pattern. No peeling or damage. | ❌ Dots appear flat (poor print height). Irregular scatter pattern (not hex grid). Visible peeling or lifted dots. Pigmented instead of clear. Dots only in small patches instead of full pocket zone coverage. |  | If dots look flat in photo but supplier claims they're raised: request a side-angle macro photo showing dot profile against the fabric surface. Photo angle matters for showing dot height.
34 | REFLECTIVE FLASH TEST | Belt photographed WITH camera flash ON. Flash should illuminate the 3M reflective strips. | Under flash: • Reflective strips should glow brightly (high retroreflectivity) • Both front and rear strips should be visible • Segmented pattern should be visible (5510 series has visible segments for stretch) • Logo reflective (5807 series) should also glow if applied Compare reflective brightness to any reflective gear you own (jacket, shoes) — it should be equally bright or brighter. | ✅ Reflective strips glow intensely under flash. Both front + rear strips visible. Segmented pattern confirms 3M 5510 series. | ❌ Strips don't glow under flash (wrong material — not reflective). Only 1 strip visible (second missing). Continuous film instead of segmented (wrong product — should be 5510 not 8712). |  | Ask supplier to send 2 versions of this photo: one without flash (normal appearance) and one WITH flash (reflective test). The comparison makes reflectivity obvious.
35 | PHONE FIT TEST | Phone pocket with a phone (or dimensional block 175×91×17mm) inserted inside. Zipper closed over phone. Belt laid flat. | Verify: • Phone fits entirely inside pocket with no part protruding • Zipper closes fully over the phone without strain or bulging • Pocket stretches to accommodate the phone but doesn't look over-stressed • The phone profile through the pocket fabric looks smooth (no extreme bulge) | ✅ Phone fully seated inside pocket. Zipper closed flat. Belt maintains shape with phone inside. | ❌ Phone protrudes above pocket opening. Zipper won't close over phone. Extreme bulge visible. Belt distorts under phone weight. |  | If supplier doesn't have an iPhone 16 Pro Max: send them a dimensional block specification (175×91×17mm) and ask them to use a cardboard cutout of those exact dimensions. This is a valid proxy.
36 | HANG TAG ATTACHED | Belt with hang tag attached via cotton cord looped through the buckle D-ring. Tag front and back visible. | Verify: • Hang tag is attached (not just placed next to belt) • Cord threaded through eyelet and D-ring • Tag front: wordmark, tagline, product descriptor — text legible • Tag back: micro-story, care icons, URL, size/color field filled in correctly • Tag paper: looks thick (350 GSM) with visible soft-touch finish | ✅ Tag professionally attached. Both sides printed correctly. Paper feels premium (as judged from photo — edges look thick, finish appears matte). | ❌ Tag missing. Cord not attached. Text printed blurry or off-center. Wrong size printed on tag. Tag paper appears flimsy (thin edges visible). |  | If tags are not yet attached in photos: acceptable if supplier confirms they'll attach before packing. Verify that tags are printed correctly by requesting a close-up of 3 different tags showing size/color variations.
37 | CARE LABEL INSIDE | Interior of belt showing the sewn-in care label. Label text must be readable in photo. | Verify FTC compliance requirements: • Fiber content: "80% Nylon, 20% Spandex" (or actual composition) • Country of origin: "Made in China" or "Imported" • Manufacturer name or RN number • Care symbols: machine wash cold, tumble dry low, no iron, no bleach (ISO 3758 symbols) • Size designation: S/M or L/XL • Website: strideher.com All text must be legible at normal reading distance. | ✅ All 6 required elements present and legible. Size designation matches the belt it's sewn into. Care symbols are standard ISO 3758. | ❌ Missing country of origin (FTC violation). Wrong fiber content. Wrong size designation sewn into the belt. Illegible text. Missing care symbols. |  | Missing country of origin is an FTC violation that can result in $10,000+ fine AND Amazon listing removal. If care label is missing COO: this is a CRITICAL defect. Halt shipment. Demand re-labeling before packing.
38 | PACKED CARTONS | All finished export cartons lined up, exterior labels visible. Plus one carton opened showing neatly packed poly-bagged units inside. | Verify: • Cartons appear sturdy (double-wall corrugated preferred for international shipping) • Exterior labels on each carton: SKU/size/color, quantity, carton number (e.g., 1 of 15) • Labels in ENGLISH (not only Chinese) • Interior: units individually poly-bagged, neatly arranged (not loose or crushed) • Packing list visible inside or on top of carton • No damage to cartons (dents, moisture marks, tape failure) | ✅ Sturdy labeled cartons. English labels with SKU, quantity, and carton number. Interior shows neatly packed poly-bagged units. Packing list present. | ❌ Unlabeled cartons (fulfillment nightmare — you open every box to find what you need). Labels in Chinese only. Units loose inside (not poly-bagged). Carton damage visible. No packing list. |  | Unlabeled cartons are the #1 logistics failure in small-batch Alibaba orders. You WILL spend 4-6 hours sorting through unlabeled cartons. Labeled cartons save that time entirely. Insist on English labels.
PHOTO INSPECTION SCORECARD — tally your results before making the payment decision
— | TOTAL SCORE | Score all 38 photo checks on 0-2 scale. 2 = Clearly passes (confident) 1 = Uncertain / borderline (acceptable but note concern) 0 = Clearly fails (defect or issue evident) Total possible: 76 points. Scale to 100: (your score ÷ 76) × 100. | YOUR SCORE: ___ / 76 = ___% DECISION: ≥80% + zero auto-reject failures → APPROVE: release 70% payment 65-79% → CONDITIONAL: request re-takes of failed items, re-score <65% → REJECT: do NOT release payment, request re-work or dispute | APPROVE ≥80% Zero auto-rejects | REJECT <65% OR any auto-reject (no YKK stamp, missing COO on label, phone doesn't fit) | TOTAL: ___/76 = ___% | Document your score and save it. If you later need to file a dispute with Alibaba, this documented inspection record is critical evidence. Screenshot every photo and save with date.

## 3B.02 Third-Party QC
P3B TASK 3B.02: THIRD-PARTY QC INSPECTION — HIRE A PROFESSIONAL TO INSPECT AT THE FACTORY
Cost: $268-$388 per inspection. That's 7-10% of your production spend for professional, objective, on-site quality verification. STRONGLY recommended for first orders.
Element | Details | QIMA (formerly AsiaInspection) | SGS | Bureau Veritas | Self-Inspect (no third party) | Recommendation
DECISION FRAMEWORK: Should you hire a third-party inspector?
When to HIRE (recommended) | ✅ HIRE a third-party inspector when: 1. FIRST ORDER with a new supplier (you have zero trust established) 2. Order value exceeds $2,000 (the inspection cost is <15% of order value) 3. You CANNOT visit the factory yourself 4. Supplier was slow or evasive during sample phase (trust concerns) 5. You're selling on Amazon (1-star reviews from defects are devastating to ranking) 6. Product is body-worn (safety and comfort tolerance is very low) StrideHer's first order checks ALL 6 boxes. | ✅ QIMA offers "Product Inspection" starting at $268/day for standard service. Booking: qima.com or Alibaba Inspection Service (same company). | ✅ SGS Pre-Shipment Inspection (PSI) starting at $300-$400. Booking: sgs.com or contact local office. | ✅ Bureau Veritas Consumer Products starting at $350-$450. Booking: bureauveritas.com | ⚠️ Self-inspect = rely entirely on supplier photos (3B.01). Acceptable ONLY if: - Budget is extremely tight - Supplier has 3+ positive verified reviews on Alibaba - Sample phase was flawless | For StrideHer first order: ★ HIRE QIMA ($268). Reason: first order, new supplier, body-worn product, $3,600 at risk, Amazon launch planned. The $268 cost is 7% of production spend. If it catches even 1 batch-wide defect, it saves $3,600+.
When to SKIP (acceptable) | ✅ SKIP third-party inspection when: 1. Repeat order with a proven supplier (2+ successful orders) 2. Order value under $1,000 (inspection cost is >25% of order) 3. You can visit the factory yourself 4. Supplier has a long track record with verified Western buyers 5. Product is not body-worn (lower safety sensitivity) Note: even if you skip, ALWAYS do the photo inspection (3B.01). |  |  |  |  | If you choose to skip third-party inspection: at minimum, complete the full 3B.01 photo inspection (30 photos, 38 checks) and the 3B.03 final approval checklist. This provides 70-80% of the protection at $0 cost.
HOW TO HIRE QIMA (step-by-step — the most common and affordable option)
Step 1: Book Online | Go to qima.com → "Book an Inspection" → select "Pre-Shipment Inspection (PSI)" OR: Alibaba.com → "Inspection Service" (QIMA is Alibaba's official inspection partner) | Fill in: • Product: Running Belt • Factory: [supplier name + address] • Inspection date: [date production completes] • Quantity: 600 units • Service: Pre-Shipment Inspection |  |  |  | Book 3-5 days before the expected production completion date. QIMA has inspectors near every major Chinese manufacturing hub (Shenzhen, Guangzhou, Xiamen, Shanghai). Typical booking-to-inspection: 48 hours.
Step 2: Provide Spec + AQL | QIMA asks you to upload: (1) your technical specification, (2) your quality acceptance criteria, and (3) your AQL standards. Upload: • P2A.03-04 Tech Spec (PDF) • P2E.01 Acceptance Criteria (PDF) • AQL standards: Critical 0, Major 2.5, Minor 4.0 | QIMA uses YOUR spec and YOUR AQL as the inspection standard. They don't impose their own — they enforce YOURS. | Same approach for SGS. Upload your spec and AQL. | Same for BV. | N/A | The quality of the inspection depends entirely on the quality of YOUR spec. Because you built P2A and P2E with measurable criteria, the inspector has clear, testable standards. Vague specs = vague inspections.
Step 3: Inspector Visits Factory | A trained QIMA inspector visits the factory on the scheduled date. They: 1. Pull a RANDOM sample of 32 units (per ISO 2859-1, same as your P2E.02 plan) 2. Inspect each unit against your spec and acceptance criteria 3. Measure dimensions with calibrated tools 4. Test zippers (smooth operation, auto-lock, YKK verification) 5. Test silicone dots (thumbnail adhesion test) 6. Verify fabric (4-way stretch test, GSM tag verification) 7. Check reflective strips (flash test) 8. Verify labeling (FTC compliance) 9. Count total units by SKU 10. Photograph defects with annotations Duration: 4-6 hours on-site. | QIMA provides: • Written inspection report (PDF, same day or next day) • Defect photos with annotations • Pass/Fail/Pending decision based on your AQL • Defect breakdown by category (critical/major/minor counts) | SGS provides similar deliverables. Typically next-day report. | BV similar. Report within 24-48 hrs. | N/A — no report. You rely only on supplier photos. | The inspector sends you the report BEFORE you release the 70% payment. If the report says FAIL: you have documented, third-party evidence for your Alibaba dispute. This is 100× stronger than "the photos looked bad."
Step 4: Review Report + Decide | You receive the inspection report (PDF, typically same day or next day). It contains: • Overall result: PASS / FAIL / PENDING • Total units inspected: 32 • Critical defects: ___ • Major defects: ___ • Minor defects: ___ • Defect photos with descriptions • Dimensional measurements • YKK zipper verification result • Recommendations Your decision: • PASS (AQL met) → release 70% payment • FAIL (AQL exceeded) → do NOT release payment, initiate re-work or dispute • PENDING (borderline) → request re-inspection after re-work | Cost: $268 standard $188 for Alibaba Trade Assurance members (discounted). Payment: credit card on qima.com. | Cost: $300-$400 depending on region and scope. | Cost: $350-$450. Most expensive but most prestigious name. | Cost: $0. Risk: highest. | COST COMPARISON AT 600 UNITS: QIMA: $268 = $0.45/unit SGS: $350 = $0.58/unit BV: $400 = $0.67/unit Self: $0 = $0/unit At $268, QIMA is the clear value leader. The cost adds $0.45 to your effective COGS — from $6.00 to $6.45/unit. Gross margin impact: 79.9% → 78.6%. Negligible.

## 3B.03 Final Approval
P3B TASK 3B.03: FINAL PRODUCTION APPROVAL — 18-ITEM VERIFICATION + SIGN-OFF FORM
Complete this checklist BEFORE releasing the 70% balance. This is the production release authorization — once signed, supplier packs and ships.
# | Verification Item | How to Verify | Pass? | Issue Found (if any) | Resolution Required | Status
UNIT COUNT VERIFICATION (must match your purchase order allocation from P3A.02)
1 | Total unit count = 600 | Supplier confirms written count. Cross-check against QIMA report if available. Verify against packing list. |  |  | If count is short: demand production of missing units BEFORE shipment. Short counts are common (5-10 units) — catch before approving.
2 | S/M count = 270 | Verify S/M subtotal from packing list or supplier confirmation. |  |  | Any size imbalance >10 units from order: flag immediately. Wrong size split = wrong inventory for demand.
3 | L/XL count = 330 | Same verification.
4 | Black count = 270 (122 S/M + 148 L/XL) | Verify color count from packing list. Supplier should provide count by color AND by size.
5 | Desert Rose count = 120 (54 S/M + 66 L/XL) | Same. |  |  | If custom colors are short: these are the hardest to re-make (lab dip required). Ensure full allocation before shipping.
6 | Alpine Sage count = 120 (54 S/M + 66 L/XL) | Same.
7 | Deep Ocean count = 90 (40 S/M + 50 L/XL) | Same.
QUALITY VERIFICATION (cross-reference with 3B.01 photo inspection and/or QIMA report)
8 | Photo inspection score ≥80% (from 3B.01) | Review your completed 3B.01 scorecard. Minimum 80% with zero auto-reject failures. |  |  | If below 80%: do NOT approve. Request supplier re-work on failed items and re-submit photos.
9 | QIMA inspection result = PASS (if hired) | Review QIMA inspection report. Overall result must be PASS or CONDITIONAL PASS with only minor defects. |  |  | If QIMA result is FAIL: do NOT approve. Reference specific defect counts and request re-work per quality agreement (P2E.05 Clause 4).
10 | YKK zippers confirmed genuine | YKK stamp verified on zipper sliders in photos (3B.01 checks #21-30) AND/OR QIMA inspector verified in person. |  |  | 🔴 If YKK not verified: AUTO-REJECT. This is a material substitution violation per quality agreement Clause 6. Do not release payment.
PACKAGING & LABELING VERIFICATION
11 | Hang tags attached to all units | Photo 36 confirms tags attached. Supplier confirms all 600 units have tags. Spot-check in carton photo (38). |  |  | Missing tags: common oversight. If 10-20 are missing, supplier can attach before shipping (10 min). If >50 missing: order tags separately or demand supplier re-attach.
12 | Care labels sewn inside all units — FTC compliant | Photo 37 confirms correct content. Verify: fiber content, COO, care symbols, size designation. ALL present and legible. |  |  | 🔴 Missing country of origin on care label = FTC violation. HALT shipment. Demand re-labeling. This is legally required for US textile sales.
13 | Correct size designation on each unit's care label | Supplier confirms: all S/M units have "S/M" on care label, all L/XL units have "L/XL." Cross-check with carton labels. |  |  | Wrong size label = customer receives misleading information = returns + 1-star reviews. If any labels are wrong: demand relabeling before shipment.
14 | Units individually poly-bagged | Carton interior photo (38) shows units in individual clear poly bags. Supplier confirms all 600 are bagged. |  |  | Un-bagged units arrive with: dust, moisture, zipper impressions on adjacent units, and tangled hang tags. Insist on individual poly-bagging.
15 | Cartons labeled in English with SKU + quantity | Carton exterior photo (38) shows English labels. Each carton labeled with: size, color, quantity, and carton number. |  |  | Unlabeled cartons = 4-6 hours of your time sorting. Labeled cartons = you know exactly which box to open for which SKU. Non-negotiable.
DOCUMENTATION VERIFICATION
16 | Packing list received (English, itemized by SKU) | Supplier provides a packing list showing: carton numbers, contents per carton (SKU + qty), total count, gross weight, net weight, carton dimensions. |  |  | No packing list = you can't verify count without opening every carton. And customs may require a packing list for clearance. Demand before approving.
17 | Commercial invoice received | Supplier provides commercial invoice showing: product description, quantity, unit price, total value, HS code (4202.92), origin country. |  |  | Commercial invoice is required for customs clearance. Without it: shipment may be held at port. Request before shipping, not after.
18 | Tracking number provided or shipping booked | Supplier confirms shipping method (air vs sea) and provides tracking number or booking confirmation. |  |  | No tracking number = you can't monitor transit. If supplier says "will ship tomorrow" without tracking: wait for actual tracking before confirming receipt.
PRODUCTION APPROVAL SIGN-OFF
— | SIGN-OFF FORM | I, [YOUR NAME], have reviewed the pre-shipment photos, inspection results, unit counts, packaging, and documentation for StrideHer Production Order #[PO NUMBER]. All 18 verification items above have been checked. Items passed: ___/18 Items with issues (resolved): ___/18 Items with issues (unresolved): ___/18 ☐ I APPROVE this production run and authorize release of the 70% balance payment ($___) via Alibaba Trade Assurance. ☐ I DO NOT APPROVE this production run. Issues listed above must be resolved before payment release. Signed: _________________________ Date: _____________

## 3B.04 Payment Release
P3B TASK 3B.04: 70% PAYMENT RELEASE PROTOCOL — 6 CONDITIONS MUST PASS BEFORE YOU PAY
Total: $2,520 (at $6.00/unit × 600 units × 70%). This is the LARGEST single payment in the entire $10K budget. Protect it.
Condition | What Must Be True | How to Verify | If It Fails | Payment Status | Dispute Script | Priority
ALL 6 CONDITIONS MUST PASS. If ANY condition fails, DO NOT release payment until resolved.
CONDITION 1: Photo Score ≥80% | Your 3B.01 pre-shipment photo inspection scored ≥80% (61/76 points) with ZERO auto-reject failures. | Complete 3B.01 photo checklist. Calculate score. Verify zero auto-reject items failed. | Score 65-79%: request re-take of failed photos. May be photo quality, not product quality. Give supplier 48 hours to re-submit clearer photos. Score <65%: major quality concern. Request QIMA inspection if not already hired. Do NOT release payment. | HOLD until ≥80% or resolution | "Thank you for the pre-shipment photos. I've reviewed them against our quality standards and identified [X] items that need attention before I can release the balance payment. Specifically: [list items]. Can you address these and re-submit photos within 48 hours?" | 🔴 CRITICAL
CONDITION 2: QIMA PASS (if hired) | QIMA inspection report shows: PASS or CONDITIONAL PASS. Critical defects = 0. Major defects ≤ AQL 2.5 threshold. Minor defects ≤ AQL 4.0 threshold. | Read QIMA report (PDF). Check summary page for overall result and defect counts. | QIMA result = FAIL: do NOT release payment. Email supplier with QIMA report attached: "Our third-party inspection found [X] critical and [Y] major defects exceeding our agreed AQL standards. Per our quality agreement (Clause 4), please re-work the defective units and schedule a re-inspection." | HOLD until PASS | "Attached is the inspection report from our quality partner. The results show [defect summary]. Per our quality agreement, we need these issues resolved before we can release the balance. Please provide a corrective action plan within 48 hours." | 🔴 CRITICAL
CONDITION 3: Unit Count Verified | Total units = 600 (±5 units acceptable). Size and color split matches order allocation within ±5 units per SKU. | Packing list from supplier. QIMA count if available. Cross-check: total cartons × units per carton = total count. | Short by 1-10 units: negotiate credit of (missing units × unit price) off the balance payment. Short by >10 units: request supplier produce additional units before shipping. OVER by 1-10 units: accept (free inventory). Over by >10 units: verify not being charged for extras. | HOLD if short >10 ACCEPT if within ±5 | "Our packing list shows [X] total units, but our order was for 600. Can you confirm the count? If the shipment is [Y] units short, we'd like to deduct [Y × $unit price] from the balance, or add the missing units to the shipment." | 🟡 HIGH
CONDITION 4: YKK Verified | YKK brand stamp confirmed on ALL zipper sliders via photo close-ups (3B.01 checks #21-30) AND/OR QIMA physical verification. | Review all 10 zipper close-up photos from 3B.01. YKK stamp must be visible on every slider. | 🔴 NO YKK stamp on any slider = material substitution. This is a BREACH of the quality agreement (Clause 6). Do NOT release payment. File Alibaba Trade Assurance dispute immediately citing material substitution. | HOLD — no exceptions. This is a deal-breaker. | "Our quality agreement specifies genuine YKK zippers (Clause 6). The pre-shipment photos do not show YKK stamps on the zipper sliders. This appears to be an unauthorized material substitution. We cannot release the balance payment until genuine YKK zippers are confirmed. Please explain and provide a corrective action plan." | 🔴 CRITICAL
CONDITION 5: FTC Labeling Compliant | Care labels on all units contain: fiber content, country of origin, manufacturer/RN, and care symbols. Verified via photo (3B.01 check #37). | Read the care label photo. All 4 FTC-required elements present and legible. | Missing country of origin: HALT shipment. Demand re-labeling. Supplier must sew corrected labels before packing. This is a LEGAL requirement, not a preference. Wrong fiber content: demand correction. Wrong fiber content is a federal misrepresentation. | HOLD if COO missing. ACCEPT if all 4 elements present. | "Our care labels appear to be missing [country of origin / correct fiber content]. This is a US Federal Trade Commission requirement for textile products — we legally cannot sell products in the US without compliant labeling. Please re-label all units before packing. We'll release payment once corrected labels are confirmed." | 🔴 CRITICAL
CONDITION 6: Packing Complete | All units individually poly-bagged, hang tags attached, cartons labeled in English with SKU + quantity, packing list in English, commercial invoice provided. | Review carton photos (3B.01 check #38). Verify supplier confirms all packing requirements met. Request packing list PDF. | Incomplete packing is NOT a payment hold — it's a "fix before you ship" request. Supplier can correct packing issues in 1-2 days at the factory. Do NOT accept shipment of loose, unlabeled goods "because we're in a hurry." | ACCEPT once packing confirmed complete. | "Before shipping, please confirm: (1) all units are individually poly-bagged, (2) hang tags are attached, (3) cartons are labeled in English with size/color/quantity, (4) packing list is included in English. Once confirmed, I'll release the balance immediately." | 🟡 HIGH
PAYMENT RELEASE — execute only when ALL 6 conditions pass
RELEASE PAYMENT | All 6 conditions confirmed: photo score ≥80%, QIMA pass (if hired), unit count verified, YKK confirmed, FTC labels compliant, packing complete. Release $2,520 via Alibaba Trade Assurance. Steps: 1. Log into Alibaba → Orders → find your order 2. Click "Confirm Goods" or "Release Payment" 3. Confirm the amount ($2,520) 4. Payment released to supplier within 24-48 hours 5. Supplier ships within 24-48 hours of receiving payment | Take a screenshot of the payment release confirmation. Save with your production documentation (3B.06). | If you cannot reach "all 6 pass" status after 2 rounds of back-and-forth with the supplier: escalate to Alibaba Trade Assurance dispute resolution. Upload: your quality agreement, photo inspection evidence, QIMA report (if available), and communication history. | ✅ RELEASED | Send a warm message after releasing: "Payment released! Thank you for your hard work on this order. Looking forward to receiving the shipment and to our next order together. Please send tracking information as soon as shipping is booked." | ✅ FINAL STEP

## 3B.05 Packing Specifications
P3B TASK 3B.05: EXPORT PACKING SPECIFICATIONS — HOW 600 UNITS SHOULD BE PACKED FOR SHIPPING
Send this specification to your supplier with the production order. Proper packing prevents: transit damage, inventory confusion, customs delays, and fulfillment errors.
Element | Specification | Why It Matters | Common Mistakes | Visual Standard | Quantity | Cost Estimate
UNIT-LEVEL PACKING (how each individual belt is prepared)
Individual Poly Bag | Each belt folded to ~20 × 15cm and placed in a clear PE poly bag (25 × 20cm or similar). Bag sealed with a fold-over flap (not heat-sealed — needs to be easily openable by customer if shipped in this bag). Suffocation warning printed on bag: "WARNING: To avoid danger of suffocation, keep this bag away from babies and children." (Required by many US states for bags >5" in any dimension.) | Poly bag protects each unit from: dust during transit, moisture in ocean shipping containers, zipper impressions from adjacent units, tangled hang tags. Suffocation warning is legally required in many US states. Including it costs nothing and eliminates liability. | Units NOT poly-bagged: arrive dusty, with zipper marks on adjacent unit's fabric. No suffocation warning: technical legal liability (enforced primarily for children's products but best practice for all). | Photo reference: belt neatly folded in clear bag, hang tag visible through bag, size sticker on bag exterior. | 600 bags (1 per unit) | $0.02-$0.05 per bag (usually included in supplier's packaging cost)
Size Sticker on Bag | Small adhesive label on the OUTSIDE of each poly bag indicating: SIZE (S/M or L/XL) and COLOR NAME. Format: "S/M — Midnight Black" or "L/XL — Desert Rose" Label size: 40 × 20mm minimum. Clear, legible, printed (not handwritten). | When you're packing orders at 11 PM for next-day shipping, you need to grab the right SKU in <5 seconds. A clear size/color label on the exterior of each bag makes this possible WITHOUT opening every bag to check. | No labels: you open 20 bags to find "S/M Desert Rose." Labels inside bag (not exterior): same problem. Handwritten labels: illegible under fulfillment pressure. | Label clearly visible through or on the exterior of the clear poly bag. | 600 labels (1 per unit) | $0.01-$0.02 per label (usually included)
Hang Tag Pre-Attached | Hang tag attached via cotton cord through eyelet → looped through belt buckle D-ring. Attached BEFORE poly-bagging. Tag should be visible through the clear bag (another reason for clear, not opaque, bags). | Pre-attaching hang tags at the factory saves you 2-3 minutes per unit (= 30 hours for 600 units). This is a task the factory does in 10 seconds per unit on their production line. | Tags shipped loose in a separate bag: you spend 20+ hours hand-attaching 600 hang tags. Tags attached after poly-bagging: you open every bag, attach, re-bag. | Tag visible through clear poly bag, neatly positioned next to buckle. | 600 tags (pre-attached) | $0 additional (tag cost already in packaging budget)
Belt Folding Method | Belt folded in thirds: (1) fold left hip pocket toward center, (2) fold right hip pocket toward center, (3) resulting rectangle approximately 20 × 15cm. Buckle on TOP of fold (visible through bag). Pockets tucked inside (protected). Elastic not stretched during folding. | Consistent folding ensures: all units fit the same way in cartons (maximizing carton efficiency), no elastic stretching during storage, and a clean first-impression when customer opens the bag. Buckle on top means the customer sees the brand name (on buckle area label) first. | Random folding: units are different sizes in cartons, some elastic stretched, unprofessional appearance. Over-tight folding: creates permanent crease lines in elastic and silicone dots (per P2D.02 care instructions — don't fold tightly for extended periods). | Folded belt fits approximately 20 × 15 × 3cm in the poly bag. | N/A | $0
CARTON-LEVEL PACKING (how units are grouped for shipping)
Export Carton Specification | Standard export carton: 5-ply (double-wall) corrugated cardboard. Recommended size: 60 × 40 × 30cm (approximately 24" × 16" × 12") Capacity: ~40-50 poly-bagged belts per carton. 600 units ÷ 45 per carton ≈ 13-14 cartons total. Gross weight per carton: ~5-7 kg (well under air freight limits). | Double-wall cartons survive the abuse of international shipping: stacking 6+ cartons high in containers, forklift handling, rain exposure during loading, and multiple handoffs between truck/port/plane/truck. Single-wall (3-ply) cartons are cheaper but crush under stack weight — resulting in damaged units at the bottom. | Single-wall cartons: collapse under stacking weight, units at bottom get crushed. Oversized cartons: too heavy to handle, waste space, higher shipping cost. Undersized cartons: units jammed in, zippers pressed against each other. | Uniform-sized cartons stacked neatly. No bulging or deformation. | 13-14 cartons | $1.50-$3.00 per carton = $20-$42 total (often included in supplier price)
Carton Labeling (CRITICAL) | Each carton labeled on TWO sides (front + one end) with a printed or clearly hand-written label in ENGLISH containing: 1. Brand: StrideHer 2. Product: Women's Running Belt 3. Size: S/M or L/XL (or MIXED if carton contains both) 4. Color: Midnight Black / Desert Rose / Alpine Sage / Deep Ocean / MIXED 5. Quantity: [X] units 6. Carton number: [X] of [total cartons] (e.g., "Carton 7 of 14") 7. Gross weight: [X] kg 8. Country of origin: Made in China | Carton labels are how you find specific SKUs without opening every box. At 14 cartons, clear labeling saves 30-60 minutes per fulfillment session. Labeling on TWO sides means you can read the label regardless of how cartons are stacked. Carton numbering ("7 of 14") lets you verify all cartons arrived. | Labels in Chinese only: useless for English-speaking fulfillment. Labels on one side only: hidden when cartons are stacked against a wall. No quantity: you don't know how many units are in each carton without opening. No carton numbering: you don't know if a carton went missing in transit. | Printed label or clearly legible marker on white sticker. Same format on all cartons. | 14 labels (2 per carton × 7 unique configurations) | $0 (supplier provides labels — include in packing instructions)
Carton Organization | Pack by SIZE first, then COLOR within size: Cartons 1-6: ALL S/M (270 units) Cartons 1-3: S/M Black (122 units, ~40/carton) Carton 4: S/M Desert Rose (54 units) Carton 5: S/M Alpine Sage (54 units) Carton 6: S/M Deep Ocean (40 units) Cartons 7-14: ALL L/XL (330 units) Cartons 7-10: L/XL Black (148 units, ~37/carton) Carton 11: L/XL Desert Rose (66 units) Carton 12: L/XL Alpine Sage (66 units) Carton 13-14: L/XL Deep Ocean (50 units, split across 2 cartons with other L/XL overflow) Never mix sizes in one carton unless carton count doesn't divide evenly. | Size-first organization means: when you get an S/M Black order, you go straight to Cartons 1-3. No hunting through 14 cartons. This saves 60+ seconds per order over the lifetime of inventory. Color grouping within size makes physical inventory counts trivial: "I know S/M Black is in Cartons 1-3. How many are left?" | Random packing (mixed sizes/colors per carton): every order requires searching through multiple cartons. "Where's S/M Alpine Sage?" becomes a 5-minute treasure hunt. This is the #1 fulfillment efficiency mistake for small D2C brands. | Packing list shows carton-by-carton breakdown matching this organization. | See carton breakdown at left | $0 (organization only — communicate to supplier)
SHIPPING DOCUMENTS (must be inside or attached to the shipment)
Packing List | Document listing: carton numbers, contents per carton (SKU + quantity), total units, total cartons, gross weight per carton, total gross weight, total net weight, carton dimensions. IN ENGLISH. Printed, not handwritten. 1 copy inside Carton #1. 1 copy emailed to you as PDF. | Packing list is required for: customs clearance (some countries), inventory verification upon receipt, and dispute evidence if count is short. Email copy ensures you have it before the shipment arrives. | No packing list: you can't verify count without opening every carton. Handwritten in Chinese: useless for US customs. | Clean, typed document in table format. SKU, quantity, weight per carton. | 2 copies (1 physical + 1 emailed PDF) | $0
Commercial Invoice | Document for customs showing: shipper (supplier), consignee (you), product description, HS code (4202.92.9000 — travel/sports bags), quantity, unit value, total value, country of origin. HS Code 4202.92 = "Travel bags, sports bags, and similar containers" — running belts fall under this classification. US duty rate: approximately 17.6-20% ad valorem (on declared value). | Required for customs clearance. Without it: shipment held at port until you provide one. HS code determines duty rate. 4202.92 is the correct classification for waist-worn carrying accessories. | Wrong HS code: higher duties or customs audit. Missing invoice: shipment held at port. Undervalued invoice (supplier declares $1/unit instead of $6): customs fraud — serious legal risk. | Professional invoice on supplier letterhead. All values in USD. | 2-3 copies (customs may require multiple) | $0

## 3B.06 Run Documentation
P3B TASK 3B.06: FIRST PRODUCTION RUN DOCUMENTATION — YOUR MANUFACTURING PLAYBOOK
Capture everything from this first run. This document becomes your reference for every future order. Without it, reorder takes weeks instead of hours.
Category | Data Field | Value (fill in during/after production) | Why You're Recording This | Where This Data Comes From | Use in Future
ORDER DETAILS
Order Info | Purchase Order Number | PO-STRIDEHER-001 | Unique identifier for this production run. Reference in all communications. | Alibaba Trade Assurance order confirmation | Reference for reorder: "Same spec as PO-001 but with [changes]"
Order Info | Order Date | [DATE] | Timeline tracking — how long from order to delivery? | Your email/order records | Compare timeline accuracy: expected vs actual
Order Info | Total Units Ordered | 600 (270 S/M + 330 L/XL) | Baseline for future orders — did this quantity last the expected 3-4 months? | P3A.02 allocation matrix | Adjust quantity for reorder based on actual sell-through rate
Order Info | Total Units Received | [FILL AFTER RECEIPT] | Verify against ordered. Short shipment = credit owed. | P2E.02 incoming inspection count | Track supplier reliability: ordered vs received accuracy
SUPPLIER DETAILS
Supplier | Company Name | [FILL] | Primary manufacturing partner identification. | Alibaba supplier profile | Direct contact for reorders, quality issues, new products
Supplier | Contact Person | [FILL] — WeChat: [ID], WhatsApp: [NUMBER], Email: [ADDRESS] | Personal contact for fast communication. WeChat is fastest for China suppliers. | Your communication history | Same contact for reorder. If contact leaves the company, request new contact.
Supplier | Factory Address | [FILL — full address in English + Chinese] | Needed for: QIMA inspector dispatch, shipping records, quality agreement reference. | Alibaba supplier profile or business license | QIMA booking requires factory address
Supplier | Alibaba Store URL | [FILL] | Quick reference to supplier's product range, reviews, and transaction history. | Alibaba.com | Verify supplier reputation before reorder (check for new negative reviews)
FINANCIAL DETAILS
Costs | Negotiated Unit Price | $[X.XX] per unit FOB [CITY] | The baseline cost. Future negotiations start here. | Final negotiated email/Trade Assurance order | Target: match or beat this price on reorder. Volume increase should yield 5-10% reduction.
Costs | Total Production Cost | $[XXXX.XX] | Total capital committed to manufacturing. | Trade Assurance payment records | Budget planning for next production run
Costs | 30% Deposit Paid | $[XXXX.XX] on [DATE] | Payment tracking. | Bank/credit card statement | Cash flow planning: know exactly when cash leaves your account
Costs | 70% Balance Paid | $[XXXX.XX] on [DATE] | Payment tracking. | Same | Same
Costs | Sample Fees | $[XXX.XX] | One-time cost (deducted from production in most cases). | Supplier invoice | Sample fees are typically NOT charged on reorders
Costs | Lab Dip Fees | $[XXX.XX] | One-time per color. Not charged on reorders if same colors. | Supplier invoice | Lab dip not needed for reorder if same colors. New colors = new lab dip.
Costs | QIMA Inspection Fee | $[XXX] or N/A | Quality insurance cost. | QIMA invoice | Consider skipping on 2nd order with same supplier if 1st order was clean
Costs | Total All-In Cost Per Unit | $[X.XX] = (production + samples + lab dip + QIMA) ÷ 600 | TRUE cost per unit including all manufacturing-related expenses. | Calculate from above | This is your REAL COGS for financial modeling. Update P0E if different from $6.50 estimate.
TIMELINE TRACKING
Timeline | Deposit Paid | [DATE] | Start of production clock. | Your records | Timeline benchmark: deposit → receipt
Timeline | Materials Sourced (Milestone 1) | [DATE] — ___ days after deposit | How long before production actually starts? | Supplier communication | If >10 days: flag for future — supplier may have sourcing delays
Timeline | 50% Sewing Complete (Milestone 2) | [DATE] — ___ days after deposit | Production pace indicator. | Supplier communication | Calculate daily production rate: units per day
Timeline | 100% Complete (Milestone 3) | [DATE] — ___ days after deposit | Total production time (deposit to completion). | Supplier communication | Expected vs actual. Document any delays and causes.
Timeline | Payment Released | [DATE] | Balance payment date. | Trade Assurance records
Timeline | Shipped | [DATE] — shipping method: [AIR/SEA] | Transit start. | Tracking number | Transit time = shipped → received
Timeline | Received | [DATE] — ___ days after shipping | Transit end. Total door-to-door time. | Your receipt | Total deposit-to-receipt: ___ days (actual vs ___ estimated)
QUALITY RESULTS
Quality | Photo Inspection Score | ___% (___/76 points) | Remote quality assessment result. | 3B.01 completed scorecard | Benchmark for future photo inspections
Quality | QIMA Result | PASS / FAIL / N/A. Defects: ___ critical, ___ major, ___ minor. | On-site quality assessment result. | QIMA inspection report | Compare across production runs. Quality should improve, not decline.
Quality | Incoming AQL Result | PASS / FAIL. Defects: ___ critical, ___ major, ___ minor out of 32 sample. | Your personal quality assessment upon receipt. | P2E.02 completed checklist | Track quality trend across production runs
Quality | Customer Defect Reports (first 90 days) | ___ reports out of ___ units sold = ___% defect rate | Real-world quality metric. The only one that ultimately matters. | Customer service records, Shopify data | Target: <2% customer-reported defect rate. If higher: escalate to supplier.
LESSONS LEARNED (fill in after 90 days of selling)
Lessons | What worked well? | [FILL — e.g., "YKK zippers are excellent — zero complaints. Desert Rose color is a hit."] | Positive reinforcement for supplier and for your own product decisions. | Your experience + customer feedback | Maintain in v2. Don't fix what isn't broken.
Lessons | What needs to change for v2? | [FILL — e.g., "Phone pocket needs 5mm more width. Gel pocket magnet too weak. Need sage color to be slightly more saturated."] | Product improvement roadmap driven by real customer data, not assumptions. | Customer feedback, field test results, your own testing | Send v2 modification list to supplier with reorder.
Lessons | Supplier performance notes | [FILL — e.g., "Communication was excellent. Production was 5 days late. Quality was on-spec. Would reorder from this supplier."] | Supplier relationship assessment. | Your experience | Decision: reorder from same supplier, switch to backup, or try new?
Lessons | What would you do differently? | [FILL — e.g., "Order 700 units next time — sold out of Black L/XL in Month 2. Hire QIMA again — worth every penny. Start reorder process at 40% inventory, not 25%."] | Process improvement for the founder. Every production run should be smoother than the last. | Reflection | Apply to P3D (reorder planning) immediately.

## 3B FOUNDER ACTIONS
P3B PRODUCTION QC & APPROVAL — FOUNDER ACTION CHECKLIST
These actions happen in a compressed 1-2 week window after production completes. Speed matters — but not at the expense of thoroughness.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
PRE-REQUISITE: Production must be 100% complete (3A.06 Milestone 3 confirmed by supplier). Do NOT start 3B until the supplier says "all units finished."
PHASE 1: INSPECT (Days 1-3 after production complete)
🔴 #1 | Send the pre-shipment photo request to supplier (exact message from Sheet 3B.01) | 15 min | $0 | 1. Copy the ENTIRE photo request message from Sheet 3B.01 (word for word) 2. Send via WeChat/WhatsApp/email to your supplier contact 3. Set expectation: "Please send within 48 hours" 4. Remind: "Select 10 RANDOM units — do not choose your best" 5. If supplier pushes for payment before photos: firmly decline: "Per our quality agreement, photos are required before balance release"
🔴 #2 | Book QIMA inspection (if decided to hire — STRONGLY recommended) | 15 min | $268-$388 | 1. Go to qima.com → Book Inspection → Pre-Shipment Inspection 2. Enter: product (running belt), factory (name + address), date (2-3 days out), quantity (600) 3. Upload: P2A.03-04 tech spec PDF + P2E.01 acceptance criteria PDF 4. Specify AQL: Critical 0, Major 2.5, Minor 4.0 5. Pay online ($268 standard / $188 if Alibaba Trade Assurance discounted) 6. QIMA assigns inspector and confirms date within 24 hours 7. Inspector visits factory, inspects, sends report same-day or next-day
🔴 #3 | Review all pre-shipment photos using 3B.01 checklist (38 items) | 2-3 hrs | $0 | 1. Print Sheet 3B.01 (or open on tablet alongside photos) 2. Open all supplier photos on a large screen (not just phone — you need to see details) 3. Score every one of the 38 photo checks: 0 (fail), 1 (borderline), 2 (pass) 4. Check ALL auto-reject items: YKK stamp, phone fit, FTC labeling, silicone adhesion 5. Calculate total score: ___/76 = ___% 6. Decision: ≥80% → proceed to approval. 65-79% → request re-takes. <65% → halt and request QIMA. 7. Save all photos and your completed checklist — this is evidence if you need to dispute
PHASE 2: APPROVE (Days 3-5)
🔴 #4 | Complete the 3B.03 Final Production Approval checklist (18 items) | 30-60 min | $0 | 1. Print Sheet 3B.03 2. Verify ALL 18 items: unit count (7 checks), quality verification (3 checks), packaging & labeling (5 checks), documentation (3 checks) 3. Mark each item: pass / issue found / resolution required 4. If ALL items pass OR all issues resolved: sign the approval form 5. If unresolved issues remain: communicate to supplier with specific fix requirements before signing
🔴 #5 | Verify all 6 payment release conditions (Sheet 3B.04) | 30 min | $0 | 1. Open Sheet 3B.04 2. Confirm each of the 6 conditions: ☐ Photo score ≥80% ☐ QIMA pass (or N/A if not hired) ☐ Unit count verified (600 ±5) ☐ YKK confirmed (stamp visible on all sliders) ☐ FTC labeling compliant (COO + fiber content + care symbols) ☐ Packing complete (poly-bagged, tagged, cartons labeled) 3. ALL 6 must pass. If any fails: hold payment, follow dispute script from 3B.04.
PHASE 3: PAY + SHIP (Days 5-7)
🔴 #6 | Release 70% balance payment via Alibaba Trade Assurance | 15 min | $2,520 | 1. Log into Alibaba → My Orders → find your order 2. Verify: order details match (quantity, price, total) 3. Click "Confirm Goods Received" or "Release Payment" (button name varies) 4. Confirm payment amount: $2,520 5. Screenshot the confirmation page 6. Send warm message to supplier: "Payment released! Please ship when ready and send tracking." 7. Save payment confirmation with your production documentation (3B.06)
🟡 #7 | Confirm packing specifications (Sheet 3B.05) with supplier before they pack | 15 min | $0 | 1. Send the packing spec from Sheet 3B.05 to supplier: "Please pack per these specifications" 2. Key points to emphasize: individual poly-bags with size stickers, cartons labeled in English on 2 sides, cartons organized by size-then-color, packing list in English inside Carton #1 3. Request: photo of first packed carton before they pack all (spot-check)
🟡 #8 | Request tracking number + shipping documents | 15 min | $0 | 1. After payment: supplier books shipping within 24-48 hours 2. Request: tracking number, commercial invoice (for customs), packing list (for inventory verification) 3. Save ALL documents in your production file 4. Set calendar reminder to check tracking daily during transit
PHASE 4: DOCUMENT (ongoing — complete within 2 weeks of receipt)
🟢 #9 | Fill in the Production Run Documentation template (Sheet 3B.06) | 1-2 hrs | $0 | 1. Open Sheet 3B.06 2. Fill in EVERY yellow-highlighted field: order details, supplier details, financial details, timeline tracking, quality results 3. Calculate your TRUE all-in cost per unit 4. After 90 days of selling: complete the "Lessons Learned" section 5. This document becomes your manufacturing playbook for all future production runs — maintain it as a living document