## P3C EXEC SUMMARY
P3C SHIPPING & LOGISTICS — EXECUTIVE SUMMARY
5 Tasks ¦ Weeks 12-14 ¦ Getting 600 units from a Chinese factory to your door/3PL. Total shipping cost: $350-$900 depending on method.
Task ID | Task | KPI | Deliverable | Status | Key Decision | Cost
3C.01 | Choose shipping method: ePacket, air express, sea freight, or rail | Method selected with cost-benefit justification | Complete shipping method comparison: 5 options scored on cost, speed, tracking, reliability, and customs complexity. Cost calculator for 600 units (~85-100 kg total). RECOMMENDATION: Air express (DHL/FedEx/UPS) for first order. | COMPLETE ✓ | AIR EXPRESS via DHL/FedEx/UPS for first order. Cost: $550-$900 total ($4-$7/kg × ~100 kg). Transit: 5-8 business days door-to-door. Why not sea freight ($200-$400, 25-40 days)? First order = speed to market matters more than saving $300. Sea freight for reorders when timing pressure is lower. | $550-$900 (air express) OR $200-$400 (sea freight)
3C.02 | Arrange shipping: supplier handles export, you receive at home or 3PL | Tracking number received, delivery date confirmed | Complete shipping arrangement guide: who handles what (supplier = export, carrier = transit, you = import), Incoterms explained (FOB vs DDP vs DAP), tracking setup, and delivery coordination. Plus: supplier communication script for shipping instructions. | COMPLETE ✓ | FOB SHENZHEN/XIAMEN recommended for first order — supplier delivers to port/airport, you pay shipping from there. Most Alibaba suppliers include factory-to-airport transport in their quote. Supplier books carrier on your behalf (common practice) OR you book via Flexport/Freightos. | $0 (arrangement)
3C.03 | Understand import duties and taxes: HS code 4202, duty rates, customs clearance | Duty estimate calculated, customs requirements documented | Complete customs and duties guide: HS code classification (4202.92.9000), US duty rate calculation (17.6-20% ad valorem), customs clearance process, required documents, de minimis thresholds, Section 301 tariff check, and total landed cost calculator. | COMPLETE ✓ | HS CODE 4202.92.9000 — "travel/sports bags and similar containers." US duty: ~17.6% + possible Section 301 tariff (25% on List 3 goods). Total duty estimate on $3,600 declared value: $630-$1,530. DHL/FedEx handle customs brokerage automatically for shipments under $2,500 (informal entry). Above $2,500: formal entry required (customs broker fee ~$150-$250). | $630-$1,530 (duties) + $0-$250 (broker fee)
3C.04 | Receive shipment: unbox, count all units, inspect 10% sample | Inspection complete, inventory verified | Complete receiving protocol: what to do when the shipment arrives, step-by-step unboxing checklist, 32-unit AQL re-inspection (cross-reference P2E.02), damage documentation for insurance claims, and short-shipment handling. | COMPLETE ✓ | Execute P2E.02 incoming inspection on arrival. 32-unit AQL sample. If QIMA already inspected at factory AND photo inspection scored ≥80%: receiving inspection can be lighter (focus on transit damage, not manufacturing defects). If no QIMA: full P2E.02 inspection at receiving. | $0 (your time: 4-6 hours)
3C.05 | Organize inventory storage: by size, by color, with clear labeling | Inventory organized, fulfillment-ready | Complete inventory storage and organization system: physical layout for home-based or 3PL storage, SKU labeling system, bin/shelf organization, pick-pack workflow, and inventory count template. | COMPLETE ✓ | Store by SIZE first, then COLOR within size (mirrors carton organization from P3B.05). Label each shelf/bin/zone with the SKU. Create a "pick sheet" for each order that tells you exactly which bin to pull from. Target: <2 minutes from order notification to packed shipment. | $0-$100 (shelving/bins if needed)

## 3C.01 Shipping Methods
P3C TASK 3C.01: SHIPPING METHOD COMPARISON — 5 OPTIONS FOR 600 UNITS (~100 KG)
Estimated shipment: 14 cartons × ~7 kg each = ~100 kg total, ~0.6 CBM volume. This is a SMALL commercial shipment — air express is the sweet spot for first orders.
Method | Cost for 600 Units | Transit Time | Tracking | Door-to-Door? | Customs Handling | Best For | Recommendation
5 SHIPPING OPTIONS — ranked by speed-to-market (most important for first order launch timing)
★ AIR EXPRESS (DHL/FedEx/UPS) RECOMMENDED | $550-$900 ($4-$7/kg) Volume weight may apply: 60×40×30cm carton = 14.4 kg vol weight × 14 cartons = ~200 kg vol weight Actual: ~100 kg Charged: higher of actual vs volumetric | 5-8 business days door-to-door (Shenzhen → US West Coast: 4-5 days. US East Coast: 6-8 days.) | ✅ Full tracking from pickup to delivery. Real-time updates. Signature on delivery. | ✅ YES Carrier picks up at factory, delivers to your door. No port visits. No trucking arrangement. | ✅ DHL/FedEx/UPS handle customs brokerage automatically for shipments under $2,500 (informal entry). Above $2,500: they still handle it but charge a broker fee (~$50-$150). You provide: commercial invoice + packing list. They do the rest. | FIRST ORDERS where speed-to-market matters. Launch timing is critical — spending $300 more on air vs sea buys you 3-4 weeks of earlier sales. At 40 units/month × $35 × 3 weeks earlier = ~$3,500 in earlier revenue. The $300 premium pays for itself 10×. | ★ USE THIS for your first 600-unit order. Reason: (1) 5-8 days vs 25-40 days sea = 3-4 weeks earlier to market, (2) full door-to-door service with customs handled, (3) real-time tracking so you know exactly when inventory arrives, (4) less risk of damage (shorter transit, fewer handling points). The volumetric weight issue may increase cost to $700-$900. Ask supplier to quote DHL/FedEx before production — they get commercial shipping rates 30-50% below retail.
AIR FREIGHT (cargo airline, not express) | $350-$600 ($2.50-$4.50/kg) Cheaper than express but requires airport pickup or local delivery arrangement. | 7-14 days Air transit: 2-3 days. Airport handling: 2-5 days. Customs + local delivery: 2-5 days. | ⚠️ Partial Tracking to airport only. Local delivery tracking varies. | ❌ NO Delivers to airport warehouse. You arrange pickup or local delivery (~$50-$100 extra). | ⚠️ YOU handle customs clearance. Need a customs broker ($150-$250) unless using a freight forwarder who includes it. | Medium-sized shipments (100-500 kg) where express is too expensive but sea is too slow. Not ideal for 100 kg — the hassle of airport pickup + customs broker offsets the savings vs express. | SKIP for first order. The savings ($200-$400 vs express) are consumed by: customs broker fee ($150-$250), airport pickup ($50-$100), and 1-2 weeks of your time coordinating. Express is simpler and only marginally more expensive at 100 kg.
SEA FREIGHT (LCL — Less than Container Load) | $200-$400 total ($150-$250 ocean freight for 0.6 CBM + $50-$150 local charges) | 25-40 days Ocean transit: 15-25 days. Port handling: 5-10 days. Customs + local delivery: 5-10 days. | ⚠️ Partial Container tracking available. Local delivery after port: varies. | ❌ NO Delivers to port warehouse. You arrange local transport from port to your address (~$100-$200). | ⚠️ YOU handle customs clearance. Formal entry required for values >$2,500. Customs broker: $150-$250. Or use Flexport (all-inclusive). | REORDERS where timing isn't launch-critical. Save $300-$500 vs air express. Use when you can plan 6-8 weeks ahead. Also: orders >500 kg where air becomes prohibitively expensive. | USE FOR REORDERS (order #2+). Once you're selling and can forecast demand, sea freight saves $300-$500 per shipment. Plan reorders 8-10 weeks before stockout (production 4 weeks + sea transit 4-5 weeks + buffer). For first order: too slow. You lose 3-4 weeks of sales.
RAIL FREIGHT (China → Europe or US via rail link) | $300-$500 Pricing varies widely. Newer service with less price standardization. | 18-25 days Faster than sea, slower than air. China → EU: 14-18 days. China → US: less established. | ⚠️ Variable Tracking available on major routes (China-EU). China-US less reliable. | ❌ NO Delivers to rail terminal. Local pickup required. | ⚠️ Same as sea — customs broker needed. | China → Europe shipments where sea is too slow and air is too expensive. The Belt and Road rail network is well-established for EU routes. China → US rail routes exist but are less mature and less reliable. | NOT RECOMMENDED for US-bound first order. Rail is strongest on China-EU corridor. For China-US: air express or sea are better-established options with more predictable pricing and transit times.
ePacket / China Post EMS | $100-$250 ($2-$4/kg) Cheapest option. But designed for small parcels, not 14-carton commercial shipments. | 15-30 days Highly variable. Can extend to 45+ days during peak season. No guaranteed delivery date. | ⚠️ Basic Tracking often stops updating after leaving China. Limited visibility during transit. | ✅ YES (nominally) But delivery may require signature and your local post office may hold large shipments. | ⚠️ Customs handled by postal service. Slow. Delay-prone. Duty collection at delivery (cash/check). | Small, low-value orders (<$500, <10 kg). Suitable for sample shipments or individual customer orders, NOT for 100 kg commercial production runs. | DO NOT USE for 600-unit production shipment. ePacket/China Post is designed for small parcels. A 100 kg, 14-carton shipment via postal service = delays, lost cartons, no recourse. The $200-$400 saved vs air express is not worth the risk of losing your entire production run in transit.
COST CALCULATOR — what your first shipment actually costs (all-in, landed)
TOTAL LANDED COST | Production: $3,600 Packaging: $330 Shipping (air): $750 (est.) Duty (17.6%): $633 Section 301 (25%): $900* Broker fee: $100 * Section 301 tariff may or may not apply — check current status (see 3C.03) TOTAL LANDED: $5,413-$6,313 Per unit landed: $9.02-$10.52 | The "landed cost" is the TRUE cost of getting product to your door. Your COGS isn't just the $6.00/unit factory price — it's $9-$10.50/unit after shipping, duties, and fees. At $34.99 retail: Gross margin on landed cost: 70-74% (vs 83% on factory cost alone) This is still EXCELLENT — most D2C brands operate at 60-70% gross margin on landed cost. |  |  |  |  | The P0E financial model estimated $6.50 COGS + $4.50 shipping/duties = $11.00 all-in cost per unit. Actual landed cost of $9-$10.50 is BETTER than the model predicted. Financial model remains valid with improved margins.

## 3C.02-03 Shipping + Customs
P3C TASKS 3C.02-03: SHIPPING ARRANGEMENT + CUSTOMS, DUTIES & HS CODE GUIDE
Your supplier handles export. DHL/FedEx handles transit + customs brokerage. You provide documents + pay duties. Here's exactly how it works.
Step / Element | What Happens | Who Does It | What You Provide | Cost | Timeline | If Something Goes Wrong
SHIPPING ARRANGEMENT (3C.02) — step by step from factory to your door
Step 1: Supplier Books Carrier | After you release the 70% balance (P3B.04), the supplier books a DHL/FedEx/UPS pickup from their factory. Most Chinese suppliers have commercial DHL/FedEx accounts with rates 30-50% below retail. They book on your behalf and charge you the shipping cost separately (or include in the unit price if negotiated per P3A.03 Lever 3). | SUPPLIER books and coordinates with carrier. | Tell supplier your preferred carrier: "Please ship via DHL Express. My delivery address is: [YOUR ADDRESS]." Provide: full delivery address, phone number, email for tracking notifications. | $0 (arrangement) | Supplier books within 24-48 hrs of balance payment. Pickup: 1-2 days after booking. | Supplier says "we don't have a DHL account": ask them to use their freight forwarder, or you book DHL pickup directly via dhl.com (more expensive). Or supplier can drop cartons at nearest DHL service point. Supplier quotes excessive shipping ($1,500+ for 100 kg): they may be quoting retail rates. Ask: "Can you check your commercial DHL rate?" Or get a competing quote from Flexport/Freightos.
Step 2: Export from China | Supplier provides export documents to the carrier: • Commercial Invoice (product description, value, HS code, origin) • Packing List (carton contents, weights, dimensions) • Export Declaration (supplier's responsibility in China) Carrier picks up cartons from factory, processes through Chinese customs (typically same day for DHL/FedEx), and loads onto aircraft. | SUPPLIER provides export docs. CARRIER handles export clearance. | Nothing — export is the supplier's responsibility. But verify they've provided the correct HS code (4202.92.9000) and accurate declared value ($3,600 for 600 units at $6.00/unit) on the commercial invoice. ⚠️ If supplier under-declares value (e.g., $600 instead of $3,600): this is customs fraud. You're liable. Insist on accurate declaration. | $0 (export fees borne by supplier under FOB terms) | 1-2 days from pickup to export clearance. | Export delay: Chinese customs rarely delays textile shipments. If delayed >3 days: supplier should check with the carrier. Most common cause: incomplete paperwork (missing HS code or value declaration). Holiday shutdowns: Chinese New Year (Jan/Feb), Golden Week (Oct 1-7), and major Chinese holidays can delay export processing by 1-2 weeks. Plan around these dates.
Step 3: Air Transit | Cartons fly from Chinese airport (Shenzhen Baoan, Guangzhou Baiyun, or Xiamen Gaoqi depending on factory location) to US destination airport. DHL/FedEx route through their hub cities (Cincinnati for DHL, Memphis for FedEx, Louisville for UPS) then to your local delivery center. | CARRIER handles entirely. | Nothing during transit. Track via carrier website or app. DHL: dhl.com/tracking FedEx: fedex.com/tracking UPS: ups.com/tracking | Included in shipping rate. | 2-4 days air transit. Plus 1-2 days hub processing. | Flight delay / re-routing: rare but happens during weather events or capacity constraints. DHL/FedEx provide proactive notifications. No action needed from you — just wait. Lost shipment: extremely rare with express carriers (<0.01% of shipments). Carrier insurance covers declared value. File a claim within 21 days.
Step 4: US Customs Clearance | Shipment arrives at US port of entry. DHL/FedEx customs brokerage team files the import entry with US Customs and Border Protection (CBP). For shipments valued under $2,500: INFORMAL ENTRY — simplified process, typically cleared in hours. For shipments valued $2,500+: FORMAL ENTRY — requires customs broker (DHL/FedEx act as your broker), takes 1-3 business days. Your shipment at ~$3,600 declared value = FORMAL ENTRY. | CARRIER (DHL/FedEx) acts as your customs broker. You approve and pay duties. | Carrier contacts you (email or portal) to: 1. Confirm import details 2. Provide duty/tax estimate 3. Request payment authorization for duties You authorize payment. Carrier pays CBP on your behalf, then bills you. | Customs broker fee: $50-$150 (included by DHL/FedEx for express shipments or charged separately). Duties: see 3C.03 section below. | 1-3 business days for formal entry. Most express shipments clear same day or next day. | Customs hold / examination: CBP randomly selects ~5% of shipments for physical examination. If selected: 3-7 day delay. No action from you — carrier handles. Examination fee: $50-$200 (carrier passes to you). Incorrect HS code: CBP may reclassify and apply different duty rate. If reclassified to a higher-duty category: you can dispute or accept. This is why correct HS classification matters. Missing documents: carrier contacts you for missing commercial invoice or packing list. Provide within 24 hours to avoid extended hold.
Step 5: Last-Mile Delivery | After customs clearance, carrier delivers cartons to your specified address (home, office, or 3PL warehouse). DHL/FedEx deliver to residential addresses but 14 cartons (~100 kg) may require a truck delivery rather than standard van. Carrier may call to schedule delivery window. Signature required for commercial shipments. | CARRIER delivers. YOU receive and sign. | Be present to receive. 14 cartons = large delivery. Have a clear path from door to storage area. You'll need to carry/dolly cartons inside. If delivering to a home: clear garage or room space for ~14 cartons (each ~60×40×30cm = 8 sq ft per layer × 2 layers = 16 sq ft minimum floor space). | Included in shipping rate. | 1-2 days after customs clearance. Total door-to-door: 5-8 business days. | Failed delivery attempt: carrier leaves a notice, reattempts next business day. After 3 failed attempts: shipment returned to local carrier facility for pickup. Damaged on delivery: inspect cartons BEFORE signing. If visible damage to cartons: note "DAMAGED" on the delivery receipt, photograph damage, and file a carrier claim within 5 days. Do NOT refuse delivery — accept, document, then claim.
CUSTOMS, DUTIES & HS CODE (3C.03) — what you owe the US government
HS Code Classification | HS CODE: 4202.92.9000 "Travel, sports, and similar bags with outer surface of textile materials" This is the correct classification for a waist-worn running belt made of nylon-spandex textile with zipper closures. Running belts, fanny packs, waist packs, and belt bags all fall under 4202.92. Subheading 9000 = "other" (not specifically enumerated elsewhere in 4202.92). | Classified by US CBP (Customs and Border Protection) based on the commercial invoice description. | Ensure your supplier's commercial invoice describes the product correctly: "Women's running waist belt, outer surface nylon-spandex textile, zippered pockets, adjustable buckle." Do NOT describe it as: "bag," "purse," "pouch," or "accessory" — these may trigger different HS codes with higher duties. | N/A | Classification is automatic based on product description. | If CBP classifies under a different HS code (e.g., 4202.22 for "handbags" — higher duty): you can file a protest (CBP Form 19) within 180 days. Or work with a customs broker to pre-classify via a binding ruling request (takes 30 days, $0 cost, provides certainty for all future shipments).
US Duty Calculation | COLUMN 1 (Most Favored Nation) DUTY RATE: HS 4202.92.9000 = 17.6% ad valorem Calculation on $3,600 declared value: $3,600 × 17.6% = $633.60 SECTION 301 TARIFF (China-specific): List 3 goods carry an ADDITIONAL 25% tariff. HS 4202 IS on List 3. $3,600 × 25% = $900.00 TOTAL DUTY ESTIMATE: $633.60 + $900.00 = $1,533.60 ⚠️ IMPORTANT: Section 301 tariffs are subject to change based on US trade policy. Check the current status at ustr.gov or hts.usitc.gov before your shipment arrives. | CBP assesses duties based on declared value on commercial invoice. DHL/FedEx collect from you and remit to CBP. | Nothing — duties are calculated automatically by CBP based on your HS code and declared value. But verify: declared value matches actual invoice. Under-declaration = fraud. Over-declaration = you pay more duty than necessary. | Estimated: $633-$1,534 Base duty: $634 Section 301: $900 (if still in effect) Total: $634-$1,534 | Duty payment due within 10 business days of entry. DHL/FedEx typically advance the duty and bill you. | Duty higher than expected: Section 301 tariffs may have changed since this document was written. Check current List 3 tariff status at ustr.gov before budgeting. Duty lower than expected: the Biden/Trump administrations have periodically adjusted Section 301 tariffs. Some product categories have been excluded. Check if HS 4202.92 has been excluded or reduced. To REDUCE duty legally: consider shipping to a Foreign Trade Zone (FTZ) for deferred duty, or restructure product to qualify for a lower-duty HS code (unlikely for textile waist belts). Most effective: increase retail price to absorb duty in margin.
Merchandise Processing Fee (MPF) | For formal entries ($2,500+ value): Merchandise Processing Fee = 0.3464% of declared value. $3,600 × 0.3464% = $12.47 Minimum: $31.67. Maximum: $614.35. You'll pay the minimum: $31.67. This is a small, unavoidable fee on every formal import entry. | CBP charges automatically. Collected by carrier along with duties. | Nothing — automatic. | $31.67 | Charged with duty payment. | Non-negotiable. Every formal entry pays MPF. It's a rounding error in your total landed cost.
Harbor Maintenance Fee (HMF) | ONLY applies to SEA FREIGHT (not air). If shipping by sea: HMF = 0.125% of declared value = $4.50. If shipping by air: $0. Not applicable. | CBP charges for sea freight only. | Nothing — automatic for sea freight. | $0 (air) $4.50 (sea) | Charged with duty payment (sea freight only). | Only relevant for reorders shipped by sea.
TOTAL LANDED COST SUMMARY
LANDED COST CALCULATOR | ITEM COST Production (600 units × $6.00) $3,600 Packaging (600 × $0.55) $330 Shipping (air express) $750 (est.) Base Duty (17.6%) $634 Section 301 (25%)* $900 MPF $32 Customs Broker (via DHL) $100 TOTAL LANDED COST: $5,446 - $6,346 (*with Section 301) PER UNIT LANDED: $9.08 - $10.58 GROSS MARGIN at $34.99: 70-74% * Check Section 301 status — if suspended/excluded, total drops to ~$5,446. | This is the TRUE cost of goods. Update your P0E financial model with actual landed cost once shipment arrives. At $9-$10.50 landed cost per unit: Gross profit: $24.49-$25.91 per unit (70-74%) After $10 CAC: $14.49-$15.91 per unit (41-45%) The financial model REMAINS VIABLE. Even with the worst-case Section 301 tariff, per-unit profitability is strong. |  |  |  | Budget $6,500 for total landed cost (production + packaging + shipping + duties + fees). This is 65% of your $10K budget, leaving $3,500 for marketing, e-commerce, legal, and contingency — tight but viable per P0E.

## 3C.04-05 Receiving + Storage
P3C TASKS 3C.04-05: RECEIVING PROTOCOL + INVENTORY ORGANIZATION SYSTEM
When 14 cartons arrive: don't rip them open excitedly. Follow this protocol. Then organize for fast fulfillment.
Step / Element | What to Do | How to Do It | Time | If Issue Found | Document | Goal
3C.04: RECEIVING PROTOCOL — what to do when the shipment arrives at your door
Step 1: External Inspection | BEFORE opening any carton: inspect ALL carton exteriors for transit damage. Check: dents, crushing, water damage, tape failure, holes/punctures. Count cartons: verify total matches packing list (should be 13-14 cartons). Check labels: verify carton numbers ("1 of 14," "2 of 14," etc.) — are all cartons present? | Walk around the delivered stack. Look at every carton from every visible side. Photograph ANY damage — even minor dents. If cartons are wet or visibly crushed: photograph BEFORE moving them. Moisture + crushed cartons = likely interior damage. | 15 min | Visible damage: photograph everything. Note on delivery receipt "RECEIVED WITH DAMAGE — [X] cartons affected." File carrier damage claim within 5 business days at carrier's website. Missing cartons: note on delivery receipt "SHORT SHIPMENT — [X] cartons received of [Y] expected." Contact carrier + supplier immediately. | Photos of ALL carton exteriors (even undamaged — baseline documentation). Delivery receipt with any damage notes. Carton count confirmation. | Catch transit damage before opening. Documentation is required for insurance claims. The delivery receipt signature is your ONLY proof if a claim is needed later.
Step 2: Count Verification | Open ALL cartons. Count total units. Verify against packing list AND against your P3A.02 allocation. Count by SKU: tally each size × color combination. Expected: 600 total (270 S/M + 330 L/XL) across 8 SKUs. | Open each carton. Count the poly-bagged units inside. Mark the count on the exterior of the carton in marker. Tally on a sheet: • S/M Black: ___ (expected: 122) • S/M Rose: ___ (expected: 54) • S/M Sage: ___ (expected: 54) • S/M Ocean: ___ (expected: 40) • L/XL Black: ___ (expected: 148) • L/XL Rose: ___ (expected: 66) • L/XL Sage: ___ (expected: 66) • L/XL Ocean: ___ (expected: 50) TOTAL: ___ (expected: 600) | 45-60 min | Short by 1-5 units: note discrepancy but don't delay. Contact supplier for credit ($6/unit × missing units). Short by 6+: contact supplier + carrier. Determine if units were left behind at origin, fell out of damaged carton in transit, or were never produced. Demand replacement shipment or credit. | SKU count sheet (save permanently — this is your opening inventory record). Any discrepancies noted with date. | Verify you received what you paid for. This count becomes your opening inventory number for tracking.
Step 3: AQL Inspection | Pull 32 random units from across all cartons (same sampling method as P2E.02). Inspect against the 24 acceptance criteria from P2E.01. IF you hired QIMA at the factory AND photo inspection scored ≥80%: you can do a LIGHTER inspection focused on transit damage only (check 10 units for crushed zippers, deformed elastic, water damage, silicone dot damage). IF no QIMA: execute the FULL P2E.02 inspection (all 24 criteria, all 32 units). | Pull every ~19th unit from the shipment. Include all sizes and colors in proportion. Full inspection: 5-7 min per unit × 32 = 2.5-3.5 hours. Light inspection (post-QIMA): 2 min per unit × 10 = 20 min. Score each unit. Tally: critical defects, major defects, minor defects. Accept/reject per P2E.02: Critical 0, Major ≤2, Minor ≤5. | Full: 3-4 hrs Light: 30 min | AQL PASS: proceed to storage and fulfillment. AQL FAIL: do NOT start selling. Photograph defects. Contact supplier with evidence + reference quality agreement (P2E.05). Demand: re-work credit, replacement units, or partial refund. If defects are fixable locally (trim loose threads, re-attach hang tags): estimate fix time. If <1 hour total: fix yourself. If >1 hour: demand supplier credit for your labor. | Completed P2E.02 inspection form. Defect photos if any found. Final AQL result: PASS/FAIL. | Catch any defects that slipped past factory QC and/or QIMA. Also catches transit-caused damage (zippers bent from crushing, silicone dots deformed from compression).
3C.05: INVENTORY STORAGE & ORGANIZATION — set up BEFORE the shipment arrives
Storage Space Requirements | You need: a clean, dry, temperature-controlled space for 14 cartons (or 600 loose poly-bagged units after unpacking). Space needed: • Cartons stacked 2 high: ~8 sq ft floor space (2m²) • Units on shelving (unpacked from cartons for fast picking): ~16-24 sq ft of shelving (2-3 shelving units) Home-based options: spare room, garage (if climate-controlled), large closet. 3PL option: if no home space, consider ShipBob, ShipMonk, or Amazon FBA (add $1-$2/unit for fulfillment). | Set up storage area BEFORE the shipment arrives. You don't want 14 cartons in your hallway while you figure out where to put them. Buy 2-3 shelving units ($30-$60 each at Walmart/Amazon/IKEA). Wire shelving or industrial shelving works best (visible from all angles, adjustable shelf heights). Label each shelf before units arrive. | 1-2 hours setup | No space: consider a 3PL immediately. ShipBob and ShipMonk accept small-volume brands (100+ orders/month). Cost: $3-$5/order for pick-pack-ship + $5-$15/month storage for your inventory volume. Moisture concern (garage): place pallets or cardboard under cartons. Use a dehumidifier if needed. Nylon-spandex is moisture-resistant but prolonged humidity can cause mildew. | Photos of storage setup. Shelf labels applied. Storage capacity confirmed. | Have a fulfillment-ready workspace BEFORE inventory arrives. First orders can ship within hours of receiving inventory.
Organization by SKU | Organize by SIZE first, then COLOR within size (mirrors carton organization from P3B.05): SHELF 1 (or ZONE 1): ALL S/M Row A: S/M Black (122 units) Row B: S/M Desert Rose (54 units) Row C: S/M Alpine Sage (54 units) Row D: S/M Deep Ocean (40 units) SHELF 2 (or ZONE 2): ALL L/XL Row A: L/XL Black (148 units) Row B: L/XL Desert Rose (66 units) Row C: L/XL Alpine Sage (66 units) Row D: L/XL Deep Ocean (50 units) Label EVERY shelf/bin/row with the SKU name in LARGE text. | Unpack cartons into organized shelves. Stack poly-bagged units neatly with the size/color sticker (from P3B.05 packing spec) facing outward. Use large labels on shelf edges: print or write "S/M — BLACK" in marker. Must be readable from 3 feet away. Keep a running count card at each bin: starting count on top, mark each unit pulled. Real-time inventory tracking without a computer. | 1-2 hours (unpacking + organizing) | Not enough shelf space for all units: keep backup stock in original cartons (labeled) and refill shelves as units sell. Only the "active" 2-3 weeks of inventory needs to be on shelves. Running out of one SKU: cross-reference sales data to see if it's a popular SKU (increase allocation on reorder) or a one-time surge. | Inventory count card at each bin/shelf position. Photo of organized storage. SKU map (which shelf = which SKU). | Grab any SKU in <15 seconds. When a "S/M Alpine Sage" order comes in, you walk to Shelf 1 Row C and pull it immediately. No searching, no opening cartons, no guessing.
Pick-Pack Workflow | When an order comes in (Shopify notification): 1. READ: size + color from order details (5 sec) 2. WALK to the correct shelf/bin (10 sec) 3. PULL the correct poly-bagged unit (5 sec) 4. VERIFY: check the size/color sticker on the bag matches the order (5 sec) 5. INSERT the insert card face-up on top of the belt in the bag (10 sec) 6. SEAL with brand sticker if not already sealed (5 sec) 7. PLACE in poly mailer (10 sec) 8. SEAL mailer (5 sec) 9. PRINT + ATTACH shipping label (30 sec) 10. DONE. Place in outgoing mail area. (5 sec) Total per order: ~90 seconds. | Set up a packing station: a table or counter near your storage shelves. On the packing station, keep: • Stack of poly mailers • Stack of insert cards (face-up) • Roll of brand stickers • Shipping label printer (Dymo 4XL or USPS labels from Shopify) • Tape (backup) • Order printouts or phone showing Shopify orders Batch orders: pack 5-10 orders at a time instead of one-by-one. Drop off at USPS/UPS together. | ~90 sec per order Batch of 10: ~15 min | Wrong item shipped (wrong size or color): this is the #1 fulfillment error. The VERIFY step (Step 4) catches it. If a wrong item is shipped: apologize, ship correct item immediately, provide prepaid return label for wrong item (or tell customer to keep it). Shipping label error: verify address against Shopify order. Use Shopify Shipping for address validation. | Each order: Shopify marks as "fulfilled" with tracking number. Daily: count orders packed vs orders received. Should match. | Target: <2 minutes per order from notification to packed. At 5-10 orders/day (early stage), this is 10-20 min of daily fulfillment work.
Inventory Tracking Spreadsheet | Simple Google Sheets tracker: Columns: SKU ¦ Opening Stock ¦ Sold Today ¦ Running Total ¦ Reorder Flag Rows (8 SKUs): • SM-BLK ¦ 122 ¦ ¦ ¦ • SM-RSE ¦ 54 ¦ ¦ ¦ • SM-SGE ¦ 54 ¦ ¦ ¦ • SM-OCN ¦ 40 ¦ ¦ ¦ • LXL-BLK ¦ 148 ¦ ¦ ¦ • LXL-RSE ¦ 66 ¦ ¦ ¦ • LXL-SGE ¦ 66 ¦ ¦ ¦ • LXL-OCN ¦ 50 ¦ ¦ ¦ Reorder Flag: turns RED when Running Total drops below 20 units for any SKU (signals reorder for that SKU). | Update daily: subtract today's orders from running total. Or: use Shopify's built-in inventory tracking (automatically deducts on each sale). Shopify sends low-stock alerts at thresholds you set (recommend: alert at 20 units per SKU). Weekly: physical count to verify Shopify number matches actual shelf count. Discrepancies = either a fulfillment error or theft (unlikely at home). | 5 min daily 15 min weekly (physical count) | Shopify count doesn't match physical count: likely a fulfillment error (shipped wrong item, or item counted twice). Investigate: check recent order packing for errors. One SKU selling out fast: shift marketing to highlight available colors. Run a "limited stock" urgency message on the product page. | Google Sheet or Shopify inventory report. Weekly physical count log. | Never be surprised by a stockout. The reorder flag (at 20 units) gives you 2-3 weeks of runway to trigger P3D reorder process before hitting zero.

## 3C FOUNDER ACTIONS
P3C SHIPPING & LOGISTICS — FOUNDER ACTION CHECKLIST
Shipping is mostly waiting. Use the transit time to finalize your Shopify store, email sequences, and launch content.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 12: ARRANGE SHIPPING (immediately after 70% balance released)
🔴 #1 | Confirm shipping method with supplier and get a DHL/FedEx quote | 30 min | $0 | 1. Message supplier: "Please ship via DHL Express to [YOUR ADDRESS]. Can you provide a shipping quote before booking?" 2. Compare their quote to online DHL rate calculator (dhl.com/express/rate) 3. If their quote is reasonable ($550-$900 for ~100 kg): approve 4. If quote seems high (>$1,000): ask "Can you check your commercial rate?" or get competing FedEx quote 5. Confirm: delivery address, phone number, email for tracking notifications
🔴 #2 | Verify commercial invoice details before supplier ships | 15 min | $0 | 1. Ask supplier to send you the commercial invoice BEFORE shipping 2. Verify: (a) product description matches HS 4202.92 classification, (b) declared value = actual invoice value ($3,600), (c) quantity = 600 units, (d) country of origin = China 3. If anything is wrong: request correction BEFORE shipment leaves China 4. ⚠️ Ensure value is NOT under-declared — this is customs fraud and you are liable
🟡 #3 | Set up storage space and shelving BEFORE shipment arrives | 2 hrs | $60-$120 | 1. Clear a room/garage area (~20 sq ft minimum) 2. Buy 2-3 wire shelving units (Amazon: "NSF Wire Shelf" ~$30-$50 each) 3. Assemble shelving 4. Label each shelf with SKU names: "S/M — BLACK," "S/M — ROSE," etc. (8 labels total) 5. Set up a packing station: table + mailers + insert cards + stickers + label printer 6. Photograph the setup for your records
WEEK 13-14: RECEIVE + INSPECT + ORGANIZE
🔴 #4 | Receive shipment: external inspection + count + AQL sample | 4-6 hrs | $0 | 1. When cartons arrive: inspect EXTERIORS before opening (Step 1 from Sheet 3C.04-05) 2. Photograph any damage. Note on delivery receipt. 3. Open all cartons and count by SKU (Step 2) — tally against P3A.02 allocation 4. Pull 32 random units and inspect per P2E.02 AQL checklist (Step 3) 5. If PASS: proceed to organizing inventory 6. If FAIL: photograph defects, contact supplier, reference quality agreement 7. This is the LAST quality gate before you start selling
🟡 #5 | Organize inventory on shelving by SKU | 1-2 hrs | $0 | 1. Unpack cartons onto labeled shelves: S/M on Shelf 1 (subdivided by color), L/XL on Shelf 2 2. Stack poly-bagged units with size/color stickers facing outward 3. Place an inventory count card at each shelf position (starting count written on card) 4. Set up the Google Sheets inventory tracker (or configure Shopify inventory tracking with 20-unit low-stock alerts) 5. Take a photo of the fully organized inventory — this is your "Day 1" reference
🟡 #6 | Pay customs duties when carrier invoices you | 15 min | $634-$1,534 | 1. DHL/FedEx will email or call with a duty/tax invoice during or after customs clearance 2. Review the invoice: verify HS code (4202.92), duty rate (17.6% + possible 25% Section 301), declared value ($3,600) 3. Pay via the carrier's online portal or by phone 4. Save the duty receipt — this is a tax-deductible business expense 5. If duty seems higher than expected: check if Section 301 tariff was applied. If you believe it shouldn't be: consult a customs broker for advice.
🟢 #7 | Set up Shopify inventory tracking + low-stock alerts | 30 min | $0 | 1. Shopify Admin → Products → StrideHer Belt → Edit variant inventory 2. Enter opening stock for each of the 8 variants (size × color) 3. Enable "Track quantity" for each variant 4. Set low-stock notification threshold: 20 units per variant 5. Shopify will email you when any variant drops below 20 — this is your reorder trigger (P3D) 6. Verify: make a test order and confirm inventory deducts correctly