## P5C EXEC SUMMARY
P5C RUNNING EVENTS & LOCAL MARKETING — EXECUTIVE SUMMARY
5 Tasks ¦ Weeks 10-20+ (ongoing) ¦ Cost: ~$200-$400 (samples + materials) ¦ In-person is the trust accelerator that digital channels can't replicate.
Task ID | Task | KPI | Deliverable | Status | Why In-Person Matters | Cost
5C.01 | Identify 5 local running events, parkruns, or club meetups to attend with product samples | 5 events identified on calendar | Complete event identification guide: 5 event types ranked by ROI (parkruns, local races, running store events, club meetups, fitness expos), research methods for finding events in any US city, evaluation criteria for selecting the best events, and a calendar planning template. | COMPLETE ✓ | A customer who TOUCHES and TRIES the product converts at 40-60% — compared to 2-4% from a website visit. Every person who puts on the belt at an event and takes 3 steps in it becomes a believer. In-person sampling creates word-of-mouth that no digital ad can replicate: "I tried this belt at parkrun and it didn't move at all." | $0 (research only)
5C.02 | Prepare event kit: 10 samples, business cards, QR code stand, phone for content | Event kit packed and ready | Complete event kit checklist: 12-item packing list, QR code setup for instant mobile purchase (Shopify QR code → product page), business card design spec, signage/banner requirements, and a "conversation playbook" for how to approach runners without being pushy. | COMPLETE ✓ | The event kit is your portable store. The QR code eliminates "I'll check it out later" (they won't). The business card is the backup for people who want to think about it. The samples are the hook — "Want to try it on for your next loop?" The phone captures content for social media. | ~$50-$80 (business cards $20-30, QR stand $10-15, signage $20-30)
5C.03 | Attend first 3 running events and document results | 3 events attended with documented results | Complete event attendance playbook: minute-by-minute event day plan, conversation scripts (opener, demo, close), results documentation template (products tried, emails captured, sales, feedback), and a post-event follow-up sequence for contacts collected. | COMPLETE ✓ | The first 3 events are the LEARNING phase. You discover: which event type draws the best audience, which pitch angle resonates, which objections come up (always sizing), and how many try-ons convert to sales. By event 4-5, you're twice as effective because you've refined the in-person pitch. | ~$70-$150 (event fees $0-$50 each + travel)
5C.04 | Partner with 2-3 local running clubs: 15% club discount, free product for group run leader | 2-3 club partnerships active | Complete running club partnership strategy: how to identify and approach clubs, partnership offer structure (15% member discount + free belt for run leader), what you get in return (event presence, member email list access, co-branded social posts), and a partnership agreement template. | COMPLETE ✓ | A running club partnership gives you: access to 50-200 active runners per club, a trusted introduction ("our club partner StrideHer..."), and recurring touchpoints (weekly group runs where your belt is visible). One club partnership is worth 10 cold influencer outreach messages because the trust is pre-built through the club. | ~$50-$100 (1-2 free belts per club partnership)
5C.05 | Create a Strava club + online running community for ongoing engagement | Strava club live with 25+ members in 90 days | Complete online community strategy: Strava club setup and content plan, optional Facebook group creation, community engagement cadence (weekly challenges, monthly milestones), and how to convert community members into customers without hard selling. | COMPLETE ✓ | An owned community is the most durable marketing asset. Social media followers can disappear (algorithm changes, platform decline). A Strava club or email list is YOURS. Members who log runs together, celebrate each other's PRs, and share tips become brand advocates organically — no selling required. | $0

## 5C.01 Event Identification
P5C TASK 5C.01: IDENTIFY 5 RUNNING EVENTS — RANKED BY ROI FOR A BOOTSTRAPPED D2C BRAND
Not all events are equal. A free parkrun with 50 women runners beats a $500 expo booth with 5,000 mixed-gender casual joggers. Quality of audience > quantity.
Event Type | Description | Why It Works for StrideHer | Where to Find | Audience Size | Audience Quality | Cost | ROI Ranking
5 EVENT TYPES — ranked by ROI for a bootstrapped single-product D2C brand
★ PARKRUN (#1 — attend weekly) | Free, timed 5K events held every Saturday morning in 350+ US locations. Casual, welcoming community. 20-200 runners per event depending on city. Mostly recreational runners with a growing half/full marathon segment. Format: runners gather, run a 5K course in a park, then socialize for 15-30 min afterward. The POST-RUN socializing window is your marketing moment. | Parkrun is the PERFECT StrideHer event: 1. FREE to attend (for you and the runners) 2. WEEKLY (you can attend every Saturday — consistent exposure) 3. FEMALE-HEAVY (parkrun skews 55-60% women globally) 4. SOCIAL post-run window (runners are relaxed, chatty, and open to trying new gear) 5. COMMUNITY-oriented (word-of-mouth spreads fast — "Did you see that running belt at parkrun?") 6. RECURRING attendees (same runners every week = multiple touchpoints → conversion over time) | parkrun.us → find your nearest event. Also: search "parkrun [YOUR CITY]" on Google/Facebook for local pages. Register as a runner (free) to participate yourself. You're a runner first, a brand second. Running the parkrun THEN talking about your belt afterward is the authentic approach. | 20-200 runners per event | ★★★★★ Highest. Mostly women, recreational to serious runners, community-oriented. EXACTLY the P0B target. | $0 (parkrun is free to attend. Your only cost: gas + 10 sample belts to carry) | ★ #1 Highest ROI
LOCAL RACES (5K, 10K, half marathon) | Local road races and fun runs organized by running clubs, charities, or race companies. 100-5,000 runners depending on race size. You attend as a spectator/vendor at the start/finish area, OR run the race yourself wearing StrideHer. The EXPO area before the race and the FINISH LINE area after are prime marketing locations. | Runners at races are: gear-conscious (they notice what others wear), in buying mode (pre-race expos are shopping environments), and emotionally heightened (post-race endorphins make them more receptive to conversation and impulse purchases). Focus on HALF MARATHON and MARATHON races — these attract your core P0B target (serious distance runners who carry gear). | RunSignUp.com → search races in your area. MarathonGuide.com → race calendar by state. Active.com → local race listings. Facebook: search "[YOUR CITY] running events." Also: local running stores often sponsor or know about every race in the area. Ask them. | 100-5,000 runners | ★★★★ High. Serious runners with gear needs. But: mixed gender and some races skew male for longer distances. | $0-$50 If spectating: $0. If running: race fee ($25-$80). Vendor booth: $100-$500 (not needed at small races). | #2
RUNNING STORE EVENTS (group runs, shoe launches, clinics) | Local specialty running stores (Fleet Feet, Jackrabbit, independent shops) host weekly group runs, shoe launch events, injury prevention clinics, and gear demo days. 10-50 attendees per event. Highly engaged, gear-interested audience. These stores are the HEART of the local running community. Their recommendation carries massive weight. | Running store events attract the MOST gear-conscious runners — people who already spend $150 on shoes and $80 on shorts. They're the exact customer who will pay $34.99 for a premium belt. The store owner's endorsement is worth 50 Instagram posts. If a Fleet Feet employee says "Have you tried StrideHer?" — that's a near-guaranteed sale. | Google: "[YOUR CITY] running store" → visit their website → check "Events" or "Group Run" page. Fleet Feet: fleetfeet.com → store locator → local store events. Jackrabbit: jackrabbitsports.com. Visit in person: introduce yourself as a local runner and brand founder. Ask about event opportunities. | 10-50 per event | ★★★★★ Highest quality. Gear enthusiasts, high-spend runners, trust the store's recommendation. | $0-$50 Most store events are free to attend. Some may ask for a small product donation for raffle/giveaway. | #3 (highest quality audience but smaller)
RUNNING CLUB MEETUPS (weekly group runs) | Local running clubs meet weekly for group runs. 10-100+ members depending on club size. Some are competitive (track clubs), others social (pub runs, beer runs, moms who run). The social clubs are your TARGET. Clubs meet at the same time and place weekly — consistent exposure opportunity. | Running club members are LOYAL and VOCAL. If the club endorses StrideHer: every member hears about it within 2 weeks through word-of-mouth at group runs. Partnership opportunity (5C.04): offer a 15% club discount + free belt for the run leader = instant distribution channel through trusted community leaders. | Road Runners Club of America (RRCA): rrca.org → club finder. Meetup.com: search "running" in your area. Facebook Groups: "[YOUR CITY] running club." Strava: search for local running clubs. Ask at your local running store — they know every club in town. | 10-100+ per meetup | ★★★★ High. Committed runners who run weekly. Strong word-of- mouth network. Female-specific clubs are ideal. | $0 Most clubs are free to join or $20-$50/year membership. | #4
FITNESS EXPOS & HEALTH FAIRS | Large-scale events: marathon expos, fitness festivals, outdoor recreation shows, women's health fairs. 1,000-50,000 attendees. Booth rental: $200-$2,000+ depending on event size. These are the "big stage" events — high visibility but high cost and competition. | Expos provide MASSIVE volume exposure but lower conversion rate per person (people are overwhelmed with booths). The cost-per-impression is similar to digital ads but the in-person TRIAL component adds conversion power. Best use: attend as a VISITOR first (scout the format, see what booths work, understand the audience). VENDOR booth only after you've validated product-market fit at parkruns and local races. | RunSignUp.com → search for expos. Race organizers often list expo vendor applications on their websites. Women's health fairs: search "[YOUR CITY] women's health expo." Marathon expos: every major marathon (NYC, Chicago, Boston, LA, etc.) has a multi-day expo with vendor booths. | 1,000-50,000 attendees | ★★★ Medium. High volume but mixed audience (casual browsers, spectators, non- runners). Conversion rate per interaction is lower than parkrun or club. | $200-$2,000+ Booth rental + signage + travel. NOT recommended until Month 6+ when budget allows. | #5 (delay until Month 6+)
EVENT CALENDAR TEMPLATE — plan your first 3 months of events
MONTH 1 Calendar | Week 1: attend local parkrun as a RUNNER (no marketing — just participate and observe the community) Week 2: attend parkrun again, this time wearing StrideHer visibly + bring 3 sample belts in your bag Week 3: attend parkrun + visit local running store, introduce yourself and ask about events Week 4: attend parkrun + first running club meetup (observe, don't pitch) | Month 1 is the OBSERVATION month. You're learning: who runs at parkrun, what the post-run social dynamic is like, which running store is most community-oriented, and which clubs have the best culture fit. Do NOT pitch heavily in Month 1. Be a runner first. Build genuine relationships. The marketing comes naturally in Month 2. | Research and calendar all Month 1 events before you attend your first one. Have a 4-week plan, not a "I'll figure it out each Saturday" approach. | 4 parkruns + 1 store visit + 1 club meetup | Build relationships before selling. Month 1 ROI: $0 in sales. Priceless in community trust. | $0-$20 | Foundation month
MONTH 2-3 Calendar | Weekly parkrun: now bring 5-10 sample belts, QR code card, business cards. Offer try-ons post-run. Bi-weekly: attend 1 running club meetup with samples. Monthly: attend 1 local race as spectator with samples. By Month 3 you should have: attended 8-12 parkruns, 4-6 club meetups, 2-3 local races, and visited 2-3 running stores. | Month 2-3 is the ACTIVATION phase. You're now a recognized face at parkrun ("the belt lady/guy"). Runners approach YOU instead of you approaching them. Target per event: 5-10 try-ons, 3-5 email captures, 1-2 on-site sales (via QR code → Shopify mobile checkout). |  | 8-12 events total across all types | Target: 50-100 try-ons 20-30 emails 10-15 sales Cost per sale: $15-$30 (competitive with digital) | $100-$200 (samples + event fees + travel) | Activation phase

## 5C.02-03 Kit + Playbook
P5C TASKS 5C.02-03: EVENT KIT CHECKLIST + EVENT DAY PLAYBOOK — FROM ARRIVAL TO FOLLOW-UP
Pack the kit the night before. Follow the playbook on event day. Document everything. Follow up within 24 hours.
Element | Details | Purpose | Setup / Action | Cost | Quantity | Notes
5C.02: EVENT KIT — 12 items to pack the night before every event
1. Sample Belts | 10 sample belts: 5 S/M + 5 L/XL. Include all 4 colors if possible (at minimum: 3 Black + 2 Desert Rose + 2 Sage + 1 Ocean per size, adjusted by inventory). These are TRY-ON samples, not giveaways. The same 10 belts go to every event — they're your demo fleet. | Runners try on the belt, adjust it, take 3 steps, feel the grip. The physical TRIAL is the most powerful conversion tool: 40-60% of people who try the belt on buy it (vs 2-4% from a website visit). A runner who feels zero bounce after 3 steps is sold. | Pack in a tote bag or backpack the night before. Organize by size (rubber band or ziplock: S/M together, L/XL together). Pre-adjust buckles to a middle position for fast try-ons. | $0 (from existing inventory — NOT additional purchase) | 10 belts | Mark sample belts with a small dot of nail polish on the inside buckle so you can identify them vs sellable inventory. These get tried on by 50+ people — they may get slightly worn.
2. QR Code Card/Stand | A printed card (or small acrylic stand) displaying a QR code that links DIRECTLY to the Shopify product page (strideher.com/products/strideher-womens-running-belt). Generate the QR code: Shopify Admin → Marketing → Create QR code, OR use qr-code-generator.com (free). Print at office supply store on heavy cardstock. | The QR code eliminates "I'll check it out later" syndrome (they won't). After a try-on: "Scan this to order — free shipping, arrives in 3 days." The runner scans, the product page opens on their phone, they buy on the spot or save for later (70% of QR scanners complete the purchase within 24 hours). | Print QR code at 3"×3" minimum (must be scannable from 2 feet away). Mount on a small acrylic stand ($5-$10 from Amazon) or print on a thick card that stands upright. Under the QR code: "Scan to shop — Free US Shipping." | $10-$15 | 1-2 cards or stands | Test the QR code yourself before every event: scan it → product page loads → add to cart works → checkout works. A broken QR code at an event is an embarrassing waste.
3. Business Cards | Minimalist card: Front: StrideHer wordmark + "The first running belt designed for women" + strideher.com Back: QR code + "PARKRUN15 — 15% off your first order" Print: Moo.com or Vistaprint, 250 cards for $20-$30. | For runners who want to think about it. The discount code (PARKRUN15 or EVENT15) is unique to events — lets you track how many sales come from in-person marketing (Shopify → Discounts → see usage count). | Order 250 cards online ($20-$30). Keep 50 in your event kit bag at all times. | $20-$30 for 250 | 50 per event | Create a unique discount code per event TYPE: PARKRUN15, RACEDAY15, CLUBRUN15. This tells you which event type drives the most online sales.
4-5. Signage | A small banner or A-frame sign (optional for parkrun, useful for races/expos): "StrideHer — Running Belts Designed for Women" + "Try one on! Ask me." Alternative: a branded tablecloth or mat if you have a table at an expo. | Visual presence that says "I'm here on purpose, not just a random runner with extra belts." Even a simple A-frame sign with the brand name makes your presence 3× more approachable — people know you WANT to be approached. | For parkrun: a sign is optional (you're mobile, not at a booth). For races/expos: essential. Print a retractable banner ($30-$50 from Vistaprint) that rolls up into a portable tube. | $0-$50 (banner) | 1 | Parkrun approach: no sign, just wear the belt visibly and have samples in your bag. Talk to people naturally post-run. Race/expo approach: set up a small table with sign, samples, QR stand, and cards.
6. Phone (content capture) | Your phone is your content studio. Capture: photos of runners trying the belt, quick video testimonials ("What do you think?"), event atmosphere B-roll, and selfies with engaged runners (with permission). | Every event generates 3-5 pieces of social media content. A runner trying on the belt and saying "whoa, it doesn't move!" on camera is more powerful than any produced ad. This is authentic, in-the-moment UGC. | Charge phone fully the night before. Bring a portable charger. Clear storage space (you'll shoot 20-50 photos/videos per event). Use IG Stories for real-time posting during the event. | $0 | 1 | ALWAYS ask permission before photographing someone. "Mind if I grab a quick photo/video of you trying it? I'd love to share it." Most runners say yes — they're excited about the new gear.
7-12. Extras | 7. Tote bag to carry everything 8. Portable charger for phone 9. Email signup sheet (clipboard + pen, or tablet with Google Form) 10. Water bottle (you're running too!) 11. Snacks for post-run energy (granola bars to share = conversation starter) 12. Sunscreen/hat depending on weather | The email signup sheet captures contacts who aren't ready to buy today but want to hear from you. Add them to the "Event Contacts" Klaviyo list → trigger a 2-email sequence: (1) "Great meeting you at [EVENT]! Here's your 15% off code: EVENT15" sent same day, (2) "How are your runs going?" sent Day 7. | Create a Google Form on your phone: "Join the StrideHer community" — fields: name, email, running distance, how you heard about us. Simple and fast (30 seconds to fill out). | $10-$20 for extras | Various | The granola bars are a genuine move: "Want a post-run snack?" opens MORE conversations than "Want to try a running belt?" Food creates connection. Connection creates sales.
5C.03: EVENT DAY PLAYBOOK — minute by minute from arrival to departure
BEFORE EVENT (night before) | 1. Pack event kit (all 12 items from above) 2. Charge phone + portable charger 3. Check weather → adjust outfit 4. Review conversation scripts (below) 5. Set alarm (arrive 30 min before event start) 6. Post an IG story: "Heading to [parkrun/race] tomorrow morning. Come say hi!" | Preparation = confidence. Walking into an event with a packed kit and a plan feels completely different from winging it with 3 belts in a grocery bag. |  | $0 |  | The night-before IG story generates anticipation and may attract followers who attend the same event — they'll seek you out.
AT THE EVENT (arrival → run) | 1. Arrive 30 min early. Survey the venue: where do people gather post-run? Where's the best spot for visibility? 2. If parkrun: register and run the event yourself. Wear StrideHer visibly. Running the event = instant credibility ("she's one of us"). 3. If race: find the spectator zone near the finish line. Cheer runners in. Wear StrideHer with a visible brand shirt or sign. 4. Take B-roll photos/video of the event atmosphere during the run. | Running the event (parkrun) transforms you from "vendor" to "fellow runner who also makes a belt." This distinction is EVERYTHING in the running community. Vendors are tolerated. Fellow runners are welcomed. | Wear the Desert Rose belt (most visually distinctive color). Pair with a dark-colored running outfit so the belt is prominently visible. If anyone asks about it DURING the run: brief answer + "I'll tell you more after the run!" | $0 |  | Don't carry samples during the run — just wear the belt. Your goal during the run is to be visible and to complete the run, not to sell. The selling happens post-run.
POST-RUN (the marketing window) ★ MOST IMPORTANT | 1. After finishing: stay in the social gathering area. Most parkruns/races have a 15-30 minute post-run window where runners hydrate, stretch, and chat. 2. Open your bag of sample belts. Have the QR stand visible. 3. Wait for someone to notice or ask about YOUR belt (they will — Desert Rose is eye-catching). OR: approach a group naturally: "How was your run? I'm [NAME] — I actually made this belt, want to try it on?" 4. For each interested runner: let them try it on, adjust to their size, encourage them to jog 10 steps. 5. After try-on: "If you love it, scan this QR code — it ships free. Or take a card for later." 6. Capture 2-3 video testimonials: "Quick 10-second review — what do you think?" 7. Collect emails for anyone interested but not buying today. 8. Post IG stories in real-time throughout this window. | The 15-30 minute post-run social window is your marketing goldmine. Runners are: endorphin-high (happy, receptive), socially engaged (chatting with other runners), physically aware of their gear (they just ran — they know what bounced), and in a community environment (peer influence is powerful). One runner trying the belt and saying "this is amazing" within earshot of 5 other runners = 5 more conversations. | CONVERSATION FLOW: OPENER: "How was your run? What are you training for?" (Show genuine interest in THEM before mentioning your product.) BRIDGE: "I actually designed this belt — I was so tired of belts that bounced or didn't fit right." TRY-ON: "Want to try it? What size are you — I've got S/M and L/XL." DEMO: Adjust the belt on them. "Take 3 steps — feel the grip dots? That's what keeps it locked in place." CLOSE: "Scan this code if you want one — free shipping. Or take a card for later. No pressure." | $0 |  | The golden ratio: spend 70% of the time LISTENING to runners talk about their running, and 30% talking about the belt. The more you listen, the more they trust you. The more they trust you, the more they buy.
AFTER EVENT (same day) | 1. Tally results: products tried on, emails collected, QR scans (check Shopify traffic from mobile), business cards distributed. 2. Post 3-5 event photos/videos to IG stories + 1 reel recap. 3. Send follow-up email to ALL collected emails within 4 hours: "Great meeting you at [EVENT]! Here's your 15% off: [CODE]. Scan to shop: [link]." | Same-day follow-up converts at 3× the rate of next-day. The runner remembers the try-on, the endorphins, the conversation. By tomorrow, they've moved on. Strike while the memory is fresh. | Use the post-event email template: "Hey [NAME], So great meeting you at [EVENT] this morning! I hope [DISTANCE] felt good. Here's the belt you tried: [link] And 15% off your first order: [CODE] Free shipping — arrives in 3-5 days. Run your way, [YOUR NAME] Founder, StrideHer" | $0 |  | Log results in a simple spreadsheet: Event Name, Date, Type, Attendees (est.), Try-Ons, Emails, QR Scans, On-Site Sales, Cards Given, Content Pieces Created. This data determines which events to repeat.

## 5C.04-05 Clubs + Community
P5C TASKS 5C.04-05: RUNNING CLUB PARTNERSHIPS + STRAVA/ONLINE COMMUNITY BUILDING
Clubs = trusted distribution channel (50-200 runners per club, pre-built trust). Strava = owned community asset (yours forever, independent of algorithms).
Element | Details | How to Execute | What You Offer | What You Get | Timeline | Success Metrics
5C.04: RUNNING CLUB PARTNERSHIPS — turn 2-3 clubs into distribution channels
Club Identification | Target: 2-3 clubs that match StrideHer's audience: 1. Women-specific running clubs (highest fit: 100% target audience) 2. Social/casual running clubs that skew female (60%+ women) 3. Half/full marathon training groups (committed distance runners who carry gear) Avoid: competitive track clubs (focused on speed, not gear), ultra-niche clubs (<10 active members), clubs run by a competing brand ambassador. | Use the discovery methods from 5C.01: RRCA.org club finder, Meetup.com, Facebook Groups, Strava clubs, and local running store referrals. Attend 1-2 runs with each candidate club BEFORE pitching a partnership. You need to: (1) see if the culture fits, (2) build rapport with the run leader, and (3) ensure the audience is actually your target market. Approach the run leader or club president after your 2nd attended run. |  |  | Month 1: identify 3-5 candidate clubs. Month 1-2: attend 2 runs per club. Month 2-3: pitch partnership to top 2-3. | Identify 3-5 candidates. Attend 2+ runs each. Narrow to 2-3 best-fit clubs.
Partnership Offer (what you give the club) | STANDARD PARTNERSHIP PACKAGE: 1. 15% CLUB DISCOUNT: unique code "[CLUBNAME]15" for all members (track usage in Shopify) 2. FREE BELT for the run leader: they wear it every week = walking billboard at every group run 3. FREE BELT for raffle/giveaway: clubs love having prizes for monthly giveaways 4. OPTIONAL: 10% commission to club treasury for every sale using their code (builds incentive for the club to promote) Total cost: 2-3 free belts per club ($12-$21 each) = $24-$63 per partnership. | PITCH SCRIPT (to run leader or club president): "Hey [NAME], I've really been enjoying running with [CLUB NAME] — the community here is exactly what I was looking for. I wanted to ask about something: I'm the founder of StrideHer — it's a running belt designed specifically for women's bodies. I'd love to offer your members a 15% discount, and I'd like to gift you a belt to try. No obligation to promote it — but if you love it and your members ask about it, I'd be thrilled. I can also donate one for your next giveaway. Would that be something the club would be open to?" Key: position it as a GIFT to the club, not a marketing ask. The club gets value (discount for members, free giveaway prize). You get distribution. | • 15% member discount code • Free belt for run leader • Free belt for raffle • Optional: 10% commission to club treasury per sale • Ongoing support: replace leader's belt if worn out, provide new belts for seasonal giveaways | • Access to 50-200 active runners per club • Trusted endorsement from run leader (worth more than 50 cold influencer DMs) • Weekly visibility at group runs • Word-of-mouth: "Our club partner makes this amazing belt..." • Email blast potential: some clubs will include you in their member newsletter • Event presence: clubs host races, fun runs, and social events where you can have a presence | Partnership active from Month 2-3. Ongoing: 3-6 month initial commitment. Renew if mutually beneficial. | Per club: 10+ uses of discount code in first 3 months. Run leader wearing belt at every group run. 5+ organic mentions in club social media or newsletter. 3-5 sales/month attributable to club partnership.
Partnership Maintenance | Maintaining the relationship is as important as establishing it: 1. MONTHLY CHECK-IN: DM or email the run leader once a month: "How's the belt holding up? Any feedback from members?" 2. SEASONAL REFRESH: offer new colors or a fresh giveaway belt every 3 months 3. RACE SUPPORT: when the club hosts a race, offer to be a sponsor (provide giveaway belts for top finishers) 4. CONTENT COLLABORATION: invite the club for a co-branded social post or "club of the month" feature on StrideHer's IG 5. LISTEN: if club members have product feedback, treat it as priority input for v2 improvements | Set monthly calendar reminders for each club: "Check in with [CLUB NAME] run leader." Track each partnership in a simple sheet: Club Name, Leader Contact, Partnership Start Date, Code Usage (monthly), Last Check-In Date, Giveaways Provided, Feedback Notes. If a partnership isn't generating any code usage after 3 months: have an honest conversation with the run leader. Either they're not actively mentioning it, or the club isn't the right audience. It's okay to gracefully end partnerships that aren't working. |  |  | Ongoing. Monthly touchpoints. Quarterly evaluation. | Partnership is healthy if: code gets 3+ uses/month, run leader wears belt regularly, and at least 1 organic mention per month in club communications.
5C.05: STRAVA CLUB + ONLINE COMMUNITY — build an owned audience independent of social algorithms
Strava Club Setup | Create: "StrideHer Running Club" on Strava. Description: "A community for women who run. All paces, all distances, all bodies. Share your miles, celebrate your wins, and run your way. Everyone welcome — you don't need to own a StrideHer belt to join." Type: "Running" club, Public, Women-focused but open to all. The "you don't need to own our product" message is critical — it signals community, not sales funnel. | Strava → Clubs → Create Club. Name: StrideHer Running Club Sport: Running Type: Public Location: [Your City] (or "Global" if you prefer) Description: see left column Cover photo: StrideHer brand photo (runners in the belt, diverse body types) | Weekly content in the club: Monday: "Weekly goal — what are you running this week?" Wednesday: "Midweek check-in — how's training going?" Friday: "Weekend plans — any races or long runs?" Sunday: "Week recap — total miles logged!" Give kudos to every member's activity. Celebrate PRs publicly in the club feed. | A Strava club of 100+ active members is: • An owned audience (no algorithm can take it away) • A product feedback channel (ask members what they think of new colors, features) • A launch channel (announce new products to engaged runners) • A content source (members' running photos + achievements = social content) • A word-of-mouth engine (members recommend StrideHer to their running friends) | Week 1: create club. Month 1: invite event contacts, customers, social followers. Target: 25 members by Month 3. 50 members by Month 6. 100+ by Year 1. | 25+ members in 90 days. Weekly engagement from 30%+ of members. At 100 members: Club becomes self-sustaining (members invite friends without you asking).
Monthly Challenges (engagement driver) | Run a monthly challenge in the Strava club to keep engagement high: Month 1: "StrideHer 50 Mile Challenge" — log 50 miles in the month (achievable for most regular runners) Month 2: "Longest Run Challenge" — longest single run wins a free belt Month 3: "Consistency Challenge" — run 20+ days in the month Month 4: "Social Challenge" — post a running photo with #StrideHerMiles Prize: a free StrideHer belt (cost: $14-$21). The prize is the product → the winner becomes a customer → they create content with the belt. | Announce each challenge on the 1st of the month via: Strava club post + IG story + email to club members. Track: Strava leaderboards handle distance/consistency automatically. For photo challenges: create a dedicated hashtag and judge entries at month-end. Announce winner publicly: "Congrats to [NAME] who logged 87 miles this month! A Desert Rose StrideHer belt is on the way!" | 1 free belt per month as prize. Weekly encouragement posts. Monthly winner announcement on all social channels. | Challenges drive: consistent engagement (members check in weekly), friendly competition (leaderboards motivate), content generation (photo challenges), and product awareness (the prize IS the product). At $14-$21/month for one belt: this is the cheapest customer acquisition channel in the entire marketing mix. | Monthly. Announce: Day 1. Mid-month check-in: Day 15. Winner: Last day. | 20+ participants per challenge. 10+ new members from challenge promotion. 1 new customer (winner) per month. 5+ social posts using #StrideHerMiles per challenge.

## 5C FOUNDER ACTIONS
P5C EVENTS & LOCAL — FOUNDER ACTION CHECKLIST
Month 1: observe + build relationships ($0). Month 2-3: activate + sell (~$200-$400). Ongoing: weekly parkrun + monthly club engagement.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 10-11: RESEARCH + KIT PREPARATION
🔴 #1 | Identify 5 local events and create a 4-week attendance calendar | 1-2 hrs | $0 | 1. Find your nearest parkrun at parkrun.us → register as a runner (free) 2. Search RunSignUp.com for local 5K/10K/half marathon races in the next 3 months 3. Google "[YOUR CITY] running store" → visit websites → find group run schedules 4. Search RRCA.org, Meetup.com, and Facebook for local running clubs 5. Create a Google Calendar with your first 4 weeks: parkrun every Saturday + 1 midweek club run + 1 race/month 6. Register for any events that require registration
🔴 #2 | Prepare event kit: order business cards, print QR code, pack samples | 1 hr + delivery time | $50-$80 | 1. Order 250 business cards from Moo.com or Vistaprint ($20-$30) — front: logo + tagline + URL, back: QR code + discount code 2. Generate QR code: Shopify Admin → Marketing → Create QR code → product page URL. Print at 3"×3" on cardstock. Mount on acrylic stand ($10 from Amazon). 3. Create discount code in Shopify: "PARKRUN15" (15% off, track usage separately from other codes) 4. Set aside 10 sample belts from inventory: 5 S/M + 5 L/XL, mix of colors. Mark with dot on interior buckle. 5. Pack everything in a tote bag. Set by the door for Saturday morning.
🔴 #3 | Create Strava club | 15 min | $0 | 1. Strava → Clubs → Create Club → name: "StrideHer Running Club" 2. Description from Sheet 5C.04-05 (inclusive, welcoming, open to all) 3. Set sport: Running. Set type: Public. 4. Upload cover photo (brand running photo from P1D) 5. Post first message: "Welcome! This is a space for women who run. Share your miles, celebrate your wins, and let's build something together. What are you training for right now?"
MONTH 1: OBSERVATION (attend events as a runner, build relationships)
🟡 #4 | Attend first 3 parkruns as a participant + visit 2 running stores + attend 1 club meetup | 3-4 hrs per event | $0-$20 | WEEK 1: parkrun — just run it, enjoy it, observe the post-run social scene. Don't pitch. WEEK 2: parkrun — wear StrideHer visibly, bring 3 sample belts "just in case" anyone asks. Visit a local running store after. WEEK 3: parkrun + attend a running club group run. Introduce yourself as a runner. Mention the belt only if asked. WEEK 4: parkrun + visit second running store. By now you're a recognized face at parkrun. Log results after each event per Sheet 5C.02-03.
MONTH 2-3: ACTIVATION (sell, partner, grow)
🟡 #5 | Bring full event kit to every parkrun + pitch 2-3 club partnerships | 4 hrs/week (Saturday parkrun + 1 weekday club) | $100-$200 | 1. Every Saturday parkrun: bring full kit (10 samples, QR stand, cards). Post-run: offer try-ons, capture 2-3 video testimonials, collect 5+ emails, give out cards. 2. Pitch partnership to 2-3 clubs you've attended (use script from Sheet 5C.04-05). Gift run leader a belt. Set up discount code. 3. Send same-day follow-up emails to all collected contacts. 4. Post 3-5 event photos/stories to IG after each event. 5. Track everything: try-ons, emails, QR scans, card distributions, on-site sales. 6. Invite every event contact to the StrideHer Strava club.
ONGOING: WEEKLY RITUAL
🟢 #6 | Weekly parkrun + monthly club engagement + Strava community management | 4-5 hrs/week total | $15-$25/month (giveaway belt) | WEEKLY: • Saturday: parkrun with full event kit (2-3 hrs including run + marketing) • 1 weekday: attend partner club's group run (1-2 hrs) MONTHLY: • Run a Strava challenge (announce Day 1, check-in Day 15, winner Day 30) • Check in with each club partner run leader • Post event recap content (1 reel compiling the month's best event moments) QUARTERLY: • Evaluate each club partnership: is the discount code being used? Is the run leader still enthusiastic? Renew or end based on data.