## P5D EXEC SUMMARY
P5D PR & MEDIA OUTREACH — EXECUTIVE SUMMARY
4 Tasks ¦ Weeks 12-18 ¦ Cost: ~$150-$300 (10 sample belts + shipping) ¦ One media placement can drive more traffic than 3 months of social posting.
Task ID | Task | KPI | Deliverable | Status | Why PR Matters | Cost
5D.01 | Build media list: 20 running gear reviewers, bloggers, YouTubers, podcast hosts | 20 qualified media contacts identified | Complete media prospecting guide: 5 media categories ranked by ROI (gear review blogs, YouTube channels, podcasts, online magazines, local media), 20-contact target list template with research fields, and qualification criteria for each category. Focus on mid-tier outlets (10K-200K audience) that actually review products — not mega-outlets that ignore indie brands. | COMPLETE ✓ | One feature in a running blog or YouTube review with 50K readers/viewers = 500-2,500 website visits in a single week. Compare to: 3 months of daily social posting for the same traffic. PR is the AMPLIFIER — a single placement multiplies all your other marketing efforts because it provides third-party credibility ("Runner's World featured this belt" vs "we say our belt is great"). | $0 (research only)
5D.02 | Craft press kit: press release, high-res photos, product specs, founder bio, brand angle | Complete digital press kit ready to send | 5-component press kit: (1) press release announcing StrideHer launch, (2) high-res product photos (from P1D), (3) one-page product spec sheet, (4) founder bio + headshot, (5) unique angle summary for journalists. All packaged as a Google Drive folder link or downloadable ZIP. This is the "one-click" asset pack that makes it EASY for a journalist to write about you. | COMPLETE ✓ | Journalists and reviewers are overwhelmed with pitches. A complete, professional press kit means they can write about you without asking 10 follow-up questions. No press kit = "I'll cover them later" (they won't). Complete press kit = "I can write this story in 30 minutes" (they will). | $0 (uses existing photos + copy)
5D.03 | Send product samples to 10 running gear reviewers with personalized pitch | 10 samples shipped with tailored pitches | Complete reviewer outreach system: personalized pitch email template, what to include in the reviewer package (product + press kit + handwritten note), follow-up cadence, and response tracking. Target: 10 outreach → 4-6 accept sample → 2-3 publish review. Each published review = a permanent backlink + ongoing referral traffic. | COMPLETE ✓ | Product reviews from trusted running sites are the gold standard of D2C credibility. A positive review on a site like The Run Commuter or Believe in the Run influences hundreds of purchases over its lifetime. These reviews rank in Google search ("StrideHer review") and provide social proof you can reference in ads, emails, and on your product page. | ~$150-$250 (10 belts COGS $60-$70 + shipping $50-$80 + press kit printing $20)
5D.04 | Pitch story angles to 5 publications: founder story, bootstrapped D2C, women in running gear | 5 personalized story pitches sent | Complete pitch strategy: 5 unique story angles tailored to different publication types (founder profile, product innovation, women in business, running industry, global D2C), with pitch email templates and publication-specific customization. These are STORY pitches — not product reviews — targeting editorial coverage that reaches broader audiences. | COMPLETE ✓ | Story pitches target EDITORIAL coverage (articles about the founder, the brand, the mission) rather than product reviews. Editorial pieces reach audiences beyond gear-heads — they attract investors, potential partners, future employees, and customers who buy based on the founder's story rather than product specs. One profile in a women's business publication creates brand legitimacy that no amount of Instagram posts can match. | $0 (email pitches only — no product samples needed for story pitches)

## 5D.01 Media List
P5D TASK 5D.01: BUILD 20-CONTACT MEDIA LIST — 5 CATEGORIES RANKED BY ROI FOR INDIE D2C
Target mid-tier outlets (10K-200K audience) that actually review indie products. Mega-outlets (Runner's World, GQ) ignore brands with <$50K revenue. Mid-tier outlets are hungry for new products.
# | Category | Why It Works | How to Find Contacts | Example Outlets | Audience Size | Response Rate | Target (# contacts)
5 MEDIA CATEGORIES — build 4 contacts per category = 20 total contacts
1 | Running Gear Review Blogs | These sites exist SPECIFICALLY to review running gear. They actively seek new products. A StrideHer review becomes a permanent, SEO-ranked page that drives traffic for years. Mid-tier running blogs are the BEST ROI media target: they're eager for content, responsive to indie brands, and their audience is exactly StrideHer's target customer. | Google: "running belt review blog" "running gear review" "best running belts" Look for: sites that have reviewed FlipBelt, SPIbelt, or Naked Running Band. These sites review running belts and will be interested in a new entrant. Check each site's "About" or "Contact" page for: editor name, email, and review submission guidelines. Also check: the P4D.04 blogger outreach targets — overlap with those. | • The Run Commuter (running gear reviews, mid-tier) • Believe in the Run (detailed gear reviews) • Road Runner Sports Blog • RunRepeat.com (running product database) • Gotta Run (gear-focused running blog) • Running Shoes Guru (expands into gear) • Run Trails (if trail/ultra adjacent) • The Wired Runner (running tech + gear) | 10K-200K monthly readers per site | 20-40% (gear review sites WANT new products to review) | 4 contacts
2 | YouTube Gear Reviewers | Running gear YouTube channels review products on camera — the most influential review format because viewers see the product in use. A video review ranks in both YouTube AND Google search for the product name. YouTube reviews have the LONGEST lifespan: a "StrideHer review" video posted today gets views for 3-5 years. | YouTube search: "running belt review" "best running belt" "running gear haul" Filter by: upload date (last 12 months), view count (5K-100K views — this is the mid-tier sweet spot). Check: channel subscriber count (5K-200K = mid-tier). Look at their "About" or "Business inquiries" section for email. Many YouTube reviewers also have Instagram — cross-reference with P5A influencer list. | • Chase the Summit (running gear reviews) • The Running Channel (UK-based, large audience) • Nick Bare (fitness/running, larger) • Sage Running (marathon-focused) • Ben Parkes (running tech reviews) • Running with James (gear + training) • The Ginger Runner (trail + road gear) • Kofuzi (running culture + gear) | 5K-500K subscribers per channel | 15-30% (YouTubers accept free products readily if relevant) | 4 contacts
3 | Running Podcasts | Running podcasts reach a captive, highly engaged audience (listeners choose to spend 30-60 minutes on running content). A founder interview or product mention on a running podcast drives: website traffic, email signups, and brand awareness among serious runners. Podcast audiences are among the most LOYAL — they trust the host's recommendations more than any other media format. | Apple Podcasts / Spotify: search "running" "marathon" "women running" → sort by relevance → check episode frequency (active = posted within last month). Listen to 1-2 episodes: does the host interview founders? Review gear? Tell personal stories? Match the show's format to your pitch angle. Contact: most podcasts have a website with a "Be a Guest" or "Contact" form. | • Ali on the Run (women's running, interviews) • The Morning Shakeout (running culture + gear) • Trail Runner Nation (trail + gear) • Running Rogue (women-focused running) • Ten Junk Miles (casual running community) • The Run Smarter Podcast (evidence-based running) • Marathon Training Academy (training + gear) • Clean Sport Collective (running integrity) | 5K-100K downloads per episode | 10-25% (podcasts need guests — a founder with a unique story is valuable content) | 4 contacts
4 | Online Magazines + Publications | Online publications (women's health, fitness, entrepreneurship) reach audiences beyond the running niche. A feature in a women's business publication or health magazine introduces StrideHer to women who run but don't follow running-specific media. These are STORY placements (founder profile, brand feature) rather than product reviews. | Search: "[publication name] + running gear" OR "[publication] + women entrepreneurs" OR "[publication] + D2C brand" Target the EDITOR or WRITER who covers your beat — not the general inbox. Find specific writers on Twitter/X or LinkedIn. Pitch: story angle, not product review. "I'd love to share the story of how I built the first running belt designed for women" — not "please review my belt." | • Women's Health (gear section) • Self (fitness gear picks) • Bustle (women's lifestyle) • Inc.com / Fast Company (D2C entrepreneur profiles) • Shopify Blog (D2C success stories — they feature merchants) • Well+Good (wellness + fitness gear) • PopSugar Fitness (women's fitness gear) • Byrdie (wellness lifestyle) | 500K-10M+ monthly readers | 5-10% (competitive — many brands pitch these outlets. Unique angle is essential) | 4 contacts
5 | Local Media (city-specific) | Local media covers "local entrepreneur launches brand" stories more readily than national outlets. A feature in your city's newspaper, business journal, or local TV morning show creates: community credibility, local customer base, and a backlink from a high-authority domain. Local media is the most UNDER-UTILIZED channel for D2C founders. Competition is low. Interest is high. | Google: "[YOUR CITY] business journal" "[YOUR CITY] entrepreneur news" "[YOUR CITY] morning show" Target: the business reporter or lifestyle/health reporter at your local newspaper, the local business journal (every US metro has one), and the local TV morning show "lifestyle segment" producer. Pitch: "Local entrepreneur launches innovative running product" — local media LOVES this angle. | • [Your City] Business Journal • [Your City] newspaper (business section) • [Your City] local TV morning show • [Your City] magazine (lifestyle section) • Local radio "community spotlight" segments • Chamber of Commerce newsletter • University alumni magazine (if applicable) • Local running magazine/blog (if your city has one) | Varies: 50K-500K local reach | 20-40% (local media is hungry for local stories. Low competition vs national outlets) | 4 contacts
MEDIA LIST TEMPLATE — create a Google Sheet with these columns for all 20 contacts
TEMPLATE | Google Sheet columns: 1. Contact Name 2. Outlet Name 3. Category (Blog / YouTube / Podcast / Magazine / Local) 4. Email or Contact Form URL 5. Audience Size (est.) 6. Recent Coverage (link to a recent article/video showing they cover running gear or D2C brands) 7. Pitch Type (product review / founder story / product mention) 8. Personalization Note (specific reference to their recent work — ESSENTIAL for response) 9. Outreach Date 10. Response (Yes / No / Pending) 11. Sample Shipped (Y/N + date) 12. Coverage Published (Y/N + URL) 13. Traffic Impact (GA4 referral data post-coverage) | Spend 3-4 hours researching and populating this list. For each contact: visit their site, read/watch 2-3 recent pieces, identify the RIGHT person (not the general inbox), and write a personalization note. The personalization note is what separates a 5% response rate from a 30% response rate. "I loved your comparison of the FlipBelt vs SPIbelt — you raised a point about women's sizing that nobody else mentions" tells the reviewer: this person actually reads my work. |  |  |  | 20 contacts across 5 categories

## 5D.02 Press Kit
P5D TASK 5D.02: COMPLETE DIGITAL PRESS KIT — 5 COMPONENTS, ONE SHAREABLE LINK
Package everything a journalist needs to write about you in one click. Google Drive folder or downloadable ZIP. No journalist should need to email you for basic info.
Component | What to Include | Content Source | Format | Why It Matters | File Name | Notes
PRESS KIT FOLDER STRUCTURE: /StrideHer-Press-Kit/ → 5 subfolders
1. PRESS RELEASE | HEADLINE: StrideHer Launches the First Running Belt Designed Specifically for Women's Bodies SUBHEAD: Adjustable fit, 3 separate zippered pockets, and a contoured profile built around women's hip geometry — addressing the #1 complaint in running belt reviews. BODY (400-500 words): • Paragraph 1: What StrideHer is + what makes it different (adjustable, 3 pockets, women-specific contour) • Paragraph 2: The problem it solves (1,250+ reviews analyzed, #1 complaint is bouncing/poor fit for women) • Paragraph 3: Founder story (condensed 100-word version from P1C.01) • Paragraph 4: Product details (price $34.99, 4 colors, 2 sizes, free US shipping, available at strideher.com) • Paragraph 5: Unique features (hidden period product pocket, YKK water-resistant zippers, 3M reflective) BOILERPLATE: "About StrideHer: StrideHer is a women-founded running gear brand on a mission to make gear that fits every body. Founded in [YEAR], StrideHer launched with its flagship adjustable running belt — the first designed specifically for women's bodies. Learn more at strideher.com." CONTACT: [YOUR NAME], Founder ¦ hello@strideher.com ¦ strideher.com | P1C.01 founder story P1C.02 positioning P0A competitive data P2A product specs | PDF (1-2 pages, formatted with brand fonts and logo) | The press release is the "source document" that journalists adapt into their own words. A well-written press release gets copied with light editing — saving the journalist time = higher publication rate. Format it like a REAL press release: headline, dateline, body paragraphs, boilerplate, contact info. Use the inverted pyramid (most important info first). | StrideHer-Press-Release-2026.pdf | Date the press release with your launch date. Send 1-2 weeks BEFORE launch to give journalists time to prepare coverage. Embargo note: "Embargoed until [LAUNCH DATE]" — tells journalists they can write the piece but not publish until your launch day.
2. PRODUCT PHOTOS (high-res) | 10-15 high-resolution product photos, organized in a subfolder: • Hero on white (front, 3 angles) • All 4 colors lineup • On-body lifestyle (2-3 photos, diverse runners) • Detail close-ups (zipper, buckle, silicone dots, reflective strips) • Pocket flat lay (showing what fits in each) • Phone fit close-up • Founder wearing the product All photos: minimum 2048px on longest side, JPEG, sRGB color profile, 300 DPI for print use. | P1D shot list (all photos should already be shot per P1D plan) | JPEG (high-res, 300 DPI) Subfolder: /Photos/ | Journalists use your photos in their articles. If you don't provide high-res, print-quality images: they either use low-quality screenshots from your website (makes you look amateur) or skip the story entirely. High-res photos = professional coverage. Label each file descriptively: "StrideHer-Desert-Rose-On-Body-Running.jpg" not "IMG_4523.jpg". | /Photos/ StrideHer-Hero-White-Front.jpg StrideHer-All-Colors-Lineup.jpg StrideHer-On-Body-Running.jpg [etc.] | Include a mix of: white-background product shots (for article headers and product listings) AND lifestyle shots (for editorial features and social sharing). Journalists choose what fits their layout — give them options.
3. PRODUCT SPEC SHEET (one-pager) | A single-page PDF with all essential product information: PRODUCT: StrideHer Women's Running Belt PRICE: $34.99 ¦ Free US Shipping SIZES: S/M (25"-33") ¦ L/XL (33"-43") COLORS: Midnight Black, Desert Rose, Alpine Sage, Deep Ocean WEIGHT: 85g (3 oz) KEY FEATURES: • Fully adjustable — one belt fits 25"-43" waists • 3 separate zippered pockets (phone, valuables with hidden mesh section, gel pocket with magnetic snap) • Zero bounce: 200+ medical-grade silicone grip dots in hexagonal grid • Women-specific contoured 4-panel profile • YKK #3 Uretek water-resistant zippers • 3M Scotchlite reflective strips for visibility • 220 GSM nylon-spandex 4-way stretch • Hidden interior pocket for period products • Duraflex adjustable buckle AVAILABLE: strideher.com PRESS CONTACT: hello@strideher.com | P2A.03-04 tech spec P2D.05 product copy | PDF (1 page, brand-formatted) | The spec sheet is the quick-reference for journalists who need product details without reading the full press release. It answers: what is it, how much, what makes it special — in 30 seconds flat. Format: clean, scannable, with a product photo at top and specs below. Use the brand color palette and fonts. | StrideHer-Product-Spec-Sheet.pdf | Include one small product photo at the top of the spec sheet. The visual reference helps journalists confirm they're describing the right product.
4. FOUNDER BIO + HEADSHOT | TWO versions of the founder bio: SHORT (50 words): "[YOUR NAME] is the founder of StrideHer, the first running belt designed specifically for women's bodies. A [distance] runner based in [CITY], [she/he/they] launched StrideHer after years of frustration with 'unisex' running gear that didn't fit. StrideHer is [her/his/their] first consumer product venture." LONG (150 words): expanded version including: running background, specific inspiration moment (the run where the belt bounced for the last time), product development journey (designed the belt, sourced manufacturing, bootstrapped on $10K), mission ("every runner deserves gear that fits"), and future vision. HEADSHOT: professional or high-quality candid photo. Options: studio headshot, running photo (preferred — shows you're a runner, not just a CEO), or action shot wearing the belt. All media use "by" lines and founder quotes — your bio + photo appear in every article. | P1C.01 founder story (adapt to 50 and 150 word versions) | PDF (bio) + JPEG (headshot, min 1000px, 300 DPI) | Journalists always need a founder quote and bio for articles. If you don't provide them: the journalist either omits the human element (weaker story) or makes something up from your website (inaccurate). Pre-written bios in two lengths let journalists pick the version that fits their layout. The running headshot is strategically important: it visually reinforces "the founder is a runner" which builds credibility for the product. | Founder-Bio-Short.pdf Founder-Bio-Long.pdf Founder-Headshot-Running.jpg Founder-Headshot-Studio.jpg | Include a photo of you RUNNING (action shot), not just standing in front of a logo. Running media wants to see that the founder runs. Business media wants to see that the founder looks professional. Provide both.
5. UNIQUE ANGLE SUMMARY | A one-page document listing 5 story angles that journalists can choose from: ANGLE 1 — PRODUCT INNOVATION: "The first running belt designed for women's bodies — why 'unisex' gear doesn't work for female runners" (best for: gear review sites, running blogs) ANGLE 2 — FOUNDER JOURNEY: "From frustrated runner to product designer: how [NAME] bootstrapped a running gear brand on $10K" (best for: entrepreneur publications, startup media) ANGLE 3 — DATA-DRIVEN DESIGN: "We analyzed 1,250+ running belt reviews. Here's what women runners actually want." (best for: data-driven publications, running culture articles) ANGLE 4 — WOMEN IN RUNNING GEAR: "Less than 5% of running gear is designed specifically for women. StrideHer is changing that." (best for: women's publications, health/wellness media) ANGLE 5 — GLOBAL D2C: "From [YOUR COUNTRY/CITY] to doorsteps worldwide: building a global D2C brand in 2026" (best for: international business media, e-commerce publications) | P1C positioning P0A competitive data P0B customer research P1C.01 founder story | PDF (1 page) | Journalists don't want to figure out the story — they want the story HANDED to them. A unique angle summary says: "Here are 5 ways you could cover StrideHer. Pick the one that fits your publication." This is the difference between a generic pitch that gets ignored and a specific pitch that gets picked up. Each angle targets a different publication type. When you pitch, choose the 1-2 angles most relevant to that specific journalist and lead with those. | StrideHer-Story-Angles.pdf | Update the angles as the brand grows. After Month 6: add "ANGLE 6 — GROWTH STORY: From 0 to 1,000 customers in 6 months." After Year 1: add awards, milestones, and expansion angles. Angles are living documents — refresh quarterly.
PRESS KIT DELIVERY: share as a single Google Drive folder link or downloadable ZIP
DELIVERY METHOD | Create a Google Drive folder: /StrideHer-Press-Kit/ /Press-Release/ /Photos/ /Product-Spec/ /Founder/ /Story-Angles/ Set sharing: "Anyone with the link can view." Short URL: create a bit.ly or strideher.com/press redirect to the Google Drive folder. Include this link in EVERY outreach email: "Full press kit here: strideher.com/press" Also: create a /pages/press page on your Shopify site that links to the same Google Drive folder. Journalists often check a brand's website for a "Press" page. | Google Drive (free) | Google Drive folder (shareable link) + Shopify /pages/press | A single shareable link that contains EVERYTHING eliminates back-and-forth emails ("Can you send high-res photos?" "What's the price?" "Do you have a founder bio?"). Every question is pre-answered. Every asset is pre-provided. The journalist writes the story without emailing you once. | strideher.com/press → redirects to Google Drive folder | Check the Drive folder link monthly: are all files current? Photos updated? Press release dated correctly? A press kit with 2024-dated materials in 2026 looks abandoned.

## 5D.03 Reviewer Outreach
P5D TASK 5D.03: PRODUCT SAMPLE OUTREACH TO 10 RUNNING GEAR REVIEWERS
Send a free belt + press kit + personalized pitch to 10 reviewers. Expect 4-6 to accept, 2-3 to publish a review. Each published review = permanent backlink + ongoing traffic.
Element | Details | Pitch Email Template | Follow-Up Cadence | Expected Results | Reviewer Package | Tracking
REVIEWER OUTREACH — personalized email pitch + product sample to 10 gear reviewers from your 5D.01 media list
PITCH EMAIL (gear review sites + YouTube) | Target: the 8 contacts in categories 1-2 (gear review blogs + YouTube channels) from your 5D.01 media list. These are PRODUCT REVIEW pitches — you're offering a free product for an honest, published review. Personalization is non-negotiable: reference a specific recent review they published. "I read your FlipBelt review and noticed you mentioned the sizing issue for women — that's exactly the problem we solved." | Subject: New running belt for your review consideration — designed specifically for women Hi [FIRST NAME], I'm [YOUR NAME], founder of StrideHer. I've been reading [OUTLET NAME] for a while — your [SPECIFIC RECENT REVIEW TITLE] was particularly helpful because [SPECIFIC DETAIL — e.g., "you raised the sizing issue that most reviewers overlook"]. I'd love to send you our belt for an honest review. StrideHer is the first running belt designed specifically for women's bodies — here's what makes it different: • Adjustable fit: S/M (25"-33") and L/XL (33"-43") — no more ordering 3 sizes • 3 separate zippered pockets: phone, valuables (with hidden mesh for period products), and gels • Zero bounce: 200+ silicone grip dots in a hexagonal grid • Contoured 4-panel design following women's hip geometry Retail: $34.99 ¦ strideher.com Full press kit: strideher.com/press I believe your readers would find this review valuable — especially women runners tired of "unisex" belts. Happy to answer any questions or share additional details. Would you be open to receiving a sample? I can have it at your door in 3-5 days. Best, [YOUR NAME] Founder, StrideHer hello@strideher.com | Day 0: send pitch email. Day 5 (no response): "Hi [NAME], just following up on my note about StrideHer. I know you're busy — happy to answer any questions if you're considering a review. No pressure either way!" Day 12 (no response): "Last follow-up from me! If the timing isn't right, totally understand. The press kit is always available at strideher.com/press if you'd like to cover us in the future. Wishing you great miles ahead." Day 12+: mark as "No Response." Move on. NEVER follow up more than 2 times. Three emails total (1 pitch + 2 follow-ups) is the maximum. | 10 outreach emails → 4-6 accept sample (40-60% for personalized, relevant pitches to mid-tier outlets). 2-3 publish a review (50% of sample recipients actually publish — some get busy, some don't like the product, some lose the sample in a pile of PR packages). Timeline: pitch to publication = 4-12 weeks. | Each reviewer receives: 1. StrideHer belt in their size/color preference (ask in acceptance reply) 2. Printed press kit (press release + spec sheet + angle summary — printed at home or office supply store) 3. Handwritten note (same approach as P5A.04: personalized, genuine, reference their work) 4. Business card with QR code 5. Insert card (standard from P2C.03) Ship via USPS Priority Mail. Include tracking. DM/email them: "Your StrideHer sample is on the way — tracking: [number]." | Track in your 5D.01 media list spreadsheet: • Outreach date • Response (Y/N/Pending) • Sample shipped (date) • Review published (Y/N) • Review URL • Review sentiment (positive/mixed/negative) • Backlink quality (DA of the site) • Traffic from review (GA4 referral data)
PITCH EMAIL (podcasts) | Target: the 4 contacts in category 3 (podcasts) from your 5D.01 media list. Podcast pitches are GUEST INTERVIEW pitches — you're offering yourself as a guest, not sending a product for review. Angle: founder story + product innovation. Podcasts want interesting STORIES and CONVERSATIONS, not product specs. | Subject: Guest pitch — founder who built the first women's running belt (unique story) Hi [HOST NAME], I'm a big fan of [PODCAST NAME] — your episode with [SPECIFIC RECENT GUEST] about [TOPIC] really resonated with me because [SPECIFIC DETAIL]. I'm [YOUR NAME], a runner and the founder of StrideHer — the first running belt designed specifically for women's bodies. I built it after years of running in "unisex" belts that never fit right, and I think my story would resonate with your listeners: • Why I analyzed 1,250+ running belt reviews before designing a single prototype • The hidden pocket for period products that no other brand has thought of • How I bootstrapped a global D2C brand on a $10K budget • What I learned about women's running gear being treated as an afterthought by the industry I can speak to: running gear design, women in running, bootstrapped entrepreneurship, and D2C brand building. Would you be interested in having me on the show? I'm flexible on timing and format. Best, [YOUR NAME] Founder, StrideHer hello@strideher.com strideher.com/press (full press kit) | Same follow-up cadence as reviewer pitch: Day 5 and Day 12. Podcast booking timelines are LONGER: hosts often schedule 2-4 months ahead. A "yes" in Month 1 may not record until Month 3 and air in Month 4. Be patient and flexible with scheduling. | 4 podcast pitches → 1-2 accept (25-50% for mid-tier podcasts with a compelling founder story). Timeline: pitch to air date = 2-6 months. Each podcast episode reaches 5K-100K listeners — your most engaged audience because they chose to listen for 30-60 minutes. | No product sample needed for podcast pitches. Just yourself, your story, and your energy. Prepare: 3-4 talking points you want to hit regardless of questions asked. Practice the founder story in a compelling 2-minute version. After recording: the host often mentions the product with a link in show notes — this is a high-quality backlink. | Track separately: • Pitch date • Response • Recording date • Air date • Episode URL • Download count (host may share) • Traffic spike (GA4 on air date)

## 5D.04 Story Pitches
P5D TASK 5D.04: 5 STORY ANGLE PITCHES TO PUBLICATIONS — FOUNDER PROFILE + BRAND FEATURE
Story pitches target EDITORIAL coverage (articles about you), not product reviews. One founder profile in a women's business publication creates brand legitimacy no Instagram post can match.
Angle | Target Publications | Subject Line | Pitch Summary (first 3 sentences of email) | Why This Angle Works | Best For | Expected Outcome
5 STORY ANGLES — each targets a different publication type. Choose the 1-2 most relevant for each pitch.
ANGLE 1: Product Innovation | Running gear blogs Women's fitness publications Health/wellness media | "The first running belt designed for women's bodies — and why it matters" | "Did you know that less than 5% of running belts are designed specifically for women? Every major brand — FlipBelt, SPIbelt, Nathan — makes 'unisex' belts that assume a straight-hipped, medium-sized body. StrideHer is the first belt built from scratch for women's hip geometry, with a contoured profile, adjustable fit, and a hidden pocket for period products that no other brand has thought to include." | The "first" angle is inherently newsworthy. Journalists cover firsts. "First women-specific running belt" is a clear, defensible claim that creates a natural headline. The period product pocket detail is the "aha" moment that makes editors lean forward — it's unexpected and emotionally resonant. | Gear review sites Women's Health Self Runner's World (online gear section) | 1-2 feature articles focusing on the product innovation and women's gear gap. Backlinks from high-DA sites. Brand recognition as the "first."
ANGLE 2: Founder Journey | Entrepreneur publications Startup media D2C/e-commerce publications | "How I bootstrapped a running gear brand on $10K (after analyzing 1,250 customer reviews)" | "I spent 3 months analyzing 1,250+ reviews of every running belt on Amazon before I designed a single prototype. What I found: the #1 complaint from women runners was bouncing and poor fit — problems every existing brand ignored because they designed for 'unisex' bodies. So I bootstrapped StrideHer on a $10K budget, sourced manufacturing through Alibaba, and launched a D2C brand from my spare room." | The "$10K bootstrap" detail is the hook. Every entrepreneur publication covers stories of resourceful founders who built real businesses with limited capital. The 1,250+ review analysis adds a data-driven dimension that elevates it beyond a typical "I had an idea" founder story. This angle positions you as a strategic, research-driven entrepreneur — not just a passionate runner who got lucky. | Inc.com Fast Company Shopify Blog Entrepreneur.com Forbes (contributor) | 1 founder profile article. Credibility that supports all future PR, fundraising, and partnership conversations. Backlink from high-authority business domain.
ANGLE 3: Data-Driven Design | Running culture publications Design/innovation media Tech-adjacent publications | "We analyzed 1,250+ running belt reviews. Here's what women runners actually want." | "Before designing a single product, we analyzed 1,250+ customer reviews across every major running belt on Amazon. We categorized 62 distinct pain points, identified 5 customer personas, and discovered that the #1 complaint from women runners — bouncing and poor fit — was never addressed by any existing brand. This data didn't just inform our design — it IS our design." | The data angle appeals to publications that cover innovation methodology, product design, and customer-centric development. It positions StrideHer as a SMART brand (data-driven decisions) not just a passionate one (founder had an idea). The specific numbers (1,250+ reviews, 62 pain points, 5 personas) add credibility that vague claims ("we talked to runners") cannot match. | FastCo Design Product Hunt The Run Commuter Running culture publications | 1-2 articles covering the methodology. Positions StrideHer as an innovation story, not just a product story. Attracts attention from potential investors/partners.
ANGLE 4: Women in Running Gear | Women's publications Feminist media Health/wellness publications | "Why the running gear industry still treats women as an afterthought — and one brand trying to change it" | "Walk into any running store and count the products designed specifically for women: you'll find sports bras and... that's about it. Running belts, vests, hydration packs, and accessories are all 'unisex' — which in practice means 'designed for men, available in pink.' StrideHer is challenging this assumption with the first running belt built from scratch for women's bodies, including a hidden pocket for period products that somehow no major brand has ever thought to include." | This angle taps into the larger cultural conversation about women's representation in sports and gear design. It positions StrideHer within a MOVEMENT, not just a product category. Women's publications actively seek stories about brands addressing gender gaps — this is editorial catnip for editors at publications like Bustle, Refinery29, or Well+Good. | Bustle Refinery29 Well+Good PopSugar Women's Running magazine | 1-2 feature articles framing StrideHer within the women's gear equity movement. Reaches audiences BEYOND the running niche — women who run casually and don't read gear blogs.
ANGLE 5: Global D2C Bootstrap | International business media E-commerce publications Emerging market entrepreneur media | "Building a global D2C brand from [YOUR CITY] — how one founder is shipping running gear worldwide on a $10K budget" | "In 2026, you don't need to be in Silicon Valley or New York to build a global consumer brand. From [YOUR CITY], I'm manufacturing in China, selling to customers in 15+ countries, and managing the entire operation from a laptop and a spare room. StrideHer is proof that the D2C model has democratized global entrepreneurship — if you have a great product and $10K, you can reach the world." | This angle resonates with publications covering: globalization of D2C, emerging market entrepreneurs, Shopify success stories, and the "new global founder" narrative. It's particularly powerful if the founder is based outside traditional startup hubs — the geographic underdog story adds an extra dimension. Shopify's own blog actively features merchant success stories — pitch them directly via Shopify Partners or their editorial team. | Shopify Blog Rest of World TechCrunch (D2C) YourStory (if South Asian founder) Global entrepreneur media | 1 profile article about global D2C entrepreneurship. Reaches potential founders who become brand advocates ("I read about StrideHer and it inspired me"). Attracts Shopify ecosystem support.

## 5D FOUNDER ACTIONS
P5D PR & MEDIA — FOUNDER ACTION CHECKLIST
Total effort: ~15-20 hours over 6 weeks. Cost: ~$150-$300. Expected: 2-3 published reviews + 1-2 editorial features = permanent brand credibility assets.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 12-13: RESEARCH + PRESS KIT CREATION
🔴 #1 | Build 20-contact media list across 5 categories | 3-4 hrs | $0 | 1. Create Google Sheet with the 13-column template from Sheet 5D.01 2. Research 4 contacts per category (gear blogs, YouTube, podcasts, magazines, local media) 3. For EACH contact: visit their site/channel, read/watch 2-3 recent pieces, find the right person's email, write a personalization note 4. Score each contact on relevance (how closely their audience matches StrideHer's target) and accessibility (how responsive they seem to indie brands) 5. Rank: top 10 = immediate outreach (5D.03), remaining 10 = future waves
🔴 #2 | Create complete digital press kit (5 components) | 3-4 hrs | $0-$20 | 1. Write press release (400-500 words) per Sheet 5D.02 template — adapt from P1C positioning + P0A data 2. Assemble 10-15 high-res product photos in a folder (from P1D shot list) 3. Create 1-page product spec sheet (adapt from P2A tech spec into a clean branded PDF — use Canva) 4. Write founder bio in 2 lengths (50 words + 150 words) + select running headshot 5. Write unique angle summary (1 page, 5 angles from Sheet 5D.04) 6. Upload all 5 components to a Google Drive folder → set sharing to "anyone with link" 7. Create Shopify page: /pages/press → link to the Google Drive folder 8. Create a short URL: strideher.com/press → Google Drive folder
WEEK 14-16: OUTREACH — REVIEWERS + STORY PITCHES
🔴 #3 | Send personalized pitches to 10 gear reviewers + 2 podcast hosts | 4-5 hrs | $0 | 1. For each of the 10 gear reviewer contacts: customize the pitch email template from Sheet 5D.03, referencing their specific recent work 2. For each of the 2 podcast contacts: customize the podcast pitch template from Sheet 5D.03 3. Send all 12 pitches over 2-3 days (don't blast all at once — stagger for tracking) 4. Log outreach date in tracking spreadsheet 5. Set Day 5 and Day 12 follow-up calendar reminders for non-responders 6. When someone accepts: ask for size/color preference, ship within 48 hours
🟡 #4 | Ship product samples to all accepting reviewers | 30 min per package | $15-$25 per package | 1. Pack reviewer package per Sheet 5D.03: belt + printed press kit pages + handwritten note + business card + insert card 2. Ship USPS Priority Mail (tracking included) 3. Email/DM: "Your StrideHer sample is on the way — tracking: [number]. Full press kit: strideher.com/press. No timeline pressure on the review — take your time with it." 4. The "no timeline pressure" line is important — it communicates confidence (you believe the product speaks for itself) and reduces the reviewer feeling obligated (which paradoxically makes them more likely to review it)
🟡 #5 | Send 5 story angle pitches to editorial publications | 2-3 hrs | $0 | 1. Select 5 contacts from categories 4-5 of your media list (online magazines + local media) 2. For each: choose the 1-2 most relevant story angles from Sheet 5D.04 3. Customize the pitch email: personalize opening (reference their recent coverage), present the chosen angle in 3 compelling sentences, include press kit link 4. Send over 1 week 5. Follow up per standard cadence (Day 5, Day 12) 6. Story pitches don't require product samples — just your story and your press kit
WEEK 16-18: FOLLOW-UP + RELATIONSHIP BUILDING
🟢 #6 | Follow up on all outstanding pitches + nurture relationships with respondents | 2-3 hrs total | $0 | 1. Day 5 follow-up on all non-responders (brief, friendly bump) 2. Day 12 final follow-up (graceful close — "always available if you cover us in the future") 3. For reviewers who accepted but haven't published: check in at Week 4 after shipping: "Hi [NAME], just checking in — any questions about the belt as you test it? No rush on the review." 4. When a review publishes: thank the reviewer publicly (comment on the article, share on social with credit), add the review link to your product page as social proof, update your press kit with "As seen in [OUTLET]" badge 5. Add all responsive media contacts to a "Media Relationships" list for future outreach (new product launches, brand milestones, seasonal stories)