## P6C EXEC SUMMARY
P6C PAID ADVERTISING — META ADS (FACEBOOK + INSTAGRAM) — EXECUTIVE SUMMARY
5 Tasks ¦ Weeks 15-20+ ¦ Budget: $10-$25/day ($300-$750/month) ¦ Paid ads are the SCALING lever — turn on revenue growth with a dial.
Task ID | Task | KPI | Deliverable | Status | Why Meta Ads | Budget
6C.01 | Set up Meta Ads Manager: Business Manager, ad account, Conversions API, payment | Ads Manager live and funded | Complete Meta Ads Manager setup: Business Manager creation, ad account configuration, payment method, Conversions API verification (installed via P4C.02), and campaign structure overview (campaign → ad set → ad hierarchy explained). This is the plumbing that must work before spending a dollar. | COMPLETE ✓ | Meta (Facebook + Instagram) reaches 3.5B monthly users. For a women's running product, Meta is the #1 paid channel because: (1) Instagram is where women runners discover products, (2) Meta's algorithm is the best in the industry at finding buyers within a target audience, (3) UGC ad creative (from P5A influencers) performs 30-50% better on Meta than any other platform, (4) the Conversions API (installed in P4C.02) feeds purchase data back to the algorithm, making it smarter with every sale. | $0 (setup only)
6C.02 | Create first campaign: $10-$15/day, 3 ad sets testing audiences | First campaign live with 3 audience tests | Complete first campaign build: campaign objective (Sales/Conversions), 3 ad sets testing different audiences (interest-based runners, lookalike from customers, broad with creative targeting), budget allocation ($10-$15/day split across 3 ad sets), and bid strategy (lowest cost, no cap). The 3-ad-set structure lets Meta's algorithm find the best audience while you learn what works. | COMPLETE ✓ | The first campaign is a LEARNING investment, not a profit center. You're spending $10-$15/day for 14 days ($140-$210 total) to learn: which audience converts, which creative resonates, and what your actual CPA (cost per acquisition) is. This data is worth 10× the ad spend because it tells you WHERE to invest the remaining $500-$600/month in ad budget for profitable scaling. | $10-$15/day = $300-$450 for first 30 days
6C.03 | Create 5 ad variations: video demo, UGC, comparison, testimonial, lifestyle | 5 ad creatives live and testing | Complete ad creative library: 5 ad variations across different formats (video, UGC, image, carousel) each targeting a different buyer psychology (demonstration, social proof, comparison, problem-solution, aspiration). Primary text + headline + description for each. UGC from P5A influencers is the #1 predicted performer — real runners speaking authentically outperform brand-produced content 2-3×. | COMPLETE ✓ | Creative is the #1 lever in Meta advertising. Audience targeting matters, but at scale, every advertiser targets the same audiences — the CREATIVE is what makes someone stop scrolling. Five variations test 5 different "hooks" to discover which emotional trigger converts your audience: is it seeing the product in use? Hearing from a real runner? Seeing a side-by-side comparison? Data > assumptions. | $0 (creative from existing assets + P5A UGC)
6C.04 | Monitor and optimize daily for first 2 weeks: kill losers, scale winners | Daily optimization log for 14 days | Complete daily optimization protocol: the 5-metric daily check (spend, CPA, ROAS, CTR, frequency), kill/scale decision framework with exact thresholds, when to make changes vs when to let the algorithm learn, and common beginner mistakes that waste 50% of ad budget. Plus a 14-day optimization log template. | COMPLETE ✓ | Meta's algorithm needs 50 conversion events to optimize (the "learning phase"). During this phase: DON'T touch the campaigns. After learning phase: optimize aggressively based on data. The daily protocol prevents the #1 beginner mistake: panicking on Day 2 (high CPA, few conversions) and killing ads before the algorithm has enough data to optimize. Patience for 7 days → then data-driven decisions. | $0 (your time: 15-20 min/day)
6C.05 | Set up retargeting: site visitors, cart abandoners, email subscribers | Retargeting campaigns live | Complete retargeting campaign strategy: 3 retargeting audiences (site visitors who didn't buy, cart abandoners, email subscribers who didn't purchase), retargeting ad creative (different from cold ads — these people already know the product), budget allocation (20-30% of total ad budget), and frequency caps to prevent ad fatigue. | COMPLETE ✓ | Retargeting converts at 3-8× the rate of cold prospecting because the audience already knows StrideHer — they visited the site, added to cart, or engaged with an email. A $5/day retargeting budget recovers 2-5 additional sales/week from "almost buyers" who just needed one more nudge. This is the highest-ROI segment of the ad budget. | $3-$5/day (20-30% of total budget) ROAS: 5-10× (the most profitable segment)

## 6C.01-02 Setup + Campaign
P6C TASKS 6C.01-02: META ADS MANAGER SETUP + FIRST CAMPAIGN BUILD (3 AUDIENCE TESTS)
Campaign structure: 1 Campaign (Sales objective) → 3 Ad Sets (audience tests) → 5 Ads (creative tests). Budget: $10-$15/day. Learning phase: 7 days. First optimization: Day 8.
Element | Configuration | Where in Ads Manager | Why This Setting | Budget | Expected Results | Common Mistakes
6C.01: META ADS MANAGER SETUP (prerequisite: P4C.02 Meta Pixel + Conversions API already installed)
Business Manager Setup | If not already created: business.facebook.com → Create Account. Business Manager contains: your ad account, pixel, pages, and team permissions. Ad Account: Business Settings → Ad Accounts → Add → Create New. Payment: Ad Account Settings → Payment Methods → add credit card. Spending Limit: set a monthly spending limit of $500 (prevents accidental overspend while learning). Timezone: set to your timezone (affects when "daily budget" resets). Currency: USD. | business.facebook.com → Business Settings | Business Manager is the professional container for all Meta advertising. Using a personal Facebook account to run ads is possible but limits: team access, pixel management, and account recovery options. Business Manager is the standard for serious advertisers. The $500 monthly spending limit is CRITICAL for a bootstrapped brand — it prevents a misconfigured campaign from burning through your entire marketing budget overnight. | $0 (setup only) Spending limit: $500/month | N/A — setup only. | Not setting a spending limit (a broad audience campaign at $50/day with no limit = $1,500/month accidentally). Not linking the Meta Pixel to the ad account (ads can't track conversions). Using personal ad account instead of Business Manager (limits features + recovery options).
Conversions API Verification | Verify that the Conversions API (installed via the Facebook & Instagram Shopify app in P4C.02) is sending server-side events. Check: Meta Events Manager → Data Sources → your pixel → Settings → Conversions API → should show "Active" with event match quality score. Event Match Quality: target 6.0+ out of 10 (higher = better attribution accuracy). The Shopify app typically achieves 7-8. | Meta Events Manager → Data Sources → [Pixel] → Settings → Conversions API | Post-iOS 14.5, the browser pixel alone misses ~40% of conversion events (blocked by Apple's App Tracking Transparency). The Conversions API sends events from Shopify's SERVER directly to Meta — bypassing browser restrictions. Without CAPI: Meta under-reports conversions by 30-40% → the algorithm under-optimizes → you get worse results for the same spend. With CAPI: near-complete conversion tracking → algorithm optimizes accurately → better ROAS. | $0 | CAPI active = higher attribution accuracy = better algorithm optimization = lower CPA over time. | Not verifying CAPI is active (many Shopify users install the app but don't complete the connection). Event Match Quality <5.0 (means customer data matching is poor — check that email, phone, and address are being passed).
6C.02: FIRST CAMPAIGN BUILD — the 3-audience test structure
Campaign Level | Create Campaign: Name: "StrideHer — Prospecting — Launch" Objective: SALES (formerly "Conversions") Campaign Budget Optimization (CBO): ON Daily Budget: $15/day Bid Strategy: Lowest Cost (no cap) CBO means Meta automatically distributes the $15/day across the 3 ad sets below based on which performs best. You don't manually allocate budgets per ad set — the algorithm decides. | Ads Manager → Create → Sales → Name + Budget + CBO ON | SALES objective tells Meta: "find people who will PURCHASE, not just click or view." This activates Meta's purchase-prediction model — the most sophisticated audience-finding algorithm in advertising. Lowest Cost bid strategy: Meta spends your budget to get the most conversions possible at the lowest cost. Don't set a cost cap as a beginner — let the algorithm find the market price for conversions first. Add caps after you know your actual CPA. | $15/day total (CBO splits across 3 ad sets) | Week 1-2: Learning phase. 1-5 purchases per day. CPA: $8-$20 (wide range during learning). Week 3-4: Optimized. 2-5 purchases/day. CPA: $6-$12 (narrowing). | Choosing "Traffic" or "Engagement" objective instead of "Sales" (Meta optimizes for CLICKS, not purchases — you get 1,000 clicks and 0 sales). Setting a cost cap too low (Meta stops spending because it can't hit your target — you get 0 impressions). Not turning CBO on (manually splitting $5/$5/$5 prevents Meta from shifting budget to the winner).
Ad Set 1: INTEREST TARGETING (runners) | Name: "Interest — Women Runners" Targeting: • Location: United States • Age: 25-44 • Gender: Women • Interests: Running, Marathon, Half Marathon, Trail Running, Jogging • AND: interested in Running Gear, Fitness Accessories, or Active Lifestyle Placements: Advantage+ (let Meta decide — IG Reels and Feed will likely dominate) Optimization: Purchases | Campaign → Add Ad Set → targeting fields | Interest targeting tells Meta: "show ads to women aged 25-44 who are interested in running." This is the most straightforward audience — it's large (5-15M people in the US) and directly relevant. The AND condition (Running + Running Gear) narrows from "anyone who liked a running post once" to "people actively interested in running equipment." This improves quality significantly. | $5/day (CBO auto- allocated — this is approximate) | Audience size: 5-15M people. Expected CPM: $8-$15. Expected CTR: 1-2%. Expected CPA: $10-$18. | Targeting too narrow (<500K audience — not enough for Meta's algorithm to optimize). Targeting too broad (all women 18-65 with no interests — wastes budget on non-runners). Stacking too many interests (Running AND Marathon AND Trail Running AND Ultra Running = audience shrinks to near-zero because all interests must match).
Ad Set 2: LOOKALIKE AUDIENCE (customer-based) | Name: "Lookalike — Customers 1%" Source Audience: your "Purchasers" custom audience from P4C.02 (Meta Pixel) Lookalike %: 1% (the top 1% of US users most similar to your buyers) Location: United States Age/Gender: leave open (let the lookalike model decide — it already knows your buyers are women 25-39) NOTE: this ad set requires at least 100 pixel events (purchases or add-to-carts) to be effective. If you don't have 100 events yet: use email list upload instead (upload Klaviyo customer list as a custom audience → create 1% lookalike from that). | Campaign → Add Ad Set → Lookalike Audience (create in Audiences section first) | Lookalike audiences are Meta's MOST POWERFUL targeting tool. The algorithm analyzes your existing customers' demographics, interests, behavior, and purchase patterns — then finds the 1% of US users who most closely match. This audience typically outperforms interest targeting by 20-40% on CPA because it's based on ACTUAL buyer data, not assumed interests. The 1% lookalike is ~2.5M people in the US — large enough for Meta to optimize, narrow enough to be highly relevant. | $5/day (CBO auto) | Audience size: ~2.5M people. Expected CPA: $7-$14 (typically lower than interest targeting). | Creating a lookalike from <100 source events (algorithm doesn't have enough data to find patterns — wait until you have 100+ purchases or use email list upload). Using a 5-10% lookalike (too broad — start with 1%, expand to 2-3% only after 1% is saturated). Layering additional interests on top of a lookalike (defeats the purpose — let the lookalike model work alone).
Ad Set 3: BROAD TARGETING (Advantage+) | Name: "Broad — Advantage+ Audience" Targeting: • Location: United States • Age: 25-44 • Gender: Women • Interests: NONE (broad targeting — let Meta's algorithm find the buyers) OR use Advantage+ Shopping Campaign (ASC): Meta's fully automated campaign type. You provide: creative + product catalog + budget. Meta handles everything else. Advantage+ is Meta's newest and most AI-driven campaign type — it often outperforms manual targeting for e-commerce. | Campaign → Advantage+ Shopping Campaign (or manual broad ad set) | Broad targeting sounds counterintuitive: "how will Meta find runners if I don't tell it I want runners?" The answer: your CREATIVE does the targeting. A video of a woman running with a belt naturally attracts runners. Meta's algorithm learns who engages + converts from the creative signal, then finds more people like them. In 2025-2026, broad targeting with strong creative often OUTPERFORMS interest targeting because Meta's algorithm has more room to optimize (larger audience = more data = faster learning). | $5/day (CBO auto) | Audience size: 50-80M people (all US women 25-44). Expected CPA: $8-$16 (wide range — depends entirely on creative quality). | Panicking when broad targeting shows high CPA in Week 1 (the algorithm is learning — give it 7+ days). Using broad targeting with weak creative (if the ad doesn't clearly show a RUNNING BELT, broad targeting shows it to yoga people, hikers, and gym-goers). Broad targeting needs your BEST creative — the video that most clearly communicates "this is a running belt for women."

## 6C.03 Ad Creatives
P6C TASK 6C.03: 5 AD CREATIVE VARIATIONS — THE #1 LEVER IN META ADVERTISING
Creative > Targeting. A great ad with broad targeting outperforms a mediocre ad with perfect targeting. Test 5 variations to find your winner.
Ad # | Format | Creative Description | Primary Text (above the fold) | Headline (below media) | Buyer Psychology | Expected Performance
5 AD VARIATIONS — assign all 5 to each ad set. Meta rotates them and shows the best performer more often.
AD 1: ★ UGC VIDEO | Video (15-30 sec) Vertical 9:16 Source: P5A influencer content | A REAL RUNNER (from P5A influencer seeding) talking to camera or showing the belt during a run. Structure: 0-3 sec: Hook ("I finally found a running belt that doesn't bounce") 3-15 sec: Show the product in use (on-body, pockets, adjustment) 15-25 sec: Key benefit ("3 separate pockets — my phone never touches my gels") 25-30 sec: CTA ("Link in my bio — use code [X] for 15% off") This should look like a REAL person's social post, NOT a produced ad. Raw, authentic, phone-filmed. | "I tried every running belt on Amazon. They all bounced or didn't fit. Then I found StrideHer — it's the first belt actually designed for women's bodies. → Adjustable (no more size guessing) → 3 separate zippered pockets → Zero bounce — 200 silicone grip dots Free shipping. 30-day guarantee. 🏃‍♀️ Shop now — link below." | StrideHer — Finally, a running belt that fits. | SOCIAL PROOF + AUTHENTICITY. UGC ads work because they bypass "ad blindness" — the viewer's brain categorizes it as "person sharing their experience" not "brand selling me something." UGC consistently outperforms brand-produced creative by 30-50% on CPA across D2C categories. | ★ PREDICTED BEST PERFORMER. Expected CTR: 1.5-3%. Expected CPA: $6-$12. UGC video is the #1 ad format for D2C in 2025-2026.
AD 2: PRODUCT DEMO | Video (15-30 sec) Vertical 9:16 Source: P5B batch video #2 or #3 | Product demonstration video showing the belt's key features: 0-3 sec: Hook (belt on waist, start running — camera at waist level showing zero bounce) 3-10 sec: Open phone pocket, insert iPhone, zip closed 10-18 sec: Open valuables pocket, show keys + card + hidden mesh section 18-25 sec: Open gel pocket, insert 4 gels, magnetic snap closed 25-30 sec: Full body shot running with text overlay: "$34.99 — Free Shipping" Clean, well-lit, product-focused. This is the "rational" ad that shows WHAT the product does. | "Your phone. Your keys. Your gels. Three separate zippered pockets — nothing touches anything it shouldn't. StrideHer is the first running belt designed specifically for women's bodies. ✓ Adjustable fit: 25"-43" ✓ Zero bounce: silicone grip dots ✓ Fits iPhone 16 Pro Max with case $34.99 · Free US Shipping · 30-Day Guarantee" | StrideHer — 3 Pockets. Zero Bounce. | DEMONSTRATION. Shows the product WORKING. Appeals to the analytical buyer who needs to SEE the pockets, see the phone fit, see the bounce test before committing. Demo ads convert the "I need proof" segment that UGC alone doesn't convince. | Expected CTR: 1-2%. Expected CPA: $8-$15. Demo ads are the "steady performer" — rarely the #1 but consistently convert at acceptable CPA.
AD 3: TESTIMONIAL CARD | Image (static) 1:1 square or 4:5 Source: Canva design with product photo + quote overlay | A clean, brand-colored image with: • Product photo (Desert Rose belt on white, occupying 50% of frame) • Testimonial quote overlay: ★★★★★ "I forgot it was there by mile 3." — [TESTER NAME] • Brand logo (small, bottom corner) • Price: $34.99 with "Free Shipping" badge Design in Canva using StrideHer brand colors (Desert Rose background or Warm White with Desert Rose accents). | "★★★★★ "I forgot it was there by mile 3." Real review from a real runner. StrideHer is the first running belt designed for women — adjustable fit, 3 zippered pockets, zero bounce. Trusted by marathon runners. Loved by every body. $34.99 · Free Shipping · 30-Day Guarantee" | "I forgot it was there by mile 3." | SOCIAL PROOF (text-based). Testimonial cards work for the "I trust other customers more than the brand" buyer. The star rating + specific quote + real name creates trust that brand copy cannot. Static images are cheaper to produce (Canva, 10 min) and sometimes outperform video on CPM. | Expected CTR: 0.8-1.5%. Expected CPA: $10-$18. Static testimonial ads have lower CTR than video but lower CPM (cheaper to show) — CPA can be competitive.
AD 4: BEFORE / AFTER COMPARISON | Video or Carousel (2-4 slides) 1:1 or 4:5 Source: P5B batch video #19 or Canva carousel | Side-by-side comparison: "Generic belt" vs "StrideHer." VIDEO VERSION: split screen showing a tube belt bouncing/riding up on the left, StrideHer staying locked in place on the right. Both worn by the same runner. CAROUSEL VERSION: Slide 1: "Your current belt" — generic tube belt, flat, one pocket, bouncing GIF Slide 2: "StrideHer" — contoured, 3 pockets, zero bounce Slide 3: Feature comparison table (6 attributes with checkmarks) Slide 4: CTA "Switch to StrideHer — $34.99, Free Shipping" | "Still running with a belt that bounces? That has one pocket for everything? That comes in 12 sizes and none of them fit? StrideHer is different. ✓ Adjustable (not fixed sizing) ✓ 3 separate pockets (not one jumbled tube) ✓ Zero bounce (not 'stays mostly in place') ✓ Designed for women (not 'unisex') Made for your body. Finally. $34.99 · Free Shipping · 30-Day Guarantee" | Still running with a belt that bounces? | PROBLEM/SOLUTION. The comparison ad works because it makes the viewer's CURRENT belt feel inadequate. "Your belt bounces, has one pocket, and wasn't designed for you" → emotional discomfort → "here's the solution" → purchase. Comparison ads create a "switching" mindset — converting runners who ALREADY OWN a belt they're not happy with. | Expected CTR: 1-2%. Expected CPA: $8-$15. Comparison ads work best for runners who already own a competing belt (conversion from competitor, not from zero).
AD 5: LIFESTYLE ASPIRATION | Video (15-30 sec) Vertical 9:16 Source: P1D lifestyle shot or P5B batch video #12 | Cinematic lifestyle video: a woman running at sunrise/sunset wearing the Desert Rose belt. Beautiful scenery. Slow-motion moments. Inspiring music (trending sound or licensed track). Minimal product focus — this is FEELING, not features. 0-5 sec: wide shot, runner on a scenic path at golden hour 5-15 sec: medium shots — running form, belt visible but not the focus 15-25 sec: close-up of the belt, then back to wide shot 25-30 sec: text overlay: "StrideHer. Run Your Way." + "$34.99 Free Shipping" This ad makes the viewer FEEL something — the freedom of a morning run, the beauty of the sport, the empowerment of gear that works. | "Some mornings, the run is the best part of the day. StrideHer was designed for those mornings. For the miles that clear your head, the trails that test your limits, and the finish lines that prove what you're made of. The first running belt designed for women. $34.99 · Free Shipping · Run Your Way." | StrideHer. Run Your Way. | ASPIRATION + EMOTION. Lifestyle ads don't sell features — they sell IDENTITY. The viewer thinks: "I want to BE that runner." The belt is secondary to the feeling. This ad reaches the "emotional buyer" who decides based on how a brand makes them FEEL, not what the product DOES. It's the widest-appeal creative but can have higher CPA (less direct purchase intent). | Expected CTR: 0.8-1.5%. Expected CPA: $12-$20. Lifestyle ads typically have higher CPA than UGC/demo but drive higher brand recall and return visitor rate.

## 6C.04 Daily Optimization
P6C TASK 6C.04: DAILY AD OPTIMIZATION — THE 5-METRIC CHECK + KILL/SCALE FRAMEWORK
Check 5 metrics daily. Do NOTHING for 7 days (algorithm learning). After Day 7: kill underperformers, scale winners. This discipline separates profitable advertisers from money-burners.
Metric | Where to Find | Day 1-7 (Learning Phase) | Day 8-14 (Optimization) | Day 15+ (Scaling) | Kill Threshold (turn off) | Scale Threshold (increase budget)
5 DAILY METRICS — check every morning in Meta Ads Manager (10 minutes)
1. SPEND ($) | Ads Manager → Columns → Performance → "Amount Spent" | Budget should be spending fully ($15/day). If underspending (<$10): audience may be too narrow, bid too low, or ad was rejected. Do NOT increase budget during learning phase. $15/day is sufficient for the algorithm to learn. | If one ad set is spending 80%+ of budget: that's CBO working — it found the best audience. Let it run. Check if the high-spend ad set is also the best CPA ad set (it should be). | After 14 days of profitable performance (ROAS >2×): increase daily budget by 20% increments. $15 → $18 → $22 → $26. Never more than 20% increase per 3-day period (larger jumps reset the learning phase). | N/A (you control the budget) | Increase budget only when ROAS is consistently >2× for 5+ consecutive days.
2. CPA (Cost Per Acquisition) | Ads Manager → Columns → Performance → "Cost per Purchase" OR: Amount Spent ÷ Purchases | Day 1-3 CPA will be HIGH ($15-$30+). This is NORMAL. The algorithm is exploring, not optimizing. Day 4-7: CPA should start declining as the algorithm identifies high-converting users. DO NOT panic at Day 2 CPA. DO NOT turn off ads because CPA is $25 on Day 2. | Day 8-14 target CPA: $8-$12. Compare CPA by ad set: • Interest targeting CPA: $___ • Lookalike CPA: $___ • Broad CPA: $___ The ad set with the lowest CPA is your winner. The ad set with the highest CPA (if >2× the lowest) is a candidate for pausing. | Ongoing target CPA: <$10 (per P0E model: $10 CAC allows profitable unit economics at $34.99 retail). If CPA consistently <$8: SCALE aggressively (increase budget 20% every 3 days). If CPA $8-$12: maintain. If CPA >$12: optimize creative or audience. | 🔴 KILL ad set if: CPA >$15 after 14 days of data (200+ impressions) AND no improvement trend (CPA flat or rising). Don't kill before Day 8. | 🟢 SCALE if: CPA <$8 for 5+ consecutive days. Increase budget 20% every 3 days until CPA rises above $10, then hold.
3. ROAS (Return on Ad Spend) | Ads Manager → Columns → Performance → "Purchase ROAS" OR: Revenue from ads ÷ Ad spend | ROAS during learning phase is unreliable — too few conversions for meaningful calculation. If you have 1 purchase from $30 spent: ROAS = $35 ÷ $30 = 1.17×. This doesn't mean your ROAS is 1.17× — it means you don't have enough data yet. Wait for 10+ purchases before evaluating ROAS. | Day 8-14 target ROAS: 2.0-3.0×. 2.0× means: every $1 spent returns $2 in revenue. At $34.99 product price with $6 COGS: $2 revenue per $1 spend = $0.50 profit per $1 spend (before other costs). Marginally profitable. 3.0× means: $1 → $3 revenue. Clearly profitable. | Ongoing target: 3.0×+. 3.0× ROAS = $10-$12 CPA on a $34.99 product. Below 2.0×: ads are break-even or losing money. Above 4.0×: ads are highly profitable — scale budget immediately. | 🔴 KILL if: ROAS <1.5× after 14 days with 10+ purchases. Below 1.5× means you're losing money on every ad dollar. | 🟢 SCALE if: ROAS >3.5× for 7+ consecutive days. This means every $1 returns $3.50+ — rare and excellent. Scale fast before competition increases.
4. CTR (Click-Through Rate) | Ads Manager → Columns → Performance → "CTR (link click-through rate)" | Day 1-7: CTR reveals which AD CREATIVE is getting attention. Even during learning phase, CTR data is useful: if Ad 1 (UGC) has 2.5% CTR and Ad 5 (lifestyle) has 0.5% CTR, the audience clearly prefers UGC — regardless of whether purchases have happened yet. Use CTR to evaluate CREATIVE quality. Use CPA to evaluate AUDIENCE quality. | Day 8-14: CTR should stabilize. Benchmarks for Meta D2C ads: • Video ads: 1-3% CTR = good • Image ads: 0.8-1.5% CTR = good • Below 0.8%: creative isn't stopping the scroll • Above 3%: exceptional creative — test more variations of this format | Ongoing: monitor for "creative fatigue" — CTR declining week over week means the same people are seeing your ad repeatedly and ignoring it. When CTR drops 30%+ from peak: refresh the creative (new video, new image, new copy). | No creative should run with CTR <0.5% after 1,000 impressions. CTR <0.5% = the ad isn't working. Pause and replace with a new creative. | CTR >2% on video or >1.5% on static = strong creative. Duplicate this ad with minor variations (different headline, different opening frame) to test if it can perform even better.
5. FREQUENCY | Ads Manager → Columns → Delivery → "Frequency" Frequency = average number of times each person has seen your ad. | Day 1-7: frequency should be 1.0-1.5 (each person has seen the ad once or twice). This is healthy exploration. Frequency above 2.0 in Week 1 means your audience is too small — Meta is showing the same ad to the same people multiple times. | Day 8-14: frequency 1.5-2.5 is acceptable. Above 3.0: audience is saturated. People have seen your ad 3+ times without buying. Continuing to show it = annoyance + wasted spend. When frequency >3.0: either expand the audience (add interests, increase lookalike %) or refresh creative. | Ongoing: monitor frequency weekly. It naturally increases over time as Meta exhausts the best prospects in your audience. Sustainable frequency: <3.0 for prospecting, <5.0 for retargeting (retargeting audiences expect to see your brand more often). | Frequency >4.0 on any prospecting ad set = pause. The audience is exhausted. Either: (a) expand audience (b) refresh creative (c) pause for 2 weeks and restart. | N/A — frequency is a health metric, not a performance metric. You don't "scale" frequency. You manage it.
OPTIMIZATION LOG TEMPLATE — fill daily for 14 days (then weekly after)
LOG TEMPLATE | Daily columns: • Date • Total Spend • Purchases (#) • CPA ($) • ROAS (×) • Best Ad Set • Best Creative • CTR (top ad) • Frequency (avg) • Action Taken • Notes Keep in a Google Sheet. Review weekly for trends. | DAYS 1-7: action = NONE. Log data but do not make changes. Write in the "Action" column: "Learning phase — no changes." The hardest part of Meta advertising is DOING NOTHING for 7 days while the algorithm learns. Every change you make resets the learning phase. | DAY 8: first optimization. Actions: 1. Identify the lowest-CPA ad set → this is your winner 2. Identify the highest-CPA ad set → if CPA is 2×+ the winner, pause it 3. Identify the best-CTR creative → this is your winning creative 4. Identify the worst-CTR creative → if CTR is <0.5%, pause it 5. Reallocate: paused ad set's budget flows to winners via CBO automatically. | DAY 15+: optimize weekly (not daily). Daily optimization becomes "data noise" after the learning phase — weekly gives cleaner signals. Weekly actions: • Check ROAS: still >2×? Continue. • Check frequency: still <3? Continue. • Check CTR: declining? Refresh creative. • Check CPA trend: rising? Investigate. • Budget adjustment: if ROAS >3× for 7 days, increase 20%.

## 6C.05 Retargeting
P6C TASK 6C.05: RETARGETING CAMPAIGNS — CONVERT "ALMOST BUYERS" AT 3-8× COLD AD CONVERSION RATES
Retargeting shows ads to people who already visited your site or engaged with your brand. They KNOW you. They just need one more nudge. Budget: $3-$5/day. ROAS: 5-10×.
Audience | Size | Ad Creative (different from cold) | Primary Text | Budget | Expected ROAS | Frequency Cap
3 RETARGETING AUDIENCES — create as a SEPARATE campaign from prospecting. Name: "StrideHer — Retargeting"
AUDIENCE 1: Site Visitors (didn't purchase) Last 14 days | 200-2,000 people (depends on traffic volume) | REMINDER creative — NOT the same ads they already saw. Best format: testimonial image or "still thinking?" video. The ad should acknowledge they visited: "Saw something you liked?" or "Still thinking about it?" — this personalization increases CTR 2× vs generic ads. Include: product image, price, free shipping badge, and a mild urgency element ("selling fast" or "free shipping ends Sunday"). | "Still thinking about StrideHer? The running belt you checked out is still available — but at our current pace, your color might not be for long. → 3 separate zippered pockets → Zero bounce — tested over 500 miles → Fits iPhone 16 Pro Max with case $34.99 · Free US Shipping · 30-Day Guarantee 🏃‍♀️ Ready when you are." | $1-$2/day (retargeting audiences are small — $1-$2 is enough to reach everyone 1-2× per week) | ROAS: 5-10× Site visitor retargeting typically converts at 3-5× the rate of cold prospecting. At $1-$2/day: 1-3 additional sales/week. CPA: $3-$8. | Max 3× per week. More than 3× = annoying. Retargeting should feel like a gentle reminder, not stalking. Set in ad set: Frequency Cap → "Show to each person no more than 3 times per 7 days."
AUDIENCE 2: Cart Abandoners Last 7 days | 50-500 people (smaller but highest intent) | URGENCY creative — these people were ONE CLICK from buying. Best format: dynamic product ad (shows the EXACT product they added to cart) + a discount incentive. Meta's Dynamic Product Ads (DPA) auto-populate with the product the viewer carted. Set up via Shopify's product catalog connected to Meta. Alternative (if DPA not set up): static image of the belt with "You left something behind" headline. | "You were so close! Your StrideHer belt is still in your cart — and we'd hate for you to miss out. Here's a little extra motivation: Use code SAVE10 for 10% off → $34.99 → $31.49 ✓ Free US shipping ✓ 30-day guarantee ✓ Free size exchanges Complete your order before your color sells out." | $1-$2/day | ROAS: 8-15× Cart abandoner retargeting is the HIGHEST-ROI ad segment. These people intended to buy. A small nudge converts 10-20% of them. CPA: $2-$5. | Max 5× per week. Cart abandoners can tolerate slightly higher frequency because they demonstrated HIGH intent. But cap at 5 — after 5 reminders, they've decided not to buy.
AUDIENCE 3: Email Subscribers (non-purchasers) Custom audience from Klaviyo list | 100-1,000 people (from newsletter + waitlist who haven't bought) | SOCIAL PROOF creative — these people know the brand (they signed up) but haven't converted. They need TRUST, not awareness. Best format: testimonial video or customer review carousel. Show them: real customers loving the product. The testimonial answers their unspoken objection: "Is it really as good as they say?" | "Hundreds of runners have tried StrideHer. Here's what they're saying: ★★★★★ "I forgot it was there by mile 3." ★★★★★ "Finally a belt that fits my hips." ★★★★★ "The hidden period pocket? Game changer." You signed up because you were curious. Now you can see why runners love it. $34.99 · Free Shipping · 30-Day Guarantee Your WELCOME10 code is still waiting — 10% off your first order." | $1/day | ROAS: 4-8× Email subscribers who haven't bought are "warm leads" who need social proof to convert. Retargeting with reviews/testimonials converts 5-10% of this audience over 30 days. | Max 2× per week. This audience is receiving EMAILS too (P4B welcome flow). Don't overwhelm them with ads ON TOP of emails. 2× per week is sufficient — they're getting 4-6 brand touchpoints per week between email + ads combined.
RETARGETING BUDGET ALLOCATION — 20-30% of total ad budget goes to retargeting
TOTAL RETARGETING BUDGET | — | At $15/day total ad budget: $3-$5/day retargeting (20-30%) $10-$12/day prospecting (70-80%) Retargeting is more EFFICIENT (higher ROAS) but has LIMITED audience (only people who already visited/engaged). You can't scale retargeting — it scales only as fast as your prospecting drives new visitors. The ideal flywheel: prospecting drives new visitors → retargeting converts the "almost buyers" → new customers feed the lookalike audience → prospecting improves → cycle repeats. | Monitor: is retargeting spend actually delivering? If the retargeting campaign only spends $0.50/day (audience too small): the audience needs more visitors. Scale prospecting to feed the retargeting funnel. If retargeting spends $5/day easily with 8×+ ROAS: your site traffic is healthy and the retargeting funnel is working. Consider increasing retargeting budget to $7-$10/day. | $3-$5/day (retargeting) $10-$12/day (prospecting) | Combined ROAS (prospecting + retargeting): 3-4× blended. Prospecting alone: 2-3× ROAS. Retargeting alone: 5-10× ROAS. Blended is what matters for overall profitability.

## 6C FOUNDER ACTIONS
P6C META ADS — FOUNDER ACTION CHECKLIST
Start ads in Week 15 (after 2+ weeks of organic sales data). Total Month 1 ad budget: $300-$450. Time: 15-20 min/day for monitoring.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 15: ADS MANAGER SETUP + CAMPAIGN BUILD
🔴 #1 | Verify Meta Ads Manager setup and Conversions API | 30 min | $0 | 1. Verify Business Manager exists (from P4C.02 setup) 2. Verify ad account is created with payment method 3. Set monthly spending limit: $500 (Settings → Payment Settings → Account Spending Limit) 4. Verify Conversions API active: Events Manager → Data Sources → CAPI status = Active 5. Verify pixel events firing: Events Manager → Test Events → browse store → PageView + ViewContent appear 6. Verify domain verified: Business Settings → Brand Safety → Domains → strideher.com = Verified All 6 must pass before creating any campaign.
🔴 #2 | Build first prospecting campaign with 3 ad sets + 5 creatives | 1-2 hrs | $0 | 1. Ads Manager → Create → Sales objective → CBO ON → $15/day 2. Ad Set 1 (Interest): women 25-44, US, interests: Running + Running Gear → Advantage+ placements → optimize for Purchases 3. Ad Set 2 (Lookalike): 1% lookalike from Purchasers custom audience (or email list upload if <100 pixel events) 4. Ad Set 3 (Broad): women 25-44, US, NO interest targeting → Advantage+ placements 5. For EACH ad set: add all 5 ad creatives from Sheet 6C.03 6. Review everything → Publish 7. Monitor: Ads Manager should show "Learning" status. DO NOT TOUCH for 7 days.
🔴 #3 | Build retargeting campaign with 3 audiences | 1 hr | $0 | 1. Create new campaign: "StrideHer — Retargeting" → Sales objective → $5/day 2. Ad Set 1: Site Visitors 14d (exclude purchasers) → "still thinking?" creative → frequency cap 3/week 3. Ad Set 2: Cart Abandoners 7d → dynamic product ad or "you left something behind" creative → frequency cap 5/week 4. Ad Set 3: Email Subscribers non-purchasers (upload Klaviyo list as custom audience) → testimonial creative → frequency cap 2/week 5. Publish. Monitor alongside prospecting campaign.
WEEKS 15-16: LEARNING PHASE (do NOTHING for 7 days)
🟡 #4 | Daily 15-min monitoring: log 5 metrics, resist urge to change anything | 15 min/day × 14 days | $15/day = $210 for 14 days | DAILY (15 minutes, every morning): 1. Open Ads Manager → check: total spend, purchases, CPA, ROAS, CTR 2. Log in your optimization spreadsheet (Sheet 6C.04 template) 3. Note: best ad set, best creative, frequency 4. Days 1-7: write "Learning — no changes" in Action column 5. Day 8: FIRST optimization — pause worst ad set (if CPA >2× best), pause worst creative (if CTR <0.5%) 6. Days 8-14: optimize every 3 days (not daily — too reactive) 7. Day 15+: shift to weekly optimization THE GOLDEN RULE: do not make more than 1 change per 3-day period. Each change resets learning. Multiple changes per day = constant reset = algorithm never optimizes.
WEEK 17+: SCALING + ONGOING MANAGEMENT
🟢 #5 | Weekly optimization: scale winners, kill losers, refresh creative | 30 min/week | Variable (increase budget as ROAS permits) | WEEKLY (every Monday): 1. Check 14-day ROAS: >3× → increase budget 20%. 2-3× → maintain. <2× → diagnose (creative fatigue? audience exhaustion?). 2. Check frequency: any ad set >3.0 → refresh creative or pause 3. Check CTR trend: declining week over week → creative fatigue → create 2 new ad variations 4. Check retargeting: audiences large enough to spend? If retargeting underspending → need more prospecting traffic 5. Test 1 new creative every 2 weeks to prevent fatigue 6. Monthly: review total ad spend vs total ad-attributed revenue. Target blended ROAS: 3×+. Total monthly spend should not exceed 25% of monthly revenue.