## P6D EXEC SUMMARY
P6D PAID ADVERTISING — GOOGLE ADS (SHOPPING + SEARCH + DISPLAY)
5 Tasks ¦ Weeks 16-20+ ¦ Budget: $5-$15/day ($150-$450/month) ¦ Google captures buyers SEARCHING for a running belt right now.
Task ID | Task | KPI | Deliverable | Status | Why Google Ads | Budget
6D.01 | Set up Google Ads account + Shopping feed via Shopify Google channel | Account live, feed synced | Complete Google Ads setup: account creation linked to GA4, Merchant Center product feed auto-synced from Shopify via Google & YouTube app, conversion tracking verified. The Shopify integration auto-generates the product feed — no manual CSV. Merchant Center verifies: product title, description, price, images, availability for all 8 variants. | COMPLETE ✓ | Google captures buyers ACTIVELY SEARCHING "running belt for women." These are the highest-intent clicks online — they typed a purchase query and are comparing options. Google Shopping puts StrideHer's product photo + price at the TOP of search results, before organic results. | $0 (setup)
6D.02 | Create Google Shopping campaign: Performance Max, $5-$10/day | PMax campaign live | Complete Performance Max campaign: Sales objective, $8/day budget, Maximize Conversions bidding, asset group with 5 product images + 15 headlines + 5 long headlines + 5 descriptions + logo. PMax automatically places ads across Google Shopping, Search, YouTube, Gmail, Display, and Discover. Google's AI optimizes placement + bid + creative combination in real-time. | COMPLETE ✓ | Shopping ads show product IMAGE + price + reviews at the TOP of Google search results — 30% higher CTR than text ads because the photo + price pre-qualifies clicks. A searcher sees StrideHer at $34.99 BEFORE seeing any website. PMax handles the complexity; you provide great assets. | $8/day = $240/mo
6D.03 | Create Google Search campaign: 10 exact-match keywords for purchase intent | Search campaign live, 10 keywords | Complete Search campaign: 10 exact-match keywords from P4D.01 (running belt for women 2,400/mo, adjustable running belt 880/mo, running belt that doesn't bounce 720/mo, etc.), 4 ad groups, 3 Responsive Search Ads with 15 headlines + 4 descriptions each, negative keyword list (50+ terms), and match type strategy. Captures text-based searchers who scroll past Shopping results. | COMPLETE ✓ | Search ads capture: searchers who prefer text links over image ads, long-tail queries Shopping doesn't match, and branded searches. At $3-$5/day, Google Search is the PRECISION channel — every click from someone who typed "running belt for women" has 5-10% conversion probability vs 1-2% from social media clicks. | $3-$5/day = $90-$150/mo
6D.04 | Set up Google Display retargeting: banner ads across 2M+ websites | Display RT campaign live | Complete GDN retargeting: audience = site visitors 30d minus purchasers (from GA4), Responsive Display Ads (auto-generated from images + headlines), frequency cap 3/day + 10/week, mobile app + sensitive content exclusions. After someone visits strideher.com, they see banner ads on news sites, blogs, apps, and YouTube for up to 30 days. | COMPLETE ✓ | GDN retargeting is the cheapest retargeting channel ($0.001-$0.005 per impression). The "mere exposure effect" — seeing StrideHer repeatedly across the web — increases purchase likelihood 20-40% over 7-14 days. At $2/day, you reach 500-2,000 past visitors daily across 2M+ websites. Converts 2-5× cold traffic rates. | $2/day = $60/mo
6D.05 | Monthly budget review: allocate $500-$800/month across Meta + Google based on ROAS | Monthly allocation framework | Complete cross-channel budget allocation: starting split (Meta $390 + Google $390 = $780/month), monthly ROAS comparison across 5 channels (Meta prospecting/retargeting, Google PMax/Search/Display), reallocation rule (shift 20% from lowest to highest ROAS channel), scaling rule (all channels >3× → increase total 20%), and the 25% cap (ad spend never exceeds 25% of monthly revenue). | COMPLETE ✓ | Without monthly review: you spend fixed amounts regardless of performance = wasted budget. With review: if Meta delivers 4× ROAS and Google delivers 2×, shift $80 from Google to Meta = $160 more revenue from same total spend. Dynamic allocation is the #1 lever for scaling ad profitability. | $500-$800/mo total (Meta + Google combined)

## 6D.01-03 Shopping + Search
P6D: GOOGLE ADS — SHOPPING CAMPAIGN + SEARCH CAMPAIGN (10 KEYWORDS + AD COPY)
PMax Shopping: $8/day, auto-optimized across all Google surfaces. Search: $3-5/day, 10 exact-match keywords targeting buyers who are searching RIGHT NOW.
# | Keyword (exact match) | Monthly Volume | Est. CPC | Intent | Ad Group | Ad Copy Headline | Ad Copy Description
1 | running belt for women | 2,400 | $0.80-$1.50 | ★★★★★ Buy | AG1: Women's Belt | Running Belt for Women ¦ Adjustable Fit | The first running belt designed for women. 3 zippered pockets, zero bounce. $34.99 free shipping.
2 | best running belt for women | 1,300 | $0.60-$1.20 | ★★★★★ Buy | AG1 | Best Running Belt for Women 2026 | Tested & compared. Adjustable, 3 pockets, silicone grip. 30-day guarantee. Shop StrideHer.
3 | adjustable running belt | 880 | $0.50-$1.00 | ★★★★ Buy | AG1 | Adjustable Running Belt ¦ 25"-43" | Stop guessing sizes. StrideHer adjusts from 25" to 43". 3 separate pockets. Free shipping.
4 | womens running belt with pockets | 590 | $0.40-$0.80 | ★★★★★ Buy | AG1 | Women's Belt with 3 Zippered Pockets | Phone, keys, gels — each in its own pocket. Designed for women runners. $34.99.
5 | running belt that doesn't bounce | 720 | $0.50-$1.00 | ★★★★★ Buy | AG2: Pain Point | Zero Bounce Running Belt ¦ Silicone Grip | 200 silicone dots eliminate bounce. Tested over 500+ miles. 30-day money-back guarantee.
6 | no bounce running belt | 320 | $0.40-$0.80 | ★★★★★ Buy | AG2 | No Bounce Running Belt — Proven | Silicone grip technology keeps it locked in place. From mile 1 to mile 26.2. Free shipping.
7 | running belt for phone | 1,100 | $0.50-$1.00 | ★★★★ Buy | AG3: Phone | Running Belt for Phone ¦ Fits Pro Max | Fits iPhone 16 Pro Max with case. YKK waterproof zipper. Separate phone pocket. $34.99.
8 | running belt iPhone 16 Pro Max | 140 | $0.30-$0.60 | ★★★★★ Buy | AG3 | Running Belt — Fits iPhone 16 Pro Max | Zippered phone pocket sized for the biggest phones + cases. Zero bounce. Free US shipping.
9 | StrideHer running belt | 0 (growing) | $0.10-$0.30 | ★★★★★ Brand | AG4: Brand | StrideHer® Official ¦ Running Belt | The original women's running belt. Adjustable, 3 pockets, zero bounce. Shop the official store.
10 | running belt for half marathon | 190 | $0.40-$0.80 | ★★★★ Buy | AG1 | Running Belt for Half Marathon | Designed for distance. Carries phone, gels, keys in 3 separate pockets. 30-day guarantee.
NEGATIVE KEYWORDS — add to campaign level to block irrelevant searches and prevent wasted spend
free, DIY, homemade, cheap, wholesale, bulk, used, repair, fix, how to make, pattern, sewing, tutorial, Amazon, eBay, Walmart, Alibaba, hydration belt, water bottle belt, fanny pack pattern, belt bag luxury, running belt review (you want organic for this, not paid), running belt comparison (same — organic blog content handles this)
PERFORMANCE MAX ASSET GROUP — provide these to Google's AI for automatic ad assembly across Shopping, Search, YouTube, Gmail, Display
IMAGES (5+) | Hero on white ¦ On-body running ¦ 3-pocket flat lay ¦ All 4 colors ¦ Phone fit close-up ¦ Detail (zipper/buckle) — from P1D. Min 1200x628 landscape + 1200x1200 square.
HEADLINES (15, max 30 chars) | Running Belt for Women ¦ Zero Bounce Belt ¦ 3 Zippered Pockets ¦ Adjustable 25"-43" ¦ Free US Shipping ¦ $34.99 Shop Now ¦ Designed for Women ¦ 30-Day Guarantee ¦ Fits iPhone Pro Max ¦ StrideHer Official ¦ Silicone Grip Tech ¦ Women's Running Gear ¦ Contoured Fit ¦ YKK Waterproof ¦ Free Size Exchanges
LONG HEADLINES (5, max 90 chars) | The First Running Belt Designed Specifically for Women's Bodies ¦ 3 Zippered Pockets, Zero Bounce, Adjustable Fit — $34.99 Free Shipping ¦ Stop Guessing Your Size — StrideHer Adjusts from 25" to 43" ¦ 200 Silicone Grip Dots Keep It Locked from Mile 1 to Mile 26.2 ¦ Phone, Keys, Gels — Each in Its Own Pocket. Finally.
DESCRIPTIONS (5, max 90 chars) | Adjustable running belt with 3 separate zippered pockets. Free US shipping. ¦ Women's running belt with zero bounce silicone grip. 30-day guarantee. ¦ Fits iPhone 16 Pro Max with case. YKK waterproof zippers. From $34.99. ¦ Contoured design follows women's hip geometry. No more "unisex" belts. ¦ Trusted by marathon runners. Free size exchanges. Ships in 24 hours.

## 6D.04-05 Retargeting + Budget
P6D: GOOGLE DISPLAY RETARGETING + MONTHLY CROSS-CHANNEL BUDGET ALLOCATION
GDN retargeting: $2/day, cheapest impression channel. Budget framework: allocate $500-$800/month across Meta + Google based on ROAS data, not guesswork.
Element | Configuration | Audience | Creative | Budget | Expected ROAS | Key Rules
GDN Retargeting Campaign | Display campaign: "StrideHer — Display Retargeting" Goal: Sales ¦ Budget: $2/day ¦ Bid: Maximize Conversions Frequency cap: 3/day, 10/week Exclusions: mobile apps, sensitive content, MFA sites Google auto-generates responsive display ads in dozens of banner sizes from your provided images + headlines. | All site visitors (last 30 days) minus Purchasers. Auto-populated from GA4 audience imported to Google Ads. Size: 400-1,600 people (depends on traffic). | Responsive Display Ad: 5 images: hero, on-body, flat lay (landscape 1200×628 + square 1200×1200) 5 headlines (30 chars): StrideHer Running Belt ¦ Still Thinking About It? ¦ Zero Bounce. 3 Pockets. ¦ Free Shipping $34.99 ¦ Designed for Women 5 descriptions (90 chars): The running belt you looked at is still available. Free shipping + 30-day guarantee. ¦ 3 separate pockets, zero bounce, adjustable fit. Ready when you are. | $2/day = $60/month Always-on campaign. Cheapest retargeting channel available. | 3-8× CPA: $5-$15 1-3 conversions per week. Display RT is steady, not explosive — it recovers 5-10% of lost visitors at very low cost. | Exclude mobile apps (accidental clicks waste 30-50% of display budget). Review placement report monthly — add low-quality sites to exclusion list. Frequency cap prevents "ad stalking" feeling. If frequency exceeds 3/day: audience too small, need more prospecting traffic.
Monthly Budget Allocation Framework | STARTING MONTHLY ALLOCATION: Meta Prospecting: $300 ($10/day) Meta Retargeting: $90 ($3/day) Google PMax Shopping: $240 ($8/day) Google Search: $90-$150 ($3-$5/day) Google Display RT: $60 ($2/day) TOTAL: $780/month (~$26/day) This is the STARTING allocation. After Month 1: reallocate based on ROAS data using the rules at right. | All audiences across both platforms. | Cross-pollinate winning creative: Best UGC video on Meta → test as YouTube ad in PMax. Best Search headline → test as Meta ad headline. Best Shopping image → test as Meta carousel. Winning creative transcends platforms. | $500-$800/mo total. Month 1-2: $300-$500 (learning). Month 3+: $500-$800 (scaling). NEVER exceed 25% of monthly revenue. | Target blended ROAS: 3×+ At 3× ROAS: $500 spend → $1,500 revenue → $1,500 - $500 - $257 COGS = $743 net. Month 1: 2× (learning). Month 2: 2.5-3×. Month 3+: 3-4×. | MONTHLY REVIEW (1st of each month): 1. Pull ROAS per channel (5 channels) 2. REALLOCATION: shift 20% from lowest-ROAS to highest-ROAS channel 3. SCALING: if ALL channels >3× → increase total budget 20% 4. PAUSING: if any channel <1.5× after 30 days → pause entirely 5. CAP: total spend ≤25% of monthly revenue Example: Meta prospecting = 4× ROAS, Google PMax = 1.5× → shift $48 from PMax to Meta. If PMax stays <1.5× next month: pause. Do NOT throw more money at <2× ROAS channels — fix the funnel first.

## 6D FOUNDER ACTIONS
P6D GOOGLE ADS — FOUNDER ACTION CHECKLIST
Start Google Ads 1-2 weeks after Meta Ads (stagger learning curves). Month 1 Google budget: $150-$400. Time: 15 min/day monitoring.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 16-17: GOOGLE ADS SETUP
🔴 #1 | Verify Google Ads account + Merchant Center product feed | 30 min | $0 | 1. Confirm Google Ads linked to GA4 (Tools → Linked Accounts) 2. Confirm Merchant Center: all 8 variants "Active" (fix any "Disapproved") 3. Confirm GA4 audiences imported (All Visitors, Cart Abandoners, Purchasers) 4. Set account daily budget limit: $25/day
🔴 #2 | Create Performance Max Shopping campaign | 45 min | $8/day | 1. Google Ads → New Campaign → Sales → Performance Max 2. Budget: $8/day. Bid: Maximize Conversions (no target ROAS for 2 weeks) 3. Upload asset group: 5 images, 15 headlines, 5 long headlines, 5 descriptions, logo (from Sheet 6D.01-03) 4. Link Merchant Center feed. Set audience signal: women 25-44, Running interests. 5. Publish. Do NOT touch for 14 days.
🔴 #3 | Create Google Search campaign with 10 keywords | 45 min | $3-$5/day | 1. New Campaign → Sales → Search. Budget: $5/day. 2. Create 4 ad groups: AG1 (women's belt), AG2 (pain point), AG3 (phone), AG4 (brand) 3. Add 10 exact-match keywords from Sheet 6D.01-03 4. Add negative keyword list (50+ terms) 5. Create 1 Responsive Search Ad per ad group (15 headlines + 4 descriptions) 6. Pin "Running Belt for Women" to position 1. Publish.
🟡 #4 | Create Google Display retargeting campaign | 30 min | $2/day | 1. New Campaign → Sales → Display. Budget: $2/day. 2. Audience: GA4 "All Visitors" minus "Purchasers" 3. Frequency cap: 3/day, 10/week 4. Upload Responsive Display Ad: 5 images + 5 headlines + 5 descriptions 5. Exclude: mobile apps + sensitive content. Publish.
ONGOING: MONITORING + MONTHLY REVIEW
🟡 #5 | Daily monitoring (15 min) + monthly cross-channel budget reallocation | 15 min/day + 1 hr/month | Variable | DAILY: check spend, conversions, CPA, ROAS per campaign. Log alongside Meta data. WEEKLY: PMax asset performance, Search terms report (add negatives), Display placement report. MONTHLY: pull ROAS for all 5 channels → reallocate 20% from lowest to highest → scale if all >3× → pause if any <1.5× → verify total ≤25% of revenue.