## P7B EXEC SUMMARY
P7B FINANCIAL PLANNING & FORECASTING — EXECUTIVE SUMMARY
5 Tasks ¦ Week 1-2 ¦ Cost: $0 ¦ Know your numbers. Know when you break even. Know when you run out of cash. Know when to reorder.
Task ID | Task | KPI | Deliverable | Status | Why This Matters | Timeline
7B.01 | Build detailed unit economics model: COGS breakdown, contribution margin, break-even | Unit economics documented | Complete per-unit P&L: every cost that touches a single belt from factory to customer doorstep, contribution margin per unit, and break-even unit volume. At $34.99 retail with ~$14.50 all-in cost per unit: contribution margin is ~$20.49/unit (58.5%). Break-even at ~$8,000 in fixed costs/month = ~390 units/month. This model tells you: "every belt you sell earns $20.49 to cover your fixed costs and profit." | COMPLETE ✓ | Unit economics is the TRUTH of any product business. A brand can look successful (100 orders/month!) but be losing money on every sale if the unit economics are negative. Your unit economics model answers: "Am I making or losing money on each individual sale?" If the answer is "losing": no amount of marketing fixes it. If "making": scale confidently. | Day 1: build the model. Update monthly with actual costs (estimates → actuals as data comes in).
7B.02 | Build 12-month cash flow forecast: weekly for months 1-3, monthly for months 4-12 | Cash flow forecast complete | Complete 12-month cash flow projection: revenue (conservative/moderate/optimistic scenarios), all expenses by category (from P7A.04 chart of accounts), cash position by week/month, and the CRITICAL metric: "when does cash hit $0?" If the model shows cash hitting $0 in Month 4: you know in Month 1 that you need to either cut costs or generate revenue faster. No surprises. | COMPLETE ✓ | Cash flow ≠ profit. A business can be PROFITABLE on paper but run out of cash because: inventory is paid upfront (Month 1) but revenue comes gradually (Months 2-6). The $10K budget covers: $3,600 inventory + $500 Shopify/tools + $1,500 ads + $500 shipping + $400 packaging + $500 samples/events = $7,000 committed. That leaves $3,000 cash reserve — which must last until revenue exceeds expenses. The cash flow forecast tells you exactly when that crossover happens. | Day 1-2: build forecast. Update weekly for months 1-3. Update monthly for months 4-12.
7B.03 | Allocate $10K budget across all projects with 25% contingency reserve | Budget allocation documented | Complete $10K budget allocation: fixed commitments ($7,500 allocated across inventory, marketing, tools, shipping, packaging, samples), 25% contingency reserve ($2,500 held for unexpected costs), and spend-trigger rules ("don't spend X until Y happens"). The contingency reserve is NON-NEGOTIABLE — unexpected costs ALWAYS appear (customs fees higher than quoted, a packaging reprint, an emergency reorder). | COMPLETE ✓ | $10K feels like a lot until you start spending. Without a budget: you spend $4K on inventory, $2K on ads in Month 1, $1.5K on tools and subscriptions, $1K on events and samples — and discover in Month 2 that you have $1.5K left with no contingency. A pre-allocated budget with a 25% contingency means you ALWAYS have a safety net. | Day 1: allocate budget. Track weekly: actual vs budget by category.
7B.04 | Set monthly financial review cadence: P&L, cash position, CAC, inventory value | Monthly financial review ritual operational | Complete monthly financial review protocol: 5 financial reports to pull (P&L, cash flow, unit economics actual vs model, CAC by channel, inventory value + turnover rate), how to interpret each, and escalation triggers (which numbers require immediate action vs monitoring). This is the financial equivalent of the P6E.01 weekly KPI review — but focused on MONEY, not marketing. | COMPLETE ✓ | Without monthly financial reviews: you discover you're unprofitable in Month 6 (when the bank account hits $0). With monthly reviews: you spot the trend in Month 2 (CAC rising, margins shrinking) and course-correct before it becomes a crisis. The monthly cadence catches problems 4 months earlier than "I'll figure out finances later." | Start: end of Month 1. Continue: last day of every month. FOREVER.
7B.05 | Define financial milestones: breakeven date, first profitable month, quarterly targets | Milestones documented with target dates | Complete financial milestone framework: 8 milestones from "first sale" to "reinvestable profit," each with a target date, the metric to track, and what achieving (or missing) the milestone means for the business. These milestones transform abstract financial goals into concrete checkpoints with consequences. | COMPLETE ✓ | Milestones create URGENCY and ACCOUNTABILITY. "I want to be profitable" is vague. "I need to hit $3,000/month revenue by Month 3 to cover fixed costs and break even" is specific, measurable, and motivating. Missing a milestone by 30% is a signal to diagnose and fix. Hitting a milestone early is a signal to scale. Without milestones: you drift. With them: you drive. | Day 2: set milestones. Review monthly: on track? Behind? Ahead?

## 7B.01 Unit Economics
P7B TASK 7B.01: UNIT ECONOMICS — EVERY COST THAT TOUCHES A SINGLE BELT, FROM FACTORY TO DOORSTEP
Contribution margin = $20.49/unit (58.5%). Every belt sold covers $20.49 of fixed costs. Break-even: ~390 units/month at $8,000 fixed costs.
# | Cost Component | Per Unit ($) | % of Retail | Source / Basis | Variable vs Fixed | Scenario: Full Price $34.99 | Scenario: Discounted $29.99
REVENUE PER UNIT
1 | Retail Price | $34.99 | 100% | P0E pricing model. Validated by competitive analysis (P0A): market range $24.99-$49.99. StrideHer positioned mid-range. | — | $34.99 | $29.99 (after 15% ambassador or WELCOME10 discount)
2 | Average Discount | ($2.50) | (7.1%) | Blended average: 50% buy at full price, 30% use WELCOME10 (10% off = $3.50), 20% use ambassador/referral codes (15% off = $5.25). Blended: $0 × 0.5 + $3.50 × 0.3 + $5.25 × 0.2 = $2.10. Round to $2.50 for conservatism. | Variable | ($0.00) | ($5.00)
— | NET REVENUE PER UNIT | $32.49 | 92.9% | Retail price minus average discount. | — | $34.99 | $29.99
VARIABLE COSTS PER UNIT (costs that scale with each order)
3 | Product COGS (manufacturing) | ($6.00) | (17.1%) | P0E model: $5.50-$6.50/unit for 600-unit run. Using $6.00 midpoint. Includes: fabric, zippers, buckle, grip dots, stitching, QC. | Variable | ($6.00) | ($6.00)
4 | Inbound Freight (amortized) | ($2.00) | (5.7%) | P3C sea freight + customs: ~$1,200 total for 600 units = $2.00/unit. Includes: factory-to-port, ocean freight, port-to-door, customs brokerage. | Variable (per batch) | ($2.00) | ($2.00)
5 | Packaging | ($1.25) | (3.6%) | P2C: poly mailer ($0.25) + brand sticker ($0.10) + insert card ($0.15) + tissue wrap ($0.15) + thank-you card ($0.10) + box/mailer ($0.50). | Variable | ($1.25) | ($1.25)
6 | Outbound Shipping | ($4.50) | (12.9%) | USPS Priority Mail via Shopify Shipping: $4.00-$5.50 per package depending on zone. Using $4.50 average (free shipping absorbed by StrideHer — NOT charged to customer). | Variable | ($4.50) | ($4.50)
7 | Payment Processing | ($1.26) | (3.6%) | Shopify Payments: 2.9% + $0.30 per transaction. On $34.99: $1.01 + $0.30 = $1.31. On $32.49 avg: $0.94 + $0.30 = $1.24. Using $1.26 average. | Variable | ($1.31) | ($1.17)
— | TOTAL VARIABLE COST/UNIT | ($15.01) | (42.9%) | Sum of items 3-7. This is the "all-in" cost of manufacturing, shipping, packaging, and processing ONE order. | Variable | ($15.06) | ($14.92)
CONTRIBUTION MARGIN
★ | CONTRIBUTION MARGIN/UNIT | $17.48 | 50.0% | Net Revenue ($32.49) minus Total Variable Cost ($15.01). Every unit sold contributes $17.48 toward fixed costs and profit. | — | $19.93 (57.0%) | $15.07 (50.3%)
FIXED COSTS (monthly, regardless of units sold)
8 | Shopify Subscription | $39.00 | — | Shopify Basic plan. $29/mo if paid annually. | Fixed
9 | Apps & SaaS Tools | $50.00 | — | Judge.me ($15) + Klaviyo (~$20 at 500 contacts) + domain ($1.17/mo amortized) + other tools (~$14). | Fixed
10 | Meta Ads | $450.00 | — | $15/day average (P6C). Range: $300-$500/month depending on ROAS performance. | Semi-fixed (discretionary)
11 | Google Ads | $390.00 | — | $13/day average (P6D). Range: $200-$450/month. | Semi-fixed
12 | Content / Marketing | $100.00 | — | Canva Pro ($13) + Later ($18) + freelance editing ($50-$100) + miscellaneous. | Semi-fixed
13 | Accounting / Admin | $25.00 | — | Wave (free) + amortized CPA cost ($300/year ÷ 12 = $25/mo). | Fixed
14 | Insurance (Month 6+) | $35.00 | — | Product liability insurance: ~$400/year = $33/mo. Not needed until Month 6. | Fixed
— | TOTAL MONTHLY FIXED COSTS | $1,089.00 | — | Sum of items 8-14. This is the minimum monthly burn rate BEFORE paying for inventory. | Fixed
— | TOTAL FIXED (w/ full ads) | $1,089.00 | — | With full ad spend included ($840/mo). | —
BREAK-EVEN ANALYSIS
★ | BREAK-EVEN UNITS/MONTH | 63 units | — | Fixed costs ($1,089) ÷ Contribution margin ($17.48) = 62.3 units → round up to 63 units/month. | — | 55 units at full price | 73 units at discounted price
★ | BREAK-EVEN REVENUE/MONTH | $2,047 | — | Break-even units (63) × average net revenue ($32.49) = $2,047/month. Or ~$68/day, ~$512/week. | — | $1,924 at full price | $2,189 at discounted
★ | BREAK-EVEN DATE TARGET | Month 5-6 | — | P0E model projects: Month 1-2 revenue covers 40-60% of fixed costs. Month 3-4: 70-90%. Month 5-6: 100%+ (breakeven). This assumes revenue growth of 15-25% month-over-month from organic + paid channels compounding. | — | Month 4-5 (optimistic) | Month 6-7 (conservative)

## 7B.02-03 Cash Flow + Budget
P7B TASKS 7B.02-03: 12-MONTH CASH FLOW FORECAST + $10K BUDGET ALLOCATION
When does cash hit $0? When does revenue exceed expenses? When can you reorder? The answers are in this forecast.
Line Item | Pre-Launch | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
REVENUE (moderate scenario)
Gross Revenue | $0 | $1,400 | $2,100 | $2,800 | $3,500 | $4,200 | $4,900 | $5,250 | $5,600 | $6,000 | $6,400 | $6,800 | $7,200
Discounts & Returns | $0 | ($280) | ($315) | ($336) | ($350) | ($378) | ($392) | ($394) | ($392) | ($390) | ($384) | ($374) | ($360)
NET REVENUE | $0 | $1,120 | $1,785 | $2,464 | $3,150 | $3,822 | $4,508 | $4,856 | $5,208 | $5,610 | $6,016 | $6,426 | $6,840
VARIABLE COSTS
Product COGS | ($3,600) | ($240) | ($360) | ($480) | ($600) | ($720) | ($840) | ($900) | ($960) | ($1,030) | ($1,098) | ($1,166) | ($1,234)
Inbound Freight/Customs | ($1,200) | $0 | $0 | $0 | $0 | $0 | ($1,200) | $0 | $0 | $0 | $0 | $0 | ($1,200)
Packaging | ($750) | ($50) | ($75) | ($100) | ($125) | ($150) | ($175) | ($188) | ($200) | ($215) | ($229) | ($244) | ($258)
Outbound Shipping | $0 | ($180) | ($270) | ($360) | ($450) | ($540) | ($630) | ($675) | ($720) | ($773) | ($823) | ($875) | ($926)
Payment Processing | $0 | ($46) | ($69) | ($92) | ($115) | ($138) | ($161) | ($173) | ($185) | ($199) | ($213) | ($227) | ($241)
Total Variable Costs | ($5,550) | ($516) | ($774) | ($1,032) | ($1,290) | ($1,548) | ($3,006) | ($1,936) | ($2,065) | ($2,217) | ($2,363) | ($2,512) | ($3,859)
FIXED COSTS
Shopify + Apps | ($0) | ($89) | ($89) | ($89) | ($89) | ($89) | ($89) | ($89) | ($89) | ($89) | ($89) | ($89) | ($89)
Meta Ads | $0 | ($150) | ($350) | ($450) | ($450) | ($450) | ($450) | ($450) | ($450) | ($450) | ($450) | ($450) | ($450)
Google Ads | $0 | $0 | ($200) | ($350) | ($390) | ($390) | ($390) | ($390) | ($390) | ($390) | ($390) | ($390) | ($390)
Content / Marketing | $0 | ($50) | ($75) | ($100) | ($100) | ($100) | ($100) | ($100) | ($100) | ($100) | ($100) | ($100) | ($100)
Samples / Events | ($300) | ($75) | ($75) | ($50) | ($50) | ($50) | ($50) | ($50) | ($50) | ($50) | ($50) | ($50) | ($50)
Admin / Insurance | $0 | ($25) | ($25) | ($25) | ($25) | ($60) | ($60) | ($60) | ($60) | ($60) | ($60) | ($60) | ($60)
Total Fixed Costs | ($300) | ($389) | ($814) | ($1,064) | ($1,104) | ($1,139) | ($1,139) | ($1,139) | ($1,139) | ($1,139) | ($1,139) | ($1,139) | ($1,139)
CASH FLOW SUMMARY
Net Cash Flow | ($5,850) | $215 | $197 | $368 | $756 | $1,135 | $363 | $1,781 | $2,004 | $2,254 | $2,514 | $2,775 | $1,842
Cumulative Cash | $4,150 | $4,365 | $4,562 | $4,930 | $5,686 | $6,821 | $7,184 | $8,965 | $10,969 | $13,223 | $15,737 | $18,512 | $20,354
(Starting: $10,000)
7B.03: $10K BUDGET ALLOCATION WITH 25% CONTINGENCY RESERVE
Category | Allocated ($) | M1: % of $10K; M2: Timing; M3: Spend Trigger; M4: Actual Spent; M5: Remaining
Inventory (600 units @ $6.00) | $3,600 | M1: 36%; M2: Month -2 (pre-launch, production payment); M3: Pay 30% deposit on PO confirmation, 70% before shipping.
Inbound Freight + Customs | $1,200 | M1: 12%; M2: Month -1 (when shipment arrives); M3: Pay freight forwarder on shipment arrival. Customs duties at port.
Packaging Materials (600 units) | $400 | M1: 4%; M2: Month -2 (order alongside inventory); M3: Order when production PO is confirmed.
Meta Ads (Month 1-3) | $950 | M1: 9.5%; M2: Months 1-3 ($150 → $350 → $450 ramp); M3: Start at $5/day Month 1. Scale to $15/day by Month 3 ONLY if ROAS >2×.
Google Ads (Month 2-3) | $550 | M1: 5.5%; M2: Months 2-3 ($200 → $350 ramp); M3: Start Month 2 after Meta learnings. Scale to $13/day by Month 3 ONLY if ROAS >2×.
Shopify + Apps (6 months) | $350 | M1: 3.5%; M2: Monthly ($39 Shopify + ~$20 apps × 6 months); M3: Pay monthly. Non-negotiable operating cost.
Samples / Influencer / Events | $400 | M1: 4%; M2: Months 1-4 (spread across seeding, events, ambassador gifts); M3: Don't spend >$100/month. Prioritize influencers in Month 1-2, events in Month 3-4.
Content / Marketing Tools | $200 | M1: 2%; M2: Months 1-6 (Canva, Later, freelance editing); M3: $30-$50/month. Increase only when content is driving measurable traffic.
Business Registration / Legal | $350 | M1: 3.5%; M2: Week 1 (LLC filing, domain, trademark filing); M3: Spend immediately — these are prerequisites for everything else.
TOTAL ALLOCATED | $8,000 | M1: 80%
CONTINGENCY RESERVE | $2,000 | M1: 20%; M2: HELD until needed; M3: Release contingency ONLY for: unexpected customs fees, emergency reorder, critical tool purchase, or unforeseen legal cost. NOT for: "I want to try more ads" or "I saw a cool tool." Discipline.
TOTAL BUDGET | $10,000 | M1: 100%

## 7B.04-05 Review + Milestones
P7B TASKS 7B.04-05: MONTHLY FINANCIAL REVIEW PROTOCOL + 8 FINANCIAL MILESTONES
Review finances on the last day of every month. Hit milestones or diagnose why you didn't. The rhythm that turns hope into data-driven growth.
Element | Details | How to Pull | Target | Action If Below Target | Action If Above Target | Frequency
7B.04: MONTHLY FINANCIAL REVIEW — 5 reports, last day of every month, 2-3 hours
1. P&L (Profit & Loss) | Monthly income statement: Net Revenue: $___ - COGS: ($___) = GROSS PROFIT: $___ - Marketing: ($___) - Shipping: ($___) - Platform fees: ($___) - G&A: ($___) = NET PROFIT (LOSS): $___ Gross margin target: 55-65% Net margin target: 10-20% by Month 6 | Wave → Reports → Profit & Loss → set date range to current month. Verify: all transactions categorized correctly. Common miscategorization: shipping costs in "COGS" instead of "Shipping" or personal expenses accidentally logged as business. | Gross margin: 55-65%. Net profit: positive by Month 5-6. Net margin: 10-20% by Month 6. | Gross margin <55%: COGS or shipping costs are higher than modeled. Investigate: did freight costs increase? Are you shipping heavier/further than expected? Is discount usage higher than projected? Net loss growing: cut discretionary spend (ads, tools) until revenue catches up. | Net margin >20%: you're under-investing in growth. Increase ad spend or accelerate reorder. Healthy growth-stage brands reinvest 60-80% of profit into inventory + marketing. Consistently profitable: consider paying yourself (Owner's Draw). | Monthly (last day of each month)
2. Cash Position | Current cash in business bank account: $___ Minus: upcoming committed expenses (next month's Shopify, scheduled ad spend, pending POs): ($___) Equals: AVAILABLE CASH: $___ Runway: Available Cash ÷ Monthly Burn Rate = ___ months of runway remaining. MINIMUM RUNWAY: 2 months. If runway drops below 2 months: cut ALL discretionary spending immediately. | Business bank account balance (Mercury/Relay/Novo dashboard). Minus: known upcoming expenses (list them). This should take 5 minutes. | Runway: >3 months. Ideal: 4-6 months of operating expenses in the bank at all times. | Runway <2 months: EMERGENCY. 1. Pause all ads immediately 2. Pause all discretionary tools 3. Fulfill existing orders only 4. Calculate: at current revenue trajectory, when does cash recover? 5. If unrecoverable: consider a personal bridge loan to the LLC (document it as Owner's Capital Contribution) | Runway >6 months: you're sitting on too much cash. Invest in: inventory reorder (production run #2), increased ad spend, or first hire. Cash should be WORKING, not sitting idle. | Monthly (+ weekly glance during Months 1-3)
3. Unit Economics Actual vs Model | Compare ACTUAL unit economics to the model in Sheet 7B.01: • Actual COGS/unit: $___ (model: $6.00) • Actual shipping/unit: $___ (model: $4.50) • Actual processing/unit: $___ (model: $1.26) • Actual contribution margin: $___ (model: $17.48) Are actuals within 10% of model? If so: model is validated. If not: update the model with actuals and recalculate break-even. | Shopify → Analytics → divide total COGS by units sold. Shipping: total shipping cost ÷ orders. Processing: Shopify Payments fee report ÷ orders. | Within 10% of model for all line items. | Any line item >15% above model: investigate. Common culprits: • COGS higher: supplier raised prices, or customs duties were higher than expected • Shipping higher: heavier packages, more distant zones, or rate increases • Processing higher: more PayPal transactions (higher fee than Shopify Payments) | Contribution margin HIGHER than model: pricing power confirmed. Consider: raising price to $37.99 or $39.99 (test via A/B). | Monthly
4. CAC by Channel | Customer Acquisition Cost by channel: • Meta Ads: spend $__ ÷ customers __ = $__ CAC • Google Ads: spend $__ ÷ customers __ = $__ CAC • Organic (social + SEO + referral): $0 CAC • Email: $0 CAC (existing subscribers) • Events/samples: spend $__ ÷ customers __ = $__ CAC BLENDED CAC: total marketing spend ÷ total new customers = $__ CAC Compare blended CAC to contribution margin: if CAC < contribution margin, you're profitable per customer. | Meta Ads Manager + Google Ads → spend. Shopify → customers by source (requires UTM tracking or channel attribution). Simplified: total ad spend ÷ total new customers this month. | Blended CAC: <$12. Meta CAC: <$10. Google CAC: <$12. Organic CAC: $0. | Blended CAC >$15: you're paying too much per customer. 1. Check ad ROAS — if <2×, reduce ad spend 2. Check organic conversion — if <1%, fix product page 3. Increase organic channels (content, community, referrals) to dilute paid CAC | Blended CAC <$8: SCALE. You're acquiring customers cheaply. Increase ad spend 20% and see if CAC holds. If it does at the higher spend level: increase again. | Monthly
5. Inventory Value + Turnover | Units remaining: ___ Inventory value at COGS: $___ Units sold this month: ___ Inventory turnover rate: units sold ÷ average inventory Days of inventory remaining: units remaining ÷ (units sold/30) = ___ days REORDER TRIGGER: when days remaining < 45 (accounting for 30-40 day production + 25-35 day shipping). | Shopify → Products → inventory count. Multiply by $6.00 COGS for value. Divide total sold this month by 30 for daily run rate. Divide remaining by daily run rate for days remaining. | Target turnover: sell through initial 600 units in 4-6 months. Reorder trigger: 45 days of inventory remaining. | Days remaining <45: REORDER NOW (P3D). Production + shipping takes 55-75 days. Ordering at 45 days means ~2-4 weeks of potential stockout. Order earlier if possible. If <30 days remaining and no PO placed: EMERGENCY — air freight may be needed ($3-$5/unit extra) to avoid full stockout. | Inventory days >120: selling slower than planned. Options: increase marketing spend, run a promotion, or accept slower sell-through and preserve cash. | Monthly (+ weekly glance at Shopify inventory dashboard)
7B.05: 8 FINANCIAL MILESTONES — concrete checkpoints from launch to reinvestable profit
MILESTONE 1 | First Sale | Shopify Orders | Day 1 of launch | If no sale Day 1: verify checkout works, email was sent, social was posted. Usually a pre-launch campaign issue, not a product issue. | Celebrate. Screenshot. Post to Stories. This is real. | Day 1
MILESTONE 2 | $1,000 cumulative revenue | Shopify Analytics | Month 1 | If behind: launch was softer than expected. Double down on email (send a "last chance" campaign) and social (increase posting frequency). | On track. The business is generating revenue. Keep executing. | Month 1
MILESTONE 3 | 50 total orders | Shopify Analytics | Month 1-2 | 50 orders = enough data to: calculate actual CAC, identify best-selling SKU, and start meaningful A/B tests. | Enough data for optimization. Begin P6E work. | Month 1-2
MILESTONE 4 | First breakeven month (net profit ≥ $0) | Wave P&L report | Month 5-6 | If Month 6 is still negative: diagnose — is it revenue (too low) or costs (too high)? Cut ads if ROAS <2×. Cut tools if unnecessary. Focus on organic channels until breakeven is achieved. | The business sustains itself. You no longer need to inject personal capital. Shift focus: from survival to growth. | Month 5-6
MILESTONE 5 | $5,000 monthly revenue | Shopify Analytics | Month 6-8 | $5K/month = ~143 orders/month = ~5 orders/day. If not hitting this: scale what's working (best ad, best channel, best content type) harder. | At $5K/month with 55% gross margin: $2,750 gross profit. After fixed costs (~$1,100): $1,650/month net. Consider: first reorder, first hire, first owner's draw. | Month 6-8
MILESTONE 6 | 100 product reviews | Judge.me | Month 6-9 | 100 reviews = powerful social proof for product page + Amazon listing. If <50 by Month 6: increase review request frequency (add a second email, include a card insert with QR to review page). | 100+ reviews at 4.5+ stars: your product page converts at maximum trust. Add review count to ads, email, and social proof badges. | Month 6-9
MILESTONE 7 | $10,000 monthly revenue | Shopify Analytics | Month 9-12 | $10K/month = ~286 orders/month = ~10/day. This is the threshold where: 3PL becomes cost-effective, a part-time hire is justified, and you can consider a second product. | $10K/month with 20% net margin = $2,000/month profit. Reinvest 60-80% into inventory + ads. Consider: expanding to Amazon (if not already), launching a V2 or accessory product, hiring first VA. | Month 9-12
MILESTONE 8 | First reinvestable profit ($2,000+ monthly net) | Wave P&L | Month 9-12 | $2K/month net = $24K/year profit. At this point: the business funds its own growth. No more personal capital needed. If not achieved by Month 12: the business model may need fundamental adjustment (pricing, product, market). | You've built a self-sustaining business on $10K. The hardest part is done. From here: compound. Reinvest profit into inventory depth, product expansion, and team building. | Month 9-12

## 7B FOUNDER ACTIONS
P7B FINANCIAL PLANNING — FOUNDER ACTION CHECKLIST
Build the models in Week 1-2. Update weekly (cash) and monthly (everything else). Know your numbers or your numbers will surprise you.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 1-2: BUILD THE FINANCIAL MODELS
🔴 #1 | Build unit economics model (Sheet 7B.01) with YOUR actual costs | 1-2 hrs | $0 | 1. Copy Sheet 7B.01 template to Google Sheets 2. Replace estimated costs with YOUR actual quotes: COGS from supplier RFQ, freight from forwarder quote, packaging from supplier, shipping from Shopify rate calculator 3. Calculate YOUR contribution margin and break-even units 4. If contribution margin <$10/unit: your business model is fragile — either raise price, lower COGS (negotiate with supplier), or reduce shipping cost (lighter packaging) 5. Bookmark this sheet — you'll update it monthly with ACTUAL data once selling
🔴 #2 | Build 12-month cash flow forecast (Sheet 7B.02) with 3 scenarios | 2-3 hrs | $0 | 1. Copy Sheet 7B.02 template to Google Sheets 2. Create 3 tabs: Conservative (50% of moderate), Moderate (as shown), Optimistic (150% of moderate) 3. Adjust revenue estimates based on YOUR waitlist size, social following, and market research 4. Fill in YOUR actual fixed costs (Shopify plan, tools you've chosen, ad budget you've committed to) 5. Find the month where "Cumulative Cash" dips lowest — this is your MAXIMUM RISK POINT. If it goes below $500: your budget is too tight. Cut costs or delay spending. 6. Update weekly during Months 1-3 with actual revenue and expenses
🔴 #3 | Allocate $10K budget per Sheet 7B.03 framework | 30 min | $0 | 1. Review the allocation template. Adjust for your specific situation. 2. Write your actual numbers into each line. 3. Set aside $2,000 contingency — move it to a separate sub-account (Relay lets you create multiple accounts) so you're not tempted to spend it. 4. Create spend-trigger rules: "I won't spend on Meta Ads until I have 50+ organic orders to confirm product-market fit" or "I won't reorder until 60% of initial inventory is sold." 5. Track actual vs budget weekly in a simple spreadsheet.
ONGOING: MONTHLY FINANCIAL RHYTHM
🟡 #4 | Monthly financial review (last day of every month, 2-3 hours) | 2-3 hrs/month | $0 | Last day of every month: 1. Pull P&L from Wave (Revenue - COGS - Expenses = Net Profit/Loss) 2. Check cash position (bank balance - upcoming committed expenses = available cash) 3. Compare unit economics actuals to model (are costs within 10% of projections?) 4. Calculate CAC by channel (ad spend ÷ new customers per channel) 5. Check inventory (days remaining, reorder trigger) 6. Check milestones (Sheet 7B.05): which have been hit? Which are behind? 7. Write 3 sentences: "This month I learned: ___. Next month I will: ___. The biggest risk is: ___." This 2-3 hour investment prevents the "where did all the money go?" surprise that kills bootstrapped businesses.
🟢 #5 | Milestone tracking + quarterly financial planning | 1 hr/quarter | $0 | Every quarter: 1. Review all 8 milestones from Sheet 7B.05: achieved, on track, behind, or at risk? 2. Update the 12-month cash flow forecast with actual data (actuals replace estimates for completed months) 3. Extend the forecast forward (add months as the business grows) 4. Set 3 financial goals for next quarter (specific: "$X revenue by Month Y" not "grow revenue") 5. Share with an advisor or mentor for accountability and external perspective. The quarterly review is when you step back from daily execution and ask: "Is this business going where I want it to go? If not, what needs to change?"

## G4 Founder Compensation
G4 REMEDIATION: FOUNDER COMPENSATION FRAMEWORK — WHEN AND HOW TO PAY YOURSELF
$0 in Months 1-6. Owner's Draw at 10-20% of net profit after breakeven. Never >50%. The discipline that prevents both burnout and bankruptcy.
Phase | Timing | Compensation | Prerequisites | Mechanics | Tax Treatment | Guardrails
THE PRINCIPLE: pay yourself enough to stay motivated, but not so much that you starve the business of growth capital.
PHASE 1 ZERO DRAW | Month 1-6 (pre-breakeven) | $0 from the business. All revenue is reinvested into: inventory, marketing, tools, and growth. Personal living expenses funded from: savings, other income (employment, freelancing), or family support. This is the "investment phase" — you're investing your time AND your money into building the business. The return comes later. | NONE — this phase is automatic from launch. The $10K budget (P7B.03) has ZERO allocation for founder compensation. Every dollar is allocated to: inventory ($3,600), marketing ($1,500), tools ($350), shipping ($500), events ($400), legal ($350), packaging ($400), and contingency ($2,000). Paying yourself from this budget = taking from one of these critical categories = weakening the launch. | N/A — no compensation to process. KEEP PERSONAL AND BUSINESS FINANCES STRICTLY SEPARATE: • Business revenue → business bank account (Mercury/Relay) ONLY • Personal expenses → personal bank account ONLY • Do NOT use the business debit card for personal purchases • Do NOT "borrow" from business for personal expenses (even if you plan to repay — this creates accounting nightmares and pierces the LLC liability shield) | For a single-member LLC owned by a non-US resident: the ENTIRE LLC profit is "pass-through" income — it's taxable to you whether you take a draw or not. Translation: you owe taxes on business profit even if $0 leaves the business bank account. Work with your CPA (P7A.03) to estimate quarterly tax obligation. In Phase 1: if the business is not yet profitable, there's no taxable income from the business. | GUARDRAIL: if personal financial pressure makes $0 compensation unsustainable, consider: 1. Part-time freelancing alongside the business (10-15 hrs/week) to cover personal expenses 2. A personal loan TO the business (documented as "Owner Capital Contribution" in Wave — this is repaid before Owner's Draws begin) 3. Extending Phase 1 beyond 6 months if breakeven takes longer Do NOT take an Owner's Draw before breakeven. This is non-negotiable.
PHASE 2 INITIAL DRAW | Month 7+ (post-breakeven, first profitable month) | 10-20% of MONTHLY NET PROFIT. Example: • Month 7 net profit: $1,200 • Owner's Draw: $120-$240 This is modest by design. The business just became profitable — it needs most of the profit to fund growth (reorder inventory, increase ads, hire VA). "Net profit" = revenue minus ALL expenses (COGS, shipping, marketing, tools, fees, taxes owed). NOT gross profit. NOT revenue. | ALL of the following must be true BEFORE taking any draw: ✅ Business has been profitable for 2+ consecutive months (not just 1 good month) ✅ Cash reserve ≥ 3 months of operating expenses (~$3,000-$4,000 in the bank) ✅ No pending large expenses (reorder PO, annual insurance, tax payment) that would deplete the reserve ✅ Inventory is funded (current stock is paid for, next reorder is budgeted) If ANY prerequisite is not met: remain in Phase 1 ($0) until all are satisfied. | OWNER'S DRAW PROCESS: 1. Last day of month: calculate net profit from P7B.04 monthly P&L review 2. Calculate draw: net profit × 10-20% 3. Transfer from business bank (Mercury/Relay) to personal bank 4. Record in Wave: create a journal entry: Debit: "Owner's Draw" (equity account) Credit: "Business Checking" (asset account) 5. This is NOT an expense — it's a distribution of equity. It does NOT appear on the P&L. It appears on the Balance Sheet as a reduction in owner's equity. FREQUENCY: monthly, on the same day as your financial review. Not ad-hoc, not weekly, not "whenever I need money." Monthly discipline prevents over-drawing. | Owner's Draw from a single-member LLC is NOT subject to payroll tax (no Social Security/Medicare withholding — unlike a salary from an S-Corp). However: all LLC profit (including the portion you DON'T draw) is subject to self-employment tax at the federal level. Work with your CPA: quarterly estimated tax payments should account for: total LLC profit (not just the draw amount). For non-US founders: consult with a US tax professional about your specific treaty obligations. | ABSOLUTE RULES: ❌ NEVER draw more than 50% of net profit (even in great months) ❌ NEVER draw if it would reduce cash reserve below 3 months of operating expenses ❌ NEVER draw to fund personal luxuries while the business needs growth capital ❌ NEVER draw without recording it in Wave (undocumented draws = accounting chaos + tax audit risk) ✅ ALWAYS calculate draw AFTER the P&L is finalized (not estimated — actual) ✅ ALWAYS maintain the 3-month cash reserve threshold ✅ ALWAYS increase the business reinvestment % before increasing the draw %
PHASE 3 GROWTH DRAW | Month 12+ (established profitability, $5K+/month revenue) | 20-35% of MONTHLY NET PROFIT. Example: • Month 14 net profit: $2,500 • Owner's Draw: $500-$875 At this stage: the business has proven sustainability, has consistent cash flow, and growth is compounding. A larger draw is justified because the founder's time and effort created this value — and founder burnout from $0 compensation for 12+ months is a real business risk. | ALL Phase 2 prerequisites PLUS: ✅ 6+ consecutive profitable months ✅ Cash reserve ≥ 4 months of operating expenses ✅ Revenue trending upward (not just stable) ✅ LTV:CAC ratio ≥ 3:1 (P9C.05 — the business model is profitable, not just the P&L) ✅ VA hired or planned (P11D.02 — the business can operate without 100% founder time) | Same process as Phase 2, just a higher percentage. OPTIONAL AT THIS STAGE: Consider switching from Draw to a fixed monthly "salary-equivalent" amount (e.g., $800/month regardless of monthly profit variance). This provides personal income stability. Mechanics: still processed as Owner's Draw (not actual payroll — that requires S-Corp election, which adds complexity not justified until $100K+ profit). BUT: the fixed amount should be BELOW the average monthly draw at 20-35% — you're choosing stability over maximization. | At $30K-$60K annual profit: discuss with CPA whether an S-Corp election would save on self-employment tax. S-Corp: you pay yourself a "reasonable salary" (subject to payroll tax) and take the remainder as distributions (not subject to SE tax). Savings: 15.3% SE tax on the distribution portion. Typically beneficial at: $50K+ annual profit. Below that: the S-Corp compliance cost ($500-$1,500/year for payroll processing + additional tax filing) exceeds the savings. | INCREASE DRAW % only when: • Revenue is growing AND • Cash reserve is above threshold AND • Business reinvestment needs are funded DECREASE DRAW % immediately when: • Revenue declines 2+ months • A large expense is approaching (reorder, new product development) • Cash reserve approaches the 3-month minimum The draw is a DIAL, not a switch. Adjust monthly based on the business's needs.
PHASE 4 MATURE DRAW | Year 2+ ($10K+/month revenue, team in place) | 30-50% of MONTHLY NET PROFIT. Example: • Month 20 net profit: $4,000 • Owner's Draw: $1,200-$2,000 At this stage: the business has a team (VA + possibly content creator), multiple revenue channels, and proven unit economics. The founder's role has shifted from "do everything" to "strategy + growth." Compensation should reflect the founder's value as CEO, not just as a worker. 50% is the ABSOLUTE CEILING. The other 50%+ funds: team compensation, inventory growth, new product development, and the war chest for Year 3. | ALL Phase 3 prerequisites PLUS: ✅ Team in place (at least 1 VA per P11D.02) ✅ Multiple revenue channels active (D2C + Amazon + at least 1 other) ✅ 12+ months of consistent profitability ✅ Cash reserve ≥ 6 months of operating expenses ✅ Annual revenue exceeding $100K | At this scale: work with CPA to formalize: 1. S-Corp election (if tax savings justify it) 2. "Reasonable salary" determination (IRS requires S-Corp owner-employees to pay themselves a "reasonable" salary before taking distributions) 3. Payroll setup (Gusto or similar, $40/month + per-employee fees) 4. Quarterly estimated tax payments automated The financial structure evolves from: "founder takes draws from an LLC" to "CEO receives salary from an S-Corp" — more complex but more tax-efficient at scale. | At $100K+ revenue: the business is a REAL COMPANY, not a side project. Founder compensation should reflect this: • Benchmark: D2C brand founders at $100K-$500K revenue typically pay themselves $30K-$80K/year (20-40% of net profit) • This is modest by corporate standards but appropriate for a bootstrapped brand reinvesting in growth • The goal: enough to live on comfortably without a second income source | YEAR 2+ ASPIRATION: Revenue: $150K-$250K Net profit: $40K-$70K Founder draw: $16K-$35K (40-50% of net profit) This is a LIVABLE income from a bootstrapped brand — the business funds your life while continuing to grow. Year 3 target: Revenue: $400K-$700K Net profit: $80K-$150K Founder draw: $40K-$75K At this point: you've built a business that provides a comfortable living AND compounds in equity value. The real wealth is in the business itself — the draw is just current income.