## P7C EXEC SUMMARY
P7C PAYMENT & INTERNATIONAL OPERATIONS — EXECUTIVE SUMMARY
4 Tasks ¦ Weeks 4-8 ¦ Cost: $0-$50 ¦ Accept global payments, ship worldwide, understand tax obligations, and track real margins.
Task ID | Task | KPI | Deliverable | Status | Why This Matters | Cost / Timeline
7C.01 | Set up multi-currency payments: Shopify Payments + PayPal + Wise | 3 payment methods active | Complete payment processing guide: Shopify Payments (primary — 2.9% + $0.30, supports 130+ currencies with auto-conversion), PayPal (secondary — captures 12-15% of customers who prefer PayPal checkout), and Wise (for receiving supplier payments and international payouts at low FX fees). Shopify Payments auto-converts international purchases to your settlement currency (USD) — the customer pays in their local currency, you receive USD. | COMPLETE ✓ | Offering only one payment method loses 10-15% of potential buyers. PayPal users abandon carts when PayPal isn't an option. International customers who see prices in a foreign currency convert 30% less than those who see local currency. Shopify Payments multi-currency + PayPal covers 95%+ of global payment preferences. Wise handles the supplier side: pay Chinese factories in CNY at 0.5% FX fee vs 3-5% at traditional banks. | $0 (Shopify Payments + PayPal are free to enable; fees deducted per transaction). Wise: $0 to open, small FX fees per transfer.
7C.02 | Research and set up international shipping rates: US, UK, EU, AU, CA | Shipping rates configured for 5 priority markets | Complete international shipping rate guide: carrier recommendations per destination (USPS First Class International for <1 lb parcels, $14-$18 to most countries), Shopify-calculated rates vs flat rates, customs form auto-generation via Shopify Shipping, and the DDP vs DDU decision (who pays customs duties — you or the customer). US is 70-80% of revenue; international is a growth lever, not the core. | COMPLETE ✓ | International orders expand your addressable market 3-5× beyond the US. A customer in London or Sydney who discovers StrideHer via Instagram should be able to buy as easily as someone in Denver. But international shipping done WRONG (surprise customs charges, $30 shipping fees, 4-week delivery) kills the experience. Done RIGHT ($14-$18 flat rate, clear customs expectations, 10-14 day delivery): international becomes 15-25% of revenue by Month 6. | $0 (rate configuration only). Actual shipping cost: $14-$18/package international vs $4.50 domestic.
7C.03 | Understand VAT/GST obligations for EU, UK, AU — set up IOSS if needed | Tax obligations documented by country | Complete international tax obligation guide: which countries require registration and collection (thresholds from 7A.05 repeated with expanded detail), IOSS setup for EU (if/when you cross €10K threshold), UK VAT registration (£85K threshold), and the practical reality: in Year 1 at <$50K total revenue, most international tax obligations don't apply. This task is about KNOWING when they trigger so you're prepared, not about acting immediately. | COMPLETE ✓ | International tax is the #1 anxiety for new D2C founders selling globally — and the #1 thing they over-prepare for in Year 1. The reality: below the thresholds (documented in 7A.05), you have NO obligation to register, collect, or remit foreign taxes. Your customer may owe import duties on receipt (DDU shipping), but that's their responsibility, not yours. This deliverable eliminates anxiety by documenting exactly when each obligation triggers. | $0 (documentation only). IOSS registration (if needed): €0 via official EU portal.
7C.04 | Set up profit margin tracker: actual vs projected margins reviewed monthly | Margin tracker operational | Complete profit margin tracking system: per-order actual margin calculation (revenue - discount - COGS - shipping - packaging - processing = actual margin), monthly P&L margin comparison to 7B.01 model, margin trend analysis (are margins improving or eroding?), and root cause diagnosis for margin deviations. This complements the 7B.04 monthly financial review with granular per-order visibility. | COMPLETE ✓ | Blended averages hide problems. Your AVERAGE margin might be 50%, but: full-price US orders earn 57% margin while discounted international orders earn 28% margin. The margin tracker reveals which order TYPES are profitable and which are margin-dilutive. This data drives decisions: "Should we continue offering free international shipping?" or "Should we reduce the ambassador discount from 20% to 15%?" | $0 (spreadsheet-based tracking using Shopify export data).

## 7C.01-02 Payments + Shipping
P7C TASKS 7C.01-02: MULTI-CURRENCY PAYMENTS + INTERNATIONAL SHIPPING RATES
Shopify Payments handles currency conversion automatically. USPS ships internationally for $14-$18. Configure once, sell globally.
Element | Configuration | Fees / Cost | When to Use | Setup Steps | Expected Impact | Notes
7C.01: PAYMENT PROCESSING — 3 methods covering 95%+ of global payment preferences
Shopify Payments (PRIMARY) | Shopify Payments is the DEFAULT and BEST payment processor for Shopify stores: • Accepts: Visa, Mastercard, Amex, Discover, Apple Pay, Google Pay, Shop Pay • Multi-currency: auto-detects visitor's country → shows prices in their local currency → settles to your account in USD • Shop Pay: 1-click checkout for returning Shopify buyers (increases conversion 1.7× per Shopify data) • Shopify Payments eliminates the need for a third-party payment gateway (Stripe, Authorize.net) • Available in: US, UK, Canada, Australia, and 20+ other countries | 2.9% + $0.30 per US transaction. 3.5% + $0.30 for international cards. 1.5% currency conversion fee for multi-currency transactions. No monthly fee. | Every transaction. This is your primary and default processor. 85-90% of orders will use Shopify Payments. | Shopify → Settings → Payments → Shopify Payments should already be active from P4A.01. Verify: 1. All card types enabled (Visa, MC, Amex, Discover) 2. Apple Pay + Google Pay enabled 3. Shop Pay enabled 4. Multi-currency: Settings → Markets → add countries (US, UK, CA, AU, EU) → enable local currency display 5. Payout schedule: set to "Daily" (fastest cash access) or "Weekly" (fewer bank transactions) | 85-90% of orders processed. Shop Pay increases conversion 1.7× for returning customers. Multi-currency increases international conversion 15-30%. | Shopify Payments is REQUIRED to avoid additional transaction fees. Without it: Shopify charges an extra 2% on top of your payment processor's fees. With it: no extra charge. If your country isn't supported by Shopify Payments: use Stripe as the gateway (similar fees).
PayPal (SECONDARY) | PayPal captures customers who: • Don't want to enter credit card details (trust PayPal's buyer protection) • Have PayPal balance they want to use • Are on mobile and have PayPal's one-tap checkout 12-15% of online shoppers prefer PayPal. Not offering it = losing those sales. PayPal Express Checkout: appears as a button on the product page AND at checkout. | 2.99% + $0.49 per US transaction. (Slightly higher than Shopify Payments, but the customers who use PayPal WOULDN'T BUY without it.) | 10-15% of orders will use PayPal. Especially: international customers and older demographics (35+). | Shopify → Settings → Payments → PayPal → Connect. If you don't have a PayPal Business account: 1. paypal.com → Sign Up → Business Account 2. Verify business email 3. Connect to Shopify via the PayPal integration PayPal Express Checkout button auto-appears on product pages and at checkout after connection. | Captures 10-15% of orders that would otherwise abandon. Particularly important for international customers. | PayPal holds funds for new sellers (21-day hold for first 3 months). Plan cash flow accordingly — those PayPal funds aren't immediately available. After 90 days of sales history: holds reduce to 0-3 days.
Wise (SUPPLIER PAYMENTS) | Wise (formerly TransferWise) is for OUTBOUND payments — paying your Chinese supplier in CNY, or transferring funds internationally at low FX rates. Not customer-facing. Customers never interact with Wise. Use cases: • Pay factory invoice in CNY at 0.5-0.7% FX fee (vs 3-5% at traditional banks) • Pay freight forwarder • Transfer funds between your USD and other currency accounts | 0.5-0.7% FX fee (vs 3-5% at traditional banks). Flat transfer fee: $1-$5 depending on amount and currency. No monthly fee. | Paying suppliers (Alibaba factory, freight forwarder). NOT for receiving customer payments. Use 2-3× per production run (deposit + balance + freight). | wise.com → Sign Up → Personal or Business account (Business recommended if paying from LLC). Connect your business bank account (Mercury/Relay/Novo) as a funding source. To pay supplier: Create transfer → enter amount in CNY → Wise converts from USD at mid-market rate → supplier receives CNY in 1-2 business days. Saves $50-$150 per production run vs bank wire transfers. | Saves 2-4% on every international payment. On a $3,600 PO: Wise fee ~$25. Bank wire fee: $30-$50 + 3% FX = $138. Savings: ~$113 per PO. | Some Alibaba suppliers accept Alibaba Trade Assurance payments directly (built-in escrow). Compare fees: Alibaba TA charges 0-3% depending on method. Wise is usually cheaper for amounts >$1,000.
7C.02: INTERNATIONAL SHIPPING RATES — 5 priority markets configured in Shopify
US (primary market) | US domestic shipping: Carrier: USPS via Shopify Shipping (discounted rates) Service: Priority Mail (2-5 business days) Cost: $4.00-$5.50 per package (Shopify rate) Weight: StrideHer belt ~150g (5.3 oz) with packaging OFFER: Free US shipping (absorb cost into margin — already modeled in 7B.01 at $4.50/unit). "Free Shipping" increases conversion 15-20%. | $4.00-$5.50 per package. Absorbed by StrideHer (free shipping to customer). | 70-80% of orders. | Shopify → Settings → Shipping → US rates. Option A: "Free shipping" flat rate (recommended — simplest, highest conversion). Option B: Shopify-calculated rates (shows exact USPS cost — slightly lower conversion but honest pricing). Recommended: Free shipping for US orders. Period. | Free shipping = 15-20% higher conversion than $5 shipping. At $34.99 with free shipping: customers perceive more value than $29.99 + $5 shipping (same total). | Use Shopify Shipping to buy labels (discounted USPS rates). Don't go to USPS.com and pay retail rates — Shopify rates are 20-40% lower.
UK | UK shipping: Carrier: USPS First Class Package International (10-14 business days) or USPS Priority Mail International (6-10 days) Cost: USPS FCPI ~$14-$16. PMI ~$26-$35. Customs: UK customers may owe import VAT (20%) + handling fee (~£8) on packages valued >£135. Below £135: usually no additional charge for low-value imports. StrideHer at $34.99 = ~£28 — BELOW the £135 threshold. Most UK orders will arrive duty-free. | $14-$16 (USPS FCPI) Charge to customer: $12-$15 flat rate (subsidize slightly to keep competitive). | 5-10% of orders (UK is the #1 international market for US D2C brands). | Shopify → Settings → Shipping → Add shipping zone: "United Kingdom" → set flat rate: $14.99. Alternative: Shopify-calculated rates (auto-calculates USPS rate based on weight/destination). Customs forms: Shopify auto-generates CN22/CN23 customs forms when you buy international labels. HS code for running belt: 4202.92 (textile outer surface travel/sports accessories). | UK is typically the first international market to develop for US-based running brands. Shared language, similar running culture (parkrun originated in UK), and favorable shipping costs. | DDU (Delivered Duty Unpaid) is standard: the customer pays any import duties on receipt. For orders <£135: duties are typically zero. If you want premium experience: DDP (Delivered Duty Paid) — you pay duties on behalf of customer. Cost: ~$3-$5 extra per package. Consider for VIP/repeat customers only.
Canada | Canada shipping: Carrier: USPS First Class Package International (~$12-$15) or UPS/DHL eCommerce (~$10-$14) Delivery: 7-14 business days Customs: Canada charges GST (5%) on imports. De minimis threshold: CAD $20. StrideHer at $34.99 USD = ~CAD $47 — above the threshold. Customer will likely owe ~CAD $2.35 GST + handling fee (~CAD $10). | $10-$15 per package. Charge: $12.99 flat rate. | 3-5% of orders. | Shopify → Settings → Shipping → Add zone: "Canada" → $12.99 flat rate. HS code: 4202.92. Country of origin: China. | Canada is the easiest international market: proximity, similar culture, English-speaking. | The CAD $10 handling fee (charged by Canada Post to the recipient for processing customs) is the #1 complaint from Canadian customers. Set expectations on the product page: "Canadian orders may incur a small customs handling fee."
EU (Germany, France, Netherlands etc.) | EU shipping: Carrier: USPS FCPI ($14-$18) or DHL eCommerce ($12-$16) Delivery: 10-21 business days via USPS. 7-14 via DHL. Customs: EU charges VAT (19-25% depending on country) on ALL imports. De minimis threshold: €0 (eliminated July 2021). Every EU import owes VAT. For orders <€150: IOSS (Import One-Stop Shop) lets you collect EU VAT at checkout and remit monthly. Without IOSS: customer pays VAT + handling fee on delivery (bad experience). If EU sales <€10K/year: IOSS registration is optional. Above €10K: required. | $14-$18 per package. Charge: $16.99 flat rate. | 3-8% of orders (EU combined). | Shopify → Settings → Shipping → Add zone: "European Union" → $16.99 flat rate. IOSS (when needed): register at the EU IOSS portal (import-one-stop-shop.ec.europa.eu). Free registration. You collect VAT at Shopify checkout (Shopify supports IOSS natively) and remit monthly. Year 1: likely below €10K EU sales. Skip IOSS for now. Customers pay VAT on delivery (DDU). Set expectations in shipping FAQ. | EU is a large market (450M people) but complex due to VAT. Start DDU (customer pays duties). Switch to IOSS when EU sales cross €10K/year — the customer experience improves dramatically (no surprise charges at delivery). | Germany and Netherlands are typically the top EU markets for US running brands. France and Scandinavia follow.
Australia | Australia shipping: Carrier: USPS FCPI ($14-$18). Delivery: 14-21 business days. Customs: Australia charges GST (10%) on ALL imports (de minimis: AUD $0). StrideHer at $34.99 USD = ~AUD $54. GST owed: ~AUD $5.40. For AU sales <AUD $75K/year: no GST registration required. Above AUD $75K: must register, collect, and remit. Year 1: almost certainly below threshold. | $14-$18 per package. Charge: $16.99 flat rate. | 2-4% of orders. | Shopify → Settings → Shipping → Add zone: "Australia" → $16.99 flat rate. | Australia has a strong running culture (parkrun originated in Australia/UK). Small but enthusiastic market. | Australia Post may charge a handling fee for processing customs. Similar to Canada — set expectations in shipping FAQ.

## 7C.03-04 Tax + Margins
P7C TASKS 7C.03-04: INTERNATIONAL TAX SUMMARY + PER-ORDER PROFIT MARGIN TRACKER
Year 1 reality: most international tax obligations don't apply below $50K revenue. The margin tracker reveals which order types are profitable and which erode margins.
Element | Details | Threshold | Your Year 1 Action | When to Revisit | Monthly Tracking | Notes
7C.03: INTERNATIONAL TAX OBLIGATIONS — summary table (expanded from 7A.05)
US Sales Tax | Owe in home state + any state where you cross economic nexus. Shopify auto-calculates and collects. You remit quarterly. | Home state: $0 threshold (owe from first sale). Other states: $100K or 200 transactions. | Register in home state (done in 7A.05). Enable Shopify tax collection. File quarterly. Ignore other states until you approach $100K. | Every $25K in revenue: check if any state is approaching nexus threshold. | Track: Shopify → Analytics → Taxes → total collected by state. Remit quarterly. | Year 1 at <$50K: you likely owe only in your home state. This is simple — one quarterly filing.
EU VAT | EU VAT (19-25%) applies to ALL imports to the EU (no de minimis since July 2021). Below €10K annual EU sales: IOSS optional. Above €10K: IOSS required. | €10,000 annual EU sales for mandatory IOSS registration. | Year 1: skip IOSS. Ship DDU (customer pays VAT on delivery). If EU sales approach €10K: register for IOSS (free) and enable in Shopify. | When EU cumulative sales exceed €5K (halfway to threshold): begin IOSS registration process. | Track: Shopify → Analytics → Sales by country → sum all EU countries. When approaching €10K: act. | IOSS improves customer experience (no surprise delivery charges) but adds: monthly filing to one EU member state, collecting VAT at checkout, remitting monthly. Manageable but not zero-effort.
UK VAT | UK VAT (20%) applies to imports. Below £85K annual UK sales: no registration required. Above £85K: must register, collect, and remit. | £85,000 annual UK sales (~$107K). Extremely unlikely in Year 1. | Year 1: no action. Ship DDU. UK customers pay VAT on delivery for orders >£135. Most StrideHer orders (~£28) = below threshold = typically duty-free. | When UK cumulative sales exceed £40K: begin VAT registration process. | Track: Shopify → Sales by country → "United Kingdom" total. | UK VAT registration is only needed at scale. Focus on US + EU first.
AU GST | Australia GST (10%) on ALL imports. Below AUD $75K annual AU sales: no registration required. | AUD $75,000 annual AU sales (~$48K USD). Very unlikely in Year 1. | Year 1: no action. Australian customers pay GST + handling on delivery. | When AU sales exceed AUD $30K: begin planning. | Track: Shopify → Sales by country → "Australia" total.
Canada GST/HST | Canada GST/HST (5-15%) on imports. Below CAD $30K annual CA sales: no registration required. | CAD $30,000 annual CA sales (~$22K USD). | Year 1: likely no action. Monitor if Canada becomes a significant market. | When CA sales exceed CAD $15K. | Track: Shopify → Sales by country → "Canada" total. | Canada has lower threshold than UK/AU — monitor if Canadian sales grow fast.
7C.04: PER-ORDER PROFIT MARGIN TRACKER — know your ACTUAL margin on every order type
Margin Tracker Template | Track actual margins by ORDER TYPE — because not all orders are equally profitable: Full-price US order: highest margin (~57%) Discounted US order (WELCOME10): ~50% Ambassador-referred order (15% off): ~45% Founding member order (HERSTRIDE20): ~43% International order (UK, $14.99 shipping charged): varies by whether shipping covers cost Free shipping international promo: LOWEST margin — may be negative Monthly: export Shopify orders → calculate actual margin per order → average by type → compare to 7B.01 model. | Model contribution margin: $17.48 (50.0%) per 7B.01. | Monthly: export Shopify orders CSV → add columns: discount applied, shipping cost (actual), COGS, packaging, processing fee → calculate: margin = revenue - discount - COGS - shipping - packaging - processing. SIMPLIFIED: Shopify → Analytics → "Net sales" minus "Cost of goods" (if COGS is entered in Shopify) = gross profit. Divide by orders = margin/order. | Monthly review (part of 7B.04 financial review). | KEY METRICS: • Overall blended margin: target 48-55% • Full-price domestic margin: target 55-60% • Discounted domestic margin: target 45-50% • International margin: target 30-45% If blended margin <45%: too many discounts active OR shipping costs higher than modeled. If international margin <20%: international shipping is underpriced — either raise international rate or reduce free international shipping offers. | The margin tracker is the TRUTH behind vanity metrics. "We sold 100 units this month!" means nothing without: "...at an average margin of 52%, generating $1,817 in contribution profit." Revenue without margin is just money passing through your hands.
Margin Erosion Red Flags | Watch for these patterns that ERODE margin over time: 1. DISCOUNT CREEP: too many active discount codes (WELCOME10 + PARKRUN15 + ambassador codes + SAVE10 cart abandoner + seasonal sales). If >60% of orders use a discount: your effective price is $29.99, not $34.99. Solution: limit active codes to 3 at any time. 2. SHIPPING COST INCREASE: USPS rate increases (annual, typically Jan/Feb). A $0.50/package increase on 100 orders/month = $50/month margin erosion. Solution: renegotiate or absorb. 3. RETURN RATE CREEP: returns cost double (outbound shipping wasted + return shipping + restocking). If return rate >5%: the sizing guide or product description needs fixing. 4. INTERNATIONAL MIX SHIFT: as international orders grow, if they carry lower margins (higher shipping, lower effective price), blended margin decreases. Solution: ensure international shipping rates cover costs. 5. AMBASSADOR COMMISSION GROWTH: 10 ambassadors at 20% commission on $5K/month = $1,000 in commissions. Monitor: is the commission-driven revenue NET positive after commissions? | Blended margin declining 2+ months in a row = red flag. Diagnose immediately. | For each red flag: 1. Discount creep → audit all active codes in Shopify Discounts. Deactivate any that aren't driving measurable incremental revenue. 2. Shipping increase → compare Shopify Shipping rates to pirateship.com rates. Switch if cheaper. 3. Returns → analyze return reasons. Top reason = sizing → improve guide. Top reason = "not what I expected" → improve product photos. 4. International mix → calculate margin per market. If UK margin <25%: raise UK shipping rate by $2. 5. Ambassador commissions → if total commission > 25% of ambassador-referred revenue: the program is too expensive. Reduce commission to 15%. | Monthly margin review catches trends before they compound. |  | The goal: maintain 48-55% blended contribution margin through Year 1. Below 45%: the business model is stressed. Above 55%: you have room to invest more aggressively in growth (ads, content, events).

## 7C FOUNDER ACTIONS
P7C PAYMENT & INTERNATIONAL — FOUNDER ACTION CHECKLIST
Configure payments + international shipping in Week 4-5. Margin tracking starts Month 1. International tax monitoring starts Month 3.
Priority | Action | Time | Cost | Step-by-Step Instructions | Done?
WEEK 4-5: PAYMENT + SHIPPING CONFIGURATION
🔴 #1 | Verify Shopify Payments multi-currency + enable PayPal | 30 min | $0 | 1. Shopify → Settings → Payments → verify Shopify Payments active with all card types + Apple Pay + Google Pay + Shop Pay 2. Settings → Markets → add: United Kingdom, Canada, European Union, Australia → enable local currency display for each 3. Connect PayPal: Settings → Payments → PayPal → Connect → sign in to PayPal Business account (create one at paypal.com if needed) 4. Test: browse strideher.com with VPN set to UK → verify prices show in £GBP. Switch to Germany → verify €EUR. 5. Place a test order with PayPal → verify PayPal option appears at checkout and processes correctly.
🔴 #2 | Configure international shipping rates for 5 priority markets | 30 min | $0 | 1. Shopify → Settings → Shipping and delivery → Add shipping zone: "United Kingdom" → flat rate $14.99 2. Add zone: "Canada" → flat rate $12.99 3. Add zone: "European Union" (select all 27 EU countries) → flat rate $16.99 4. Add zone: "Australia" → flat rate $16.99 5. Add zone: "Rest of World" → flat rate $19.99 (or disable if you don't want to ship everywhere initially) 6. Verify: all zones have correct HS code for customs: 4202.92 7. Add shipping FAQ to your Shopify pages: estimated delivery times per destination, customs responsibility note for international orders
🟡 #3 | Set up Wise account for supplier payments | 15 min | $0 | 1. wise.com → Sign Up → Business account (use LLC name + EIN) 2. Connect funding source: your business bank account (Mercury/Relay/Novo) 3. Test: create a small transfer ($10) to verify connection works 4. Bookmark for future use: every production PO payment goes through Wise (saves 2-4% FX vs bank wires)
MONTH 1+: ONGOING TRACKING
🟡 #4 | Set up monthly margin tracking per Sheet 7C.03-04 | 30 min/month | $0 | Monthly (integrate with 7B.04 financial review): 1. Shopify → Analytics → export orders CSV for the month 2. In Google Sheets: add columns for each cost component (COGS $6, shipping $4.50 domestic / $15 international, packaging $1.25, processing 2.9%+$0.30) 3. Calculate margin per order → average by order type (full price domestic, discounted domestic, international) 4. Compare blended margin to 7B.01 target (50%) 5. Check for red flags from Sheet 7C.03-04 (discount creep, shipping cost increases, return rate, international mix) 6. If blended margin <45% for 2 consecutive months: diagnose and act immediately
🟢 #5 | Monitor international tax thresholds quarterly | 15 min/quarter | $0 | Every quarter: Shopify → Analytics → Sales by Country. Check: EU cumulative total (threshold: €10K). UK total (threshold: £85K). CA total (threshold: CAD $30K). AU total (threshold: AUD $75K). If any market is at 50% of threshold: begin registration research. If any market is at 75% of threshold: complete registration before crossing. Year 1 reality: almost certainly below all thresholds. This is a 15-minute quarterly check that prevents surprise obligations.