## DASHBOARD
D2C RUNNING BELT BRAND — GTM MASTER TRACKER
Complete Launch Playbook ¦ March 2026 ¦ Target: $29–39 DTC ¦ Alibaba Mfg ¦ Global D2C ¦ $10K Bootstrap Budget
Project | Description | Duration | Subprojects | Total Tasks | Completed | % Complete | Status | Budget ($10K) | Critical Path? | Dependencies
P0 | Market Research & Concept Validation | Wk 1–6 | 7 | 42 | 0 | 0% | Not Started | $700 | YES | —
P1 | Brand Development & Identity | Wk 4–8 | 5 | 28 | 0 | 0% | Not Started | $600 | YES | P0
P2 | Product Design & Engineering | Wk 4–10 | 5 | 27 | 0 | 0% | Not Started | $400 | YES | P0
P3 | Manufacturing & First Production Run | Wk 8–14 | 4 | 22 | 0 | 0% | Not Started | $3,500 | YES | P2
P4 | Digital Infrastructure & E-Commerce | Wk 6–12 | 5 | 28 | 0 | 0% | Not Started | $500 | YES | P1
P5 | Content, Community & Influencer Marketing | Wk 8–20 | 5 | 26 | 0 | 0% | Not Started | $600 | NO | P1, P3
P6 | Launch Execution & Paid Acquisition | Wk 12–20 | 5 | 25 | 0 | 0% | Not Started | $1,500 | YES | P3, P4, P5
P7 | Financial Operations & Cash Flow | Wk 1–Ongoing | 4 | 18 | 0 | 0% | Not Started | $200 | YES | —
P8 | Legal, Compliance & IP Protection | Wk 1–10 | 4 | 16 | 0 | 0% | Not Started | $600 | YES | —
P9 | Customer Experience & Retention | Wk 12–Ongoing | 4 | 18 | 0 | 0% | Not Started | $100 | NO | P4, P6
P10 | Supply Chain & Fulfillment | Wk 10–Ongoing | 4 | 16 | 0 | 0% | Not Started | $400 | NO | P3
P11 | Growth & Scaling Roadmap | Mo 6–18 | 4 | 18 | 0 | 0% | Not Started | $800+ | NO | P6
P12 | Sustainability & Brand Purpose | Wk 4–Ongoing | 3 | 12 | 0 | 0% | Not Started | $100 | NO | P0, P1
TOTAL |  |  | 59 | 296 | 0 | 0% |  | $10,000

## P0
P0: MARKET RESEARCH & CONCEPT VALIDATION ¦ Weeks 1–6 ¦ 7 Subprojects ¦ 42 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
0A: Running Belt Competitive Intelligence (Wk 1–2) — 8 tasks
0A.01 | 0A | Map all running belt products across 4 pricing tiers: Budget (<$20), Value ($20–35), Mid ($35–55), Premium ($55+) | Founder | Wk 1 | Critical | Not Started | Products mapped with full specs | 25+ products across all tiers |  | 0% | Cover: FlipBelt, SPIbelt, Naked, Nathan, Fitletic, Lululemon, Salomon, CamelBak, generic Amazon brands. 15+ data points per product. | Competitive database
0A.02 | 0A | Purchase top 5 competitor products (FlipBelt Classic, SPIbelt Original, Naked Running Band, Nathan Zipster, Fitletic Bolt) for hands-on testing | Founder | Wk 1 | Critical | Not Started | Products received and tested | 5 competitor products purchased |  | 0% | Budget: ~$200. Run 5+ miles in each. Document bounce, comfort, capacity, sweat, access, durability. | Competitor test report
0A.03 | 0A | Analyze Amazon reviews for top 5 competitors: extract top 10 complaints and top 10 praise points for each | Founder | Wk 1–2 | High | Not Started | Review analysis complete | 250+ reviews analyzed per product |  | 0% | Use 1-star and 5-star reviews. Key themes: bounce, sizing, chafing, phone fit, zipper quality, sweat-through. | Review analysis doc
0A.04 | 0A | Map competitor pricing strategies: MSRP, sale frequency, Amazon vs D2C pricing, bundle offers, subscription models | Founder | Wk 1–2 | High | Not Started | Pricing matrix complete | All 5 tiers mapped |  | 0% | Track: FlipBelt ($28–65), SPIbelt ($20–39), Naked ($50–95), Nathan ($20–50), Fitletic ($15–80). | Pricing matrix
0A.05 | 0A | Identify and document 3 specific unmet needs / market gaps from competitor analysis | Founder | Wk 2 | Critical | Not Started | Gap analysis documented | 3+ validated gaps identified |  | 0% | Known gaps: sustainability-first brand, women-specific design, smart tech integration, adjustable + high-capacity combo. | Gap analysis
0A.06 | 0A | Analyze competitor SEO: top 20 keywords each for FlipBelt, SPIbelt, Naked using Ubersuggest/free SEMrush | Founder | Wk 2 | Medium | Not Started | SEO audit complete | 60+ keywords mapped |  | 0% | Focus on: search volume, difficulty, CPC. Identify low-competition long-tail opportunities. | SEO keyword map
0A.07 | 0A | Document competitor social media strategy: posting frequency, content types, engagement rates, follower counts | Founder | Wk 2 | Medium | Not Started | Social audit complete | 5 brands audited |  | 0% | FlipBelt ~32K IG, SPIbelt ~46K IG, Naked ~18K IG, Nathan ~73K IG, Fitletic ~5K IG. | Social media audit
0A.08 | 0A | Map competitor distribution channels: D2C site, Amazon, REI, Dick's, specialty running stores, international | Founder | Wk 2 | Medium | Not Started | Channel map complete | All channels mapped per brand |  | 0% | Key insight: Naked avoids Amazon entirely (premium control). FlipBelt dominates Amazon (18K+ reviews). | Distribution map
0B: Target Customer Research (Wk 1–3) — 7 tasks
0B.01 | 0B | Define 3 primary customer personas: Casual Jogger, Serious Racer, Ultra/Trail Runner with demographics and psychographics | Founder | Wk 1–2 | High | Not Started | Personas documented | 3 detailed personas |  | 0% | Include: age, gender, income, running frequency, gear spend, media consumption, purchase triggers. | Persona document
0B.02 | 0B | Join 5+ running communities (r/running, r/trailrunning, Strava clubs, FB groups) and lurk/document pain points for 2 weeks | Founder | Wk 1–3 | High | Not Started | Community insights documented | 50+ pain points collected |  | 0% | Search terms: "running belt recommendation", "phone while running", "best running belt". Screenshot and categorize. | Community research doc
0B.03 | 0B | Create and distribute a 10-question Google Forms survey to 3+ running groups/forums | Founder | Wk 2 | High | Not Started | Survey distributed | 100+ responses |  | 0% | Questions: current belt brand, price paid, #1 complaint, ideal features, willingness to pay, purchase channel preference. | Survey + results
0B.04 | 0B | Conduct 5 phone/video interviews with runners of varying levels (5K to ultra) about their belt/carrying frustrations | Founder | Wk 2–3 | High | Not Started | Interviews completed | 5 interviews (30 min each) |  | 0% | Recruit from local running club or Reddit. Record with permission. Focus on unmet needs. | Interview transcripts
0B.05 | 0B | Analyze Google Trends for "running belt", "running fanny pack", "phone holder running" — identify seasonality and growth | Founder | Wk 2 | Medium | Not Started | Trends analysis complete | 5+ search terms analyzed |  | 0% | Peak months: Jan (resolutions), Mar-May (spring races), Aug-Sep (fall training). Compare 5yr trend. | Trends report
0B.06 | 0B | Research running participation statistics: US runners, global runners, marathon finishers, trail running growth | Founder | Wk 2 | Medium | Not Started | Market sizing data collected | TAM/SAM/SOM estimated |  | 0% | 50M+ US runners, 14.8M trail runners (12% YoY growth), marathon finishers up 26% in H1 2024. | Market size doc
0B.07 | 0B | Identify which customer segment to target FIRST based on research (recommended: women marathoners or eco-conscious runners) | Founder | Wk 3 | Critical | Not Started | Primary segment selected | 1 segment chosen with rationale |  | 0% | Must be specific enough to own, large enough to sustain. Avoid "all runners" — that's not a niche. | Segment decision doc
0C: Product Concept Development (Wk 2–4) — 6 tasks
0C.01 | 0C | Define the ONE core differentiator for your belt based on gap analysis (e.g., eco-first, women-specific, adjustable+capacity) | Founder | Wk 2–3 | Critical | Not Started | Differentiator documented | 1 clear USP statement |  | 0% | Test: "We are the ONLY running belt that ___." If you can't complete this, keep refining. | USP statement
0C.02 | 0C | Create initial product spec sheet: material, dimensions, pockets, closure, sizing system, weight target, color options | Founder | Wk 3 | High | Not Started | Spec sheet created | Full spec documented |  | 0% | Benchmark: FlipBelt=tube/spandex, SPIbelt=expandable/nylon, Naked=mesh/12sizes. Where do you innovate? | Product spec v1
0C.03 | 0C | Sketch 3–5 rough product concepts (hand-drawn or Canva) showing key design features | Founder | Wk 3 | High | Not Started | Concepts sketched | 3–5 concepts |  | 0% | Focus on: pocket layout, closure mechanism, sizing approach, material zones, reflective elements. | Concept sketches
0C.04 | 0C | Define target price point and work backwards to required COGS (target 70%+ gross margin at $29–39 retail) | Founder | Wk 3–4 | Critical | Not Started | Price/margin model built | Retail price + target COGS |  | 0% | At $35 retail, need COGS <$10.50 for 70% margin. Alibaba belts: $3–8/unit at 200–500 MOQ. | Pricing model
0C.05 | 0C | Test product concept with 10 runner friends: show sketches, describe features, ask willingness to pay | Founder | Wk 4 | High | Not Started | Concept feedback collected | 10+ people tested |  | 0% | Use "would you buy this at $X?" not "do you like it?" — purchase intent is what matters. | Concept test results
0C.06 | 0C | Finalize v1 product concept based on all research — create a 1-page product brief | Founder | Wk 4 | Critical | Not Started | Product brief finalized | 1-page brief approved |  | 0% | Brief covers: target customer, USP, specs, price, positioning vs competitors, launch channel. | Product brief v1
0D: Alibaba Supplier Scouting (Wk 3–5) — 6 tasks
0D.01 | 0D | Search Alibaba for "running belt manufacturer" — identify and shortlist 15+ suppliers with Gold Supplier status and Trade Assurance | Founder | Wk 3 | High | Not Started | Supplier longlist created | 15+ suppliers identified |  | 0% | 3,759+ running belt suppliers on Alibaba. Filter: Gold Supplier, Trade Assurance, 3+ years, reviews. | Supplier longlist
0D.02 | 0D | Send RFQ (Request for Quote) to top 10 suppliers with your product spec sheet and ask: MOQ, unit price at 200/500/1000, sample cost, lead time | Founder | Wk 3–4 | High | Not Started | RFQs sent | 10 RFQs sent |  | 0% | Include: product specs, material preferences, desired features. Ask for their product catalog too. | RFQ tracker
0D.03 | 0D | Compare all supplier responses: price, MOQ, sample cost, lead time, communication quality, portfolio quality | Founder | Wk 4 | High | Not Started | Comparison matrix complete | All responses compared |  | 0% | Red flags: no Trade Assurance, won't send samples, MOQ >500, no custom capability, poor English. | Supplier comparison matrix
0D.04 | 0D | Order 3–5 samples from top 3 suppliers ($50–150 total including shipping) | Founder | Wk 4–5 | Critical | Not Started | Samples ordered | 3–5 samples from 3 suppliers |  | 0% | Sample cost typically $5–20/unit + $20–50 shipping. Some suppliers offer free samples (you pay shipping). | Sample order confirmation
0D.05 | 0D | Test all samples: run 5+ miles in each, wash 3 times, stress-test zippers/seams, measure against spec | Founder | Wk 5 | Critical | Not Started | Sample testing complete | All samples tested |  | 0% | Grade each on: material quality, stitching, bounce, comfort, capacity, durability, phone fit. | Sample test report
0D.06 | 0D | Select primary supplier and negotiate final terms: price, MOQ, payment terms, customization options | Founder | Wk 5 | Critical | Not Started | Supplier selected | 1 primary + 1 backup supplier |  | 0% | Negotiate: 30% deposit / 70% before shipping. Ask for better price at 500 units. Get written agreement. | Supplier agreement
0E: Financial Feasibility (Wk 3–5) — 5 tasks
0E.01 | 0E | Build unit economics model: COGS + shipping + packaging + transaction fees + marketing CAC = contribution margin | Founder | Wk 3–4 | Critical | Not Started | Unit economics modeled | Positive contribution margin |  | 0% | Target: COGS $5–8, packaging $1–2, shipping $4–6, Shopify+payment 5%, CAC <$15. Need >$10 contribution. | Unit economics model
0E.02 | 0E | Build 6-month cash flow projection with $10K starting capital — week by week | Founder | Wk 4 | High | Not Started | Cash flow model built | 6 months projected |  | 0% | Key constraint: timing of inventory purchase vs revenue. First inventory purchase is largest cash outflow. | Cash flow model
0E.03 | 0E | Calculate breakeven: units needed to recover $10K investment at projected margins | Founder | Wk 4 | High | Not Started | Breakeven calculated | Breakeven unit count known |  | 0% | At $35 price, 70% margin = $24.50 gross profit. $10K / $24.50 = ~408 units to breakeven (before CAC). | Breakeven analysis
0E.04 | 0E | Define budget allocation across all projects: product (40%), marketing (20%), ops (15%), contingency (25%) | Founder | Wk 4 | High | Not Started | Budget allocated | $10K fully allocated |  | 0% | Product: $4,000 ¦ Marketing: $2,000 ¦ Ops/tech: $1,500 ¦ Contingency: $2,500. | Budget allocation
0E.05 | 0E | Set 6-month revenue targets: Month 1 (launch), Month 3, Month 6 with conservative/moderate/aggressive scenarios | Founder | Wk 5 | Medium | Not Started | Revenue targets set | 3 scenarios modeled |  | 0% | Conservative: 50 units/mo by M6. Moderate: 100/mo. Aggressive: 200/mo. | Revenue targets
0F: Niche Validation & Positioning (Wk 4–6) — 5 tasks
0F.01 | 0F | Write 3 alternative positioning statements and test with 10+ runners: eco belt, women's belt, ultra-slim belt, smart belt | Founder | Wk 4 | High | Not Started | Positioning tested | 3 positions tested with 10+ people |  | 0% | Format: "For [target], [brand] is the [category] that [key benefit] because [reason to believe]." | Positioning test results
0F.02 | 0F | Validate chosen niche has sufficient search volume: target 5,000+ monthly searches for core keyword cluster | Founder | Wk 4–5 | High | Not Started | Search volume validated | 5,000+ monthly searches |  | 0% | "running belt" = 40K+/mo. "women's running belt" = 3K+. "eco running belt" = low. Adjust niche accordingly. | Search validation
0F.03 | 0F | Identify 5 potential brand names and check domain availability, trademark conflicts (USPTO TESS), and social handle availability | Founder | Wk 5 | High | Not Started | Name candidates vetted | 5 names checked |  | 0% | Check: .com domain, @handle on IG/TikTok/X, USPTO TESS search, Amazon brand search. | Name availability matrix
0F.04 | 0F | Create a simple landing page (Carrd.co, $19/yr) with product concept + email signup to test interest pre-launch | Founder | Wk 5–6 | High | Not Started | Landing page live | Page live with email capture |  | 0% | Drive traffic via Reddit posts, running forum posts, social media. Goal: 100+ signups in 2 weeks. | Landing page URL
0F.05 | 0F | Analyze landing page signup rate and early feedback to validate or pivot concept before production | Founder | Wk 6 | Critical | Not Started | Validation decision made | Go / No-Go / Pivot decided |  | 0% | >5% signup rate = strong signal. 2–5% = decent. <2% = rethink positioning or product. | Go/No-Go decision
0G: Competitive Intelligence Deep Dives (Wk 2–4) — 5 tasks
0G.01 | 0G | Reverse-engineer Naked Running Band's success: 12-size system, Exopower mesh, athlete roster, no-Amazon strategy | Founder | Wk 2–3 | Medium | Not Started | Naked case study complete | Full strategy documented |  | 0% | Key insight: Naked proves premium ($55+) works with elite athlete validation + specialty retail. | Naked case study
0G.02 | 0G | Reverse-engineer FlipBelt's Amazon dominance: listing optimization, review strategy, pricing, PPC approach | Founder | Wk 2–3 | Medium | Not Started | FlipBelt case study complete | Amazon strategy documented |  | 0% | 18K+ reviews, 4.6 stars. Study: title, bullets, images, A+ content, pricing vs MAP, review velocity. | FlipBelt case study
0G.03 | 0G | Reverse-engineer SPIbelt's bootstrap journey: $150K→$7M in 3 years, marathon expo strategy, medical niche expansion | Founder | Wk 3 | Medium | Not Started | SPIbelt case study complete | Growth playbook documented |  | 0% | Key lesson: started at Austin Marathon expo. Medical belt niche = unique moat. Woman-founded story resonates. | SPIbelt case study
0G.04 | 0G | Study Gymshark and Tracksmith D2C playbooks: influencer seeding, community building, content strategy at bootstrap stage | Founder | Wk 3–4 | Medium | Not Started | D2C case studies complete | 2 case studies documented |  | 0% | Gymshark: micro-influencer seeding from garage. Tracksmith: 280% growth via community + content + premium positioning. | D2C playbook doc
0G.05 | 0G | Audit top 10 Amazon "running belt" listings: price, reviews, images, bullet points, search rank, estimated monthly sales | Founder | Wk 3–4 | Medium | Not Started | Amazon audit complete | 10 listings audited |  | 0% | Generic brands like MAXTOP sell 31K+ units/mo at <$20. Note: volume ≠ brand. Study review complaints for opportunity. | Amazon audit

## P1
P1: BRAND DEVELOPMENT & IDENTITY ¦ Weeks 4–8 ¦ 5 Subprojects ¦ 28 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
1A: Brand Naming & Trademark (Wk 4–6) — 6 tasks
1A.01 | 1A | Brainstorm 25+ brand name candidates: consider run, stride, carry, light, free, naked-inspired, eco, trail themes | Founder | Wk 4 | High | Not Started | Name candidates generated | 25+ options |  | 0% | Test: memorable, easy to spell, available .com, works internationally, not too close to competitors. | Name brainstorm list
1A.02 | 1A | Shortlist to top 5 names and test with 15+ runners for memorability, pronunciation, brand associations | Founder | Wk 4–5 | High | Not Started | Names tested | 15+ people surveyed |  | 0% | Ask: "What product do you think this brand sells?" and "Would you trust this brand?" | Name test results
1A.03 | 1A | Verify top 3 names: .com domain available, IG/TikTok handles free, no USPTO trademark conflicts (Class 028 sporting goods) | Founder | Wk 5 | Critical | Not Started | All checks passed | Top 3 fully verified |  | 0% | USPTO TESS: free search. Domain: Namecheap/GoDaddy. Social: direct search on each platform. | Verification matrix
1A.04 | 1A | Select final brand name and register domain (.com mandatory, consider .co and country-specific) | Founder | Wk 5 | Critical | Not Started | Domain registered | .com secured |  | 0% | Budget: $10–15/year for .com. Also register social handles immediately on IG, TikTok, X, Facebook. | Domain registration
1A.05 | 1A | File USPTO trademark application (Class 028) — can self-file for $250–350 via TEAS Plus | Founder | Wk 5–6 | High | Not Started | TM application filed | Filing confirmation received |  | 0% | TEAS Plus = $250/class. Use ™ symbol immediately; ® only after registration (~8–12 months). | TM filing confirmation
1A.06 | 1A | Register matching social media handles on Instagram, TikTok, X/Twitter, Facebook, YouTube, Pinterest | Founder | Wk 5 | High | Not Started | All handles secured | 6+ platforms registered |  | 0% | Even if you won't use all platforms immediately — reserve the handles before someone else does. | Handle registration list
1B: Visual Identity & Logo (Wk 5–7) — 6 tasks
1B.01 | 1B | Create mood board: collect 20+ visual references from brands you admire (running + non-running) | Founder | Wk 5 | High | Not Started | Mood board complete | 20+ references collected |  | 0% | Pinterest board or Canva. Study: Tracksmith (heritage), Janji (adventure), Satisfy (counter-culture), On (minimal). | Mood board
1B.02 | 1B | Define brand color palette: primary color, secondary, accent, neutral. Max 4 colors + black/white | Founder | Wk 5 | High | Not Started | Colors selected | 4-color palette defined |  | 0% | Use Coolors.co (free). Avoid: competitor colors (FlipBelt=orange, SPIbelt=red/teal, Naked=dark blue). | Color palette
1B.03 | 1B | Design logo via Canva Pro ($13/mo), 99designs ($299 contest), or Fiverr ($50–200) | Founder | Wk 5–6 | High | Not Started | Logo designed | Final logo approved |  | 0% | Need: primary logo, icon mark, wordmark, all-white version. Must work at 16px (favicon) and on dark/light. | Logo files (SVG, PNG)
1B.04 | 1B | Select brand typography: 1 heading font + 1 body font (Google Fonts = free for web and print) | Founder | Wk 6 | Medium | Not Started | Typography selected | 2 fonts chosen |  | 0% | Sans-serif is safest for athletic brands. Popular: Inter, Montserrat, DM Sans, Plus Jakarta Sans. | Typography guide
1B.05 | 1B | Create simple brand guidelines document: logo usage, colors with hex codes, typography, tone of voice, imagery style | Founder | Wk 6–7 | Medium | Not Started | Brand guide created | 1 document covering all elements |  | 0% | Keep it to 3–5 pages. This ensures consistency across all touchpoints as you scale. | Brand guidelines PDF
1B.06 | 1B | Design product packaging: branded poly mailer, hang tag, size/care label, insert card with QR code for reviews | Founder | Wk 7 | High | Not Started | Packaging designed | All packaging elements designed |  | 0% | Budget: Custom poly mailers ($0.15–0.30/ea at 500+), hang tags ($0.05–0.10), insert cards ($0.03–0.05). | Packaging design files
1C: Brand Story & Messaging (Wk 5–7) — 6 tasks
1C.01 | 1C | Write founder story: why you created this brand, what problem you're solving, your personal running journey | Founder | Wk 5 | High | Not Started | Founder story written | 300–500 word story |  | 0% | Every successful brand in this space (SPIbelt, FlipBelt, Naked) was founded by a runner solving their own problem. | Founder story
1C.02 | 1C | Craft brand tagline (3–6 words): test 5+ options with runners | Founder | Wk 5–6 | High | Not Started | Tagline selected | Final tagline chosen |  | 0% | Competitors: Naked="Run. Free." SPIbelt="The Original Running Belt." FlipBelt="Never Slow Down." | Tagline
1C.03 | 1C | Write positioning statement: For [target], [brand] is the [category] that [benefit] because [reason to believe] | Founder | Wk 6 | Critical | Not Started | Positioning statement finalized | 1 clear statement |  | 0% | This drives ALL marketing decisions. Post it above your desk. | Positioning statement
1C.04 | 1C | Write product description copy: 3 versions (short 50 words, medium 150 words, long 400 words) for different channels | Founder | Wk 6 | High | Not Started | Product copy written | 3 lengths of copy |  | 0% | Focus on benefits (not features). "Runs so light you forget it's there" > "Made from 4-way stretch mesh." | Product copy doc
1C.05 | 1C | Define brand voice guidelines: tone (confident/friendly/expert), vocabulary, do's and don'ts | Founder | Wk 6 | Medium | Not Started | Voice guidelines documented | Guidelines complete |  | 0% | Running brands that succeed: authentic, knowledgeable, community-first, not salesy. Think friend who knows gear. | Voice guidelines
1C.06 | 1C | Write "About Us" page copy, FAQ content (15+ questions), and email welcome series copy (3 emails) | Founder | Wk 7 | Medium | Not Started | Website copy written | All copy complete |  | 0% | FAQ must cover: sizing, returns, materials, care instructions, shipping, vs competitors. | Website copy doc
1D: Brand Photography & Visual Assets (Wk 6–8) — 5 tasks
1D.01 | 1D | Plan product photography shoot: 10+ flat-lay shots, 5+ on-model running shots, 3+ lifestyle/context shots | Founder | Wk 6 | High | Not Started | Shot list planned | 18+ shots planned |  | 0% | DIY setup: iPhone 12+, natural window light, white foam board ($5), clean background. Total cost: <$20. | Photography shot list
1D.02 | 1D | Shoot all product photos: white background product shots (front, back, detail, capacity demo, phone-in-pocket) | Founder | Wk 7 | Critical | Not Started | Product photos shot | 10+ product shots |  | 0% | Must show: the belt worn, items fitting inside, phone visibility, size on different body types. | Product photo set
1D.03 | 1D | Shoot lifestyle/running photos: action shots of runner wearing belt outdoors in 3+ settings (road, trail, urban) | Founder | Wk 7 | High | Not Started | Lifestyle photos shot | 5+ action shots |  | 0% | Ask a running friend to model. Early morning or golden hour light. Show the product in real use context. | Lifestyle photo set
1D.04 | 1D | Edit all photos: color correction, background removal for product shots, crop for web and social formats | Founder | Wk 7–8 | High | Not Started | Photos edited | All photos export-ready |  | 0% | Use Canva (free) or remove.bg for background removal. Export: 2000x2000 for Shopify, 1080x1080 for IG. | Edited photo library
1D.05 | 1D | Create 3 short product demo videos (15–30 sec each): capacity test, bounce test, "what fits inside" unboxing | Founder | Wk 7–8 | High | Not Started | Demo videos created | 3 videos ready |  | 0% | Shoot on iPhone, vertical format (9:16) for TikTok/Reels. These are your #1 conversion asset. | Video assets
1E: Pre-Launch Community Building (Wk 5–8) — 5 tasks
1E.01 | 1E | Set up Instagram and TikTok accounts with brand identity, bio, link-in-bio to landing page/waitlist | Founder | Wk 5 | High | Not Started | Accounts live | Both platforms active |  | 0% | Bio formula: [What you are] ¦ [For whom] ¦ [USP] ¦ [CTA link]. Use Linktree or Beacons for link-in-bio. | Social accounts
1E.02 | 1E | Create content calendar: 3–4 posts/week for weeks 5–8 covering behind-the-scenes, product development, running tips | Founder | Wk 5 | High | Not Started | Content calendar created | 4 weeks planned |  | 0% | Content pillars: 1) Behind-the-scenes journey, 2) Running tips/education, 3) Product teasers, 4) Community reposts. | Content calendar
1E.03 | 1E | Post daily on TikTok for 30 days: running belt comparisons, "day in the life" building a brand, running content | Founder | Wk 5–8 | High | Not Started | Posting streak maintained | 30 posts in 30 days |  | 0% | TikTok rewards consistency. Even 200 views/video builds algorithm trust. Aim for 1 viral hit. | Content archive
1E.04 | 1E | Engage authentically in 5+ running subreddits and Facebook groups (contribute value, don't just promote) | Founder | Wk 5–8 | Medium | Not Started | Community engagement active | 20+ valuable contributions |  | 0% | Rule: 10 helpful comments for every 1 mention of your brand. Build reputation first. | Engagement log
1E.05 | 1E | Grow pre-launch email waitlist to 200+ subscribers via landing page, social, and community engagement | Founder | Wk 5–8 | High | Not Started | Waitlist growing | 200+ subscribers |  | 0% | Incentive: "Be first to know + founding member pricing." Each email subscriber is worth $5–15 in future revenue. | Waitlist count

## P2
P2: PRODUCT DESIGN & ENGINEERING ¦ Weeks 4–10 ¦ 5 Subprojects ¦ 27 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
2A: Product Architecture & Specifications (Wk 4–6) — 6 tasks
2A.01 | 2A | Define product architecture: tube-style (FlipBelt) vs. belt-with-pockets (SPIbelt) vs. band-style (Naked) vs. hybrid | Founder | Wk 4 | Critical | Not Started | Architecture decided | Decision documented with rationale |  | 0% | Each has tradeoffs: tube=seamless but sizing issues, belt=adjustable but bounces, band=minimal but capacity limits. | Architecture decision
2A.02 | 2A | Define sizing system: S/M/L/XL (simple, higher risk of poor fit) vs. measured waist sizes vs. adjustable (best for launch) | Founder | Wk 4–5 | Critical | Not Started | Sizing system chosen | System defined |  | 0% | Recommendation for launch: adjustable belt (like SPIbelt) = fewer SKUs, fewer returns, simpler inventory. | Sizing decision
2A.03 | 2A | Create detailed technical spec sheet for supplier: dimensions, materials, thread type, closure hardware, pocket count, reflective placement | Founder | Wk 5 | Critical | Not Started | Tech spec complete | Full spec with drawings |  | 0% | Include: 4-way stretch fabric, YKK zippers (#3 minimum), 3M reflective strips, adjustable buckle, phone window option. | Tech spec v1
2A.04 | 2A | Specify material requirements: main body fabric (nylon/spandex blend), lining (moisture-wicking mesh), elastic (LYCRA grade) | Founder | Wk 5 | High | Not Started | Materials specified | All materials defined with GSM/composition |  | 0% | Key: 4-way stretch nylon-spandex (80/20 blend, 200–280 GSM). Mesh lining for breathability. Anti-chafe binding. | Material spec
2A.05 | 2A | Design pocket layout: main phone pocket (must fit 6.7" phones with case), secondary zip pocket, gel/key loops | Founder | Wk 5–6 | High | Not Started | Pocket layout finalized | Layout accommodates all essentials |  | 0% | Test with: iPhone 16 Pro Max (6.7"), Samsung S24 Ultra (6.8"), plus case. #1 running belt complaint = phone doesn't fit. | Pocket layout drawing
2A.06 | 2A | Define color/pattern options for launch: start with 3–4 colors max (black mandatory, 1 bright, 1 neutral, 1 pattern) | Founder | Wk 6 | Medium | Not Started | Colors selected | 3–4 launch colors |  | 0% | Black is always #1 seller (50%+ of sales). Add 1 bold color for social media pop. Fewer colors = simpler inventory. | Color selection
2B: Prototyping & Sample Development (Wk 5–8) — 6 tasks
2B.01 | 2B | Send finalized tech spec to top 3 Alibaba suppliers for custom sample production | Founder | Wk 5 | Critical | Not Started | Spec sent to suppliers | 3 suppliers engaged |  | 0% | Include: tech drawings, material specs, color references (Pantone if possible), size range needed. | Supplier communications
2B.02 | 2B | Review and approve pre-production samples from each supplier (typical lead time: 7–14 days) | Founder | Wk 6–7 | Critical | Not Started | Samples received | 3+ custom samples in hand |  | 0% | Budget: $15–40 per custom sample + $25–50 shipping per supplier. Total: ~$150–250. | Sample photos + notes
2B.03 | 2B | Conduct rigorous testing on each sample: 10+ mile run test, wash/dry 5x, measure stretch recovery, zipper stress test | Founder | Wk 7 | Critical | Not Started | Testing protocol complete | All samples tested against spec |  | 0% | Create scoring rubric: comfort (1-10), bounce (1-10), capacity (1-10), durability (1-10), aesthetics (1-10). | Test scorecards
2B.04 | 2B | Give samples to 5 runners of different body types/sizes for 1-week field test with structured feedback form | Founder | Wk 7–8 | High | Not Started | Field testing complete | 5 testers, 5+ runs each |  | 0% | Feedback form: fit rating, bounce rating, comfort rating, what they stored, any issues, would they buy at $X? | Field test feedback
2B.05 | 2B | Document all needed modifications and send revision spec to selected supplier for v2 sample | Founder | Wk 8 | High | Not Started | Revision spec sent | All changes documented |  | 0% | Common revisions: pocket sizing, elastic tension, zipper placement, waistband width, reflective strip position. | Revision spec
2B.06 | 2B | Approve final production sample (PP sample) — this is the exact spec that will be manufactured | Founder | Wk 8–9 | Critical | Not Started | PP sample approved | Written approval sent to factory |  | 0% | DO NOT PROCEED to production without approving PP sample. Keep this sample as your quality reference. | PP sample approval
2C: Packaging & Unboxing Design (Wk 7–9) — 5 tasks
2C.01 | 2C | Design branded poly mailer or recyclable kraft mailer with logo print | Founder | Wk 7 | High | Not Started | Mailer designed | Design file ready for print |  | 0% | Recyclable packaging = brand differentiator if going eco route. Custom poly mailers: $0.15–0.30 at 500+. | Mailer design file
2C.02 | 2C | Design product hang tag with brand story, care instructions, and premium feel | Founder | Wk 7 | Medium | Not Started | Hang tag designed | Print-ready file |  | 0% | Include: brand tagline, 1 sentence story, care icons, website URL, social handles. Kraft paper = eco feel. | Hang tag file
2C.03 | 2C | Design insert card: thank you message + QR code to review page + 10% off next purchase code + social handles | Founder | Wk 7–8 | High | Not Started | Insert card designed | Print-ready file |  | 0% | This is your #1 tool for getting reviews. Make the CTA crystal clear. Budget: $0.03–0.05/card at 500+. | Insert card file
2C.04 | 2C | Source packaging suppliers: Alibaba (bulk), Sticker Mule (small qty), Packlane, or supplier-provided packaging | Founder | Wk 8 | Medium | Not Started | Packaging supplier selected | Quotes received from 3+ suppliers |  | 0% | Option: have your belt supplier include packaging in production (often cheaper). Ask for packaging samples. | Packaging quotes
2C.05 | 2C | Order packaging: 300+ poly mailers, 300+ hang tags, 500+ insert cards (order extra inserts for events) | Founder | Wk 8–9 | High | Not Started | Packaging ordered | Order confirmed |  | 0% | Total packaging budget: $100–200 for 300 units. Include in per-unit COGS calculation. | Packaging PO
2D: Size Guide & Product Documentation (Wk 8–9) — 5 tasks
2D.01 | 2D | Create detailed size guide with waist measurements, fit photos on 3+ body types, and "how to measure" instructions | Founder | Wk 8 | High | Not Started | Size guide created | Guide with photos |  | 0% | Size-related returns are the #1 cost killer for running belt brands. A great size guide saves thousands. | Size guide
2D.02 | 2D | Write care instructions: washing, drying, storage, zipper maintenance | Founder | Wk 8 | Medium | Not Started | Care instructions written | Instructions complete |  | 0% | Machine wash cold, air dry, no fabric softener, close zippers before washing. Simple icons + text. | Care card copy
2D.03 | 2D | Create "What Fits Inside" content: photograph belt holding phone, gels, keys, card, cash, earbuds | Founder | Wk 8–9 | High | Not Started | Capacity content created | Photo + video showing capacity |  | 0% | This content sells product. Show: iPhone Pro Max, 4 gels, car key, credit card, $20 bill, AirPods case. | Capacity photos/video
2D.04 | 2D | Create product comparison table: your belt vs FlipBelt vs SPIbelt vs Naked on 10+ attributes | Founder | Wk 9 | Medium | Not Started | Comparison table created | Fair comparison of 4+ belts |  | 0% | Attributes: price, weight, capacity, adjustable?, phone fits?, # pockets, material, bounce rating, eco-friendly? | Comparison table
2D.05 | 2D | Write product page copy: headline, subheadline, 5 bullet features, long description, social proof section | Founder | Wk 9 | High | Not Started | Product page copy finalized | All copy written |  | 0% | Study Naked Running Band and FlipBelt product pages for inspiration. Lead with benefits, not specs. | Product page copy
2E: Quality Standards & Testing Protocols (Wk 8–10) — 5 tasks
2E.01 | 2E | Define quality acceptance criteria: stitching standards, zipper pull force, elastic recovery %, color consistency | Founder | Wk 8 | High | Not Started | QA criteria documented | Written standards |  | 0% | Key checks: no loose threads, zipper opens/closes 1000x without failure, elastic retains 90%+ after 50 washes. | QA document
2E.02 | 2E | Create incoming quality inspection checklist for when production units arrive | Founder | Wk 8–9 | High | Not Started | Inspection checklist created | Checklist ready |  | 0% | Check 10% of units minimum on arrival: stitching, zippers, sizing accuracy, color matching, packaging. | QA checklist
2E.03 | 2E | Test production samples for skin safety: no harmful dyes, OEKO-TEX Standard 100 compliance if claiming eco-friendly | Founder | Wk 9 | Medium | Not Started | Safety testing passed | Lab results received |  | 0% | Ask supplier for existing test certificates. If claiming eco/sustainable, you need documentation to back it up. | Safety certificates
2E.04 | 2E | Define return/defect handling process: what constitutes a defect, replacement vs refund, communication templates | Founder | Wk 9 | Medium | Not Started | Defect policy documented | Process documented |  | 0% | Industry standard: <3% defect rate acceptable. Factory should replace defective units free. | Defect policy
2E.05 | 2E | Establish production quality agreement with supplier: defect rate tolerance, replacement terms, inspection rights | Founder | Wk 9–10 | High | Not Started | Quality agreement signed | Signed agreement |  | 0% | Put it in writing before placing production order. Cover: defect threshold, rework costs, delivery penalties. | Quality agreement

## P3
P3: MANUFACTURING & FIRST PRODUCTION RUN ¦ Weeks 8–14 ¦ 4 Subprojects ¦ 22 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
3A: Production Order & Payment (Wk 8–10) — 6 tasks
3A.01 | 3A | Finalize production quantity for first run: recommended 250–300 units across all sizes/colors | Founder | Wk 8 | Critical | Not Started | Quantity decided | 250–300 units |  | 0% | Don't over-order. 300 units at $6/ea = $1,800. Better to sell out and reorder than sit on $5K of inventory. | Production order qty
3A.02 | 3A | Determine size/color split based on market data: recommend 40% black, 25% color 2, 20% color 3, 15% color 4 | Founder | Wk 8 | High | Not Started | SKU split defined | Units allocated per SKU |  | 0% | If adjustable belt: fewer size SKUs needed. If fixed sizes: S(20%), M(35%), L(30%), XL(15%) is typical split. | SKU allocation
3A.03 | 3A | Negotiate final per-unit price with supplier: target $5–8/unit at 300 qty including custom branding | Founder | Wk 8–9 | High | Not Started | Price negotiated | Written price confirmation |  | 0% | Leverage: "We plan to reorder 500–1000 units within 3 months if quality is good." Suppliers value repeat business. | Price agreement
3A.04 | 3A | Arrange payment via Alibaba Trade Assurance (buyer protection): 30% deposit, 70% before shipping | Founder | Wk 9 | Critical | Not Started | Deposit paid | Payment confirmed |  | 0% | ALWAYS use Trade Assurance — it's Alibaba's escrow protection. Never wire money directly outside the platform. | Payment receipt
3A.05 | 3A | Confirm production timeline: typical 15–30 days for 300 units of a running belt | Founder | Wk 9 | High | Not Started | Timeline confirmed | Expected ship date known |  | 0% | Get written confirmation of production start date and estimated completion. Add 1 week buffer to your plan. | Production timeline
3A.06 | 3A | Request progress photos/video from factory at 25%, 50%, and 100% completion milestones | Founder | Wk 9–12 | Medium | Not Started | Progress updates received | 3 progress updates |  | 0% | Good factories will send photos proactively. If they resist, that's a warning sign. | Progress photos
3B: Quality Control & Inspection (Wk 12–13) — 6 tasks
3B.01 | 3B | Request pre-shipment photos of 10 random units from the completed batch | Founder | Wk 12 | High | Not Started | Photos received | 10 units photographed |  | 0% | Check: branding placement, color accuracy, stitching quality, zipper function, size labels. | Pre-ship photos
3B.02 | 3B | Option: hire third-party QC inspector via Alibaba Inspection Service ($100–300) for on-site factory check | Founder | Wk 12 | Medium | Not Started | Inspection decision made | Inspect or skip (document rationale) |  | 0% | Worth it for first order. Inspector checks random sample (AQL 2.5 standard) and sends detailed report. | Inspection report
3B.03 | 3B | Review and approve final production: confirm unit count, packaging, labeling accuracy | Founder | Wk 12 | Critical | Not Started | Production approved | Written shipping approval sent |  | 0% | Common issues: wrong size labels, color variance from sample, loose threads, zipper pulls missing. | Approval confirmation
3B.04 | 3B | Pay remaining 70% balance upon satisfactory inspection / pre-shipment approval | Founder | Wk 12 | Critical | Not Started | Final payment made | Payment confirmed |  | 0% | Only release final payment after you're satisfied with pre-shipment photos/inspection results. | Payment receipt
3B.05 | 3B | Confirm packing: units individually poly-bagged, size labeled, packed in export cartons with packing list | Founder | Wk 12 | Medium | Not Started | Packing confirmed | Packing spec met |  | 0% | Request: individual poly bags, size stickers, organized by color/size in cartons, total carton count + weight. | Packing confirmation
3B.06 | 3B | Document full production run details: final unit cost, total cost, units per SKU, factory contact, quality notes | Founder | Wk 12–13 | Medium | Not Started | Production record filed | Full documentation |  | 0% | This becomes your reference for reorders. Include what went well and what to change next time. | Production record
3C: Shipping & Logistics (Wk 12–14) — 5 tasks
3C.01 | 3C | Choose shipping method: ePacket/China Post (cheap/slow: 15–30 days, $2–4/kg) vs air express (fast: 5–10 days, $5–8/kg) | Founder | Wk 12 | High | Not Started | Shipping method selected | Method chosen with cost estimate |  | 0% | 300 belts ≈ 15–25 kg. Air express: ~$120–200. Sea freight not worth it for <500 kg. ePacket: $50–100. | Shipping decision
3C.02 | 3C | Arrange shipping: supplier handles export, you receive at home/3PL. Get tracking number. | Founder | Wk 12–13 | High | Not Started | Shipment dispatched | Tracking number received |  | 0% | Most Alibaba suppliers ship DDP (Delivered Duty Paid) for small orders — they handle customs. | Tracking info
3C.03 | 3C | Understand import duties and taxes: running belts typically classified HS 4202 (bags/cases), duty ~5–17% depending on country | Founder | Wk 12 | Medium | Not Started | Duties researched | Duty rate known |  | 0% | For <$800 value shipments to US, de minimis exemption may apply. Research your specific country's rules. | Duty research
3C.04 | 3C | Receive shipment: unbox, count all units, inspect 10% random sample against quality checklist | Founder | Wk 13–14 | Critical | Not Started | Shipment received and inspected | Unit count matches, quality acceptable |  | 0% | Document any defects immediately. Photo/video everything. Contact supplier within 48 hours if issues found. | Receiving report
3C.05 | 3C | Organize inventory storage: by size, by color, with clear labeling for fast fulfillment | Founder | Wk 14 | Medium | Not Started | Inventory organized | All SKUs sorted and accessible |  | 0% | For 300 units, a closet or spare room works fine. Use clear bins or shelves, labeled by SKU. | Inventory system
3D: Reorder Planning (Wk 13–14) — 5 tasks
3D.01 | 3D | Calculate reorder point: when inventory hits X units, trigger next production order (lead time buffer) | Founder | Wk 13 | High | Not Started | Reorder point set | Threshold defined per SKU |  | 0% | Formula: reorder point = (daily sales rate × lead time in days) + safety stock. At 3 sales/day + 30 day lead = 120 units. | Reorder thresholds
3D.02 | 3D | Set up inventory tracking: spreadsheet with columns for each SKU, units received, units sold, units on hand | Founder | Wk 13 | High | Not Started | Inventory tracker live | Real-time stock visibility |  | 0% | Start with Google Sheets. Shopify also tracks inventory automatically. Reconcile weekly. | Inventory tracker
3D.03 | 3D | Document lessons learned from first production run: what to change in v2 (materials, sizing, packaging, supplier) | Founder | Wk 14 | Medium | Not Started | Lessons documented | Written improvement list |  | 0% | First production is always a learning experience. Track everything for continuous improvement. | Lessons learned doc
3D.04 | 3D | Get reorder pricing from supplier for 500+ units (should be 10–20% cheaper per unit) | Founder | Wk 14 | Medium | Not Started | Reorder pricing received | Written quote for next order |  | 0% | Negotiate: volume discount, faster production time, payment terms (net 30 after initial trust-building). | Reorder quote
3D.05 | 3D | Identify backup supplier in case primary has quality or delivery issues | Founder | Wk 14 | Medium | Not Started | Backup supplier identified | 1 backup with samples/quote |  | 0% | Never depend on a single supplier. Keep your #2 supplier warm with occasional sample orders. | Backup supplier info

## P4
P4: DIGITAL INFRASTRUCTURE & E-COMMERCE ¦ Weeks 6–12 ¦ 5 Subprojects ¦ 28 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
4A: Shopify Store Setup (Wk 6–9) — 7 tasks
4A.01 | 4A | Create Shopify account (Basic plan: $29/mo or $1/mo for first 3 months with trial offer) | Founder | Wk 6 | Critical | Not Started | Shopify account active | Store created |  | 0% | Use Shopify over WooCommerce — better for D2C, faster setup, built-in payments. $1/mo trial = best deal. | Store URL
4A.02 | 4A | Select and customize theme: Dawn (free) or Sense (free) — both are clean, fast, mobile-optimized | Founder | Wk 6–7 | High | Not Started | Theme customized | Brand colors/fonts/logo applied |  | 0% | Dawn is best free theme for single-product brands. Don't buy a paid theme yet — free themes convert fine. | Theme setup
4A.03 | 4A | Build product page with: 8+ photos, video, description, size guide, comparison, reviews section, FAQ accordion | Founder | Wk 8–9 | Critical | Not Started | Product page live | All content elements present |  | 0% | Product page is your #1 revenue driver. Study Naked Running Band and FlipBelt product pages for structure. | Product page URL
4A.04 | 4A | Set up essential pages: Home, About, FAQ, Contact, Shipping Policy, Returns Policy, Privacy Policy, Terms | Founder | Wk 8 | High | Not Started | All pages live | 8+ pages published |  | 0% | Shopify has free policy generators. "About" page should tell your founder story prominently. | All page URLs
4A.05 | 4A | Configure shipping rates: free shipping threshold ($50+?), flat rate options, international shipping zones | Founder | Wk 9 | High | Not Started | Shipping configured | Rates set for all zones |  | 0% | Recommendation: free shipping on all orders (build shipping cost into product price). Simplicity converts. | Shipping settings
4A.06 | 4A | Set up payment processing: Shopify Payments (US/UK/CA) or Stripe/PayPal for other countries | Founder | Wk 9 | Critical | Not Started | Payments working | Test transaction successful |  | 0% | Shopify Payments: 2.9% + $0.30. If outside supported countries, use Stripe + PayPal as backup. | Payment configuration
4A.07 | 4A | Place test order through entire checkout flow: add to cart → checkout → payment → confirmation email → fulfillment | Founder | Wk 9 | Critical | Not Started | Full flow tested | Order placed and fulfilled end-to-end |  | 0% | Use Shopify Bogus Gateway for testing without real charges. Check mobile flow especially — 70%+ orders are mobile. | Test order confirmation
4B: Email Marketing Setup (Wk 7–10) — 6 tasks
4B.01 | 4B | Set up Klaviyo account (free up to 250 contacts) and integrate with Shopify | Founder | Wk 7 | High | Not Started | Klaviyo connected | Integration active |  | 0% | Klaviyo > Mailchimp for e-commerce. Free tier is generous enough for launch. Email drives 30%+ of D2C revenue. | Klaviyo setup
4B.02 | 4B | Create welcome email flow (3 emails): welcome + brand story → product education → social proof + CTA | Founder | Wk 8 | High | Not Started | Welcome flow live | 3 emails automated |  | 0% | Email 1: welcome + 10% off code. Email 2 (day 2): "Why we built this." Email 3 (day 4): reviews + CTA to buy. | Welcome flow emails
4B.03 | 4B | Create abandoned cart flow (3 emails): reminder (1hr) → social proof (24hr) → urgency/discount (48hr) | Founder | Wk 8–9 | Critical | Not Started | Cart abandonment flow live | 3 emails automated |  | 0% | Abandoned cart flows recover 5–15% of lost sales. The #1 most profitable email automation for any store. | Cart recovery flow
4B.04 | 4B | Create post-purchase flow (3 emails): order confirmation → shipping update → review request (14 days post-delivery) | Founder | Wk 9 | High | Not Started | Post-purchase flow live | 3 emails automated |  | 0% | Review request email at day 14 = sweet spot (enough time to test, before they forget). Include QR code/direct link. | Post-purchase flow
4B.05 | 4B | Design email templates matching brand identity: header, footer, product blocks, CTA buttons | Founder | Wk 9 | Medium | Not Started | Templates designed | Consistent brand templates |  | 0% | Keep emails simple — plain text often outperforms heavily designed emails for small brands. | Email templates
4B.06 | 4B | Set up signup popup on Shopify: offer 10% off first order for email signup | Founder | Wk 9–10 | High | Not Started | Popup live | Popup showing on site |  | 0% | Use Klaviyo's built-in popup. Show after 5 seconds or on exit intent. Expected signup rate: 3–8%. | Popup configuration
4C: Analytics & Tracking (Wk 7–9) — 5 tasks
4C.01 | 4C | Install Google Analytics 4 with Shopify integration and enable enhanced e-commerce tracking | Founder | Wk 7 | High | Not Started | GA4 live | All ecommerce events firing |  | 0% | Free and essential. Track: page views, add to cart, checkout initiated, purchase, revenue. | GA4 setup
4C.02 | 4C | Install Meta Pixel (Facebook/Instagram) for ad tracking and retargeting | Founder | Wk 7 | High | Not Started | Meta Pixel live | All conversion events tracking |  | 0% | Even if not running ads yet — install the pixel to build retargeting audiences from day 1. | Meta Pixel setup
4C.03 | 4C | Set up Google Search Console and submit sitemap for SEO indexing | Founder | Wk 8 | Medium | Not Started | GSC active | Sitemap submitted |  | 0% | Free. Shopify auto-generates sitemap. Submit to Google to start getting indexed. | GSC setup
4C.04 | 4C | Install Hotjar or Microsoft Clarity (free) for heatmaps and session recordings | Founder | Wk 8 | Medium | Not Started | Heatmap tool installed | Recordings active |  | 0% | Watch 20 session recordings after launch to see where customers get confused or drop off. | Heatmap tool
4C.05 | 4C | Create tracking spreadsheet: daily dashboard of traffic, conversion rate, revenue, orders, AOV, email signups | Founder | Wk 9 | Medium | Not Started | Dashboard created | Daily tracking active |  | 0% | Start simple: Google Sheet with date, sessions, orders, revenue, conversion rate, email signups. | Tracking dashboard
4D: SEO & Content Foundation (Wk 8–12) — 5 tasks
4D.01 | 4D | Conduct keyword research: target 20 keywords for product pages, collection pages, and future blog content | Founder | Wk 8 | High | Not Started | Keywords identified | 20+ target keywords |  | 0% | Primary: "best running belt" (40K/mo). Long-tail: "running belt for iPhone 16", "no bounce running belt", "eco running belt". | Keyword list
4D.02 | 4D | Optimize product page SEO: title tag, meta description, H1, image alt text, URL slug | Founder | Wk 9 | High | Not Started | On-page SEO complete | All elements optimized |  | 0% | Title: "[Brand] Running Belt — [Key Feature] ¦ Free Shipping". Keep meta description under 155 characters. | SEO checklist
4D.03 | 4D | Write and publish 3 SEO-optimized blog posts: "Best Running Belts 2026", "How to Carry Phone While Running", "Running Belt vs Armband" | Founder | Wk 10–12 | Medium | Not Started | Blog posts published | 3 posts (1,500+ words each) |  | 0% | Long-form content drives organic traffic over time. Include your product naturally. Add comparison tables. | 3 blog posts
4D.04 | 4D | Set up basic link building: submit to 5+ running gear directories, reach out to 3 running bloggers for reviews | Founder | Wk 10–12 | Medium | Not Started | Link building started | 5+ directory submissions |  | 0% | Free directories: running gear lists, startup directories, product hunt. Blogger outreach: offer free product for honest review. | Link building tracker
4D.05 | 4D | Optimize site speed: compress images (TinyPNG), minimize apps, test Google PageSpeed score (target 80+) | Founder | Wk 10 | Medium | Not Started | Site speed optimized | PageSpeed score 80+ |  | 0% | Shopify Dawn theme is already fast. Main drag: uncompressed images. Use WebP format, lazy loading. | PageSpeed score
4E: Amazon Preparation (Wk 10–12) — 5 tasks
4E.01 | 4E | Decide: launch on Amazon alongside Shopify, or D2C-only first? (Recommendation: D2C first 3 months, then add Amazon) | Founder | Wk 10 | High | Not Started | Amazon strategy decided | Decision documented |  | 0% | Pros: discovery + credibility. Cons: 15% fee, price pressure, brand control loss. Start D2C to learn, then expand. | Amazon decision
4E.02 | 4E | If Amazon: create Amazon Seller account (Professional: $39.99/mo) and apply for brand registry | Founder | Wk 10–11 | Medium | Not Started | Account created | Seller account active |  | 0% | Brand Registry requires trademark (pending TM works). Gives access to A+ Content, Brand Store, vine reviews. | Amazon account
4E.03 | 4E | Prepare Amazon listing: title (200 chars), 5 bullet points, A+ content, 7+ images, backend keywords | Founder | Wk 11–12 | Medium | Not Started | Listing drafted | All elements prepared |  | 0% | Study top-selling FlipBelt and SPIbelt listings. Title formula: Brand + Product + Key Feature + Size + Use Case. | Amazon listing draft
4E.04 | 4E | Plan Amazon launch strategy: initial pricing (match or undercut key competitor), Vine reviews (30 free units) | Founder | Wk 11–12 | Medium | Not Started | Launch strategy planned | Strategy documented |  | 0% | Amazon Vine: send 30 units for free reviews from trusted reviewers. Critical for new listing credibility. | Amazon launch plan
4E.05 | 4E | Decide fulfillment: FBA (Amazon warehouses) vs FBM (ship yourself). FBA recommended for Prime badge and convenience. | Founder | Wk 12 | Medium | Not Started | Fulfillment decided | FBA or FBM chosen |  | 0% | FBA fees: ~$3–5/unit for running belts. Worth it for Prime badge which increases conversion 2–3x. | Fulfillment decision

## P5
P5: CONTENT, COMMUNITY & INFLUENCER MARKETING ¦ Weeks 8–20 ¦ 5 Subprojects ¦ 26 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
5A: Influencer Seeding Program (Wk 8–14) — 6 tasks
5A.01 | 5A | Build target influencer list: 30 micro-influencers (1K–50K followers) in running/fitness niche on IG and TikTok | Founder | Wk 8–9 | High | Not Started | Influencer list built | 30+ candidates identified |  | 0% | Focus on engagement rate (>3%) not follower count. Running coaches, local elites, marathon bloggers. | Influencer database
5A.02 | 5A | Craft personalized outreach DMs/emails: product gift offer in exchange for honest review (no payment required) | Founder | Wk 9 | High | Not Started | Outreach templates created | 2–3 message templates |  | 0% | Template: personal compliment + why you chose them + free product offer + no strings attached. Keep it genuine. | Outreach templates
5A.03 | 5A | Send outreach to first batch of 15 influencers and track response rate | Founder | Wk 10 | High | Not Started | Outreach sent | 15 influencers contacted |  | 0% | Expect 20–30% acceptance rate = 3–5 seeded products. Follow up once if no reply after 5 days. | Outreach tracker
5A.04 | 5A | Ship free product to accepted influencers with branded packaging + personalized handwritten note | Founder | Wk 10–11 | High | Not Started | Products shipped | All accepted influencers received product |  | 0% | Cost: ~$15/seeded unit (product + shipping). Budget 20 units = $300. This is the Gymshark playbook. | Shipping confirmations
5A.05 | 5A | Track and repost all influencer content: save posts, stories, TikToks. Request permission to use as ads/testimonials | Founder | Wk 11–14 | High | Not Started | Content tracked | 10+ pieces of influencer content |  | 0% | UGC (user-generated content) converts 4x better than brand-created content in ads. This is gold. | UGC content library
5A.06 | 5A | Send second wave: 15 more influencers based on learnings from wave 1 response rates and content quality | Founder | Wk 12–14 | Medium | Not Started | Wave 2 sent | 15 more contacted |  | 0% | Refine targeting based on which niches/follower ranges produced best content from wave 1. | Wave 2 tracker
5B: Content Marketing & Social Media (Wk 8–Ongoing) — 6 tasks
5B.01 | 5B | Create content pillar strategy: 1) Product demos, 2) Running tips, 3) Behind-the-scenes, 4) Community/UGC reposts | Founder | Wk 8 | High | Not Started | Content strategy defined | 4 pillars documented |  | 0% | Ratio: 40% educational/entertaining, 30% product, 20% community, 10% promotional. | Content strategy doc
5B.02 | 5B | Batch-create 20 pieces of short-form video content (15–60 sec) for TikTok and Instagram Reels | Founder | Wk 9–10 | High | Not Started | Content batch created | 20 videos ready to post |  | 0% | Formats: "What fits in my running belt", "Running belt bounce test", "Runner tries X for the first time", "Running belt comparison". | Video content library
5B.03 | 5B | Establish posting schedule: TikTok daily, Instagram 4–5x/week, stories daily, engage in comments 30 min/day | Founder | Wk 10 | High | Not Started | Schedule active | Consistent posting maintained |  | 0% | Use Later.com (free tier) or Buffer for scheduling. Consistency matters more than perfection. | Content calendar
5B.04 | 5B | Create 5 "pillar" long-form YouTube videos: running belt buying guide, honest comparisons, marathon prep gear | Founder | Wk 12–16 | Medium | Not Started | YouTube videos published | 5 videos live |  | 0% | YouTube = long-term SEO play. "Best running belt" searches happen constantly. Low competition for quality content. | YouTube channel
5B.05 | 5B | Engage in 5+ running communities daily: Reddit r/running, r/marathontraining, Strava clubs, Facebook groups | Founder | Wk 10–Ongoing | Medium | Not Started | Community engagement active | 5+ daily interactions |  | 0% | Be genuinely helpful. Recommend your product only when directly relevant. Build reputation as gear expert. | Engagement log
5B.06 | 5B | Track content performance weekly: impressions, engagement rate, follower growth, website clicks, sales attributed | Founder | Wk 12–Ongoing | Medium | Not Started | Performance tracking active | Weekly metrics review |  | 0% | Kill underperforming content types. Double down on what works. Aim for 3%+ engagement rate. | Performance tracker
5C: Running Community & Events (Wk 10–18) — 5 tasks
5C.01 | 5C | Identify 5 local running events, parkruns, or club meetups to attend with product samples | Founder | Wk 10 | High | Not Started | Events identified | 5+ events on calendar |  | 0% | SPIbelt launched at Austin Marathon. Events = direct customer contact + immediate feedback + sales. | Event calendar
5C.02 | 5C | Prepare event kit: 10 sample products, business cards, QR code stand for instant purchase, phone for content capture | Founder | Wk 11 | High | Not Started | Event kit ready | All materials prepared |  | 0% | QR code → Shopify product page with event-exclusive 10% discount code. Capture email of everyone who tries product. | Event kit checklist
5C.03 | 5C | Attend first 3 running events and document results: products tried, emails captured, sales, feedback received | Founder | Wk 12–16 | High | Not Started | Events attended | 3 events completed |  | 0% | Target: 20+ product trials per event, 10+ emails captured, 3–5 direct sales. Photo/video everything for content. | Event results tracker
5C.04 | 5C | Partner with 2–3 local running clubs: offer club member discount (15%), provide free product for group leaders | Founder | Wk 14–16 | Medium | Not Started | Club partnerships active | 2–3 partnerships established |  | 0% | Running clubs = organic word-of-mouth machine. Club leaders are trusted influencers within their community. | Partnership agreements
5C.05 | 5C | Create a Strava club or online running community branded to your belt for ongoing engagement | Founder | Wk 16–18 | Medium | Not Started | Community launched | Online community active |  | 0% | Strava club is free. Host monthly challenges, share running tips, feature customer stories. | Community URL
5D: PR & Media Outreach (Wk 12–18) — 4 tasks
5D.01 | 5D | Build media list: 20 running gear reviewers, bloggers, YouTubers, and podcast hosts | Founder | Wk 12 | Medium | Not Started | Media list built | 20+ contacts |  | 0% | Targets: Trail & Kale, Road Trail Run, iRunFar, The Running Channel, RunRepeat, GearJunkie. | Media contact list
5D.02 | 5D | Craft press kit: press release, high-res photos, product specs, founder bio, and unique brand angle | Founder | Wk 13 | Medium | Not Started | Press kit ready | Complete kit |  | 0% | Host press kit on Google Drive or Dropbox with easy sharing link. Include lifestyle photos. | Press kit folder
5D.03 | 5D | Send product samples to 10 running gear reviewers with personalized pitch focused on what makes your belt different | Founder | Wk 14–16 | Medium | Not Started | Samples sent to media | 10 reviewers seeded |  | 0% | Even 1 review from a trusted running site can drive hundreds of sales. Be patient — reviewers get many pitches. | Media outreach tracker
5D.04 | 5D | Pitch story angles to 5 publications: "bootstrapped founder", "from Pakistan to global D2C", "sustainable running gear" | Founder | Wk 16–18 | Medium | Not Started | Pitches sent | 5 publications pitched |  | 0% | Your unique angle: launching a global D2C running brand from Pakistan on $10K. That's a story editors want to tell. | Pitch tracker
5E: Referral & Ambassador Program (Wk 14–20) — 5 tasks
5E.01 | 5E | Set up referral program: give $5, get $5 (or 15% off) using Shopify app (ReferralCandy or Smile.io free tier) | Founder | Wk 14 | High | Not Started | Referral program live | App installed and configured |  | 0% | Runners are the most recommendation-driven consumers. A referral program turns every customer into a salesperson. | Referral program
5E.02 | 5E | Design ambassador program: 10 "founding ambassadors" get free product + 20% commission on referred sales | Founder | Wk 14–15 | High | Not Started | Ambassador program designed | Program structure documented |  | 0% | Recruit from: your best early customers, local runners, micro-influencers who already posted about your product. | Ambassador program doc
5E.03 | 5E | Recruit first 10 ambassadors from early customers and influencer contacts | Founder | Wk 16–18 | Medium | Not Started | Ambassadors recruited | 10 ambassadors active |  | 0% | Give each ambassador a unique discount code to share. Track sales per ambassador. | Ambassador roster
5E.04 | 5E | Create ambassador content kit: product photos, brand assets, suggested captions, hashtags, talking points | Founder | Wk 16 | Medium | Not Started | Content kit created | Shareable asset folder |  | 0% | Make it easy for ambassadors to create content. Provide templates they can personalize. | Ambassador kit
5E.05 | 5E | Track ambassador performance monthly: content created, referral sales, engagement, and optimize program | Founder | Wk 18–Ongoing | Medium | Not Started | Tracking active | Monthly performance review |  | 0% | Reward top performers with exclusive product, higher commission, or featured spotlight on social media. | Ambassador tracker

## P6
P6: LAUNCH EXECUTION & PAID ACQUISITION ¦ Weeks 12–20 ¦ 5 Subprojects ¦ 25 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
6A: Pre-Launch Campaign (Wk 12–14) — 5 tasks
6A.01 | 6A | Build launch countdown: 14-day email sequence to waitlist teasing product reveals, behind-the-scenes, founder story | Founder | Wk 12 | High | Not Started | Countdown sequence live | 5+ countdown emails drafted |  | 0% | Day -14: "Something's coming". Day -7: "First look". Day -3: "Founding member pricing". Day -1: "Tomorrow." | Email sequence
6A.02 | 6A | Create "Founding Member" offer: first 50 buyers get 20% off + exclusive founding member tag/perk | Founder | Wk 12 | High | Not Started | Founding offer created | Discount code + landing page ready |  | 0% | Scarcity drives action. "Only 50 available" creates urgency. Tag founding members for future loyalty perks. | Founding member offer
6A.03 | 6A | Coordinate launch day social media blitz: 3+ posts across IG, TikTok, stories, reels | Founder | Wk 13 | High | Not Started | Launch content scheduled | All posts ready to publish |  | 0% | Pre-schedule on Later or Buffer. Include: launch announcement, product demo video, founder story, countdown. | Launch content
6A.04 | 6A | Brief all ambassadors and influencers on launch date — ask them to post on launch day | Founder | Wk 13 | High | Not Started | Launch team briefed | All partners notified |  | 0% | Send them: launch date, discount code to share, key product points, brand hashtag. Coordinate timing. | Launch briefing
6A.05 | 6A | Final QA: test entire purchase flow, email automations, tracking pixels, inventory counts one more time | Founder | Wk 13–14 | Critical | Not Started | Final QA passed | All systems go |  | 0% | Place 2–3 test orders from different devices (mobile, desktop). Check every email fires correctly. | QA checklist
6B: Launch Week Execution (Wk 14–15) — 5 tasks
6B.01 | 6B | LAUNCH DAY: Send launch email to full waitlist, publish all social content, activate founding member pricing | Founder | Wk 14 | Critical | Not Started | Store live and selling | First orders received |  | 0% | Best launch days: Tuesday or Wednesday (highest email open rates). Time: 9 AM in your primary market timezone. | Launch confirmation
6B.02 | 6B | Monitor all channels hour-by-hour on launch day: orders, site traffic, email opens, social engagement, customer questions | Founder | Wk 14 | Critical | Not Started | Real-time monitoring active | All issues caught within 1 hour |  | 0% | Have laptop open all day. Respond to every comment, DM, and email within 30 minutes. First impressions matter. | Launch day log
6B.03 | 6B | Fulfill all launch day/week orders within 24 hours: pack, label, ship, send tracking email | Founder | Wk 14–15 | Critical | Not Started | All orders shipped | Average fulfillment <24 hours |  | 0% | Fast shipping builds trust and drives positive reviews. Hand-write a thank you note on first 50 orders. | Fulfillment log
6B.04 | 6B | Post daily launch week content: customer reactions, sales milestones, behind-the-scenes packing, shoutouts | Founder | Wk 14–15 | High | Not Started | Daily content posted | 7 days of launch content |  | 0% | "50 sold in first 48 hours" — celebrate milestones publicly. Builds social proof and FOMO. | Launch week content
6B.05 | 6B | Compile launch week results: total orders, revenue, traffic sources, conversion rate, email performance, social metrics | Founder | Wk 15 | High | Not Started | Launch report complete | Full metrics documented |  | 0% | Target: 30–50 orders in week 1 (ambitious for $10K budget). Even 15–20 is solid for validation. | Launch week report
6C: Paid Advertising — Meta Ads (Wk 15–20) — 5 tasks
6C.01 | 6C | Set up Meta Ads Manager, create Business Manager, verify domain, configure Conversions API | Founder | Wk 15 | High | Not Started | Ads Manager configured | All tracking working |  | 0% | Free to set up. Takes 1–2 hours. Essential for running any Facebook or Instagram ads. | Ads Manager setup
6C.02 | 6C | Create first ad campaign: $10–15/day budget, 3 ad sets testing different audiences (runners, marathoners, fitness enthusiasts) | Founder | Wk 15–16 | High | Not Started | Campaign launched | Ads live and spending |  | 0% | Start with Advantage+ Shopping campaigns (Meta's AI does the targeting). Use video ads — they outperform static 3x. | Campaign structure
6C.03 | 6C | Create 5 ad variations: video demo, UGC/influencer content, before/after comparison, testimonial, lifestyle | Founder | Wk 15–16 | High | Not Started | Ad creatives ready | 5 variations live |  | 0% | Creative is 80% of ad performance. Best format: 15-sec vertical video with hook in first 3 seconds. | Ad creative library
6C.04 | 6C | Monitor and optimize ads daily for first 2 weeks: kill losers, scale winners, test new audiences | Founder | Wk 16–18 | High | Not Started | Daily optimization active | Target: CPA <$15, ROAS >2.5x |  | 0% | Week 1: let it learn (don't touch). Week 2: kill ads with CPA >$20. Scale ads with CPA <$12. | Ad performance tracker
6C.05 | 6C | Set up retargeting campaigns: target site visitors who didn't purchase, cart abandoners, and email subscribers | Founder | Wk 17–18 | High | Not Started | Retargeting live | Retargeting audiences active |  | 0% | Retargeting converts 3–5x better than cold traffic. Show: customer reviews, "still thinking about it?", limited stock. | Retargeting campaigns
6D: Paid Advertising — Google (Wk 16–20) — 5 tasks
6D.01 | 6D | Set up Google Ads account and Shopping feed via Shopify's Google channel integration | Founder | Wk 16 | Medium | Not Started | Google Ads configured | Shopping feed active |  | 0% | Google Shopping shows your product with image and price directly in search results. High-intent traffic. | Google Ads setup
6D.02 | 6D | Create Google Shopping campaign: $5–10/day budget targeting "running belt" and related purchase-intent keywords | Founder | Wk 16–17 | Medium | Not Started | Shopping campaign live | Ads showing for target keywords |  | 0% | Google Shopping captures buyers actively searching. Lower volume than Meta but higher intent and conversion. | Shopping campaign
6D.03 | 6D | Create Google Search campaign: 10 exact-match keywords like "best running belt", "running belt for phone" | Founder | Wk 17 | Medium | Not Started | Search campaign live | 10+ keywords active |  | 0% | Start with exact match only to control spend. Expand to phrase match once you have conversion data. | Search campaign
6D.04 | 6D | Set up Google retargeting: display ads to site visitors across the Google Display Network | Founder | Wk 18 | Medium | Not Started | Display retargeting live | Retargeting audience active |  | 0% | Low cost ($1–3 CPM), keeps brand visible. Use product images with review stars and price. | Display retargeting
6D.05 | 6D | Monthly ad budget review: allocate $500–800/month across Meta + Google based on performance data | Founder | Wk 20 | High | Not Started | Budget optimized | Best-performing channel gets 60%+ of budget |  | 0% | Typical split for running belts: 60% Meta (discovery), 30% Google (intent), 10% testing new channels. | Budget allocation
6E: Launch Metrics & Optimization (Wk 16–20) — 5 tasks
6E.01 | 6E | Establish weekly KPI review cadence: traffic, conversion rate, AOV, CAC, ROAS, email revenue %, review count | Founder | Wk 16 | High | Not Started | Weekly review active | Dashboard reviewed every Monday |  | 0% | Target KPIs: 2%+ conversion rate, <$15 CAC, 3:1+ LTV:CAC, 30%+ email revenue share, 4.5+ avg review rating. | KPI dashboard
6E.02 | 6E | A/B test product page: test 2 hero images, 2 headlines, price display format, CTA button text | Founder | Wk 16–18 | Medium | Not Started | A/B tests running | 2+ tests active |  | 0% | Use Shopify's built-in A/B testing or free Google Optimize alternative. Test 1 variable at a time. | Test results
6E.03 | 6E | Analyze first 30 days of customer data: who bought, where from, what drove them, what almost stopped them | Founder | Wk 18 | High | Not Started | Customer analysis complete | Profile of ideal customer validated |  | 0% | Look at: age/gender breakdown, geographic distribution, top traffic sources, most common landing page, exit pages. | Customer analysis
6E.04 | 6E | Collect and respond to first 20+ product reviews: identify patterns in praise and complaints | Founder | Wk 18–20 | High | Not Started | Reviews collected | 20+ reviews with analysis |  | 0% | Send review request email at day 14 post-delivery. Offer 10% off next order for review. Respond to ALL reviews. | Review analysis
6E.05 | 6E | Create 90-day optimization plan based on all launch data: what to scale, what to fix, what to kill | Founder | Wk 20 | High | Not Started | 90-day plan created | Written plan with priorities |  | 0% | Focus resources on what the data says works. Cut what doesn't. Avoid gut-feel decisions — follow the numbers. | 90-day plan

## P7
P7: FINANCIAL OPERATIONS & CASH FLOW ¦ Weeks 1–Ongoing ¦ 4 Subprojects ¦ 18 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
7A: Business Setup & Banking (Wk 1–4) — 5 tasks
7A.01 | 7A | Register business entity (LLC or equivalent in your country) and obtain tax ID / EIN | Founder | Wk 1–2 | Critical | Not Started | Business registered | Legal entity active |  | 0% | For Pakistan-based founder selling globally: consider US LLC (Wyoming/Delaware) via Stripe Atlas ($500) for payment access. | Registration docs
7A.02 | 7A | Open business bank account separate from personal finances | Founder | Wk 2–3 | Critical | Not Started | Bank account open | Account active with deposits |  | 0% | Options: Wise Business (multi-currency, great for global), Mercury (US startups), or local bank. | Bank account
7A.03 | 7A | Set up accounting: Wave (free) or QuickBooks ($15/mo) — track every dollar from day 1 | Founder | Wk 3 | High | Not Started | Accounting system active | All transactions tracked |  | 0% | Wave is free and sufficient for early stage. Connect bank account for automatic transaction import. | Accounting setup
7A.04 | 7A | Create chart of accounts for D2C running belt business: COGS, shipping, marketing, platform fees, packaging | Founder | Wk 3 | Medium | Not Started | Chart of accounts created | All categories defined |  | 0% | Key categories: product COGS, shipping/fulfillment, marketing (ads, influencers), platform fees, packaging, SaaS tools. | Chart of accounts
7A.05 | 7A | Set up Shopify tax settings and understand sales tax obligations (Shopify auto-calculates for US) | Founder | Wk 3–4 | High | Not Started | Tax settings configured | Correct tax collection active |  | 0% | Nexus rules vary by state/country. Shopify auto-collects for US states with economic nexus. | Tax configuration
7B: Financial Modeling & Budgeting (Wk 2–6) — 5 tasks
7B.01 | 7B | Build detailed unit economics model: COGS breakdown, contribution margin, break-even analysis | Founder | Wk 2–3 | Critical | Not Started | Unit economics modeled | Positive contribution margin |  | 0% | At $35 price: COGS $6, packaging $1.50, shipping $5, Shopify fees $1.75 = $20.75 gross profit (59%). | Unit economics spreadsheet
7B.02 | 7B | Build 12-month cash flow forecast with weekly granularity for months 1–3, monthly for months 4–12 | Founder | Wk 3–4 | High | Not Started | Cash flow model built | 12 months projected |  | 0% | Critical constraint: inventory purchase timing vs revenue realization. Plan for cash gaps. | Cash flow model
7B.03 | 7B | Allocate $10K budget across all projects with 25% contingency reserve | Founder | Wk 4 | High | Not Started | Budget allocated | All projects funded |  | 0% | Proposed: Product $3,500 ¦ Marketing $2,000 ¦ E-commerce $500 ¦ Legal/IP $500 ¦ Contingency $2,500 ¦ Tools $1,000. | Budget allocation
7B.04 | 7B | Set monthly financial review cadence: P&L review, cash position, CAC tracking, inventory value | Founder | Wk 5 | Medium | Not Started | Monthly review scheduled | First review completed |  | 0% | Set calendar reminder for last Sunday of each month. 1 hour review prevents cash flow surprises. | Review schedule
7B.05 | 7B | Define financial milestones: breakeven date target, first profitable month target, revenue targets by quarter | Founder | Wk 5–6 | Medium | Not Started | Milestones defined | Written targets with dates |  | 0% | Realistic targets: breakeven by month 4–5, $3K/mo revenue by month 6, $5K/mo by month 9. | Financial milestones
7C: Payment & International Operations (Wk 4–8) — 4 tasks
7C.01 | 7C | Set up multi-currency payment processing: Shopify Payments + PayPal + Wise for receiving global payments | Founder | Wk 4–5 | High | Not Started | Multi-currency active | Accept USD, EUR, GBP, AUD minimum |  | 0% | Wise Business account gives you USD, EUR, GBP bank details for receiving payments. Low FX fees. | Payment setup
7C.02 | 7C | Research and set up international shipping rates: US, UK, EU, Australia, Canada as priority markets | Founder | Wk 5–6 | High | Not Started | International shipping configured | Rates set for 5+ countries |  | 0% | Options: Shopify Shipping (discounted DHL/USPS), ShipStation, Pirate Ship (US), or local post for Pakistan. | Shipping rates
7C.03 | 7C | Understand VAT/GST obligations for selling to EU, UK, Australia — set up IOSS if needed | Founder | Wk 6–7 | Medium | Not Started | Tax obligations mapped | Compliance plan documented |  | 0% | EU IOSS: required for shipments <€150. UK: VAT registration if selling >£39/mo. Consult a tax professional for specifics. | Tax compliance plan
7C.04 | 7C | Set up profit margin tracker: actual vs projected margins reviewed monthly | Founder | Wk 7–8 | Medium | Not Started | Margin tracker active | Monthly review process |  | 0% | Track: gross margin per unit sold, blended CAC, net margin after all costs. Adjust pricing if margins thin. | Margin tracker
7D: Inventory & COGS Management (Wk 8–Ongoing) — 4 tasks
7D.01 | 7D | Set up inventory tracking: Shopify inventory + spreadsheet backup with reorder alerts | Founder | Wk 8 | High | Not Started | Inventory system live | Real-time stock visibility |  | 0% | Shopify tracks automatically. Add spreadsheet for: PO history, landed costs, aging analysis. | Inventory system
7D.02 | 7D | Calculate landed cost per unit (product + shipping + duties + packaging + fulfillment labor) | Founder | Wk 10 | High | Not Started | Landed cost calculated | True COGS known per SKU |  | 0% | This is your real COGS, not just the factory price. Include everything that touches the product before the customer gets it. | Landed cost calc
7D.03 | 7D | Track inventory turnover rate: target selling through initial batch in 60–90 days | Founder | Wk 14–Ongoing | Medium | Not Started | Turnover tracked | Monthly turnover calculated |  | 0% | 300 units / 90 days = 3.3 units/day or ~100/month. If tracking below this, increase marketing or adjust pricing. | Turnover tracker
7D.04 | 7D | Plan reorder timing: place next PO when 30–45 days of inventory remain (accounting for production + shipping lead time) | Founder | Wk 16–Ongoing | High | Not Started | Reorder system active | Never stock out |  | 0% | Stockouts kill momentum. Better to slightly overstock than miss sales. Second order: increase to 500 units for better pricing. | Reorder calendar

## P8
P8: LEGAL, COMPLIANCE & IP PROTECTION ¦ Weeks 1–10 ¦ 4 Subprojects ¦ 16 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
8A: Business Formation & Structure (Wk 1–4) — 4 tasks
8A.01 | 8A | Research optimal business structure for international D2C: domestic entity vs US LLC vs both | Founder | Wk 1 | Critical | Not Started | Structure decided | Entity type chosen with rationale |  | 0% | For Pakistan → global: US LLC (Wyoming) via Stripe Atlas ($500) gives access to US payment rails and Shopify Payments. | Entity decision
8A.02 | 8A | Form business entity and obtain all required registrations/tax IDs | Founder | Wk 1–3 | Critical | Not Started | Entity formed | Registration complete |  | 0% | DIY: $100–300. Stripe Atlas: $500 (includes LLC, bank account, Stripe integration). LegalZoom: $79–259. | Formation docs
8A.03 | 8A | Obtain required business licenses and permits for e-commerce in your jurisdiction | Founder | Wk 3–4 | High | Not Started | Licenses obtained | All required licenses active |  | 0% | Requirements vary by location. Most e-commerce businesses need: business license, reseller permit (for wholesale). | License copies
8A.04 | 8A | Set up business insurance: product liability insurance ($300–500/year for small D2C brands) | Founder | Wk 4 | Medium | Not Started | Insurance active | Policy in force |  | 0% | Product liability protects against injury claims. Not strictly required at launch but strongly recommended. | Insurance policy
8B: Intellectual Property (Wk 3–8) — 4 tasks
8B.01 | 8B | File trademark application for brand name (Class 028 — sporting goods) in primary market | Founder | Wk 3–4 | High | Not Started | TM application filed | Filing receipt received |  | 0% | USPTO TEAS Plus: $250/class. Madrid Protocol for international: ~$650+. Can use ™ immediately, ® after registration. | TM filing receipt
8B.02 | 8B | File trademark for logo mark separately if significantly different from word mark | Founder | Wk 5 | Medium | Not Started | Logo TM filed | Filing receipt received |  | 0% | Optional at launch stage but recommended if logo is distinctive. Additional $250/class. | Logo TM receipt
8B.03 | 8B | If product has genuinely novel design feature, research design patent or utility patent feasibility | Founder | Wk 5–6 | Low | Not Started | Patent research complete | Decision made (file or skip) |  | 0% | Provisional patent: $1,600+ with attorney, $150 self-file. Only worth it if truly novel. Most running belts aren't patentable. | Patent decision
8B.04 | 8B | Register copyright for website content, photography, and brand materials | Founder | Wk 7–8 | Low | Not Started | Copyright registered | Registration certificate |  | 0% | Copyright is automatic upon creation but registration ($55) enables statutory damages in infringement cases. | Copyright registration
8C: E-Commerce Compliance (Wk 4–8) — 4 tasks
8C.01 | 8C | Create and publish required legal pages: Privacy Policy, Terms of Service, Returns/Refund Policy, Shipping Policy | Founder | Wk 4–5 | Critical | Not Started | Legal pages published | All 4 pages live on site |  | 0% | Use Shopify's free policy generators as starting point. Customize for your specific business practices. | Legal page URLs
8C.02 | 8C | Ensure GDPR compliance: cookie consent banner, data processing disclosure, right to deletion process | Founder | Wk 5–6 | High | Not Started | GDPR compliant | Cookie banner + privacy controls active |  | 0% | Required if selling to EU/UK customers. Use Shopify's built-in cookie banner or free app like CookieBot. | GDPR checklist
8C.03 | 8C | Set up consumer protection compliance: clear pricing, accurate product descriptions, honest marketing claims | Founder | Wk 6 | Medium | Not Started | Compliance review done | All claims verified |  | 0% | Don't claim "waterproof" if it's "water-resistant". Don't say "eco-friendly" without documentation to back it up. | Claims review
8C.04 | 8C | Review product labeling requirements: country of origin, material composition, care instructions | Founder | Wk 6–8 | Medium | Not Started | Labeling compliant | All labels meet requirements |  | 0% | US FTC requires: fiber content, country of origin, care instructions on textile products. Ensure labels are correct. | Label review
8D: Contracts & Agreements (Wk 6–10) — 4 tasks
8D.01 | 8D | Create supplier agreement template: quality standards, payment terms, IP ownership, dispute resolution | Founder | Wk 6–7 | High | Not Started | Agreement template ready | Signed with primary supplier |  | 0% | Key clauses: IP ownership of custom designs, quality guarantee, production timelines, confidentiality. | Supplier agreement
8D.02 | 8D | Create influencer/ambassador agreement template: deliverables, usage rights, disclosure requirements, compensation | Founder | Wk 7–8 | Medium | Not Started | Agreement template ready | Ready for use |  | 0% | Must include: FTC disclosure requirement (#ad or #sponsored), content usage rights, exclusivity terms. | Influencer agreement
8D.03 | 8D | Understand FTC endorsement guidelines: all paid/gifted product must be disclosed in influencer content | Founder | Wk 7 | Medium | Not Started | FTC guidelines understood | Brief created for all partners |  | 0% | FTC requires clear disclosure: #ad or #sponsored visible in post. Non-compliance = fines for both brand and influencer. | FTC compliance brief
8D.04 | 8D | Create website terms of use and customer agreement covering: limitation of liability, dispute resolution, governing law | Founder | Wk 8–10 | Medium | Not Started | Terms created | Published on website |  | 0% | Start with Shopify template and customize. For a bootstrapped brand, perfect legal docs < good legal docs now. | Terms of use

## P9
P9: CUSTOMER EXPERIENCE & RETENTION ¦ Weeks 12–Ongoing ¦ 4 Subprojects ¦ 18 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
9A: Customer Support Infrastructure (Wk 12–14) — 5 tasks
9A.01 | 9A | Set up support email (support@yourbrand.com) with auto-responder promising <24hr response time | Founder | Wk 12 | High | Not Started | Support email active | Auto-response working |  | 0% | Founder handles all support directly for first 6 months. This is feature, not bug — you learn directly from customers. | Support email
9A.02 | 9A | Create 20 support response templates: shipping inquiries, sizing help, returns, product care, wholesale inquiries | Founder | Wk 12–13 | High | Not Started | Templates created | 20+ templates ready |  | 0% | Templates save time. Personalize each one before sending — never send robotic copy-paste responses. | Template library
9A.03 | 9A | Define and publish returns/exchange policy: 30-day no-questions-asked return for unused product | Founder | Wk 12 | High | Not Started | Returns policy live | Policy published on site |  | 0% | Generous return policy increases conversion rate more than it increases returns. Target: <5% return rate for running belts. | Returns policy
9A.04 | 9A | Set up live chat on Shopify: Tidio (free tier) or Shopify Inbox for real-time customer questions | Founder | Wk 13 | Medium | Not Started | Live chat active | Chat widget installed |  | 0% | Live chat increases conversion 10–15%. Set "away" hours for when you can't respond. Auto-message to set expectations. | Chat widget
9A.05 | 9A | Create size recommendation tool or quiz: help customers choose correct size before purchase (reduces returns) | Founder | Wk 13–14 | High | Not Started | Size tool live | Tool on product page |  | 0% | Simple: "Measure your waist at belly button. If 28-32 choose S, 32-36 choose M..." with photos. Reduces size-related returns 50%. | Size tool
9B: Review & Feedback Collection (Wk 14–Ongoing) — 4 tasks
9B.01 | 9B | Install Shopify review app: Judge.me (free tier) or Loox (photo reviews, $9.99/mo) | Founder | Wk 14 | High | Not Started | Review app installed | App active on product page |  | 0% | Judge.me free tier is excellent. Auto-sends review request emails. Displays reviews with photos on product page. | Review app
9B.02 | 9B | Set up automated review request: email at day 14 post-delivery with one-click star rating + photo upload | Founder | Wk 14 | High | Not Started | Review requests automated | Emails sending automatically |  | 0% | Offer 10% off next order for photo review. Photo reviews convert 3x better than text-only. | Review automation
9B.03 | 9B | Create feedback collection system beyond reviews: quarterly customer survey, post-support satisfaction check | Founder | Wk 16 | Medium | Not Started | Feedback system active | Multiple feedback channels |  | 0% | Google Forms survey every 3 months: "What do you love?", "What would you change?", "What other products do you want?" | Feedback system
9B.04 | 9B | Respond to every review within 48 hours: thank positive reviewers, address negative reviews with empathy + solution | Founder | Ongoing | High | Not Started | Response habit established | 100% response rate |  | 0% | How you handle negative reviews defines your brand. Always offer to make it right. Others read your responses. | Response protocol
9C: Customer Loyalty & Retention (Wk 16–Ongoing) — 5 tasks
9C.01 | 9C | Set up referral program: "Give $5, Get $5" using ReferralCandy or Smile.io free tier | Founder | Wk 16 | High | Not Started | Referral program live | App installed and active |  | 0% | Runners recommend gear constantly. A formal referral program captures this behavior and rewards it. | Referral program
9C.02 | 9C | Create VIP email segment for repeat customers: early access to new products, exclusive discounts, birthday offers | Founder | Wk 18 | Medium | Not Started | VIP segment active | Segment defined in Klaviyo |  | 0% | Repeat customers spend 67% more than new customers. Invest disproportionately in retention. | VIP program
9C.03 | 9C | Design cross-sell strategy: complementary products (running socks, reflective gear) or bundle offers | Founder | Wk 20 | Medium | Not Started | Cross-sell strategy defined | Strategy documented |  | 0% | Eventually you'll expand product line. For now, consider bundling belt + running-related partner products. | Cross-sell plan
9C.04 | 9C | Track Net Promoter Score (NPS) quarterly: "How likely are you to recommend us to a friend? (0–10)" | Founder | Wk 20 | Medium | Not Started | NPS tracking active | First NPS score collected |  | 0% | NPS > 50 = excellent for D2C. Running brands should aim for 60+ given passionate customer base. | NPS tracker
9C.05 | 9C | Analyze customer lifetime value (LTV): track repeat purchase rate, time between purchases, average spend | Founder | Month 6+ | Medium | Not Started | LTV analysis started | LTV calculated |  | 0% | Target: LTV:CAC ratio > 3:1. If LTV is low, focus on retention and product expansion before acquiring more customers. | LTV analysis
9D: Returns, Exchanges & Quality Loop (Wk 14–Ongoing) — 4 tasks
9D.01 | 9D | Set up returns management: self-service portal (Shopify free returns) or manual process with prepaid labels | Founder | Wk 14 | High | Not Started | Returns process live | Customers can initiate returns |  | 0% | Start manual (email support@). Upgrade to self-service portal once volume exceeds 5+ returns/month. | Returns process
9D.02 | 9D | Track return reasons: categorize every return (wrong size, didn't like, defect, changed mind) for product improvement | Founder | Ongoing | High | Not Started | Return tracking active | All returns categorized |  | 0% | If >30% of returns are sizing: fix your size guide. If defects: contact supplier. Data drives improvement. | Return reason tracker
9D.03 | 9D | Create exchange-first process: offer exchange before refund to save the sale and improve customer experience | Founder | Wk 15 | Medium | Not Started | Exchange process active | Exchange option offered first |  | 0% | "Wrong size? We'll send the right size free and you can return the original at your convenience." Saves ~40% of returns. | Exchange process
9D.04 | 9D | Feed return/complaint data back to product development: monthly summary of top 3 product issues to address in v2 | Founder | Monthly | High | Not Started | Feedback loop active | Monthly product issue report |  | 0% | This closes the loop between customer experience and product improvement. Essential for v2 development. | Product issue reports

## P10
P10: SUPPLY CHAIN & FULFILLMENT ¦ Weeks 10–Ongoing ¦ 4 Subprojects ¦ 16 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
10A: Fulfillment Operations (Wk 10–14) — 4 tasks
10A.01 | 10A | Set up home fulfillment station: packing table, label printer (Rollo $200 or use Shopify shipping labels), supplies | Founder | Wk 10–11 | High | Not Started | Fulfillment station ready | Can pack 20+ orders/day |  | 0% | Start with home fulfillment for first 300 units. Move to 3PL when exceeding 5+ orders/day consistently. | Station setup
10A.02 | 10A | Configure Shopify Shipping: generate labels, automate tracking emails, set up shipping carriers | Founder | Wk 11–12 | High | Not Started | Shipping configured | Test labels printed successfully |  | 0% | Shopify Shipping gives discounted USPS/DHL rates. For international: DHL eCommerce or local postal service. | Shipping config
10A.03 | 10A | Create SOP for order fulfillment: receive order → pick → quality check → pack → label → ship → update tracking | Founder | Wk 12 | Medium | Not Started | SOP documented | Written process |  | 0% | Consistency matters even when you're the only person. Document now so it's easy to delegate later. | Fulfillment SOP
10A.04 | 10A | Set fulfillment targets: same-day for orders before 2 PM, next-day for afternoon orders | Founder | Wk 12 | High | Not Started | Targets set | Fulfillment SLA defined |  | 0% | Fast shipping = positive reviews = more sales. Amazon has set the expectation. Beat it with handwritten notes. | SLA document
10B: International Shipping (Wk 12–16) — 4 tasks
10B.01 | 10B | Research and select international shipping solution: DHL eCommerce, Shopify Markets, or local postal service | Founder | Wk 12–13 | High | Not Started | Solution selected | Carrier chosen with rates |  | 0% | DHL eCommerce: best balance of cost and reliability for small parcels globally. Shopify Markets handles duties/taxes. | Carrier selection
10B.02 | 10B | Set up customs documentation: commercial invoices, HS codes (4202.92 for running belts), country of origin labels | Founder | Wk 13–14 | Medium | Not Started | Customs docs ready | Templates created |  | 0% | Most shipping labels auto-generate customs forms. Ensure product value + HS code are correct to avoid delays. | Customs templates
10B.03 | 10B | Test international shipments: send 1 test package each to US, UK, Australia, Canada — track delivery time and experience | Founder | Wk 14–15 | Medium | Not Started | Test shipments delivered | 4 test deliveries tracked |  | 0% | Send to friends/family in target markets. Track: delivery time, duties charged to recipient, packaging condition. | Test delivery results
10B.04 | 10B | Consider 3PL for US fulfillment if based outside US: ShipBob, ShipHero, or Deliverr — get quotes for 100+ orders/mo | Founder | Wk 15–16 | Medium | Not Started | US 3PL evaluated | Quotes received |  | 0% | Makes sense when US orders exceed 50/month. Cost: $3–5/order + storage. Provides faster US delivery. | 3PL evaluation
10C: Inventory Management (Wk 14–Ongoing) — 4 tasks
10C.01 | 10C | Implement SKU naming system: [COLOR]-[SIZE]-[VERSION] (e.g., BLK-M-V1, GRN-L-V1) | Founder | Wk 14 | Medium | Not Started | SKU system implemented | All products have SKUs |  | 0% | Consistent SKUs prevent confusion as you add colors, sizes, and product versions. Set convention early. | SKU system
10C.02 | 10C | Set up weekly inventory count: physical count reconciled with Shopify inventory every Sunday | Founder | Wk 14 | High | Not Started | Weekly counts active | Counts match Shopify +/- 2% |  | 0% | Discrepancies happen (shipping errors, returns, samples). Weekly counts prevent surprises. | Inventory log
10C.03 | 10C | Define safety stock levels: minimum inventory per SKU to maintain while reorder is in transit | Founder | Wk 16 | High | Not Started | Safety stock defined | Per-SKU minimums set |  | 0% | Rule of thumb: safety stock = 2 weeks of sales per SKU. Adjust based on actual velocity data. | Safety stock levels
10C.04 | 10C | Create reorder calendar aligned with production lead times and seasonal demand peaks (Jan, Mar, Aug) | Founder | Wk 18 | Medium | Not Started | Reorder calendar created | Calendar with trigger dates |  | 0% | Plan reorders 6–8 weeks before anticipated demand spikes. Marathon season prep starts in January. | Reorder calendar
10D: Packaging Optimization (Wk 16–Ongoing) — 4 tasks
10D.01 | 10D | Analyze packaging costs per order: mailer + insert card + tape + label = target <$1.50/order | Founder | Wk 16 | Medium | Not Started | Packaging costs tracked | Per-order cost known |  | 0% | Packaging adds up. Optimize: bulk-order mailers (500+), use Canva for insert cards (print at home or bulk order). | Packaging cost analysis
10D.02 | 10D | Design v2 unboxing experience based on customer feedback: what impressed them, what felt cheap, what was missing | Founder | Wk 20 | Low | Not Started | V2 packaging designed | Updated design files |  | 0% | Unboxing is a marketing moment. Include: insert card, size guide, product care card, brand sticker. | V2 packaging design
10D.03 | 10D | Evaluate eco-friendly packaging options: recycled mailers, compostable bags, FSC-certified paper | Founder | Wk 20 | Low | Not Started | Eco options evaluated | Decision made |  | 0% | If eco-friendly is your brand angle, packaging must match the message. Recyclable kraft mailers cost ~$0.05 more. | Eco packaging evaluation
10D.04 | 10D | Source branded thank-you stickers and branded tape for premium feel at minimal cost | Founder | Wk 20 | Low | Not Started | Branded materials ordered | Materials in stock |  | 0% | Sticker Mule: 50 custom stickers for $25. Custom tape: $30/roll. Small details = big brand impression. | Branded materials

## P11
P11: GROWTH & SCALING ROADMAP ¦ Months 6–18 ¦ 4 Subprojects ¦ 18 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
11A: Product Line Expansion (Mo 6–12) — 5 tasks
11A.01 | 11A | Analyze customer feedback and sales data to identify #1 most-requested product improvement or new product | Founder | Mo 6 | High | Not Started | Data analysis complete | Top request identified |  | 0% | Let customers tell you what to build next. Don't guess. Survey + review analysis + support ticket themes. | Product request analysis
11A.02 | 11A | Develop v2 of running belt incorporating all customer feedback from v1 (sizing, materials, features) | Founder | Mo 7–9 | High | Not Started | V2 spec created | Spec sent to supplier |  | 0% | V2 should address top 3 complaints from v1 reviews. This is your competitive advantage over competitors who don't iterate. | V2 product spec
11A.03 | 11A | Explore complementary product: running flask pocket, reflective add-on, women-specific variant, hydration version | Founder | Mo 8–10 | Medium | Not Started | New product evaluated | Go/no-go decision |  | 0% | Naked expanded: bands → vests → shoes. SPIbelt: belts → medical → eco. What's your natural expansion? | Product expansion plan
11A.04 | 11A | If expanding: prototype, test, and validate new product following the same P2 process | Founder | Mo 9–12 | Medium | Not Started | New product validated | Customer testing complete |  | 0% | Don't skip validation for product #2. Apply everything you learned from product #1. | New product validation
11A.05 | 11A | Create product bundle: belt + complementary item at 15% discount vs buying separately | Founder | Mo 10 | Medium | Not Started | Bundle created | Bundle live on Shopify |  | 0% | Bundles increase AOV by 20–30%. Even bundling 2 belt colors ("trail pack") can work. | Bundle listing
11B: Channel Expansion (Mo 6–12) — 5 tasks
11B.01 | 11B | Launch on Amazon (if not already) following P4E process: listing, A+ content, Vine reviews, PPC | Founder | Mo 6–7 | High | Not Started | Amazon listing live | First sales on Amazon |  | 0% | Amazon adds a discovery channel. Manage brand perception by maintaining premium pricing close to D2C. | Amazon launch
11B.02 | 11B | Research wholesale opportunities: 5 specialty running stores in your primary market | Founder | Mo 8–9 | Medium | Not Started | Wholesale prospects identified | 5+ stores contacted |  | 0% | Wholesale pricing: 50% off retail (keystone markup). Your belt at $35 retail = $17.50 wholesale. Margin still works at $6 COGS. | Wholesale prospect list
11B.03 | 11B | Create wholesale one-sheet: product info, wholesale pricing, terms, MOQ, imagery for store use | Founder | Mo 9 | Medium | Not Started | Wholesale sheet created | Professional 1-pager ready |  | 0% | Include: product photos, wholesale pricing (tiered), suggested retail, shipping terms, return policy. | Wholesale one-sheet
11B.04 | 11B | Explore race expo opportunities: apply to 3–5 marathon expos as a vendor (SPIbelt's origin strategy) | Founder | Mo 8–10 | Medium | Not Started | Expo applications submitted | 3–5 applications sent |  | 0% | Expo booth: $500–1,500 for mid-size races. Direct access to 5,000–15,000 runners. High conversion rate. | Expo applications
11B.05 | 11B | Evaluate TikTok Shop and Instagram Shopping as additional sales channels | Founder | Mo 10–12 | Low | Not Started | Social commerce evaluated | Decision made |  | 0% | TikTok Shop is growing fast for D2C brands. If your TikTok content performs well, this is a natural extension. | Social commerce plan
11C: International Expansion (Mo 9–18) — 4 tasks
11C.01 | 11C | Analyze sales data by country: identify top 3 international markets by revenue | Founder | Mo 9 | Medium | Not Started | Market analysis complete | Top 3 markets identified |  | 0% | Likely: US #1, UK #2, Australia/Canada #3. Use Shopify Analytics geographic data. | Market ranking
11C.02 | 11C | For top international market: set up localized shopping experience (currency, shipping, language if needed) | Founder | Mo 10–12 | Medium | Not Started | Localization live | Market-specific experience active |  | 0% | Shopify Markets handles multi-currency, duties estimation, and local payment methods. Enable for top markets. | Localization setup
11C.03 | 11C | Explore regional fulfillment: 3PL in UK/EU and/or Australia to reduce international shipping time and cost | Founder | Mo 12–15 | Low | Not Started | 3PL evaluated | Quotes received |  | 0% | Makes financial sense when shipping 30+ orders/month to a specific region. Ship bulk inventory to 3PL, they fulfill locally. | 3PL evaluation
11C.04 | 11C | Consider international Amazon marketplaces: Amazon UK, Amazon DE, Amazon AU for additional discovery | Founder | Mo 15–18 | Low | Not Started | International Amazon evaluated | Decision made |  | 0% | Amazon Global Selling makes it relatively easy to list on international marketplaces. Start with UK. | International Amazon plan
11D: Team & Operations Scaling (Mo 9–18) — 4 tasks
11D.01 | 11D | Identify first hire/contractor needs: customer support VA, social media manager, or fulfillment help | Founder | Mo 9 | Medium | Not Started | Hiring needs identified | Priority roles listed |  | 0% | First hire is usually: VA for customer support ($4–8/hr) or fulfillment help. Frees founder for growth tasks. | Hiring plan
11D.02 | 11D | Hire first virtual assistant or part-time contractor for highest-leverage delegation | Founder | Mo 10–12 | Medium | Not Started | First hire made | Person onboarded |  | 0% | Upwork, OnlineJobs.ph, or local part-time help. Start with 10–20 hours/week. Document all processes first. | VA onboarding
11D.03 | 11D | Evaluate upgrading from self-fulfillment to 3PL when consistently exceeding 5 orders/day | Founder | Mo 12–15 | Medium | Not Started | 3PL decision made | Cost comparison complete |  | 0% | Break-even: self-fulfillment is cheaper below ~150 orders/month. Above that, 3PL saves time and scales better. | 3PL evaluation
11D.04 | 11D | Create SOPs for all recurring tasks: fulfillment, customer support, content creation, ad management, inventory | Founder | Mo 12–18 | Medium | Not Started | SOPs documented | All key processes written down |  | 0% | If you can't document it, you can't delegate it. SOPs are the foundation of scaling beyond a one-person operation. | SOP library

## P12
P12: SUSTAINABILITY & BRAND PURPOSE ¦ Weeks 4–Ongoing ¦ 3 Subprojects ¦ 12 Tasks
STATUS KEY: Complete = Delivered ¦ In Progress = Actively working ¦ Not Started = Pending ¦ Blocked = Dependency issue ¦ Needs Validation = Verify data
ID | Sub | Task | Owner | Timeline | Priority | Status | KPI / Success Metric | Target | Actual | % Done | Notes / Evidence | Deliverable
12A: Sustainable Product Development (Wk 4–Ongoing) — 4 tasks
12A.01 | 12A | Research sustainable materials: recycled polyester (rPET), recycled nylon (ECONYL), organic cotton blends, PFC-free DWR | Founder | Wk 4–6 | Medium | Not Started | Material options documented | 3+ sustainable alternatives identified |  | 0% | rPET costs 10–20% more than virgin polyester. Worth it if sustainability is your brand angle. ECONYL (from fishing nets) is premium. | Material research
12A.02 | 12A | If eco is your angle: source supplier capable of providing recycled/sustainable fabrics with certifications (GRS, OEKO-TEX) | Founder | Wk 6–10 | Medium | Not Started | Eco supplier identified | Supplier with certifications found |  | 0% | Ask Alibaba suppliers specifically: "Do you offer GRS-certified recycled polyester?" Many do but don't advertise it. | Eco supplier list
12A.03 | 12A | Calculate carbon footprint of product lifecycle: manufacturing, shipping, use, end-of-life | Founder | Mo 6–8 | Low | Not Started | Footprint estimated | Per-unit carbon impact known |  | 0% | Use free calculators (e.g., 2050 Materials). Even an estimate differentiates you from competitors who ignore this. | Carbon footprint
12A.04 | 12A | Design repair/refurbish program: take back used belts, refurbish, resell at discount (like Naked re[NEW]) | Founder | Mo 12+ | Low | Not Started | Program designed | Program structure documented |  | 0% | Naked's re[NEW] line sells refurbished bands at 50% off. Reduces waste, captures value, builds brand loyalty. | Refurbish program
12B: Brand Purpose & Community Impact (Wk 8–Ongoing) — 4 tasks
12B.01 | 12B | Define brand purpose beyond profit: what cause/community does your brand support? Running access? Environment? Inclusion? | Founder | Wk 8–10 | Medium | Not Started | Purpose defined | Written purpose statement |  | 0% | Examples: Naked supports Native Women Running + DOVE Project. Janji donates % to clean water. SPIbelt supports medical communities. | Purpose statement
12B.02 | 12B | Identify 1–2 charitable partners or initiatives to support: 1% for the Planet, local running charity, inclusion programs | Founder | Wk 10–14 | Medium | Not Started | Partners identified | 1–2 partnerships defined |  | 0% | 1% for the Planet: donate 1% of revenue to environmental nonprofits. Powerful credibility signal for eco brands. | Charity partnerships
12B.03 | 12B | Communicate brand purpose authentically on website, packaging, and social media — don't greenwash | Founder | Wk 14+ | Medium | Not Started | Purpose communicated | Purpose visible across touchpoints |  | 0% | Only claim what you can prove. "We're working toward sustainability" is honest. "We're the most eco brand" without proof is greenwashing. | Purpose messaging
12B.04 | 12B | Track and report impact annually: materials saved, donations made, community supported, carbon reduced | Founder | Year 1+ | Low | Not Started | Impact tracked | Annual impact report |  | 0% | Even small numbers matter when you're transparent. "In year 1, we diverted X kg of waste and donated $Y." | Impact report
12C: Long-Term Brand Building (Mo 6–Ongoing) — 4 tasks
12C.01 | 12C | Develop 3-year brand vision: where do you want the brand to be in 2029? Product range, revenue, team, markets | Founder | Mo 6 | Medium | Not Started | Vision documented | Written 3-year vision |  | 0% | Think big but plan realistically. Year 1: survive + validate. Year 2: grow + expand. Year 3: scale + dominate niche. | 3-year vision
12C.02 | 12C | Plan annual brand milestones: product launches, event sponsorships, community milestones, revenue targets | Founder | Mo 6 | Medium | Not Started | Milestones planned | Annual calendar with targets |  | 0% | Align with running calendar: Jan (resolution products), Spring (marathon gear), Fall (training season), Dec (gifting). | Annual milestone plan
12C.03 | 12C | Build relationships with 2–3 running publications for ongoing editorial coverage and credibility | Founder | Mo 8–Ongoing | Medium | Not Started | Media relationships active | 2–3 regular contacts |  | 0% | Consistent editorial coverage > one-time PR blast. Become a source they trust for running gear insights. | Media relationships
12C.04 | 12C | Document lessons learned, processes, and playbooks that could help other bootstrapped D2C founders | Founder | Ongoing | Low | Not Started | Playbook being built | Key learnings documented |  | 0% | Sharing your journey builds brand affinity and community. Many successful D2C founders became thought leaders. | Brand playbook

## SUMMARY
SUBPROJECT-LEVEL COMPLETION SUMMARY
Track progress across all 13 projects and 56 subprojects ¦ 278 total tasks ¦ Updated: March 2026
# | Subproject | Tasks | Done | % Complete | Status | Owner | Key Deliverable
P0: MARKET RESEARCH & CONCEPT VALIDATION (42 tasks)
1 | 0A: Running Belt Competitive Intelligence (Wk 1–2) | 8 | 0 | 0% | Not Started | Founder | Competitive database
2 | 0B: Target Customer Research (Wk 1–3) | 7 | 0 | 0% | Not Started | Founder | Persona document
3 | 0C: Product Concept Development (Wk 2–4) | 6 | 0 | 0% | Not Started | Founder | USP statement
4 | 0D: Alibaba Supplier Scouting (Wk 3–5) | 6 | 0 | 0% | Not Started | Founder | Supplier longlist
5 | 0E: Financial Feasibility (Wk 3–5) | 5 | 0 | 0% | Not Started | Founder | Unit economics model
6 | 0F: Niche Validation & Positioning (Wk 4–6) | 5 | 0 | 0% | Not Started | Founder | Positioning test results
7 | 0G: Competitive Intelligence Deep Dives (Wk 2–4) | 5 | 0 | 0% | Not Started | Founder | Naked case study
P1: BRAND DEVELOPMENT & IDENTITY (28 tasks)
8 | 1A: Brand Naming & Trademark (Wk 4–6) | 6 | 0 | 0% | Not Started | Founder | Name brainstorm list
9 | 1B: Visual Identity & Logo (Wk 5–7) | 6 | 0 | 0% | Not Started | Founder | Mood board
10 | 1C: Brand Story & Messaging (Wk 5–7) | 6 | 0 | 0% | Not Started | Founder | Founder story
11 | 1D: Brand Photography & Visual Assets (Wk 6–8) | 5 | 0 | 0% | Not Started | Founder | Photography shot list
12 | 1E: Pre-Launch Community Building (Wk 5–8) | 5 | 0 | 0% | Not Started | Founder | Social accounts
P2: PRODUCT DESIGN & ENGINEERING (27 tasks)
13 | 2A: Product Architecture & Specifications (Wk 4–6) | 6 | 0 | 0% | Not Started | Founder | Architecture decision
14 | 2B: Prototyping & Sample Development (Wk 5–8) | 6 | 0 | 0% | Not Started | Founder | Supplier communications
15 | 2C: Packaging & Unboxing Design (Wk 7–9) | 5 | 0 | 0% | Not Started | Founder | Mailer design file
16 | 2D: Size Guide & Product Documentation (Wk 8–9) | 5 | 0 | 0% | Not Started | Founder | Size guide
17 | 2E: Quality Standards & Testing Protocols (Wk 8–10) | 5 | 0 | 0% | Not Started | Founder | QA document
P3: MANUFACTURING & FIRST PRODUCTION RUN (22 tasks)
18 | 3A: Production Order & Payment (Wk 8–10) | 6 | 0 | 0% | Not Started | Founder | Production order qty
19 | 3B: Quality Control & Inspection (Wk 12–13) | 6 | 0 | 0% | Not Started | Founder | Pre-ship photos
20 | 3C: Shipping & Logistics (Wk 12–14) | 5 | 0 | 0% | Not Started | Founder | Shipping decision
21 | 3D: Reorder Planning (Wk 13–14) | 5 | 0 | 0% | Not Started | Founder | Reorder thresholds
P4: DIGITAL INFRASTRUCTURE & E-COMMERCE (28 tasks)
22 | 4A: Shopify Store Setup (Wk 6–9) | 7 | 0 | 0% | Not Started | Founder | Store URL
23 | 4B: Email Marketing Setup (Wk 7–10) | 6 | 0 | 0% | Not Started | Founder | Klaviyo setup
24 | 4C: Analytics & Tracking (Wk 7–9) | 5 | 0 | 0% | Not Started | Founder | GA4 setup
25 | 4D: SEO & Content Foundation (Wk 8–12) | 5 | 0 | 0% | Not Started | Founder | Keyword list
26 | 4E: Amazon Preparation (Wk 10–12) | 5 | 0 | 0% | Not Started | Founder | Amazon decision
P5: CONTENT, COMMUNITY & INFLUENCER MARKETING (26 tasks)
27 | 5A: Influencer Seeding Program (Wk 8–14) | 6 | 0 | 0% | Not Started | Founder | Influencer database
28 | 5B: Content Marketing & Social Media (Wk 8–Ongoing) | 6 | 0 | 0% | Not Started | Founder | Content strategy doc
29 | 5C: Running Community & Events (Wk 10–18) | 5 | 0 | 0% | Not Started | Founder | Event calendar
30 | 5D: PR & Media Outreach (Wk 12–18) | 4 | 0 | 0% | Not Started | Founder | Media contact list
31 | 5E: Referral & Ambassador Program (Wk 14–20) | 5 | 0 | 0% | Not Started | Founder | Referral program
P6: LAUNCH EXECUTION & PAID ACQUISITION (25 tasks)
32 | 6A: Pre-Launch Campaign (Wk 12–14) | 5 | 0 | 0% | Not Started | Founder | Email sequence
33 | 6B: Launch Week Execution (Wk 14–15) | 5 | 0 | 0% | Not Started | Founder | Launch confirmation
34 | 6C: Paid Advertising | 5 | 0 | 0% | Not Started | Founder | Ads Manager setup
35 | 6D: Paid Advertising | 5 | 0 | 0% | Not Started | Founder | Google Ads setup
36 | 6E: Launch Metrics & Optimization (Wk 16–20) | 5 | 0 | 0% | Not Started | Founder | KPI dashboard
P7: FINANCIAL OPERATIONS & CASH FLOW (18 tasks)
37 | 7A: Business Setup & Banking (Wk 1–4) | 5 | 0 | 0% | Not Started | Founder | Registration docs
38 | 7B: Financial Modeling & Budgeting (Wk 2–6) | 5 | 0 | 0% | Not Started | Founder | Unit economics spreadsheet
39 | 7C: Payment & International Operations (Wk 4–8) | 4 | 0 | 0% | Not Started | Founder | Payment setup
40 | 7D: Inventory & COGS Management (Wk 8–Ongoing) | 4 | 0 | 0% | Not Started | Founder | Inventory system
P8: LEGAL, COMPLIANCE & IP PROTECTION (16 tasks)
41 | 8A: Business Formation & Structure (Wk 1–4) | 4 | 0 | 0% | Not Started | Founder | Entity decision
42 | 8B: Intellectual Property (Wk 3–8) | 4 | 0 | 0% | Not Started | Founder | TM filing receipt
43 | 8C: E-Commerce Compliance (Wk 4–8) | 4 | 0 | 0% | Not Started | Founder | Legal page URLs
44 | 8D: Contracts & Agreements (Wk 6–10) | 4 | 0 | 0% | Not Started | Founder | Supplier agreement
P9: CUSTOMER EXPERIENCE & RETENTION (18 tasks)
45 | 9A: Customer Support Infrastructure (Wk 12–14) | 5 | 0 | 0% | Not Started | Founder | Support email
46 | 9B: Review & Feedback Collection (Wk 14–Ongoing) | 4 | 0 | 0% | Not Started | Founder | Review app
47 | 9C: Customer Loyalty & Retention (Wk 16–Ongoing) | 5 | 0 | 0% | Not Started | Founder | Referral program
48 | 9D: Returns, Exchanges & Quality Loop (Wk 14–Ongoing) | 4 | 0 | 0% | Not Started | Founder | Returns process
P10: SUPPLY CHAIN & FULFILLMENT (16 tasks)
49 | 10A: Fulfillment Operations (Wk 10–14) | 4 | 0 | 0% | Not Started | Founder | Station setup
50 | 10B: International Shipping (Wk 12–16) | 4 | 0 | 0% | Not Started | Founder | Carrier selection
51 | 10C: Inventory Management (Wk 14–Ongoing) | 4 | 0 | 0% | Not Started | Founder | SKU system
52 | 10D: Packaging Optimization (Wk 16–Ongoing) | 4 | 0 | 0% | Not Started | Founder | Packaging cost analysis
P11: GROWTH & SCALING ROADMAP (18 tasks)
53 | 11A: Product Line Expansion (Mo 6–12) | 5 | 0 | 0% | Not Started | Founder | Product request analysis
54 | 11B: Channel Expansion (Mo 6–12) | 5 | 0 | 0% | Not Started | Founder | Amazon launch
55 | 11C: International Expansion (Mo 9–18) | 4 | 0 | 0% | Not Started | Founder | Market ranking
56 | 11D: Team & Operations Scaling (Mo 9–18) | 4 | 0 | 0% | Not Started | Founder | Hiring plan
P12: SUSTAINABILITY & BRAND PURPOSE (12 tasks)
57 | 12A: Sustainable Product Development (Wk 4–Ongoing) | 4 | 0 | 0% | Not Started | Founder | Material research
58 | 12B: Brand Purpose & Community Impact (Wk 8–Ongoing) | 4 | 0 | 0% | Not Started | Founder | Purpose statement
59 | 12C: Long-Term Brand Building (Mo 6–Ongoing) | 4 | 0 | 0% | Not Started | Founder | 3-year vision
GRAND TOTAL |  | 296 | 0 | 0%